## Projects
| RD Projects | [22 empty] | 26 | 27
# | Projects |  | PM | TASK COMPLETE | Status |  | Note | Month 2025 - 2026 | [13 empty] | Month 2026 - 2027
1 | Features | [6 empty] | April | May | June | July | August | September | October | November | December | January | February | March |  |  | April | May | June |  | July | August | September | October | November | December | January | February | March
| Adjust | Zan | Mean | 100% | Done
| CleverTap | Jack | Mean | 100% | Done
| Ecommerce Shopify | Aek | Mean | 100% | Done
| AWS Migration | A | Win | 30% | In Progress | Timeline | Dev 85%, UAT 0%, Prod 0%
| Thana Datamart API (New Datamart) | Zan | Win | 80% | In Progress | Timeline | - Token Light Speed (Dev sp21) Lightspeed Token [5P] Create OM API Connect [5P] Integrate new token flow to light speed service and retest send data - [3P] Update mapping light speed enhancement (Dev sp21) - API send to CT (SA est sp21, Dev sp22) | [11 empty] | dev env
| Thana City (Out of Scope OM) | Zan, Aek | Win | 60% | In Progress | Timeline | - POS transaction API ของ Light Speed - POS Master data (End of Feb TBC) - Shopify webhook and View tables | [13 empty] | sa, dev
| Vimi Termination | Zan, Aek | Mean | 60% | In Progress | Timeline | https://docs.google.com/spreadsheets/d/1HlvYW4TgA-JaRO8mMb0kbMwip2YzqJ738MSP5CJ1sls/edit?gid=1729294108#gid=1729294108 | [12 empty] | api 13 |  | submit app 30/31 Mar , Release 3 April
| New Point Engine | Aom, Jack | Mook | 15% | In Progress | Timeline
| Subscription Short-Distance (Support App, A920) | Aek, Zan | Mean | 100% | Done |  | RR App and A920 (ไม่ต้องทำแล้ว รอ confirm) | [14 empty] | monitoring 1 - 3 apr
| Pay with Point | Aom, Zan | P'Pop | 90% | In Progress | Timeline
| Turtle Plus member tier upgrade & downgrade | Zan | Mean | 10% | In Progress |  | Upgrade ใช้ solution เดิม(ตอนนี้), Downgrade -> ทำไฟล์ run script
| PayPoint (Point Marketplace) integration | Zan, Aek | Mean | 0% | In Progress |  | Provided spec
| SSO Migration | A | Win | 0% | To Do
| Cloud Samsung |  |  | 0% | In Progress
| Review App Handover document |  |  | 0% | Done
| Unified App |  |  | 0% | In Progress
| Rcash PLoan |  |  | 0% | In Progress
| Tech Debt |  |  | 0% | In Progress

## Sprint Resource
Total Manhour/Sprint
Sprint | Date | Aek | Aom | Zan | Jack | A | Mai | Mac | Mos | Nim | Arm | Total All | Total Dev | Stories Point : Dev | Remark
6 | 25 Aug - 5 Sep | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | [6 empty] | 1 -> 2h -> 7200
| day | 7.5 | 7.5 | 7.5 | 8 | 7.5 | 8 | 8 | 7 | [5 empty] | มีวันหยุด 0 วัน | 2 -> 4h -> 14400
| hour | 48.75 | 48.75 | 48.75 | 52 | 48.75 | 52 | 52 | 45.5 |  |  | 396.5 |  |  | Aom 0.5, Zan 0.5, Aek 0.5, A 0.5, Mos 1 | 3 -> 1d -> 28800
7 | 8 Sep - 19 Sep | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | [5 empty] | 5 -> 2d -> 57600
| day | 8 | 7.5 | 8 | 8 | 8 | 8 | 8 | 7.5 | 7 |  |  |  |  | มีวันหยุด 0 วัน | 8 -> 3d -> 86400
| hour | 52 | 48.75 | 52 | 52 | 52 | 52 | 52 | 48.75 | 45.5 |  | 455 |  |  | Aom 0.5, Mos 0.5, Nim 1
8 | 22 Sep - 3 Oct | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | [5 empty] | Mos 7.5
| day | 7 | 7 | 8 | 7 | 8 | 7 | 8 | 8 | 8 |  |  |  |  | มีวันหยุด 0 วัน | Nim 5
| hour | 45.5 | 45.5 | 52 | 45.5 | 52 | 45.5 | 52 | 52 | 52 |  | 442 |  |  | Aek 1, Aom 1, Mai 1, Jack 1 | Arm 4
9 | 6 Oct - 17 Oct | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5
| day | 4.5 | 7 | 5 | 6 | 7 | 3 | 7 | 6.5 | 7 |  |  |  |  | มีวันหยุด 1 วัน
| hour | 29.25 | 45.5 | 32.5 | 39 | 45.5 | 19.5 | 45.5 | 42.25 | 45.5 |  | 344.5 |  |  | Aek 2.5, Zan 2, Mai 4, Jack 1, Mos 0.5
| point | 10 | 17 | 12 | 14 | 17 | 7 | 17 | 15 | 17
10 | 20 Oct - 31 Oct | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5
| day | 6 | 7 | 7 | 5 | 6 | 7 | 7 | 7 | 7 |  |  |  |  | มีวันหยุด 1 วัน
| hour | 39 | 45.5 | 45.5 | 32.5 | 39 | 45.5 | 45.5 | 45.5 | 45.5 |  | 383.5 |  |  | Aek 1, Jack 2, A 1
| point | 14 | 17 | 17 | 12 | 14 | 17 | 17 | 17 | 17
11 | 3 Nov - 14 Nov | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5
| day | 7 | 7 | 8 | 7 | 7.5 | 8 | 6 | 6.5 | 7 | 7 |  |  |  | มีวันหยุด 0 วัน
| hour | 45.5 | 45.5 | 52 | 45.5 | 48.75 | 52 | 39 | 42.25 | 45.5 | 45.5 | 461.5 |  |  | Jack 1, Nim 1, Mac 2, Aek 1, Aom 1, Arm 1, A 0.5, Mos 1.5
| point | 17 | 17 | 19 | 17 | 18 | 19 | 14 | 15 | 17 | 17
12 | 17 Nov - 28 Nov | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5
| day | 8 | 6 | 7 | 8 | 7.5 | 8 | 8 | 6 | 8 | 6 |  |  |  | มีวันหยุด 0 วัน
| hour | 52 | 39 | 45.5 | 52 | 48.75 | 52 | 52 | 39 | 52 | 39 | 471.25 |  |  | Zan 1, Aom 2, Mos 2, A 0.5, Arm 2
| point | 19 | 14 | 17 | 19 | 18 | 19 | 19 | 14 | 19 | 14
13 | 1 Dec - 12 Dec | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5
| day | 6 | 3 | 7 | 7 | 7 | 5 | 7 | 6.5 | 5 | 7 |  |  |  | มีวันหยุด 1 วัน
| hour | 39 | 19.5 | 45.5 | 45.5 | 45.5 | 32.5 | 45.5 | 42.25 | 32.5 | 45.5 | 393.25 |  |  | Aom 4, Mai 2, Nim 2, Aek 1, Mos 0.5
|  | 14 | 7 | 17 | 17 | 17 | 12 | 17 | 15 | 12 | 17
14 | 15 Dec - 26 Dec | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5
| day | 6 | 6 | 8 | 7 | 7 | 8 | 8 | 7 | 7 | 7.5 |  |  |  | มีวันหยุด 0 วัน
| hour | 39 | 39 | 52 | 45.5 | 45.5 | 52 | 52 | 45.5 | 45.5 | 48.75 | 464.75 |  |  | Nim 1, A 1, Aek 2, Aom 2, Jack 1, Arm 0.5, Mos 1
| point | 14 | 14 | 19 | 17 | 17 | 19 | 19 | 17 | 17 | 18
15 | 29 Dec - 9 Jan | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5
| day | 2.5 | 5 | 4.5 | 4 | 4.5 | 5 | 6 | 5.5 | 5 | 6 |  |  |  | มีวันหยุด 2 วัน + ลาสิ้นปี-ปีใหม่กันเยอะ
| hour | 16.25 | 32.5 | 29.25 | 26 | 29.25 | 32.5 | 39 | 35.75 | 32.5 | 39 | 312 |  |  | Jack 2, A 1.5, Aek 3.5, Aom 1, Zan 1.5, Mai 1, Nim 1, Mos 0.5
| point | 6 | 12 | 10 | 9 | 10 | 12 | 14 | 13 | 12 | 14
16 | 12 Jan - 23 Jan | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5
| day | 7 | 6 | 6.5 | 7 | 5.5 | 6 | 7 | 7 | 7 | 5 |  |  |  | มี Team Building 1 วัน
| hour | 45.5 | 39 | 42.25 | 45.5 | 35.75 | 39 | 45.5 | 45.5 | 45.5 | 32.5 | 416 |  |  | A 1.5, Arm 2, Aom 1, Zan 0.5, Mai 1
| point | 17 | 14 | 15 | 17 | 13 | 14 | 17 | 17 | 17 | 12
17 | 26 Jan - 6 Feb | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5
| day | 8 | 8 | 7 | 5 | 8 | 8 | 8 | 8 | 6 | 2 |  |  |  | มีวันหยุด 0 วัน
| hour | 52 | 52 | 45.5 | 32.5 | 52 | 52 | 52 | 52 | 39 | 13 | 338 |  |  | Nim 2, Arm 1, Arm 5, Jack 3, Zan 1
| point | 19 | 19 | 17 | 12 | 19 | 19 | 19 | 19 | 14 | 4
18 | 9 Feb - 20 Feb | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| day | 7 | 4.5 | 5 | 7 | 6.5 | 6 | 6 | 6.5 | 7 | 0 |  |  |  | มีวันหยุด 1 วัน ตรุษจีน
| hour | 49 | 31.5 | 35 | 49 | 45.5 | 42 | 42 | 45.5 | 49 | 0 | 388.5 | 224 |  | Aom 2.5, Zan 2, Mai 1, Mac 1, Arm 9, Mos 0.5, A 0.5
| point | 21 | 13 | 15 | 21 | 19 | 18 | 18 | 19 | 21 | 0 | 165 | 95 | 21
19 | 23 Feb - 6 Mar | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| day | 6 | 5 | 6 | 7 | 7 | 6 | 6 | 7 | 7 | 6.5 |  |  |  | มีวันหยุด 1 วัน มาฆบูชา
| hour | 42 | 35 | 42 | 49 | 49 | 42 | 42 | 49 | 49 | 45.5 | 444.5 | 276.5 |  | Aek 1, Aom 2, Zan 1, Mac 1, Mai 1, Arm 0.5
| point | 18 | 15 | 18 | 21 | 21 | 18 | 18 | 21 | 21 | 19 | 190 | 118 | 21
20 | 9 Mar - 20 Mar | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| day | 8 | 7 | 7.5 | 8 | 7 | 7 | 7.5 | 7 | 7 | 8 |  |  |  | มีวันหยุด 0 วัน
| hour | 56 | 49 | 52.5 | 56 | 49 | 49 | 52.5 | 49 | 49 | 56 | 518 | 304.5 |  | Aom 1, A 1, Mai 1, Mos 1, Nim 1, Zan 0.5, Mac 0.5
| point | 24 | 21 | 22 | 24 | 21 | 21 | 22 | 21 | 21 | 24 | 221 | 130 | 24
21 | 23 Mar - 3 Apr | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| day | 7 | 7 | 8 | 8 | 7 | 8 | 8 | 8 | 7 | 7.5 |  |  |  | มีวันหยุด 0 วัน
| hour | 49 | 49 | 56 | 56 | 49 | 56 | 56 | 56 | 49 | 52.5 | 528.5 | 318.5 |  | A 1, Aom 1, Aek 2, Nim 1, Arm 0.5
| point | 21 | 21 | 24 | 24 | 21 | 24 | 24 | 24 | 21 | 22 | 226 | 136 | 24
22 | 6 Apr - 17 Apr | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| day | 3 | 0 | 3 | 3 | 4 | 4 | 3 | 4 | 4 | 4 |  |  |  | มีวันหยุด 4 วัน : วันจักรี 1 (SP), สงกรานต์ 3
| hour | 21 | 0 | 21 | 21 | 28 | 28 | 21 | 28 | 28 | 28 | 224 | 161 |  | Aom 5, Aek 3, Zan 2, Mac 2, Jack 1
| point | 9 | 0 | 9 | 9 | 12 | 12 | 9 | 12 | 12 | 12 | 96 | 69 | 12
23 | 20 Apr - 1 May | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| day | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 6 | 7 | 6 |  |  |  | มีวันหยุด 1 วัน วันแรงงาน (SR)
| hour | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 42 | 49 | 42 | 476 | 280 |  | A 1 (SP), Mos 1, Arm 1
| point | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 18 | 21 | 18 | 204 | 120 | 21
24 | 4 May - 15 May | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| day | 7 | 5 | 6 | 7 | 6 | 7 | 7 | 7 | 7 | 7 |  |  |  | มีวันหยุด 1 วัน วันฉัตรมงคล (SP)
| hour | 49 | 35 | 42 | 49 | 42 | 49 | 49 | 49 | 49 | 49 | 462 | 287 |  | Aom 2, Zan 1, A 1
| point | 21 | 15 | 18 | 21 | 18 | 21 | 21 | 21 | 21 | 21 | 198 | 123 | 21
25 | 18 May - 29 May | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| day | 8 | 7 | 8 | 8 | 7 | 4 | 8 | 8 | 8 | 8 |  |  |  | มีวันหยุด 0 วัน
| hour | 56 | 49 | 56 | 56 | 49 | 28 | 56 | 56 | 56 | 56 | 518 | 301 |  | Mai 5, A 1, Aom 2
| point | 24 | 21 | 24 | 24 | 21 | 12 | 24 | 24 | 24 | 24 | 222 | 129 | 24
26 | 1 Jun - 12 Jun | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| day | 5 | 5.5 | 4.5 | 5 | 7 | 6 | 7 | 7 | 7 | 7 |  |  |  | มีวันหยุด 1 วัน วันเฉลิมพระราชินี
| hour | 35 | 38.5 | 31.5 | 35 | 49 | 42 | 49 | 49 | 49 | 49 | 427 | 287 |  | Aek 2, Jack 2, Zan 2.5, Aom 1.5, Mai 1
| point | 15 | 16 | 13 | 15 | 21 | 18 | 21 | 21 | 21 | 21 | 182 | 123 | 21
27 | 15 Jun - 26 Jun | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| day | 7 | 8 | 8 | 8 | 7 | 8 | 8 | 8 | 7 | 8 |  |  |  | มีวันหยุด 0 วัน
| hour | 49 | 56 | 56 | 56 | 49 | 56 | 56 | 56 | 49 | 56 | 539 | 322 |  | Aek 1, Nim 1, A 1
| point | 21 | 24 | 24 | 24 | 21 | 24 | 24 | 24 | 21 | 24 | 231 | 138 | 24
28 | 29 Jun - 10 Jul | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| day | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 7 | 8 |  |  |  | มีวันหยุด 0 วัน
| hour | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 49 | 56 | 553 | 329 |  | Nim 1, Mac 1
| point | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 21 | 24 | 237 | 141 | 24
P000078
P000100

## Resource Allocate
Resource Plan – Sprint 19 23 Feb - 6 Mar
Capacity รวมทั้งทีม 118.5 SP | 118.5
Allocation each project (exclude PE) | #REF!
Allocation PE | #REF!
New Point Engine | #REF! | 3
Vimi Termination | #REF! | 1
Thana | #REF! | 2
Datamart | #REF! | 1
AWS | #REF! | 1
Dev Support | #REF!
Remaining | #REF!
Name | Availability | Capacity | Total Workload | PE (SP) | VIMI (SP) | Thana (SP) |  | Datamart (SP) | AWS (SP) | Dev Support (SP)
A | 7 | 21 | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | 2
Mac | 6 | 18 | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
Mai | 6 | 18 | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF!
Mos | 7 | 21 | #REF! | #REF! | #REF! |  |  | #REF! |  | #REF!
Nim | 7 | 21 | #REF! | #REF! | #REF! |  |  | #REF! |  | 2
Arm | 6.5 | 19.5 | #REF! | #REF! | #REF! |  |  | #REF! |  | 3
Total |  | 118.5 | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
Resource Plan – Sprint 20 9 Mar - 20 Mar
Capacity รวม 130.5 SP | 130.5
Allocation each project (exclude PE) | #REF!
Allocation PE | #REF!
New Point Engine | #REF! | 4
Vimi Termination | #REF! | 1
Thana | #REF! | 2
Datamart | #REF! | 0
AWS | #REF! | 0
Dev Support | #REF! | 1
Remaining | #REF!
Name | Availability | Capacity | Total Workload | PE (SP) | VIMI (SP) | Thana (SP) |  | AWS (SP) | Adhoc (SP) | Dev Support (SP)
A | 7 | 21 | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | 1
Mac | 7.5 | 22.5 | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF!
Mai | 7 | 21 | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF!
Mos | 7 | 21 | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF!
Nim | 7 | 21 | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF!
Arm | 8 | 24 | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF!
Total |  | 130.5 | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
Resource Plan – Sprint 21 23 Mar - 3 Apr | 226.5
Capacity SA รวม 90 SP | 90
Capacity DEV รวม 136.5 SP | 136.5
Allocation each project (exclude PE) | 24
Allocation PE | 112.5 | 110
New Point Engine | 110 | 6
Vimi Termination | 3 | 1
Thana | 11 | 1
Datamart | 4 | 1
AWS | 0 | 0
Adhoc | 0
Dev Support | 6
Name | Availability | Capacity | Total Workload | New PE | VIMI | Thana | Datamart | AWS | Adhoc | Dev Support
Aek | 7 | 21 | 23 | 3 |  |  |  |  | 17 | 3
Aom | 7 | 21 | 31 | 23 | [5 empty] | 8
Zan | 8 | 24 | 33 |  |  | 8 | 3 |  | 21 | 1
Jack | 8 | 24 | 15 | 15
|  | 90 | 102
A | 7 | 21 | 21 | 21
Mac | 8 | 24 | 23 | 8 |  | 11 | 4
Mai | 8 | 24 | 21 | 18 | [5 empty] | 3
Mos | 8 | 24 | 23 | 23
Nim | 7 | 21 | 20 | 17 | 3
Arm | 7.5 | 22.5 | 26 | 23 | [5 empty] | 3
Total |  | 136.5 | 134 | 110 | 3 | 11 | 4 | 0 | 0 | 6
|  | 226.5 | 236 | 151 | 3 | 19 | 7 | 0 | 38 | 18
Resource Plan – Sprint 22 *Long weekend 6 Apr - 17 Apr | 96
Capacity SA รวม 45 SP | 27
Capacity รวม 84 SP | 69
Allocation each project (exclude PE) | 19
Allocation PE | 50 | 41
New Point Engine | 10 | 0
Vimi Termination |  | 0
Thana |  | 0
Datamart |  | 0
AWS |  | 0
Adhoc
Dev Support | 2
Name | Availability | Capacity | Total Workload | New PE | VIMI | Thana | Datamart | AWS | Adhoc | Dev Support | Ecom
Aek | 3 | 9 | 14 | 2 |  |  |  |  | 6 |  | 6
Aom | 0 | 0 | 0
Zan | 3 | 9 | 0
Jack | 3 | 9 | 0
|  | 27 | 14
A | 4 | 12 | 10 | 5 |  |  |  |  | 5
Mac | 3 | 9 | 9 |  | 3 | 6
Mai | 4 | 12 | 12 | 12
Mos | 4 | 12 | 8 | 8
Nim | 4 | 12 | 11 | 6 | 5
Arm | 4 | 12 | 10 | 10
Total |  | 69 | 60 | 41 | 8 | 6 | 0 | 0 | 5 | 0 | 0
|  | 96 | 74 | 43 | 8 | 6 | 0 | 0 | 11 | 0 | 6
Resource Plan – Sprint 23 20 Apr - 1 May | 204
Capacity SA รวม 81 SP | 84
Capacity รวม 186 SP | 120
Allocation each project (exclude PE) | 44
Allocation PE | 76 | 80
New Point Engine |  | 0
Vimi Termination |  | 0
Thana |  | 0
Datamart |  | 0
AWS |  | 0
Adhoc
Dev Support | 0
Name | Availability | Capacity | Total Workload | New PE | VIMI | Thana | Datamart | AWS | Adhoc | Dev Support | Ecom | PWP | VGI
Aek | 7 | 21 | 22 | [5 empty] | 15 | 2 | 5
Aom | 7 | 21 | 24 | 21 |  |  |  |  | 1 | 2
Zan | 7 | 21 | 21 |  |  | 5 |  |  | 11 |  |  | 5
Jack | 7 | 21 | 22 | 8 |  |  |  |  | 3 | 2 |  |  | 9
|  | 84 | 89
A | 7 | 21 | 22 | 19 |  |  |  |  | 3
Mac | 7 | 21 | 24 |  |  | 21 |  |  | 3
Mai | 7 | 21 | 21 | 13 |  | 5 |  |  | 3
Mos | 6 | 18 | 19 | 16 |  |  |  |  | 3
Nim | 7 | 21 | 20 | 17 |  |  |  |  | 3
Arm | 6 | 18 | 18 | 15 |  |  |  |  | 3
Total |  | 120 | 124 | 80 | 0 | 26 | 0 | 0 | 18 | 0 | 0 | 0 | 0
|  | 204 | 213 | 109 | 0 | 31 | 0 | 0 | 48 | 6 | 5 | 5 | 9
Resource Plan – Sprint 24 4 May - 15 May | 198
Capacity SA | 75
Capacity DEV | 123
Allocation each project (exclude PE) | 58
Allocation PE | 65 | 73
New Point Engine
Vimi Termination
Thana
Datamart
AWS
Adhoc
Dev Support
Name | Availability | Capacity | Total Workload | New PE | VIMI | Thana | Datamart | AWS | Adhoc | Dev Support | Ecom | PWP | VGI | Tech Debt
Aek | 7 | 21 | 23 | [5 empty] | 13 | 1 | 9
Aom | 5 | 15 | 18 | 18
Zan | 6 | 18 | 19 |  | 3 | 8 |  |  | 8
Jack | 7 | 21 | 20 | 8 | [5 empty] | 3 |  |  | 9
|  | 75 | 80
A | 6 | 18 | 16 | 12 | [9 empty] | 4
Mac | 7 | 21 | 19 | 8 |  | 11
Mai | 7 | 21 | 16 | 10 |  |  |  |  | 5 | 1
Mos | 7 | 21 | 16 | 16
Nim | 7 | 21 | 17 | 17
Arm | 7 | 21 | 18 | 10 |  |  |  |  | 5 |  |  |  |  | 3
Total |  | 123 | 102 | 99 | 3 | 19 | 0 | 0 | 31 | 5 | 0 | 0 | 0 | 7
|  | 198 | 182 | 99 | 3 | 19 | 0 | 0 | 31 | 5 | 9 | 0 | 9 | 7
Resource Plan – Sprint 25 18 May - 29 May | 222
Capacity SA | 93
Capacity DEV | 129
Allocation each project (exclude PE) | 7
Allocation PE | 122 | 19
New Point Engine | 6
Vimi Termination
Thana
Datamart
AWS
Adhoc
Dev Support
Name | Availability | Capacity | Total Workload | New PE | VIMI | Thana | Datamart | AWS | Adhoc | Dev Support | Ecom | PWP | VGI | Tech Debt
Aek | 8 | 24 | 24 | [5 empty] | 12 |  | 12
Aom | 7 | 21 | 21 | 12 |  |  |  |  | 6 | 3
Zan | 8 | 24 | 23 | 8 |  | 5 |  |  | 10
Jack | 8 | 24 | 24 | 12 | [8 empty] | 12
|  | 93 | 92
A | 7 | 21 | 19 | [5 empty] | 6 |  | 5 |  |  | 8
Mac | 8 | 24 | 22 |  |  | 2 |  |  |  |  | 8 |  |  | 12
Mai | 4 | 12 | 12 | [5 empty] | 12
Mos | 8 | 24 | 26 | 10 |  |  |  |  | 8 |  |  |  |  | 8
Nim | 8 | 24 | 21 | 3 |  |  |  |  | 10 |  |  |  |  | 8
Arm | 8 | 24 | 21 | 6 |  |  |  |  | 7 |  |  |  |  | 8
Total |  | 129 | 121 | 51 | 0 | 7 | 0 | 0 | 71 | 3 | 13 | 0 | 0 | 44
|  | 222 | 213 | [8 empty] | 0 | 12 | 44
Resource Plan – Sprint 26 1 Jun - 12 Jun | 183
Capacity SA รวม 81 SP | 60
Capacity รวม 162 SP | 123
Allocation each project (exclude PE) | 0
Allocation PE | 123 | 21
New Point Engine | 4 | 0
Vimi Termination |  | 0
Thana |  | 0
Datamart |  | 0
AWS |  | 0
Adhoc
Dev Support | 10
Name | Availability | Capacity | Total Workload | New PE | VIMI | Thana | Datamart | AWS | Adhoc | Dev Support | Ecom | PWP | VGI | Unified App | Samsung | Tech Debt | Tech Debt
Aek | 5 | 15 | 20 | 4 |  |  |  |  | 7 |  | 8 |  |  |  | 1
Aom | 5.5 | 16.5 | 30 | [5 empty] | 20 | [6 empty] | 10
Zan | 4.5 | 13.5 | 20 |  |  | 8 |  |  | 12
Jack | 5 | 15 | 15 | 7 | [9 empty] | 8
|  | 60 | 85
A | 7 | 21 | 20 | [5 empty] | 3 |  | 12 |  |  |  |  | 5
Mac | 7 | 21 | 20 |  |  | 17 |  |  | 3
Mai | 6 | 18 | 15 | 6 |  |  |  |  | 8 | 1
Mos | 7 | 21 | 12 | 9 |  | 3
Nim | 7 | 21 | 13 | 2 | 8 | [9 empty] | 3
Arm | 7 | 21 | 11 | 4 | [12 empty] | 7
Total |  | 123 | 91 | 32 | 8 | 28 | 0 | 0 | 53 | 1 | 12 | 0 | 0 | 0 | 3 | 5 | 7
|  | 183 | 176 | [7 empty] | 20 | 0 | 0 | 8 | 4 | 15 | 7
Resource Plan – Sprint 27 15 Jun - 26 Jun | 231
Capacity SA รวม 93 SP | 93
Capacity รวม 207 SP | 138
Allocation each project (exclude PE) | 0
Allocation PE | 138 | 4
New Point Engine |  | 0
Vimi Termination |  | 0
Thana |  | 0
Datamart |  | 0
AWS |  | 0
Adhoc
Dev Support | 19
Name | Availability | Capacity | Total Workload | New PE | VIMI | Thana | AWS | Adhoc | Dev Support | Ecom | PWP | VGI | Unified App | Samsung | Tech Debt
Aek | 7 | 21 | 24 | 1 |  |  |  | 5 |  | 8 |  |  | 2 | 8
Aom | 8 | 24 | 32 | 16 |  |  |  | 8 | [5 empty] | 8
Zan | 8 | 24 | 26 |  |  | 8 |  | 13 |  |  |  |  | 5
Jack | 8 | 24 | 24 | 8 |  |  |  | 5 |  |  |  | 3 | 8
|  | 93 | 106
A | 7 | 21 | 5 | [7 empty] | 5
Mac | 8 | 24 | 3 |  |  | 3
Mai | 8 | 24 | 5 | [7 empty] | 5
Mos | 8 | 24 | 4 | 4
Nim | 7 | 21 | 5 | [7 empty] | 5
Arm | 8 | 24 | 5 | [7 empty] | 5
Total |  | 138 | 27 | 29 | 0 | 11 | 0 | 31 | 0 | 0 | 20 | 0 | 0 | 0 | 0
|  | 231 | 133 | [7 empty] | 20 | 3 | 15 | 16 | 0

## Billing 2025
Service | Period | Date | Status | Billing | Billing Account | License | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
Miro | Yearly | 2026-09-26 | Active | Link | Aek | 5 Accounts | - | - | - | - | - | 60.99 | - | - | 960 | 182.61 | - | - | - | - | -
Mailchimp | Monthly | 12 | Active | Link | P'Tong, Aek, P'Su | 41 blocks | 520 | 560 | 620 | 620 | 700 | 780 | 896 | 676 | 676 | 676 | 676 | 676 | 676 | 676 | 676
Github | Monthly | 21 | Active | Link | Aek, A, Pui, Neung, P'Su |  | 150.99 | 131.18 | 120.39 | 96.09 | 149.76 | 105.12 | 103.78 | 110.78 | 97.66 | 129.79 | 125.91 | 123.63 | 119.64 | 139.68 | 151.29
Atlassian (Jira) | Monthly | 10 | Active | Link | P'Tong, Aek, A, P'Su |  | 424.4 | 414.8 | 414.8 | 391.4 | 408.4 | 440.06 | 906.36 | 1028.84 | 994.25 | 1006.66 | 1269.14 | 1391.2 | 1435.21 | 1179.92 | 1320.71
Uptime_robot | Yearly | 2026-09-18 | Active |  | Pui, Neung |  | - | - | - | - | - | - | - | - | 648 | - | - | - | - | - | -
Bitly | Yearly | 2026-06-29 | Active | Link | Aek, A |  | - | - | - | - | - | 96 | - | - | - | - | - | - | - | - | -
101domain.com (rbt.one) | Yearly | 2026-12-12 | Active | Link | P'Tong, Aek, A, P'Su |  | - | - | - | - | - | - | - | - | - | 38.19 | - | - | - | - | -
Cypress | Yearly | 2026-03-01 | Cancelled |  | Aek, A |  | - | - | 799 | - | - | - | - | - | - | - | - | - | - | - | -
Smartsheet | Monthly | 4 | Cancelled |  | P'Hym | - | 27 | 27 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | - | - | -
LINE OA | Monthly | 1 | Cancelled |  | P'Hym, Zan |  | - | - | - | - | - | - | 40 | 40 | - | - | - | - | - | - | -
Buffer Jira + 50% | [6 empty] | 212.2 | 207.4 | 207.4 | 195.7 | 204.2 | 220.03 | 453.18 | 514.42 | 497.125 | 503.33 | 634.57 | 695.6 | 717.605 | 589.96 | 660.355
[6 empty] | THB | 46710.65 | 46913.3 | 76915.65 | 46871.65 | 52442.6 | 60837 | 85236.2 | 84211.4 | 136816.225 | 90040.3 | 95956.7 | 102285.05 | 103195.925 | 90494.6 | 98292.425
JIra Users | [9 empty] | 17 | 18 | 24 | 42 | 42 | 39 | 35 | 40 | 45 | 46 | 41 | 42
Year 2025 | 1046680.075
GCloud | Monthly | 1 | Active |  | P'Yo, A |  | 7567.47 | 7037.99 | 7699.45 | 7753.38 | 9103.31 | 8970.96 | 9092.62 | 13186.36 | 22225.59 | 10667.12 | 10406.61 | 10888.43 | 11336.8 | 10323.53
GCloud | [5 empty] | THB | 264861.45 | 246329.65 | 269480.75 | 271368.3 | 318615.85 | 313983.6 | 318241.7 | 461522.6 | 777895.65 | 373349.2 | 364231.35 | 381095.05 | 396788 | 361323.55

## Forecast Billing 2026
Service | Period | Date | Status | Billing Account | License | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
Miro | Yearly | 2026-09-26 | Active | Aek | 5 Accounts | - | - | 60.99 | - | - | 960 | 182.61 | - | - | - | -
Mailchimp | Monthly | 12 | Active | P'Tong, Aek, P'Su | 41 blocks | 676 | 676 | 676 | 676 | 676 | 676 | 676 | 676 | 676 | 676 | 676 | 676
Github | Monthly | 21 | Active | Aek, A, Pui, Neung |  | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150
Atlassian | Monthly | 10 | Active | P'Tong, Aek, A, P'Su | 41 users | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500
Uptime_robot | Yearly | 2026-09-18 | Active | Pui, Neung |  | - | - | - | - | - | 648 | - | - | - | - | - | -
Bitly | Yearly | 2026-06-29 | Active | Aek, A |  | - | - | 96 | - | - | - | - | - | - | - | - | -
101domain.com (rbt.one) | Yearly | 2026-12-12 | Active | P'Tong, Aek, A, P'Su |  | - | - | - | - | - | - | 38.19 | - | - | - | - | -
AIS | Monthly | 23 | Active | 7200 | • 062-308-5741 • 062-308-5731 • 062-308-5725
Cursor AI | Monthly |  | To Do |  | 16 | 640 | 640 | 640 | 640 | 640 | 640 | 640 | 640 | 640 | 640 | 640 | 640
Buffer Jira + 50% | [5 empty] | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750
[5 empty] | THB | 130060 | 130060 | 135554.65 | 130060 | 130060 | 186340 | 137788 | 130060 | 130060 | 130060 | 130060 | 130060
JIra Users | [5 empty] | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 41
Year 2026 | 1637422.65
GCloud | Monthly | 1 | Active | P'Yo, A |  | 7753.38 | 9103.31 | 8970.96 | 9092.62 | 13186.36 | 22225.59 | 10667.12 | 10406.61 | 10888.43 | 11336.8 | 10323.53
GCloud |  |  |  |  | THB | 271368.3 | 318615.85 | 313983.6 | 318241.7 | 461522.6 | 777895.65 | 373349.2 | 364231.35 | 381095.05 | 396788 | 361323.55

## Summarize Sprint 26
Column 1 | Total Stories Point | Total Manhour | Point Done | Manhour Done | Note
18 May - 29 May
Dev Resource Available | 21 | 427
Meeting Planned |  |  |  |  | Ref
Additional Meeting |  |  |  |  | Ref
Deployment |  | 2 |  |  | 2 ครั้ง 1. 3 คน 2. 1 คน
Development Sprint Total | 425 | 472.17 | 121 | 136.17
Ad-hoc Mid Sprint | 0 | 0 | 0 | 0 | 2 tasks
Requirement changes after refinement? | 0 |  | 0 | 0 | 0 tasks
Aek | 33 | 47.5 | 13 | 15.5
A | 83 | 220 | 4 | 8
Aom | 35 | 0.67 | 17 | 0.67
Zan | 17 | 0 | 0 | 0
Mai | 32 | 52 | 11 | 28
Mac | 56 | 56 | 5 | 0
Mos | 51 | 86 | 39 | 74
Jack | 12 | 0 | 9 | 0
Nim | 41 | 8 | 12 | 8
Arm | 64 | 0 | 10 | 0

## Sprint 26
Issue Type | Issue key | Issue id | Summary | Assignee | Assignee Id | Reporter | Reporter Id | Priority | Status | Resolution | Created | Updated | Due date | Custom field (Story Points) | Labels | Labels | Labels | Labels | Labels | Original estimate | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint
Sub-task | DPE-700 | 54668 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | To Do |  | 12/Jun/26 4:33 PM | 12/Jun/26 4:33 PM | [8 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-699 | 54667 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | To Do |  | 12/Jun/26 4:33 PM | 12/Jun/26 4:33 PM | [8 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-698 | 54666 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | To Do |  | 12/Jun/26 4:33 PM | 12/Jun/26 4:33 PM | [8 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-697 | 54665 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | To Do |  | 12/Jun/26 4:33 PM | 12/Jun/26 4:33 PM | [8 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-696 | 54664 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | To Do |  | 12/Jun/26 4:33 PM | 12/Jun/26 4:33 PM | [8 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-695 | 54663 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | To Do |  | 12/Jun/26 4:33 PM | 12/Jun/26 4:33 PM | [8 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-694 | 54662 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 12/Jun/26 4:17 PM | 12/Jun/26 4:18 PM | [8 empty] | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-693 | 54661 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 12/Jun/26 4:17 PM | 12/Jun/26 4:18 PM | [8 empty] | [Dev][RD][New PE] Sprint 26
Story | DEVRDSUP-638 | 54659 | [SUP-734][Need support] ดึง Point จาก User คืน | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Highest | Done |  | 12/Jun/26 3:41 PM | 12/Jun/26 4:28 PM | 12/Jun/26 12:00 AM | 1 | hop | reverseTXN |  |  |  | 1800 | [Dev][All Project] Sprint 26
Story | DPE-692 | 54648 | [Dev][RD][PE Middleware] Enhance Get Offer List - Add Offer Type Filter | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 12/Jun/26 10:49 AM | 12/Jun/26 4:18 PM |  |  | point-engine-proxy | [5 empty] | [Dev][RD][New PE] Sprint 26
Bug | DPE-689 | 54599 | [S4][RR BOF] Offer name is updated when update the general details | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 10/Jun/26 5:05 PM | 11/Jun/26 1:34 PM | [8 empty] | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-688 | 54595 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 10/Jun/26 4:33 PM | 11/Jun/26 1:34 PM | [8 empty] | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-687 | 54594 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 10/Jun/26 4:33 PM | 10/Jun/26 4:48 PM | [8 empty] | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-686 | 54582 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 10/Jun/26 3:48 PM | 11/Jun/26 2:59 PM | [8 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | RDTHANA-518 | 54577 | [SA][RD][TDM] Prepare access control callback request example | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Review |  | 10/Jun/26 1:46 PM | 10/Jun/26 1:47 PM |  | 1 | [6 empty] | [Dev][RD][Thana] Sprint 26
Story | DEVRDSUP-633 | 54566 | [SUP-726][SUB] รบกวนออกแพ็กเกจ ปรับเป็น PAID(Confirmed) เรียบร้อย // Order ID: 20260608-0004808 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Thanakrit Chanthaworn | 712020:3fc982cb-c268-4f1d-9265-d3dd8fb08304 | Medium | Done |  | 09/Jun/26 6:03 PM | 12/Jun/26 2:00 PM | 12/Jun/26 12:00 AM | 1 | bts | prod-issue | sub |  |  | 600 | [Dev][All Project] Sprint 26
Story | RDAPS-494 | 54557 | [SA][RD] Prepare Callback payload |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 09/Jun/26 2:52 PM | 09/Jun/26 2:52 PM | [8 empty] | [Dev][All Project] Sprint 26
Story | RDAPS-493 | 54556 | [SA][RD] Prepare task sprint #27 - Zan | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Progress |  | 09/Jun/26 2:50 PM | 11/Jun/26 9:46 AM |  | 8 | [6 empty] | [Dev][All Project] Sprint 26
Story | DEV-16 | 54555 | [SA][RD][Tech Debt][HRS][DB] Coordinate Staging DB Instance Type Upgrade for Pre-Production Validation | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | To Do |  | 09/Jun/26 2:37 PM | 09/Jun/26 3:11 PM |  |  | DB | HRS | Staging | TechDebt |  |  | [Dev][RD][TechDebt] Sprint 26
Sub-task | DEV-15 | 54542 | [QA] Test Execution - UAT | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 08/Jun/26 6:11 PM | 08/Jun/26 6:11 PM | [8 empty] | [Dev][All Project] Sprint 24 | [Dev][RD][TechDebt] Sprint 25 | [Dev][RD][TechDebt] Sprint 26
Sub-task | DEV-14 | 54540 | [QA] Test Execution - STG | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 08/Jun/26 6:03 PM | 08/Jun/26 6:10 PM | [8 empty] | [Dev][All Project] Sprint 24 | [Dev][RD][TechDebt] Sprint 25 | [Dev][RD][TechDebt] Sprint 26
Sub-task | DPE-680 | 54539 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 08/Jun/26 6:01 PM | 09/Jun/26 4:28 PM | [8 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-679 | 54538 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 08/Jun/26 6:01 PM | 08/Jun/26 6:01 PM | [8 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-678 | 54537 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 08/Jun/26 6:01 PM | 09/Jun/26 3:37 PM | [8 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-677 | 54536 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 08/Jun/26 6:01 PM | 08/Jun/26 6:01 PM | [8 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DEVRDSUP-631 | 54535 | [QA] Retest - STG |  |  | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 08/Jun/26 5:58 PM | 08/Jun/26 6:02 PM | [8 empty] | [Dev][All Project] Sprint 24 | [Dev][All Project] Sprint 25 | [Dev][All Project] Sprint 26
Sub-task | DPE-676 | 54534 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 08/Jun/26 5:32 PM | 08/Jun/26 5:32 PM | [8 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-675 | 54533 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 08/Jun/26 5:32 PM | 08/Jun/26 5:32 PM | [8 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DEVRDSUP-630 | 54527 | [SUP-722]0880069567996 Line Pay (บัตรใหม่) แต่ระบบหลังบ้านเป็น RC ค่ะ จึงทำให้ลูกค้าไม่สามารถเติมเที่ยวเข้าบัตรได้ | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Thanakrit Chanthaworn | 712020:3fc982cb-c268-4f1d-9265-d3dd8fb08304 | Medium | Done |  | 08/Jun/26 5:21 PM | 12/Jun/26 2:00 PM | 11/Jun/26 12:00 AM | 1 | prod-issue | sub |  |  |  | 1800 | [Dev][All Project] Sprint 26
Story | DEVRDSUP-629 | 54520 | [SUP-721][Access SSO backoffice] Request to create new user N'Nampheung | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Thanakrit Chanthaworn | 712020:3fc982cb-c268-4f1d-9265-d3dd8fb08304 | Highest | Done |  | 08/Jun/26 2:35 PM | 12/Jun/26 2:00 PM | 08/Jun/26 12:00 AM | 1 | BURequest | sso-backoffice | sso-user |  |  | 600 | [Dev][All Project] Sprint 26
Story | DEVRDECOM-254 | 54514 | [DEV][RD][Ecom][Gustron][SA] Impact analysis - guest checkout without Rabbit Connect login | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Progress |  | 08/Jun/26 1:16 PM | 12/Jun/26 9:24 AM |  | 2 | Gustron | impact-analysis | SA |  |  |  | [Dev][RD][Ecom] Sprint 26
Sub-task | DPE-674 | 54507 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 08/Jun/26 10:49 AM | 08/Jun/26 11:20 AM | [8 empty] | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-673 | 54506 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 08/Jun/26 10:49 AM | 08/Jun/26 11:20 AM | [8 empty] | [Dev][RD][New PE] Sprint 26
Story | DPE-672 | 54505 | [Dev][RD][PE Proxy Scheduler] Implement Discord notification after each command processed | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 08/Jun/26 10:38 AM | 12/Jun/26 10:00 AM |  |  | point-engine-proxy-scheduler | [5 empty] | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-671 | 54503 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 08/Jun/26 9:48 AM | 08/Jun/26 9:49 AM | [8 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-670 | 54496 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 06/Jun/26 1:31 AM | 08/Jun/26 3:06 PM | [8 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-669 | 54495 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 06/Jun/26 1:31 AM | 06/Jun/26 1:31 AM | [8 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DEVRDSUP-627 | 54488 | [SUP-719][Turtle][PL] Request to resend failed point issue TXN to resolve user's complain. The point issue TXN from POS was failed. | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 05/Jun/26 3:47 PM | 12/Jun/26 2:00 PM | 09/Jun/26 12:00 AM | 1 | partner-loyalty | turtle |  |  |  | 900 | [Dev][All Project] Sprint 26
Bug | DEVRDSUP-626 | 54483 | [SUP-712]Review of Turtle Coupon Data, missing coupon data on 21&24 May 2026. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Highest | RETESTING |  | 05/Jun/26 11:39 AM | 12/Jun/26 1:04 PM | 12/Jun/26 12:00 AM |  | data | sub | turtle |  |  |  | [Dev][All Project] Sprint 26
Sub-task | DPE-667 | 54482 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 05/Jun/26 11:33 AM | 05/Jun/26 11:34 AM | [8 empty] | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-666 | 54481 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 05/Jun/26 11:33 AM | 05/Jun/26 11:34 AM | [8 empty] | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-665 | 54480 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 05/Jun/26 11:33 AM | 05/Jun/26 11:34 AM | [8 empty] | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-664 | 54479 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 05/Jun/26 11:33 AM | 05/Jun/26 11:34 AM | [8 empty] | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Bug | DPE-663 | 54477 | [S3][NPE] Unable to credit/debit points when using an offer containing special characters | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Solution Proposal Pending |  | 05/Jun/26 10:36 AM | 05/Jun/26 1:56 PM | [8 empty] | [Dev][RD][New PE] Sprint 26
Story | DPE-662 | 54473 | [Dev][RD][BOF] Improve product creation | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 05/Jun/26 9:48 AM | 12/Jun/26 10:00 AM |  |  | rr-backoffice | [5 empty] | [Dev][RD][New PE] Sprint 26
Story | DPE-661 | 54466 | [Dev][RD][PE Middleware] Prevent Debit/Credit Transaction Creation When Offer Name Is Missing | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 04/Jun/26 2:41 PM | 12/Jun/26 1:29 PM | 12/Jun/26 12:00 AM | 3 | point-engine-proxy |  |  |  |  | 28800 | [Dev][RD][New PE] Sprint 26
Story | DEVRDSUP-623 | 54444 | [SUP-713][SUB] : Request to export receipt due to Incomplete Emails Received by BTSC (MAY26) | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Done |  | 02/Jun/26 5:35 PM | 12/Jun/26 2:00 PM | 05/Jun/26 12:00 AM | 1 | sub |  |  |  |  | 7200 | [Dev][All Project] Sprint 26
Sub-task | RDAPS-492 | 54443 | [QA] Test Execution Verify Enhance clear member card cache after add card success | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 02/Jun/26 2:53 PM | 02/Jun/26 5:30 PM | [8 empty] | [Dev][All Project] Sprint 25 | [Dev][All Project] Sprint 26
Sub-task | DPE-660 | 54440 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 02/Jun/26 1:57 PM | 05/Jun/26 4:17 PM | [8 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-659 | 54439 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 02/Jun/26 1:57 PM | 04/Jun/26 4:56 PM | [8 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Bug | DEVRDSUP-622 | 54438 | [SUP-714][Incident] – Member Data Import Issue ¦ Member imported but SSO is not mapped. | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Highest | Closed |  | 02/Jun/26 1:11 PM | 12/Jun/26 1:04 PM | 02/Jun/26 12:00 AM |  | hop | hr-solution |  |  |  |  | [Dev][All Project] Sprint 26
Sub-task | DEVRDSUP-621 | 54437 | [SODA] Update config file for RR DevOps | Soda Team | 712020:c2762549-600f-4b8e-80d0-86600ba589a5 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 02/Jun/26 11:57 AM | 02/Jun/26 2:28 PM | [8 empty] | [Dev][All Project] Sprint 26
Sub-task | DEVRDSUP-620 | 54436 | [DevOps] Switch periodically at 9AM on Tuesday from 2June - 21July 2026. | Pui Wigrom Naddakul | 61d40990ce3652006ab55354 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | In Progress |  | 02/Jun/26 11:56 AM | 05/Jun/26 1:35 PM | [8 empty] | [Dev][All Project] Sprint 26
Story | DEVRDSUP-619 | 54435 | [SUP-715][UAT] Request to switch API from CleverTap's loyalty to uLoyalty for ST team for training. Switch on every Tuesday 9AM-12PM until end of July26. | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | In Progress |  | 02/Jun/26 11:50 AM | 12/Jun/26 2:00 PM | 21/Jul/26 12:00 AM |  | app | turtle |  |  |  |  | [Dev][All Project] Sprint 26
Story | RDTHANA-510 | 54418 | [DEV][RD][TDM] Callback API x FITNESS_IN event | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 02/Jun/26 9:42 AM | 11/Jun/26 5:07 PM | 05/Jun/26 12:00 AM | 2 | [6 empty] | [Dev][RD][Thana] Sprint 26
Story | RDTHANA-509 | 54417 | [DEV][RD][TDM] Callback API x GATE_OUT event | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 02/Jun/26 9:41 AM | 11/Jun/26 5:07 PM | 05/Jun/26 12:00 AM | 2 | [6 empty] | [Dev][RD][Thana] Sprint 26
Story | RDTHANA-508 | 54416 | [DEV][RD][TDM] Callback API x GATE_IN event | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 02/Jun/26 9:41 AM | 11/Jun/26 5:07 PM | 04/Jun/26 12:00 AM | 3 | [6 empty] | [Dev][RD][Thana] Sprint 26
Story | RDTHANA-507 | 54415 | [DEV][RD][POC] Shopify Data | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 02/Jun/26 9:20 AM | 12/Jun/26 9:30 AM | [8 empty] | [Dev][RD][Thana] Sprint 26
Story | DRST-102 | 54414 | [DEV][RD][VIMI] Remove BTS daily + ScheduleService (MyCity only) | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 02/Jun/26 9:04 AM | 12/Jun/26 1:46 PM |  | 3 | [6 empty] | [Dev RD][VIMI Termi] Sprint 26
Story | DRST-101 | 54413 | [DEV][RD][VIMI] Remove subscription transaction export PG (subscriptions_report) | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 02/Jun/26 9:03 AM | 12/Jun/26 1:46 PM |  | 2 | No-QA | [5 empty] | [Dev RD][VIMI Termi] Sprint 26
Story | DRST-100 | 54412 | [DEV][RD][VIMI] Remove subscription coupon import (subscriptions_product) | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 02/Jun/26 9:03 AM | 12/Jun/26 1:46 PM |  | 1 | No-QA | [5 empty] | [Dev RD][VIMI Termi] Sprint 26
Sub-task | DPE-658 | 54411 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 01/Jun/26 5:38 PM | 05/Jun/26 4:24 PM | [8 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-657 | 54410 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 01/Jun/26 5:38 PM | 04/Jun/26 4:56 PM | [8 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-656 | 54409 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 01/Jun/26 5:38 PM | 05/Jun/26 4:24 PM | [8 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-655 | 54408 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 01/Jun/26 5:38 PM | 05/Jun/26 4:56 PM | [8 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-654 | 54407 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 01/Jun/26 5:38 PM | 04/Jun/26 4:56 PM | [8 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-653 | 54406 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 01/Jun/26 5:38 PM | 04/Jun/26 4:56 PM | [8 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-652 | 54405 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 01/Jun/26 5:38 PM | 05/Jun/26 4:56 PM | [8 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-651 | 54404 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 01/Jun/26 5:38 PM | 04/Jun/26 4:56 PM | [8 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | RDTHANA-506 | 54402 | [DEV][RD][POC] Shopify x Clevertrap | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Review |  | 01/Jun/26 4:52 PM | 12/Jun/26 1:53 PM | 12/Jun/26 12:00 AM | 5 | [6 empty] | [Dev][RD][Thana] Sprint 26
Story | DRST-99 | 54398 | [DEV][RD][VIMI] Remove e-receipt export (MyCity + S3 subscription) | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 01/Jun/26 4:04 PM | 12/Jun/26 1:46 PM |  | 2 | No-QA | [5 empty] | [Dev RD][VIMI Termi] Sprint 26
Story | RDAPS-490 | 54389 | [SA][RD] Meeting Sprint 26 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 01/Jun/26 10:37 AM | 02/Jun/26 10:07 AM | 12/Jun/26 12:00 AM | 5 | [6 empty] | [Dev][All Project] Sprint 26
Epic | RDAPS-489 | 54388 | [SA][RD] Meeting Sprint 26 |  |  | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | To Do |  | 01/Jun/26 10:36 AM | 01/Jun/26 10:36 AM | [8 empty] | [Dev][All Project] Sprint 26
Epic | RDAPS-488 | 54387 | [SA][RD] Meeting Sprint 26 |  |  | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | To Do |  | 01/Jun/26 10:35 AM | 01/Jun/26 10:35 AM | [8 empty] | [Dev][All Project] Sprint 26
Sub-task | DPE-649 | 54385 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 01/Jun/26 10:29 AM | 01/Jun/26 2:48 PM | [8 empty] | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-648 | 54384 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 01/Jun/26 10:28 AM | 01/Jun/26 10:45 AM | [8 empty] | [Dev][RD][New PE] Sprint 26
Story | DEVRDECOM-253 | 54375 | [DEV][RD][Ecom][Gustron][POC] Banner auto login from RR app (Browser Share Session Cookie) | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Low | In Review |  | 31/May/26 7:14 AM | 12/Jun/26 9:24 AM | 09/Jun/26 12:00 AM | 5 | No-QA | poc | rr-ecommerce-shopify |  |  | 57600 | [Dev][RD][Ecom] Sprint 26
Story | RDAPS-487 | 54344 | [SA][RD] Prepare task for sprint 27 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 29/May/26 5:09 PM | 12/Jun/26 2:55 PM |  | 1 | [5 empty] | 7200 | [Dev][All Project] Sprint 26
Story | RDAPS-486 | 54343 | [SA][RD] Team Support & Management Sprint 26 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 29/May/26 5:08 PM | 12/Jun/26 10:13 AM |  | 3 | [5 empty] | 28800 | [Dev][All Project] Sprint 26
Story | RDAPS-485 | 54342 | [SA][RD] Meeting Sprint 26 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 29/May/26 5:08 PM | 12/Jun/26 10:14 AM |  | 2 | [5 empty] | 14400 | [Dev][All Project] Sprint 26
Story | RDAPS-484 | 54341 | [Dev][RD][Adhoc] Open DevOps ticket for Lens access (Staging & UAT) | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Review |  | 29/May/26 4:41 PM | 12/Jun/26 1:51 PM |  | 1 | access | devops | lens | staging | uat |  | [Dev][All Project] Sprint 26
Story | RDTHANA-505 | 54339 | [DEV][RD][TDM] Integrate queue and retry to coin revoke api | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 29/May/26 3:23 PM | 11/Jun/26 5:07 PM | 12/Jun/26 12:00 AM | 3 | No-QA |  |  |  |  | 28800 | [Dev][RD][Thana] Sprint 26
Story | RDTHANA-504 | 54338 | [DEV][RD][TDM] Log invalid generic transaction requests to S3 | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 29/May/26 2:46 PM | 11/Jun/26 5:07 PM | 09/Jun/26 12:00 AM | 5 | [6 empty] | [Dev][RD][Thana] Sprint 26
Story | DEVRDSS-12 | 54334 | [SA][RD][Samsung] Sync up with BSS teams | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 29/May/26 10:40 AM | 12/Jun/26 12:53 PM |  | 2 | [6 empty] | [Dev][RD][Samsung] Sprint 26
Story | RDAPS-483 | 54330 | [Dev][RD][Adhoc] Update GCloud Cost for Rcash, RR, and BSS Tabs in Cost Tracking Google Sheet for May | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 29/May/26 8:40 AM | 12/Jun/26 1:51 PM | 03/Jun/26 12:00 AM | 1 | cost-management | finance | gcloud | report |  | 7200 | [Dev][All Project] Sprint 26
Story | DEVRDUA-1 | 54323 | [SA][RD][Unified App] Assess project feasibility and implementation options | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Progress |  | 28/May/26 5:38 PM | 12/Jun/26 10:27 AM |  |  | architecture | feasibility | sa | unified-app |  |  | [Dev][RD][Unified] Sprint 26
Story | RDTHANA-503 | 54322 | [DEV][RD][TDM] Add is_legacy to callback API | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 28/May/26 5:16 PM | 11/Jun/26 5:07 PM | 29/May/26 12:00 AM | 1 | [6 empty] | [Dev][RD][Thana] Sprint 25 | [Dev][RD][Thana] Sprint 26
Story | DEV-12 | 54321 | [DEV][RD][TechDebt] Provide RR Operation & Incident API matrix in central sheet | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Review |  | 28/May/26 5:12 PM | 12/Jun/26 1:04 PM | 04/Jun/26 12:00 AM | 5 | api-mapping | devops | incident | operations |  | 57600 | [Dev][RD][TechDebt] Sprint 26
Story | DEVRDECOM-252 | 54320 | [Dev][RD][Ecom][Turtle] Auto prefill location/phone and branch | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | To Do |  | 28/May/26 4:16 PM | 12/Jun/26 4:31 PM |  | 8 | [6 empty] | [Dev][RD][Ecom] Sprint 26
Story | DEVRDECOM-251 | 54312 | [DEV][RD][Ecom] Filter unnecessary logs to reduce observability cost | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | High | Done |  | 28/May/26 3:02 PM | 12/Jun/26 9:24 AM | 05/Jun/26 12:00 AM | 2 | cost-optimization | log-filtering |  |  |  | 14400 | [Dev][RD][Ecom] Sprint 26
Story | RDAPS-482 | 54310 | [Dev][RD][Adhoc][HR Solution] Turtle Upgrade/Downgrade tier batch | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 28/May/26 2:19 PM | 11/Jun/26 5:07 PM | 08/Jun/26 12:00 AM | 8 | [5 empty] | 86400 | [Dev][All Project] Sprint 26
Story | DEVRRBOF-211 | 54308 | [Dev][RD][Order API][SUB] Support crm_case_ref and crm_note on POST /v1/orders/update for Payment Inquiry | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 28/May/26 1:51 PM | 12/Jun/26 12:57 PM | 11/Jun/26 12:00 AM | 3 | [6 empty] | [Dev][RD][BOF] Sprint 26
Story | DPE-646 | 54304 | [Dev][RD][CT] Adjust config MAU filtering | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 28/May/26 1:45 PM | 12/Jun/26 10:01 AM | 12/Jun/26 12:00 AM | 1 | CleverTap | No-QA |  |  |  |  | [Dev][RD][New PE] Sprint 26
Bug | DEVRDSUP-613 | 54302 | [SUP-703]"Point_Issued" events duplicate data in Clevertap | Pan:Paliwan Boonhian | 62e8dfd1432ef494c8c98577 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Closed |  | 28/May/26 1:08 PM | 12/Jun/26 10:20 AM | 16/Jun/26 12:00 AM |  | CleverTap | prod-issue |  |  |  |  | [Dev][All Project] Sprint 26
Bug | DEVRDSUP-612 | 54301 | [SUP-702]"checkin" events are also being recorded as "charged" events in Clevertap | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Enhancement |  | 28/May/26 1:06 PM | 12/Jun/26 1:04 PM | 16/Jun/26 12:00 AM | [7 empty] | [Dev][All Project] Sprint 26
Story | DEVRDSUP-611 | 54299 | [SUP-701][Need Support] BTSG – Import User (Employee ID เปลี่ยน) | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Highest | Done |  | 28/May/26 11:48 AM | 12/Jun/26 2:00 PM | 29/May/26 12:00 AM |  | hop | hr-solution |  |  |  |  | [Dev][All Project] Sprint 25 | [Dev][All Project] Sprint 26
Story | DEVRDSUP-610 | 54298 | [SUP-706][SSO][Access] Request SSO back office access for HOP AE 28/05/2026 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 28/May/26 11:36 AM | 12/Jun/26 2:00 PM | 11/Jun/26 12:00 AM | 1 | [5 empty] | 300 | [Dev][All Project] Sprint 26
Story | RDAPS-481 | 54294 | [Dev][RD][Adhoc] Estimate Point expire 2026 - Donation | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 28/May/26 9:52 AM | 12/Jun/26 1:51 PM |  | 2 | [6 empty] | [Dev][All Project] Sprint 26
Story | DPE-645 | 54292 | [Dev][RD][BFF] Revise transaction type filter logic for earn / burn history | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 28/May/26 7:37 AM | 12/Jun/26 1:29 PM |  | 1 | BFF | [5 empty] | [Dev][RD][New PE] Sprint 26
Story | DEVRDSUP-605 | 54238 | [SUP-697]Group Rewards - Lucky Draw Apple_Jun26 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 26/May/26 2:43 PM | 12/Jun/26 2:00 PM | 04/Jun/26 12:00 AM | 1 | BURequest | groupReward | rem |  |  | 1800 | [Dev][All Project] Sprint 25 | [Dev][All Project] Sprint 26
Story | DPE-627 | 54234 | [Dev][RD][UAT][Line Pay Web] Prepare code and environment for UAT | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 26/May/26 2:17 PM | 12/Jun/26 10:26 AM |  | 1 | [6 empty] | [Dev][RD][New PE] Sprint 26
Story | DPE-626 | 54233 | [Dev][RD][UAT][Line Pay API] Prepare code and environment for UAT | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 26/May/26 2:17 PM | 12/Jun/26 10:26 AM |  | 1 | [6 empty] | [Dev][RD][New PE] Sprint 26
Story | DPE-625 | 54232 | [Dev][RD][UAT][RR Issue Point Function] Prepare code and environment for UAT | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 26/May/26 2:17 PM | 12/Jun/26 10:26 AM |  | 2 | [6 empty] | [Dev][RD][New PE] Sprint 26
Story | DPE-624 | 54231 | [Dev][RD][UAT][RR CleverTap Service] Prepare code and environment for UAT | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 26/May/26 2:17 PM | 12/Jun/26 10:26 AM |  | 2 | [6 empty] | [Dev][RD][New PE] Sprint 26
Story | DPE-623 | 54230 | [Dev][RD][UAT][RR Athena Service] Prepare code and environment for UAT | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 26/May/26 2:17 PM | 12/Jun/26 10:26 AM |  | 2 | [6 empty] | [Dev][RD][New PE] Sprint 26
Story | DPE-622 | 54229 | [Dev][RD][UAT][RR Cronjob] Prepare code and environment for UAT | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 26/May/26 2:17 PM | 12/Jun/26 10:26 AM |  | 1 | [6 empty] | [Dev][RD][New PE] Sprint 26
Story | DPE-621 | 54228 | [Dev][RD][UAT][RR Scheduler] Prepare code and environment for UAT | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 26/May/26 2:17 PM | 12/Jun/26 10:00 AM |  | 1 | [6 empty] | [Dev][RD][New PE] Sprint 26
Story | DPE-620 | 54227 | [Dev][RD][UAT][Redemption Consumer] Prepare code and environment for UAT | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 26/May/26 2:16 PM | 12/Jun/26 10:26 AM |  | 2 | [5 empty] | 0 | [Dev][RD][New PE] Sprint 26
Story | DPE-619 | 54226 | [Dev][RD][UAT][RR Member] Prepare code and environment for UAT | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 26/May/26 2:16 PM | 12/Jun/26 10:26 AM | [8 empty] | [Dev][RD][New PE] Sprint 26
Story | DPE-618 | 54225 | [Dev][RD][UAT][RR Member Acquisition] Prepare code and environment for UAT | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 26/May/26 2:16 PM | 12/Jun/26 10:26 AM | [8 empty] | [Dev][RD][New PE] Sprint 26
Story | DPE-617 | 54224 | [Dev][RD][UAT][RR Voucher Validator] Prepare code and environment for UAT | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 26/May/26 2:16 PM | 12/Jun/26 10:26 AM | [8 empty] | [Dev][RD][New PE] Sprint 26
Story | DPE-616 | 54223 | [Dev][RD][UAT][HR Solution] Prepare code and environment for UAT | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 26/May/26 2:16 PM | 12/Jun/26 10:26 AM | [8 empty] | [Dev][RD][New PE] Sprint 26
Story | DPE-615 | 54222 | [Dev][RD][UAT][Rabbit Sky Frontend] Prepare code and environment for UAT | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 26/May/26 2:16 PM | 12/Jun/26 10:26 AM | [8 empty] | [Dev][RD][New PE] Sprint 26
Story | DPE-614 | 54221 | [Dev][RD][UAT][Rabbit Sky API] Prepare code and environment for UAT | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 26/May/26 2:16 PM | 12/Jun/26 10:26 AM | [8 empty] | [Dev][RD][New PE] Sprint 26
Story | DPE-613 | 54220 | [Dev][RD][UAT][RR Pay with Point API] Prepare code and environment for UAT | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | To Do |  | 26/May/26 2:16 PM | 12/Jun/26 10:26 AM | [8 empty] | [Dev][RD][New PE] Sprint 26
Story | DPE-612 | 54219 | [Dev][RD][UAT][RR Aphrodite] Prepare code and environment for UAT | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 26/May/26 2:15 PM | 12/Jun/26 10:26 AM |  | 2 | [6 empty] | [Dev][RD][New PE] Sprint 26
Story | DPE-611 | 54218 | [Dev][RD][UAT][GoUtil] Prepare code and environment for UAT | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 26/May/26 2:15 PM | 12/Jun/26 10:26 AM |  | 2 | [6 empty] | [Dev][RD][New PE] Sprint 26
Story | DPE-610 | 54217 | [Dev][RD][UAT][RR Ecommerce Shopify] Prepare code and environment for UAT | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 26/May/26 2:15 PM | 12/Jun/26 10:26 AM |  | 2 | [6 empty] | [Dev][RD][New PE] Sprint 26
Story | DPE-609 | 54216 | [Dev][RD][UAT][RR BackOffice] Prepare code and environment for UAT | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 26/May/26 2:15 PM | 12/Jun/26 10:26 AM |  | 2 | [6 empty] | [Dev][RD][New PE] Sprint 26
Story | DPE-608 | 54215 | [Dev][RD][UAT][Redemption API] Prepare code and environment for UAT | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 26/May/26 2:15 PM | 12/Jun/26 10:26 AM |  | 2 | [5 empty] | 0 | [Dev][RD][New PE] Sprint 26
Story | DPE-607 | 54214 | [Dev][RD][UAT][RR Order Service] Prepare code and environment for UAT | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 26/May/26 2:15 PM | 12/Jun/26 10:26 AM |  | 2 | [6 empty] | [Dev][RD][New PE] Sprint 26
Story | DPE-606 | 54213 | [Dev][RD][UAT][Partner Loyalty API] Prepare code and environment for UAT | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 26/May/26 2:15 PM | 12/Jun/26 10:26 AM | [8 empty] | [Dev][RD][New PE] Sprint 26
Story | DPE-605 | 54212 | [Dev][RD][UAT][Rabbit CMS API] Prepare code and environment for UAT | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 26/May/26 2:15 PM | 12/Jun/26 10:00 AM | [8 empty] | [Dev][RD][New PE] Sprint 26
Story | DPE-604 | 54211 | [Dev][RD][UAT][Exclusive Store API] Prepare code and environment for UAT | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 26/May/26 2:15 PM | 12/Jun/26 10:00 AM | [8 empty] | [Dev][RD][New PE] Sprint 26
Story | DPE-603 | 54210 | [Dev][RD][UAT][Point Engine Proxy Scheduler] Prepare code and environment for UAT | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 26/May/26 2:15 PM | 12/Jun/26 10:29 AM |  | 3 | [6 empty] | [Dev][RD][New PE] Sprint 26
Story | DPE-602 | 54209 | [Dev][RD][UAT][Point Engine Proxy API] Prepare code and environment for UAT | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 26/May/26 2:14 PM | 12/Jun/26 10:26 AM |  | 3 | [6 empty] | [Dev][RD][New PE] Sprint 26
Story | DPE-601 | 54208 | [Dev][RD][UAT][BFF] Prepare code and environment for UAT | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 26/May/26 2:14 PM | 12/Jun/26 10:26 AM |  | 2 | [5 empty] | 0 | [Dev][RD][New PE] Sprint 26
Story | DPE-600 | 54207 | [Dev][RD][UAT][SSO] Prepare code and environment for UAT | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 26/May/26 2:08 PM | 12/Jun/26 10:26 AM | 12/Jun/26 12:00 AM | 1 | No-QA |  |  |  |  | 7200 | [Dev][RD][New PE] Sprint 26
Story | DEVRRBOF-209 | 54205 | [Dev][RD][SUB] Payment inquiry button on package TXN detail for initiating package once the payment is confirmed | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 26/May/26 1:53 PM | 12/Jun/26 12:57 PM |  | 5 | [6 empty] | [Dev][RD][BOF] Sprint 26
Story | DEVRRBOF-208 | 54204 | [Dev][RD][SUB] Toggle on/off radio button for Credit / Debit Card Payment Method | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 26/May/26 1:52 PM | 12/Jun/26 12:57 PM |  | 2 | [6 empty] | [Dev][RD][BOF] Sprint 26
Story | DEV-10 | 54186 | [DEV][RD][HRS] Enhance package issue on Local | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 26/May/26 10:26 AM | 02/Jun/26 10:04 AM | 01/Jun/26 12:00 AM | 3 | [5 empty] | 28800 | [Dev][RD][TechDebt] Sprint 25 | [Dev][RD][TechDebt] Sprint 26
Story | RDTHANA-501 | 54158 | [DEV][RD][TDM] Generic Transaction — Enum others + {field}_note | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 22/May/26 11:17 AM | 11/Jun/26 5:07 PM | 02/Jun/26 12:00 AM | 3 | [6 empty] | [Dev][RD][Thana] Sprint 26
Story | DPE-597 | 54154 | [Dev][RD][PE Proxy Scheduler] Implement Discord Error Notifications | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 22/May/26 9:17 AM | 12/Jun/26 10:00 AM |  |  | No-QA | point-engine-proxy-scheduler |  |  |  |  | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DEV-9 | 54151 | [SA][RD][Tech Debt] Investigate and Fix Daily Sales Tracking Receipt ID not gen | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 21/May/26 5:04 PM | 11/Jun/26 5:18 PM |  | 5 | [6 empty] | [Dev][RD][TechDebt] Sprint 26
Story | DEV-8 | 54148 | [SA][RD][Tech Debt][AppPerf] Prepare Agenda & Pre-requirements for Soda Team Alignment Meeting | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 21/May/26 4:06 PM | 12/Jun/26 1:04 PM |  | 5 | [6 empty] | [Dev][RD][TechDebt] Sprint 26
Story | DEV-7 | 54141 | [DEV][RD][Tech Debt][Algolia] Optimize Algolia usage |  |  | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | To Do |  | 21/May/26 2:41 PM | 21/May/26 2:42 PM | [8 empty] | [Dev][RD][TechDebt] Sprint 26
Story | DEV-6 | 54140 | [SA][RD][Tech Debt][Algolia] Discussion with Soda | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | To Do |  | 21/May/26 2:40 PM | 21/May/26 2:41 PM | [8 empty] | [Dev][RD][TechDebt] Sprint 26
Bug | DEVRDSUP-599 | 54132 | [SUP-643]Event Charged in Clevertap and data format mismatch | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Thanakrit Chanthaworn | 712020:3fc982cb-c268-4f1d-9265-d3dd8fb08304 | Medium | Closed |  | 21/May/26 9:57 AM | 12/Jun/26 1:04 PM |  |  | partner-loyalty | [5 empty] | [Dev][All Project] Sprint 25 | [Dev][All Project] Sprint 26
Bug | DEVRDSUP-596 | 54091 | [SUP-689]NBO][Rewards][Subscription] - Upload code double | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Low | Resolved |  | 20/May/26 5:12 PM | 12/Jun/26 1:04 PM | 25/Jun/26 12:00 AM |  | rem | sub |  |  |  |  | [Dev][All Project] Sprint 25 | [Dev][All Project] Sprint 26
Bug | DEVRDSUP-595 | 54089 | [SUP-688]Event properties are not appearing in the user profile | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Thanakrit Chanthaworn | 712020:3fc982cb-c268-4f1d-9265-d3dd8fb08304 | Medium | Closed |  | 20/May/26 4:47 PM | 12/Jun/26 1:32 PM | 09/Jun/26 12:00 AM |  | CleverTap | prod-issue | rr-app |  |  |  | [Dev][All Project] Sprint 25 | [Dev][All Project] Sprint 26
Story | DEVRDSUP-594 | 54087 | [SUP-625][RR Member Account] CS-20260300026232 // Cannot add RC into RR Member account [RD SSO show- "Rabbit card already in use." / Member ID 30245337 | Game (Krittapas Tanaprasitpattana) | 712020:85e9f474-8ee8-45ba-9249-cde16fa1cd35 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 20/May/26 4:35 PM | 09/Jun/26 10:27 AM | 22/Jun/26 12:00 AM | 1 | [5 empty] | 7200 | [Dev][All Project] Sprint 25 | [Dev][All Project] Sprint 26
Story | DEV-5 | 54037 | [DEV][RD][TechDebt] Enhance command re register support by options | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 18/May/26 1:45 PM | 11/Jun/26 5:20 PM | 20/May/26 12:00 AM |  | hr-solution | No-QA |  |  |  |  | [Dev][RD][TechDebt] Sprint 25 | [Dev][RD][TechDebt] Sprint 26
Story | RDTHANA-493 | 54033 | [DEV][RD][TDM][POC] Get Shopify data for BU Dashboard | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 18/May/26 10:43 AM | 02/Jun/26 9:19 AM | 26/May/26 12:00 AM | 8 | No-QA |  |  |  |  | 86400 | [Dev][RD][Thana] Sprint 25 | [Dev][RD][Thana] Sprint 26
Story | RDTHANA-492 | 54027 | [DEV][RD][TDM] Enhance Generic transaction | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 18/May/26 9:56 AM | 02/Jun/26 9:19 AM | 19/May/26 12:00 AM | 1 | No-QA |  |  |  |  | 7200 | [Dev][RD][Thana] Sprint 25 | [Dev][RD][Thana] Sprint 26
Story | DPE-579 | 54025 | [DEV][RD][NPE] Investigate member count discrepancy between DA and RD due to email matching issues | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Review |  | 18/May/26 9:43 AM | 02/Jun/26 11:11 AM |  | 8 | [6 empty] | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DEVRDSS-11 | 53973 | [DEV][RD][Samsung][SSO-Backoffice] Update RR profile cards list to show multiple cloud cards | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready to Staging |  | 15/May/26 8:06 PM | 12/Jun/26 12:52 PM |  | 3 | [6 empty] | [Dev][RD][Samsung] Sprint 25 | [Dev][RD][Samsung] Sprint 26
Story | DEVRDSS-10 | 53972 | [DEV][RD][Samsung][CloudID] Enhance updateLastStatus and send data to CleverTap | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Progress |  | 15/May/26 7:11 PM | 12/Jun/26 12:53 PM |  | 3 | [6 empty] | [Dev][RD][Samsung] Sprint 26
Story | DEVRDSS-9 | 53971 | [DEV][RD][Samsung][CloudID] Update endpoint tokens/latest path to V2 | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready to Staging |  | 15/May/26 7:01 PM | 12/Jun/26 12:53 PM |  | 3 | [6 empty] | [Dev][RD][Samsung] Sprint 25 | [Dev][RD][Samsung] Sprint 26
Story | DEVRDSS-6 | 53970 | [DEV][RD][Samsung][CloudID] Create v2 API for Get User Cards with Multiple Cards Support | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready to Staging |  | 15/May/26 6:57 PM | 12/Jun/26 12:53 PM | 20/May/26 12:00 AM | 3 | [5 empty] | 28800 | [Dev][RD][Samsung] Sprint 25 | [Dev][RD][Samsung] Sprint 26
Story | DEVRDSS-7 | 53968 | [DEV][RD][Samsung][SSO] Enhance API get card list | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready to Staging |  | 15/May/26 6:37 PM | 12/Jun/26 12:53 PM | 27/May/26 12:00 AM | 5 | [5 empty] | 57600 | [Dev][RD][Samsung] Sprint 25 | [Dev][RD][Samsung] Sprint 26
Story | DEVRDSS-8 | 53967 | [DEV][RD][Samsung][BFF] Enhance API get card list | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready to Staging |  | 15/May/26 6:37 PM | 12/Jun/26 12:53 PM | 29/May/26 12:00 AM | 2 | [5 empty] | 14400 | [Dev][RD][Samsung] Sprint 25 | [Dev][RD][Samsung] Sprint 26
Story | RDAPS-467 | 53897 | [DEV][RD][BFF] Enhance clear member card cache after add card success | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 14/May/26 3:35 PM | 12/Jun/26 1:51 PM |  | 2 | [6 empty] | [Dev][All Project] Sprint 25 | [Dev][All Project] Sprint 26
Story | DEVRDECOM-248 | 53892 | [DEV][RD][Ecom][Gustron][POC] Banner auto login from RR app (SSO Bootstrap / One-time Ticket) | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Low | In Progress |  | 14/May/26 2:40 PM | 12/Jun/26 11:02 AM | 11/Jun/26 12:00 AM | 5 | No-QA | poc | rr-ecommerce-shopify |  |  | 57600 | [Dev][RD][Ecom] Sprint 26
Story | RDTHANA-491 | 53889 | [DEV][RD][TDM] Enhance generic transaction support more payment type | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 14/May/26 2:02 PM | 02/Jun/26 9:19 AM | 19/May/26 12:00 AM | 1 | [5 empty] | 7200 | [Dev][RD][Thana] Sprint 25 | [Dev][RD][Thana] Sprint 26
Story | DEV-2 | 53859 | [DEV][RD][Tech Debt][SSO] Improve performance (Relational) | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 14/May/26 9:24 AM | 02/Jun/26 10:04 AM | 15/May/26 12:00 AM | 1 | [5 empty] | 7200 | [Dev][RD][TechDebt] Sprint 24 | [Dev][RD][TechDebt] Sprint 25 | [Dev][RD][TechDebt] Sprint 26
Story | DEV-1 | 53858 | [DEV][RD][Tech Debt][PL] Fix Log File Permission Issue to Prevent Root-Owned File Blocking Application Logs | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 14/May/26 9:19 AM | 02/Jun/26 10:04 AM | 15/May/26 12:00 AM | 3 | [5 empty] | 28800 | [Dev][RD][TechDebt] Sprint 24 | [Dev][RD][TechDebt] Sprint 25 | [Dev][RD][TechDebt] Sprint 26
Story | DPE-531 | 53720 | [Dev][RD][SSO-User DB] Create database view for active RC cards info | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 07/May/26 3:05 PM | 02/Jun/26 10:19 AM | 15/May/26 12:00 AM | 1 | DE | [5 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-530 | 53712 | [Dev][RD][IPF] Change the webhook issue point to use Point Engine Proxy | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 07/May/26 2:51 PM | 12/Jun/26 1:29 PM | 15/May/26 12:00 AM | 3 | rr-issue-point-function |  |  |  |  | 28800 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-527 | 53706 | [QA] Test Execution - API | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 07/May/26 2:41 PM | 11/Jun/26 3:40 PM | [8 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-523 | 53702 | [QA] Test Execution - API | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 07/May/26 2:39 PM | 12/Jun/26 11:20 AM | [8 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-522 | 53701 | [QA] Test Execution - API | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 07/May/26 2:39 PM | 12/Jun/26 11:26 AM | [8 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-520 | 53699 | [QA] Test Execution - API | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 07/May/26 2:38 PM | 12/Jun/26 3:10 PM | [8 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-519 | 53698 | [Dev][RD][SSO-User DB] Create database view for registration_sources | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 07/May/26 2:16 PM | 02/Jun/26 10:19 AM | 15/May/26 12:00 AM | 1 | DE | [5 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-513 | 53665 | [Dev][RD][PEP][Database] Request Production PostgreSQL Provisioning for Point Engine Proxy | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Done |  | 06/May/26 2:24 PM | 12/Jun/26 10:38 AM |  | 3 | [6 empty] | [Dev][RD][New PE] Sprint 26
Story | DEVRDECOM-246 | 53605 | [DEV][RD][Ecom][Turtle] Custom delivery option in email order confirmation | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 05/May/26 9:44 AM | 12/Jun/26 9:24 AM |  | 3 | shopify-custom-order-comfirmation |  |  |  |  | 57600 | [Dev][RD][Ecom] Sprint 24 | [Dev][RD][Ecom] Sprint 25 | [Dev][RD][Ecom] Sprint 26
Story | RDTHANA-484 | 53566 | [DEV][RD][TDM] Access control API on landing zone | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 30/Apr/26 2:24 PM | 02/Jun/26 9:19 AM | 11/May/26 12:00 AM | 3 | [5 empty] | 28800 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 25 | [Dev][RD][Thana] Sprint 26
Story | DEV-4 | 53559 | [Dev][RD][RRS] Optimize MongoDB Bulk Update Coupons Status to Reduce IO Wait (Batch Size Tuning) | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 30/Apr/26 1:43 PM | 12/Jun/26 1:47 PM |  | 5 | [6 empty] | [Dev][All Project] Sprint 24 | [Dev][RD][TechDebt] Sprint 25 | [Dev][RD][TechDebt] Sprint 26
Story | DEV-13 | 53553 | [Dev][RD][Tech Debt][RRS] Improve upload coupon code logic and refactor | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 30/Apr/26 9:33 AM | 11/Jun/26 5:18 PM | 15/May/26 12:00 AM | 5 | [6 empty] | [Dev][All Project] Sprint 24 | [Dev][RD][TechDebt] Sprint 25 | [Dev][RD][TechDebt] Sprint 26
Story | DPE-506 | 53505 | [Dev][RD][ORD] Enhance Pay with Point Flow to Handle CleverTap Payment Provider | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 29/Apr/26 11:30 AM | 12/Jun/26 1:29 PM | 15/May/26 12:00 AM | 2 | [5 empty] | 14400 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Bug | DEVRDSUP-564 | 53463 | [SUP-655][SUB][OfficerApp] BTS admin reported that 1 of the voucher couldn't be mark used, A920 displayed "Usage card is missing" 27/04/2026. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Low | Open |  | 28/Apr/26 3:20 PM | 12/Jun/26 1:04 PM | 19/Jun/26 12:00 AM |  | a920 | bts | OfficerApp | prod-issue | sub |  | [Dev][All Project] Sprint 24 | [Dev][All Project] Sprint 25 | [Dev][All Project] Sprint 26
Sub-task | DPE-486 | 53397 | [QA] Test execution STG | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | In Progress |  | 25/Apr/26 12:46 PM | 27/May/26 1:02 PM | [8 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-485 | 53395 | [QA] Test execution STG | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | In Progress |  | 25/Apr/26 12:46 PM | 27/May/26 1:02 PM | [8 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-484 | 53393 | [QA] Test execution STG | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | In Progress |  | 25/Apr/26 12:46 PM | 22/May/26 10:06 AM | [8 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-483 | 53391 | [QA] Create Sky Web Switch Account test cases | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | In Progress |  | 25/Apr/26 12:40 PM | 26/May/26 10:11 AM | [8 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-482 | 53389 | [QA] Create Sky API Switch account test cases | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 25/Apr/26 12:38 PM | 26/May/26 10:10 AM | [8 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-481 | 53387 | [QA] Create Sky API Reactivate test cases | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 25/Apr/26 12:38 PM | 26/May/26 10:10 AM | [8 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-480 | 53385 | [QA] Test execution STG | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 25/Apr/26 12:36 PM | 16/May/26 2:51 PM | [8 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-479 | 53383 | [QA] Create Sky API Register Member test cases | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 25/Apr/26 12:35 PM | 30/Apr/26 11:48 AM | [8 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Bug | DEVRDSUP-556 | 53335 | [SUP-647][NBO][SUBSCRIPTION][REWARDS] - "Draft/ Inactive/ Active Rewards" check duplicate codes with "Expired Rewards" | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Resolved |  | 23/Apr/26 3:30 PM | 12/Jun/26 1:12 PM | 19/Jun/26 12:00 AM |  | rem | sub |  |  |  |  | [Dev][All Project] Sprint 24 | [Dev][All Project] Sprint 25 | [Dev][All Project] Sprint 26
Story | RDAPS-453 | 53332 | [DEV][RD][Adhoc] Gather and Document Rabbit SDK Project Information | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Review |  | 23/Apr/26 2:22 PM | 12/Jun/26 1:51 PM |  | 1 | [5 empty] | 7200 | [Dev][All Project] Sprint 26
Story | DPE-466 | 53282 | [Dev][RD][PE Proxy Scheduler] Enhance command for importing RC retail transactions#2 | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 22/Apr/26 10:06 AM | 12/Jun/26 1:46 PM | 23/Apr/26 12:00 AM | 1 | point-engine-proxy-scheduler | [5 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-465 | 53281 | [Dev][RD][PE Proxy Scheduler] Enhance command for importing RW retail transactions#2 | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 22/Apr/26 10:06 AM | 12/Jun/26 1:46 PM | 23/Apr/26 12:00 AM | 2 | point-engine-proxy-scheduler | [5 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-464 | 53271 | Dev][RD][PE Proxy Scheduler] Enhance command to import RC BTS trip transactions | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 22/Apr/26 8:37 AM | 12/Jun/26 1:46 PM | 29/Apr/26 12:00 AM | 3 | point-engine-proxy-scheduler | [5 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-463 | 53270 | Dev][RD][PE Proxy Scheduler] Enhance command to import RW BTS trip transactions#1 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 22/Apr/26 8:35 AM | 12/Jun/26 1:46 PM | 27/Apr/26 12:00 AM | 3 | point-engine-proxy-scheduler | [5 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-462 | 53267 | [Dev][RD][PE Proxy Scheduler] Enhance Offer Import Logic for Multi Transaction Type Support | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 21/Apr/26 4:37 PM | 12/Jun/26 1:46 PM | 24/Apr/26 12:00 AM | 3 | point-engine-proxy-scheduler | [5 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DEVRDECOM-240 | 52950 | [DEV][RD][Ecom][Turtle] Custom delivery option in checkout page | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 09/Apr/26 1:56 PM | 12/Jun/26 9:24 AM |  | 5 | shopify-checkout-ui-extension |  |  |  |  | 57600 | [Dev][RD][Ecom] Sprint 23 | [Dev][RD][Ecom] Sprint 24 | [Dev][RD][Ecom] Sprint 25 | [Dev][RD][Ecom] Sprint 26
Bug | DEVRDSUP-544 | 52910 | [SUP-632]Turtle plus data mismatch between clevertap and master file | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Closed |  | 07/Apr/26 3:02 PM | 12/Jun/26 1:04 PM |  |  | CleverTap | hr-solution | turtle |  |  |  | [Dev][All Project] Sprint 23 | [Dev][All Project] Sprint 24 | [Dev][All Project] Sprint 25 | [Dev][All Project] Sprint 26
Story | DPE-430 | 52638 | [Dev][RD][PE Proxy Scheduler] Enhance command for importing RW retail transactions#1 | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 01/Apr/26 7:41 PM | 12/Jun/26 1:46 PM | 22/Apr/26 12:00 AM | 3 | point-engine-proxy-scheduler | [5 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-429 | 52629 | [Dev][RD][PE Proxy Scheduler] Enhance command for importing RC retail transactions#1 | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 01/Apr/26 4:16 PM | 12/Jun/26 1:46 PM | 21/Apr/26 12:00 AM | 3 | point-engine-proxy-scheduler | [5 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-426 | 52550 | [Dev][RD][Rewards DB] Create database view for products reporting | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 01/Apr/26 1:28 PM | 02/Jun/26 10:19 AM | 30/Apr/26 12:00 AM | 1 | DE | [5 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-415 | 52057 | [Dev][RD][Promo Code][APIs Gateway] Mapping APIs for Promo Code | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 30/Mar/26 4:26 PM | 08/Jun/26 10:16 AM |  | 1 | [6 empty] | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-414 | 52056 | [Dev][RD][Promo Code][BFF] Create API to apply Promo Code | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 30/Mar/26 4:24 PM | 12/Jun/26 1:12 PM | 29/May/26 12:00 AM | 5 | BFF |  |  |  |  | 57600 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-413 | 52055 | [Dev][RD][Promo Code][PE Middleware] Create API to apply Promo Code | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 30/Mar/26 4:24 PM | 12/Jun/26 1:12 PM | 29/May/26 12:00 AM | 5 | point-engine-proxy |  |  |  |  | 57600 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-406 | 51719 | [Dev][RD][PEP DB] Create database view for standard offer code reporting | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 27/Mar/26 11:46 AM | 11/Jun/26 3:14 PM | 30/Apr/26 12:00 AM | 3 | DE |  |  |  |  | 14400 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-402 | 51633 | [Dev][RD][PL DB] Create database view for partner reversal transactions reporting | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 26/Mar/26 4:54 PM | 02/Jun/26 10:19 AM | 14/May/26 12:00 AM | 1 | DE |  |  |  |  | 7200 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-399 | 51496 | [Dev][RD][Rewards DB] Create database view for `packages` reporting | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 25/Mar/26 4:44 PM | 11/Jun/26 1:45 PM | 30/Apr/26 12:00 AM | 3 | DE |  |  |  |  | 14400 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Epic | RDTHANA-464 | 50601 | Enhance Lightspeed txn |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 22/Mar/26 11:17 PM | 02/Jun/26 9:19 AM | 03/Apr/26 12:00 AM | [7 empty] | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 25 | [Dev][RD][Thana] Sprint 26
Story | DPE-316 | 46990 | [Dev][RD][PEP DB] Create database view for standard merchants code reporting | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 07/Mar/26 12:11 PM | 02/Jun/26 10:19 AM | 30/Apr/26 12:00 AM | 3 | DE | [5 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-315 | 46989 | [Dev][RD][LP DB] Create database view for LP card binding reporting | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 07/Mar/26 12:08 PM | 02/Jun/26 10:19 AM | 24/Apr/26 12:00 AM | 3 | DE | [5 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-314 | 46988 | [Dev][RD][SSO-User DB] Create database view for active RC cards info | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 07/Mar/26 11:36 AM | 11/Jun/26 1:45 PM | 30/Apr/26 12:00 AM | 3 | DE | [5 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-312 | 46986 | [Dev][RD][PL DB] Create database view for partner transactions reporting | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 07/Mar/26 10:57 AM | 08/Jun/26 1:56 PM | 14/May/26 12:00 AM | 1 | DE |  |  |  |  | 7200 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-311 | 46985 | [Dev][RD][PL DB] Create database view for partner unbind reporting | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 07/Mar/26 10:57 AM | 02/Jun/26 10:19 AM | 12/May/26 12:00 AM | 2 | DE |  |  |  |  | 14400 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-310 | 46952 | [Dev][RD][PL DB] Create database view for partner binding reporting | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 07/Mar/26 5:36 AM | 02/Jun/26 10:19 AM | 12/May/26 12:00 AM | 1 | DE |  |  |  |  | 7200 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-303 | 45986 | Dev][RD][PE Proxy Scheduler] Implement command to import RW BTS trip transactions | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Ready To Test |  | 01/Mar/26 8:49 PM | 12/Jun/26 1:46 PM | 03/Apr/26 12:00 AM | 5 | point-engine-proxy-scheduler |  |  |  |  | 86400 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-302 | 45985 | Dev][RD][PE Proxy Scheduler] Implement command to import RC BTS trip transactions | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Ready To Test |  | 01/Mar/26 8:49 PM | 12/Jun/26 1:46 PM | 01/Apr/26 12:00 AM | 8 | point-engine-proxy-scheduler |  |  |  |  | 115200 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-301 | 45984 | [Dev][RD][PE Proxy Scheduler] Implement command for importing RW retail transactions | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 01/Mar/26 8:47 PM | 12/Jun/26 1:46 PM | 02/Apr/26 12:00 AM | 8 | point-engine-proxy-scheduler |  |  |  |  | 72000 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-296 | 45845 | [Dev][RD][PE Proxy Scheduler] Implement command for importing RC retail transactions | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 27/Feb/26 1:40 PM | 12/Jun/26 1:46 PM | 31/Mar/26 12:00 AM | 8 | point-engine-proxy-scheduler | [5 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-295 | 45844 | [Dev][RD][PE Proxy Scheduler] Implement command to import merchant codes and offers from file | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 27/Feb/26 1:39 PM | 12/Jun/26 1:46 PM | 27/Mar/26 12:00 AM | 8 | point-engine-proxy-scheduler | [5 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Epic | RDTHANA-431 | 42991 | Lighspeed Polling |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 11/Feb/26 3:07 PM | 02/Jun/26 9:19 AM | 06/Mar/26 12:00 AM | [7 empty] | [Dev][RD][Thana] Sprint 19 | [Dev][RD][Thana] Sprint 20 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 18 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 25 | [Dev][RD][Thana] Sprint 26
Story | DPE-177 | 42712 | [Dev][RD][Performacne] Define Load Test Scenarios | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 10/Feb/26 3:55 PM | 09/Jun/26 10:02 AM |  | 13 | [6 empty] | [Dev][RD][New PE] Sprint 26
Story | DPE-167 | 42224 | [Dev][RD][RLP Web] Middleware | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 07/Feb/26 7:22 PM | 08/Jun/26 2:13 PM | 30/Apr/26 12:00 AM | 5 | [5 empty] | 7200 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-160 | 42217 | [Dev][RD][Rewards Member] Switch account | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 07/Feb/26 3:30 PM | 02/Jun/26 10:19 AM | 10/Apr/26 12:00 AM | 3 | [6 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-140 | 42127 | [Dev][RD][PWP] Cancel transaction | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 6:35 PM | 12/Jun/26 4:33 PM |  | 5 | [6 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-138 | 42114 | [Dev][RD][RLP] Payment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Ready To Test |  | 06/Feb/26 2:53 PM | 12/Jun/26 3:10 PM | 23/Apr/26 12:00 AM | 3 | [5 empty] | 28800 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-136 | 42112 | [Dev][RD][RLP] Command users:resend-binding | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 2:53 PM | 12/Jun/26 1:29 PM | 23/Apr/26 12:00 AM | 3 | [5 empty] | 28800 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-135 | 42111 | [Dev][RD][RLP] Bulk register by card | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 06/Feb/26 2:53 PM | 12/Jun/26 1:29 PM | 23/Apr/26 12:00 AM | 3 | [5 empty] | 28800 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-134 | 42110 | [Dev][RD][RLP] Register by card | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 06/Feb/26 2:53 PM | 12/Jun/26 1:29 PM | 28/Apr/26 12:00 AM | 2 | [5 empty] | 14400 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-122 | 42097 | [Dev][RD][ECS] Cancel transaction | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 06/Feb/26 1:43 PM | 12/Jun/26 1:29 PM |  | 3 | [6 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-121 | 42096 | [Dev][RD][ECS] Refund transaction | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 06/Feb/26 1:43 PM | 12/Jun/26 1:29 PM |  | 5 | [6 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-120 | 42095 | [Dev][RD][ECS] Cronjob: Daily sync issue point | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 06/Feb/26 1:43 PM | 12/Jun/26 1:29 PM | 17/Apr/26 12:00 AM | 8 | ecommerce-shopify-api |  |  |  |  | 57600 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-116 | 42091 | [Dev][RD][VLD] Add card (mark use) | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 06/Feb/26 1:43 PM | 12/Jun/26 1:29 PM | 17/Apr/26 12:00 AM | 2 | [6 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-110 | 42053 | [Dev][RD][APH] Submit data enrichment | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 06/Feb/26 12:11 PM | 12/Jun/26 1:29 PM | 17/Apr/26 12:00 AM | 3 | [5 empty] | 28800 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-109 | 42052 | [Dev][RD][APH] Survey processing | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 06/Feb/26 12:11 PM | 12/Jun/26 1:29 PM | 17/Apr/26 12:00 AM | 3 | [5 empty] | 28800 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-107 | 42050 | [Dev][RD][PWP] Refund transaction | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 12:10 PM | 12/Jun/26 4:33 PM |  | 5 | [6 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-106 | 42049 | [Dev][RD][PWP] Confirm payment | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 12:10 PM | 12/Jun/26 4:33 PM | 09/Apr/26 12:00 AM | 5 | [6 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-98 | 41971 | [Dev][RD][ORD] Disable sending order transaction data to DA | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 05/Feb/26 4:49 PM | 12/Jun/26 1:29 PM |  | 3 | [5 empty] | 28800 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-97 | 41970 | [Dev][RD][ORD] Refund order (Partial Item) | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 05/Feb/26 4:48 PM | 12/Jun/26 1:29 PM | 14/May/26 12:00 AM | 3 | [6 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-96 | 41969 | [Dev][RD][ORD] Refund order (Full Items) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 05/Feb/26 4:48 PM | 12/Jun/26 1:29 PM | 13/May/26 12:00 AM | 5 | [6 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-95 | 41968 | [Dev][RD][ORD] Place subscription order | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 05/Feb/26 4:48 PM | 12/Jun/26 1:29 PM | 27/Mar/26 12:00 AM | 5 | [6 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-92 | 41965 | [Dev][RD][Sky Web] Switch Account | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 05/Feb/26 4:46 PM | 12/Jun/26 1:46 PM | 19/Mar/26 12:00 AM | 5 | sky-web |  |  |  |  | 57600 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-91 | 41964 | [Dev][RD][Sky] Switch account API | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:46 PM | 12/Jun/26 1:46 PM | 19/Mar/26 12:00 AM | 3 | sky-api |  |  |  |  | 28800 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-90 | 41963 | [Dev][RD][Sky][Member] Reactivate | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:46 PM | 12/Jun/26 1:46 PM | 12/Mar/26 12:00 AM | 2 | sky-api | [5 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-89 | 41962 | [Dev][RD][Sky][Member] Register Member | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:46 PM | 12/Jun/26 1:46 PM | 13/Mar/26 12:00 AM | 3 | sky-api |  |  |  |  | 28800 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Epic | DEVRDECOM-107 | 31506 | Shopify Webhook |  |  | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | To Do |  | 23/Sep/25 9:52 AM | 02/Jun/26 10:01 AM | [8 empty] | [Dev][RD][Ecom] Sprint 8 | [Dev][RD][Ecom] Sprint 9 | [Dev][RD][Ecom] Sprint 10 | [Dev][RD][Ecom] Sprint 11 | [Dev][RD][Ecom] Sprint 12 | [Dev][RD][Ecom] Sprint 13 | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15 | [Dev][RD][Ecom] Sprint 16 | [Dev][RD][Ecom] Sprint 23 | [Dev][RD][Ecom] Sprint 24 | [Dev][RD][Ecom] Sprint 25 | [Dev][RD][Ecom] Sprint 26

## Summarize Sprint 25
Column 1 | Total Stories Point | Total Manhour | Point Done | Manhour Done | Note
18 May - 29 May
Dev Resource Available | 21 | 462
Meeting Planned |  |  |  |  | Ref
Additional Meeting |  |  |  |  | Ref
Deployment |  | 2 |  |  | 2 ครั้ง 1. 1 คน 2. 2 คน
Development Sprint Total | 548 | 804.17 | 300 | 448.17
Ad-hoc Mid Sprint | 0 | 0 | 0 | 0 | 2 tasks
Requirement changes after refinement? | 0 |  | 0 | 0 | 0 tasks
Aek | 35 | 91 | 27 | 59
A | 89 | 230 | 27 | 68
Aom | 47 | 0.17 | 43 | 0.17
Zan | 9 | 0 | 1 | 0
Mai | 73 | 146 | 55 | 118
Mac | 84 | 176 | 57 | 120
Mos | 71 | 121 | 32 | 51
Jack | 5 | 0 | 5 | 0
Nim | 64 | 40 | 39 | 32
Arm | 71 | 0 | 14 | 0

## Sprint 25
Issue Type | Issue key | Issue id | Summary | Assignee | Assignee Id | Reporter | Reporter Id | Priority | Status | Resolution | Created | Updated | Due date | Custom field (Story Points) | Labels | Labels | Labels | Labels | Labels | Original estimate | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint
Sub-task | RDAPS-492 | 54443 | [QA] Test Execution Verify Enhance clear member card cache after add card success | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 02/Jun/26 2:53 PM | 02/Jun/26 5:30 PM | [8 empty] | [Dev][All Project] Sprint 25 | [Dev][All Project] Sprint 26
Sub-task | DPE-660 | 54440 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | To Do |  | 02/Jun/26 1:57 PM | 02/Jun/26 1:57 PM | [8 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-659 | 54439 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 02/Jun/26 1:57 PM | 02/Jun/26 2:11 PM | [8 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-658 | 54411 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | To Do |  | 01/Jun/26 5:38 PM | 01/Jun/26 5:39 PM | [8 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-657 | 54410 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 01/Jun/26 5:38 PM | 02/Jun/26 2:11 PM | [8 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-656 | 54409 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | To Do |  | 01/Jun/26 5:38 PM | 01/Jun/26 5:38 PM | [8 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-655 | 54408 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | To Do |  | 01/Jun/26 5:38 PM | 01/Jun/26 5:38 PM | [8 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-654 | 54407 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 01/Jun/26 5:38 PM | 02/Jun/26 2:11 PM | [8 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-653 | 54406 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 01/Jun/26 5:38 PM | 02/Jun/26 2:11 PM | [8 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-652 | 54405 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | To Do |  | 01/Jun/26 5:38 PM | 01/Jun/26 5:38 PM | [8 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-651 | 54404 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 01/Jun/26 5:38 PM | 02/Jun/26 2:11 PM | [8 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Bug | DPE-647 | 54331 | [S3][Coupon] Push coupon is not working properly | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 29/May/26 9:55 AM | 01/Jun/26 9:58 AM | [8 empty] | [Dev][RD][New PE] Sprint 25
Story | RDTHANA-503 | 54322 | [DEV][RD][TDM] Add is_legacy to callback API | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 28/May/26 5:16 PM | 02/Jun/26 9:19 AM | 29/May/26 12:00 AM | 1 | [6 empty] | [Dev][RD][Thana] Sprint 25 | [Dev][RD][Thana] Sprint 26
Sub-task | DEV-11 | 54313 | [QA] Test execution verify Enhance getMemberTier | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 28/May/26 3:08 PM | 02/Jun/26 10:11 AM | [8 empty] | [Dev][RD][TechDebt] Sprint 24 | [Dev][RD][TechDebt] Sprint 25
Story | DEVRDSUP-611 | 54299 | [SUP-701][Need Support] BTSG – Import User (Employee ID เปลี่ยน) | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Highest | In Progress |  | 28/May/26 11:48 AM | 04/Jun/26 10:28 AM | 29/May/26 12:00 AM |  | hop | hr-solution |  |  |  |  | [Dev][All Project] Sprint 25 | [Dev][All Project] Sprint 26
Story | DEVRDSUP-609 | 54296 | [SUP-705][PROD] Request to create BU in HR Solution | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Done |  | 28/May/26 10:54 AM | 28/May/26 5:18 PM | 29/May/26 12:00 AM | 1 | hop |  |  |  |  | 600 | [Dev][All Project] Sprint 25
Story | DEVRDSUP-608 | 54287 | [SUP-699]User properties birthday has changed in Clevertap again | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Thanakrit Chanthaworn | 712020:3fc982cb-c268-4f1d-9265-d3dd8fb08304 | Medium | Done |  | 27/May/26 5:43 PM | 02/Jun/26 7:04 PM | 01/Jun/26 12:00 AM |  | CleverTap | prod-issue | rr-app |  |  |  | [Dev][All Project] Sprint 25
Bug | DPE-644 | 54280 | [S3][RR-BOF][ATN] Campaign Issue Point flow is not working properly | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 27/May/26 12:51 PM | 01/Jun/26 3:06 PM | [8 empty] | [Dev][RD][New PE] Sprint 25
Bug | DPE-643 | 54275 | [S3][PL] Get Internal Server Error when reverse transaction | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 27/May/26 11:19 AM | 28/May/26 4:58 PM | [8 empty] | [Dev][RD][New PE] Sprint 25
Bug | DPE-642 | 54272 | [S4][REM] Data source is incorrect for refund coupon flow | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed ( Change Request) |  | 27/May/26 10:34 AM | 28/May/26 4:58 PM | [8 empty] | [Dev][RD][New PE] Sprint 25
Story | RDAPS-480 | 54264 | [Dev][RD][SA] Meeting Sprint25 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 27/May/26 9:15 AM | 01/Jun/26 10:12 AM |  | 8 | [6 empty] | [Dev][All Project] Sprint 25
Sub-task | DPE-641 | 54261 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 26/May/26 11:59 PM | 01/Jun/26 2:50 PM | [8 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-640 | 54260 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 26/May/26 11:59 PM | 01/Jun/26 2:50 PM | [8 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-639 | 54259 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 26/May/26 11:51 PM | 01/Jun/26 2:51 PM | [8 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-638 | 54258 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 26/May/26 11:51 PM | 26/May/26 11:51 PM | [8 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-637 | 54255 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 26/May/26 11:27 PM | 01/Jun/26 2:50 PM | [8 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-636 | 54254 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 26/May/26 11:27 PM | 26/May/26 11:40 PM | [8 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-635 | 54253 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 26/May/26 10:40 PM | 26/May/26 10:40 PM | [8 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-634 | 54252 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 26/May/26 10:40 PM | 26/May/26 10:40 PM | [8 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-633 | 54250 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 26/May/26 9:57 PM | 29/May/26 11:20 AM | [8 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-632 | 54249 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 26/May/26 9:57 PM | 28/May/26 3:46 PM | [8 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-631 | 54248 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 26/May/26 9:37 PM | 28/May/26 3:35 PM | [8 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-630 | 54247 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 26/May/26 9:37 PM | 28/May/26 3:35 PM | [8 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Bug | DPE-629 | 54245 | [S4][SSO-User] RABBIT_CARD_FACE_TYPE value on CleverTab is not correctly | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 26/May/26 4:23 PM | 28/May/26 4:58 PM | [8 empty] | [Dev][RD][New PE] Sprint 25
Bug | DPE-628 | 54244 | [S3][REM] Unable to refund coupon for zero point redeemed txn | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 26/May/26 4:18 PM | 28/May/26 4:58 PM | [8 empty] | [Dev][RD][New PE] Sprint 25
Test Execution | QA-3080 | 54241 | [TX][Sprint #25][Member] Rabbit Sky API and Rabbit web member | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | In Progress |  | 26/May/26 3:34 PM | 27/May/26 10:45 AM | [8 empty] | [Dev][RD][New PE] Sprint 25
Test Plan | QA-3079 | 54240 | [TP][Sprint #25][Member] Rabbit Sky API and Rabbit Sky web member |  |  | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 26/May/26 3:29 PM | 26/May/26 3:31 PM | [8 empty] | [Dev][RD][New PE] Sprint 25
Story | DEVRDSUP-605 | 54238 | [SUP-697]Group Rewards - Lucky Draw Apple_Jun26 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | To Do |  | 26/May/26 2:43 PM | 04/Jun/26 10:28 AM | 29/May/26 12:00 AM |  | BURequest | groupReward | rem |  |  |  | [Dev][All Project] Sprint 25 | [Dev][All Project] Sprint 26
Story | DEVRDSUP-604 | 54188 | [SUP-696]SUB : Disable Credit/Debit Card Payment for BBL Package (JUNE2026 Package) | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Thanakrit Chanthaworn | 712020:3fc982cb-c268-4f1d-9265-d3dd8fb08304 | Medium | Done |  | 26/May/26 10:31 AM | 29/May/26 9:40 AM | 29/May/26 12:00 AM | 1 | BURequest | sub |  |  |  | 600 | [Dev][All Project] Sprint 25
Story | DEV-10 | 54186 | [DEV][RD][HRS] Enhance package issue on Local | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 26/May/26 10:26 AM | 02/Jun/26 10:04 AM | 01/Jun/26 12:00 AM | 3 | [5 empty] | 28800 | [Dev][RD][TechDebt] Sprint 25 | [Dev][RD][TechDebt] Sprint 26
Bug | DPE-599 | 54176 | [S3][Redemption API] Able to redeem rewards with inactive merchant | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 25/May/26 2:08 PM | 28/May/26 4:58 PM | [8 empty] | [Dev][RD][New PE] Sprint 25
Story | DEVRDECOM-250 | 54168 | [DEV][RD][Ecom] Regression Test | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | High | Done |  | 22/May/26 5:12 PM | 29/May/26 10:22 AM |  | 3 | No-QA | rr-ecommerce-shopify |  |  |  |  | [Dev][RD][Ecom] Sprint 25
Story | DEVRDSUP-602 | 54167 | [SUP-694][SUB] Urgent! CS-20260500028131>> รบกวนออกแพ็กเกจและ Mark used Order ID 20260509-0001238 // หักเงินแต่ไม่ได้แพ็กเกจ OPN ปรับสถานะจาก Failed --->> Paid เรียบร้อย | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 22/May/26 5:00 PM | 22/May/26 5:15 PM |  | 1 | [6 empty] | [Dev][All Project] Sprint 25
Story | DPE-597 | 54154 | [Dev][RD][PE Proxy Scheduler] Implement Discord Error Notifications | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | To Do |  | 22/May/26 9:17 AM | 02/Jun/26 11:19 AM |  |  | No-QA | point-engine-proxy-scheduler |  |  |  |  | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | RDAPS-479 | 54146 | [SA][RD][Adhoc] Consent Tracking Report for Legal Compliance | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 21/May/26 3:53 PM | 25/May/26 9:58 AM |  | 1 | [5 empty] | 1800 | [Dev][All Project] Sprint 25
Bug | DEVRDSUP-599 | 54132 | [SUP-643]Event Charged in Clevertap and data format mismatch | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Thanakrit Chanthaworn | 712020:3fc982cb-c268-4f1d-9265-d3dd8fb08304 | Medium | Resolved |  | 21/May/26 9:57 AM | 04/Jun/26 10:27 AM |  |  | partner-loyalty | [5 empty] | [Dev][All Project] Sprint 25 | [Dev][All Project] Sprint 26
Story | DPE-596 | 54131 | [Dev][RD][PE Middleware][UnitTest] Implement Unit Test Coverage for `GET /v1/wallets/{id}/point-history` | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 21/May/26 9:48 AM | 28/May/26 4:49 PM | 22/May/26 12:00 AM | 2 | No-QA | point-engine-proxy |  |  |  |  | [Dev][RD][New PE] Sprint 25
Story | DPE-595 | 54130 | [Dev][RD][PE Middleware][UnitTest] Implement Unit Test Coverage for `GET /v1/wallets/{id}/point-expiring` | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 21/May/26 9:43 AM | 28/May/26 4:48 PM | 29/May/26 12:00 AM |  | No-QA | point-engine-proxy |  |  |  | 14400 | [Dev][RD][New PE] Sprint 25
Story | DPE-594 | 54129 | [Dev][RD][PE Middleware][UnitTest] Implement Unit Test Coverage for `POST /v1/wallets/{id}/debit` | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 21/May/26 9:42 AM | 28/May/26 4:48 PM | 29/May/26 12:00 AM |  | No-QA | point-engine-proxy |  |  |  | 14400 | [Dev][RD][New PE] Sprint 25
Story | DPE-593 | 54128 | [Dev][RD][PE Middleware][UnitTest] Implement Unit Test Coverage for `POST /v1/wallets/{id}/credit` | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 21/May/26 9:42 AM | 28/May/26 4:48 PM | 29/May/26 12:00 AM |  | No-QA | point-engine-proxy |  |  |  | 14400 | [Dev][RD][New PE] Sprint 25
Story | DPE-592 | 54127 | [Dev][RD][PE Middleware][UnitTest] Implement Unit Test Coverage for `POST /v1/wallets/reversal` | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 21/May/26 9:41 AM | 28/May/26 4:49 PM | 21/May/26 12:00 AM | 2 | No-QA | point-engine-proxy |  |  |  |  | [Dev][RD][New PE] Sprint 25
Story | RDTHANA-500 | 54124 | [DEV][RD] Enhance generic transaction support request revert for void/fail transaction | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Highest | Done |  | 21/May/26 1:13 AM | 29/May/26 9:35 AM | 21/May/26 12:00 AM | 3 | No-QA | [5 empty] | [Dev][RD][Thana] Sprint 25
Bug | DPE-591 | 54123 | [S3][PE Proxy] Able to reverse point with invalid offer | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed ( Change Request) |  | 20/May/26 11:19 PM | 22/May/26 10:54 AM | [8 empty] | [Dev][RD][New PE] Sprint 25
Bug | DPE-590 | 54122 | [S4][PE Proxy] The response contains an incorrect field name | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 20/May/26 10:48 PM | 22/May/26 10:54 AM | [8 empty] | [Dev][RD][New PE] Sprint 25
Story | DEVRDSUP-597 | 54093 | [SUP-690][SUB] Urgent! CS-20260500028044>> รบกวนออกแพ็กเกจ Order ID 20260519-0002216 // หักเงินแต่ไม่ได้แพ็กเกจ OPN ปรับสถานะจาก Failed --->> Paid เรียบร้อย | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 20/May/26 5:36 PM | 21/May/26 1:54 PM | 25/May/26 12:00 AM | 1 | bts | rr-app | sub |  |  |  | [Dev][All Project] Sprint 25
Bug | DEVRDSUP-596 | 54091 | [SUP-689]NBO][Rewards][Subscription] - Upload code double | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Low | ACCEPTED |  | 20/May/26 5:12 PM | 04/Jun/26 10:30 AM | 25/Jun/26 12:00 AM |  | rem | sub |  |  |  |  | [Dev][All Project] Sprint 25 | [Dev][All Project] Sprint 26
Bug | DEVRDSUP-595 | 54089 | [SUP-688]Event properties are not appearing in the user profile | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Thanakrit Chanthaworn | 712020:3fc982cb-c268-4f1d-9265-d3dd8fb08304 | Medium | Resolved |  | 20/May/26 4:47 PM | 04/Jun/26 10:27 AM | 09/Jun/26 12:00 AM |  | CleverTap | prod-issue | rr-app |  |  |  | [Dev][All Project] Sprint 25 | [Dev][All Project] Sprint 26
Story | DEVRDSUP-594 | 54087 | [SUP-625][RR Member Account] CS-20260300026232 // Cannot add RC into RR Member account [RD SSO show- "Rabbit card already in use." / Member ID 30245337 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | In Review |  | 20/May/26 4:35 PM | 04/Jun/26 10:29 AM |  | 1 | [5 empty] | 7200 | [Dev][All Project] Sprint 25 | [Dev][All Project] Sprint 26
Story | DEVRDECOM-249 | 54086 | [DEV][RD][Ecom] Add Shopify customers/create webhook handler to sync shopify_members and update Shopify customer profile | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | High | Done |  | 20/May/26 4:33 PM | 29/May/26 10:22 AM | 22/May/26 12:00 AM | 5 | No-QA | rr-ecommerce-shopify |  |  |  | 57600 | [Dev][RD][Ecom] Sprint 25
Bug | DPE-589 | 54079 | [S2][PE Proxy] Unable to reverse/refund point | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 20/May/26 9:45 AM | 22/May/26 10:54 AM | [8 empty] | [Dev][RD][New PE] Sprint 25
Bug | DPE-588 | 54073 | [S4][SSO-User] Marking data on CT detail is incorrect | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 19/May/26 5:01 PM | 28/May/26 5:07 PM | 25/May/26 12:00 AM | [7 empty] | [Dev][RD][New PE] Sprint 25
Bug | DPE-587 | 54070 | [S2][PE Proxy] Unable to debit point | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 19/May/26 3:26 PM | 22/May/26 10:54 AM | [8 empty] | [Dev][RD][New PE] Sprint 25
Bug | DPE-586 | 54069 | [S2][PE Proxy] Unable to credit point | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 19/May/26 3:20 PM | 22/May/26 10:53 AM | [8 empty] | [Dev][RD][New PE] Sprint 25
Sub-task | RDTHANA-499 | 54064 | [QA] Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 19/May/26 1:45 PM | 19/May/26 5:53 PM | [8 empty] | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 25
Sub-task | RDTHANA-497 | 54062 | [QA] Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 19/May/26 1:44 PM | 20/May/26 9:29 AM | [8 empty] | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 25
Sub-task | RDTHANA-496 | 54061 | [QA] Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 19/May/26 1:44 PM | 19/May/26 5:09 PM | [8 empty] | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 25
Sub-task | RDTHANA-495 | 54060 | [QA] Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 19/May/26 1:44 PM | 19/May/26 5:07 PM | [8 empty] | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 25
Sub-task | RDTHANA-494 | 54059 | [QA] Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 19/May/26 1:43 PM | 19/May/26 6:08 PM | [8 empty] | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 25
Sub-task | DPE-585 | 54058 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 19/May/26 1:32 PM | 21/May/26 2:23 PM | [8 empty] | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-584 | 54057 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 19/May/26 1:32 PM | 20/May/26 10:13 PM | [8 empty] | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-583 | 54056 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 19/May/26 1:32 PM | 20/May/26 8:32 PM | [8 empty] | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-582 | 54055 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 19/May/26 1:32 PM | 19/May/26 4:46 PM | [8 empty] | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-581 | 54054 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 19/May/26 1:32 PM | 20/May/26 8:58 PM | [8 empty] | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-580 | 54053 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 19/May/26 1:32 PM | 19/May/26 4:46 PM | [8 empty] | [Dev][RD][New PE] Sprint 25
Story | DEVRDSUP-592 | 54052 | [SUP-686][SUB] Receipt is not generated after SUB transaction is made (TXN Date 18 May 2026) | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Thanakrit Chanthaworn | 712020:3fc982cb-c268-4f1d-9265-d3dd8fb08304 | Medium | Done |  | 19/May/26 12:05 PM | 20/May/26 11:17 AM |  | 1 | [6 empty] | [Dev][All Project] Sprint 25
Story | RDAPS-478 | 54045 | [Dev][VGI][VGIONE] Update Meta API version | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Highest | Done |  | 18/May/26 4:22 PM | 27/May/26 9:52 AM |  | 5 | vgi-one | [5 empty] | [Dev][All Project] Sprint 25
Story | RDAPS-477 | 54039 | [DEV][RD] Support DevOps | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 18/May/26 2:51 PM | 28/May/26 11:57 AM |  | 1 | [5 empty] | 7200 | [Dev][All Project] Sprint 25
Story | DEVRDSS-4 | 54038 | [SA][RD][Samsung] Analysis and Design | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 18/May/26 2:37 PM | 29/May/26 10:20 AM |  | 1 | [6 empty] | [Dev][RD][Samsung] Sprint 25
Story | DEV-5 | 54037 | [DEV][RD][TechDebt] Enhance command re register support by options | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 18/May/26 1:45 PM | 02/Jun/26 10:04 AM | 20/May/26 12:00 AM |  | hr-solution | No-QA |  |  |  |  | [Dev][RD][TechDebt] Sprint 25 | [Dev][RD][TechDebt] Sprint 26
Story | RDTHANA-493 | 54033 | [DEV][RD][TDM][POC] Get Shopify data for BU Dashboard | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 18/May/26 10:43 AM | 02/Jun/26 9:19 AM | 26/May/26 12:00 AM | 8 | No-QA |  |  |  |  | 86400 | [Dev][RD][Thana] Sprint 25 | [Dev][RD][Thana] Sprint 26
Story | RDTHANA-492 | 54027 | [DEV][RD][TDM] Enhance Generic transaction | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 18/May/26 9:56 AM | 02/Jun/26 9:19 AM | 19/May/26 12:00 AM | 1 | No-QA |  |  |  |  | 7200 | [Dev][RD][Thana] Sprint 25 | [Dev][RD][Thana] Sprint 26
Story | DPE-579 | 54025 | [DEV][RD][NPE] Investigate member count discrepancy between DA and RD due to email matching issues | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Review |  | 18/May/26 9:43 AM | 02/Jun/26 11:11 AM |  | 8 | [6 empty] | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-576 | 54019 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 17/May/26 4:26 PM | 25/May/26 7:09 PM | [8 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-575 | 54018 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 17/May/26 4:26 PM | 25/May/26 7:09 PM | [8 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-574 | 54017 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 17/May/26 4:26 PM | 21/May/26 2:25 PM | [8 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-573 | 54016 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 17/May/26 4:26 PM | 20/May/26 10:13 PM | [8 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-572 | 54015 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 17/May/26 4:26 PM | 21/May/26 2:23 PM | [8 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-571 | 54014 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 17/May/26 4:26 PM | 20/May/26 2:40 PM | [8 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-570 | 53996 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 17/May/26 11:15 AM | 01/Jun/26 4:07 PM | [8 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-569 | 53995 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 17/May/26 11:15 AM | 17/May/26 4:13 PM | [8 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-568 | 53994 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 17/May/26 11:11 AM | 25/May/26 7:09 PM | [8 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-567 | 53993 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 17/May/26 11:11 AM | 25/May/26 7:09 PM | [8 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-566 | 53992 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 17/May/26 11:11 AM | 25/May/26 2:45 PM | [8 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-565 | 53991 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 17/May/26 11:11 AM | 26/May/26 2:35 PM | [8 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-564 | 53990 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 17/May/26 11:11 AM | 28/May/26 11:21 AM | [8 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-563 | 53989 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 17/May/26 11:11 AM | 25/May/26 7:09 PM | [8 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-562 | 53988 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 17/May/26 11:11 AM | 22/May/26 4:47 PM | [8 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-561 | 53987 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 17/May/26 11:11 AM | 26/May/26 7:37 PM | [8 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-560 | 53986 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 17/May/26 11:11 AM | 21/May/26 5:35 PM | [8 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-559 | 53985 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 17/May/26 11:11 AM | 25/May/26 7:09 PM | [8 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-558 | 53984 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 17/May/26 11:10 AM | 25/May/26 2:45 PM | [8 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-557 | 53983 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 17/May/26 11:10 AM | 22/May/26 10:15 AM | [8 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-556 | 53982 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 17/May/26 11:10 AM | 25/May/26 2:45 PM | [8 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-555 | 53981 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 17/May/26 11:10 AM | 22/May/26 10:20 AM | [8 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-554 | 53980 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 17/May/26 11:10 AM | 01/Jun/26 9:53 AM | [8 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-553 | 53979 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 17/May/26 11:10 AM | 01/Jun/26 9:53 AM | [8 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-552 | 53976 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 16/May/26 3:14 PM | 02/Jun/26 10:07 AM | [8 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-551 | 53975 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 16/May/26 3:14 PM | 16/May/26 3:26 PM | [8 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | DEVRDSS-11 | 53973 | [DEV][RD][Samsung][SSO-Backoffice] Update RR profile cards list to show multiple cloud cards | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready to Staging |  | 15/May/26 8:06 PM | 04/Jun/26 8:46 AM |  | 3 | [6 empty] | [Dev][RD][Samsung] Sprint 25 | [Dev][RD][Samsung] Sprint 26
Story | DEVRDSS-9 | 53971 | [DEV][RD][Samsung][CloudID] Update endpoint tokens/latest path to V2 | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready to Staging |  | 15/May/26 7:01 PM | 04/Jun/26 8:46 AM |  | 3 | [6 empty] | [Dev][RD][Samsung] Sprint 25 | [Dev][RD][Samsung] Sprint 26
Story | DEVRDSS-6 | 53970 | [DEV][RD][Samsung][CloudID] Create v2 API for Get User Cards with Multiple Cards Support | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready to Staging |  | 15/May/26 6:57 PM | 04/Jun/26 8:46 AM | 20/May/26 12:00 AM | 3 | [5 empty] | 28800 | [Dev][RD][Samsung] Sprint 25 | [Dev][RD][Samsung] Sprint 26
Story | DEVRDSS-2 | 53969 | [SA][RD][Samsung] Analysis and Design | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 15/May/26 6:51 PM | 29/May/26 3:29 PM |  | 3 | [5 empty] | 28800 | [Dev][RD][Samsung] Sprint 25
Story | DEVRDSS-7 | 53968 | [DEV][RD][Samsung][SSO] Enhance API get card list | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready to Staging |  | 15/May/26 6:37 PM | 04/Jun/26 8:46 AM | 27/May/26 12:00 AM | 5 | [5 empty] | 57600 | [Dev][RD][Samsung] Sprint 25 | [Dev][RD][Samsung] Sprint 26
Story | DEVRDSS-8 | 53967 | [DEV][RD][Samsung][BFF] Enhance API get card list | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready to Staging |  | 15/May/26 6:37 PM | 04/Jun/26 8:46 AM | 29/May/26 12:00 AM | 2 | [5 empty] | 14400 | [Dev][RD][Samsung] Sprint 25 | [Dev][RD][Samsung] Sprint 26
Sub-task | DPE-550 | 53966 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 15/May/26 4:32 PM | 26/May/26 2:47 PM | [8 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-549 | 53965 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 15/May/26 4:32 PM | 16/May/26 3:02 PM | [8 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | DPE-548 | 53949 | [Dev][RD][PE Middleware] Enhance Reversal API Transaction Type Validation | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 15/May/26 1:05 PM | 29/May/26 12:02 PM | 29/May/26 12:00 AM | 3 | point-engine-proxy | [5 empty] | [Dev][RD][New PE] Sprint 25
Story | DPE-547 | 53948 | [Dev][RD][PE Middleware] Enhance Debit API Transaction Type Validation | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 15/May/26 1:04 PM | 29/May/26 12:02 PM | 20/May/26 12:00 AM | 3 | point-engine-proxy | [5 empty] | [Dev][RD][New PE] Sprint 25
Story | DPE-546 | 53947 | [Dev][RD][PE Middleware] Enhance Credit API Transaction Type Validation | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 15/May/26 1:03 PM | 29/May/26 12:02 PM | 19/May/26 12:00 AM | 3 | point-engine-proxy | [5 empty] | [Dev][RD][New PE] Sprint 25
Story | DPE-541 | 53936 | [Dev][RD] UAT - Prepare deployment checklist | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 15/May/26 8:59 AM | 01/Jun/26 10:10 AM |  | 5 | No-QA | [5 empty] | [Dev][RD][New PE] Sprint 25
Story | DEVRDSS-5 | 53899 | [DEV][RD][Samsung] Update API spec for RR App | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 14/May/26 3:46 PM | 29/May/26 3:28 PM | 20/May/26 12:00 AM | 1 | Document | No-QA |  |  |  | 7200 | [Dev][RD][Samsung] Sprint 25
Story | RDAPS-467 | 53897 | [DEV][RD][BFF] Enhance clear member card cache after add card success | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 14/May/26 3:35 PM | 02/Jun/26 5:30 PM |  | 2 | [6 empty] | [Dev][All Project] Sprint 25 | [Dev][All Project] Sprint 26
Story | DEVRDECOM-247 | 53891 | [DEV][RD][Ecom][Gustron] Setup shop SSO login & logout on shopify website | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 14/May/26 2:38 PM | 29/May/26 10:22 AM |  | 1 | No-QA | rr-ecommerce-shopify |  |  |  | 7200 | [Dev][RD][Ecom] Sprint 25
Bug | DEVRDSUP-588 | 53890 | [S3][RR-Backoffice][Rewards] Some deeplink is not displayed | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Pass : Waiting for deployment |  | 14/May/26 2:19 PM | 28/May/26 4:47 PM | 15/May/26 12:00 AM | [7 empty] | [Dev][RD][New PE] Sprint 25 | [Dev][All Project] Sprint 24
Story | RDTHANA-491 | 53889 | [DEV][RD][TDM] Enhance generic transaction support more payment type | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 14/May/26 2:02 PM | 02/Jun/26 9:19 AM | 19/May/26 12:00 AM | 1 | [5 empty] | 7200 | [Dev][RD][Thana] Sprint 25 | [Dev][RD][Thana] Sprint 26
Bug | DPE-538 | 53888 | [S3][BFF] The point history response filtered by date and time is incorrect | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed ( Change Request) |  | 14/May/26 1:41 PM | 01/Jun/26 1:31 PM | [8 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DEVRDSUP-583 | 53887 | [Dev] Resend previous ETLs from 06/05/2026 → TO DO | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 14/May/26 1:29 PM | 27/May/26 9:16 AM | [8 empty] | [Dev][All Project] Sprint 25
Story | DEVRDSUP-582 | 53885 | [SUP-677][RDxDA][ETL] Replacement Encryption Key and Request to Resend Affected Files (from 2026-05-06) | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 14/May/26 1:27 PM | 26/May/26 10:23 AM | 27/May/26 12:00 AM |  | etl | [5 empty] | [Dev][All Project] Sprint 25
Story | DEV-3 | 53866 | [DEV][RD][Tech Debt][HRS] : Enhance getMemberTier — Cache, Bug Fix & Cache Invalidation | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 14/May/26 9:47 AM | 29/May/26 7:10 PM |  | 3 | [6 empty] | [Dev][RD][TechDebt] Sprint 24 | [Dev][RD][TechDebt] Sprint 25
Story | DEV-2 | 53859 | [DEV][RD][Tech Debt][SSO] Improve performance (Relational) | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 14/May/26 9:24 AM | 02/Jun/26 10:04 AM | 15/May/26 12:00 AM | 1 | [5 empty] | 7200 | [Dev][RD][TechDebt] Sprint 24 | [Dev][RD][TechDebt] Sprint 25 | [Dev][RD][TechDebt] Sprint 26
Story | DEV-1 | 53858 | [DEV][RD][Tech Debt][PL] Fix Log File Permission Issue to Prevent Root-Owned File Blocking Application Logs | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 14/May/26 9:19 AM | 02/Jun/26 10:04 AM | 15/May/26 12:00 AM | 3 | [5 empty] | 28800 | [Dev][RD][TechDebt] Sprint 24 | [Dev][RD][TechDebt] Sprint 25 | [Dev][RD][TechDebt] Sprint 26
Story | DEVRDUA-2 | 53857 | [SA][RD][Unified App] Info Preparation | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 14/May/26 8:22 AM | 29/May/26 10:20 AM |  | 1 | [6 empty] | [Dev][All Project] Sprint 24 | [Dev][RD][Unified] Sprint 25
Story | RDTHANA-490 | 53844 | [DEV][RD][TDM] Enhance merchant detail to transaction without coin Event | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 13/May/26 2:46 PM | 19/May/26 5:53 PM | 14/May/26 12:00 AM | 3 | [6 empty] | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 25
Bug | RDTHANA-489 | 53730 | [DEV][RD] Refund webhook event not sync to datamart view table | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Highest | Closed |  | 08/May/26 12:36 AM | 29/May/26 9:35 AM | [8 empty] | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 25
Story | DPE-531 | 53720 | [Dev][RD][SSO-User DB] Create database view for active RC cards info | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 07/May/26 3:05 PM | 02/Jun/26 10:19 AM | 15/May/26 12:00 AM | 1 | DE | [5 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-530 | 53712 | [Dev][RD][IPF] Change the webhook issue point to use Point Engine Proxy | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready To Test |  | 07/May/26 2:51 PM | 02/Jun/26 11:11 AM | 15/May/26 12:00 AM | 3 | rr-issue-point-function |  |  |  |  | 28800 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-528 | 53707 | [QA] Test Execution - API | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 07/May/26 2:41 PM | 27/May/26 11:16 AM | [8 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-527 | 53706 | [QA] Test Execution - API | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 07/May/26 2:41 PM | 27/May/26 11:10 AM | [8 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-526 | 53705 | [QA] Test Execution - API | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 07/May/26 2:41 PM | 27/May/26 11:10 AM | [8 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-525 | 53704 | [QA] Test Execution - API | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 07/May/26 2:41 PM | 27/May/26 11:09 AM | [8 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-524 | 53703 | [QA] Test Execution - API | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 07/May/26 2:40 PM | 27/May/26 11:09 AM | [8 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-523 | 53702 | [QA] Test Execution - API | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 07/May/26 2:39 PM | 27/May/26 11:10 AM | [8 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-522 | 53701 | [QA] Test Execution - API | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 07/May/26 2:39 PM | 27/May/26 11:10 AM | [8 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-521 | 53700 | [QA] Test Execution - API | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 07/May/26 2:38 PM | 27/May/26 11:31 AM | [8 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-520 | 53699 | [QA] Test Execution - API | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 07/May/26 2:38 PM | 27/May/26 11:10 AM | [8 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-519 | 53698 | [Dev][RD][SSO-User DB] Create database view for registration_sources | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 07/May/26 2:16 PM | 02/Jun/26 10:19 AM | 15/May/26 12:00 AM | 1 | DE | [5 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | RDAPS-463 | 53685 | [Dev][RD][SA] Meeting Sprint24 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 07/May/26 9:16 AM | 27/May/26 9:15 AM |  | 5 | [6 empty] | [Dev][All Project] Sprint 24 | [Dev][All Project] Sprint 25
Story | DPE-514 | 53674 | [Dev][RD][PE Middleware] Enhance Reversal API | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 06/May/26 3:49 PM | 29/May/26 12:02 PM | 15/May/26 12:00 AM | 3 | point-engine-proxy |  |  |  |  | 28800 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | DEVRDSUP-572 | 53659 | [SUP-637][Earning BTS Point] #20260100023991 - บัตร RW 08800450771444 -Please check Eligible Trips and Point | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | To Do |  | 06/May/26 11:19 AM | 20/May/26 7:48 PM | [8 empty] | [Dev][All Project] Sprint 24 | [Dev][All Project] Sprint 25
Story | DPE-512 | 53647 | [Dev][RD][REM] Implement Point Reversal if Coupon Allocation Fails After Deduction | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 05/May/26 3:36 PM | 29/May/26 12:32 PM | 15/May/26 12:00 AM | 2 | redemption-api |  |  |  |  | 14400 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | DPE-510 | 53618 | [Dev][RD][REM] Add point_provider to redeem API | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 05/May/26 11:42 AM | 29/May/26 12:32 PM | 15/May/26 12:00 AM |  | redemption-api |  |  |  |  | 3600 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | DPE-509 | 53616 | [Dev][RD][PL] Add point_provider to transactions and redeems table | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 05/May/26 11:29 AM | 26/May/26 8:04 PM | 15/May/26 12:00 AM | 1 | partner-loyalty |  |  |  |  | 7200 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | DPE-508 | 53606 | [Dev][RD][PWP] Refactor QR Scan API to Use Config-Based Point Provider | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 05/May/26 9:53 AM | 26/May/26 4:04 PM |  | 2 | No-QA | [5 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | DEVRDECOM-246 | 53605 | [DEV][RD][Ecom][Turtle] Custom delivery option in email order confirmation | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 05/May/26 9:44 AM | 02/Jun/26 10:01 AM |  | 3 | shopify-custom-order-comfirmation |  |  |  |  | 57600 | [Dev][RD][Ecom] Sprint 24 | [Dev][RD][Ecom] Sprint 25 | [Dev][RD][Ecom] Sprint 26
Story | DEVRDECOM-245 | 53604 | [DEV][RD][Ecom][Gustron] Sync shopify events to Clevertap | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 05/May/26 9:41 AM | 29/May/26 10:22 AM |  | 1 | No-QA | rr-ecommerce-shopify |  |  |  | 600 | [Dev][RD][Ecom] Sprint 25
Story | DEVRDECOM-244 | 53603 | [DEV][RD][Ecom][Gustron] Sync transaction data from shopify to RR data mart | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 05/May/26 9:38 AM | 29/May/26 10:22 AM |  | 1 | No-QA | rr-ecommerce-shopify |  |  |  | 600 | [Dev][RD][Ecom] Sprint 25
Story | DEVRDECOM-243 | 53602 | [DEV][RD][Ecom][POC][Gustron] Banner auto login from RR app | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 05/May/26 9:36 AM | 30/May/26 6:52 AM |  | 2 | rr-ecommerce-shopify |  |  |  |  | 14400 | [Dev][RD][Ecom] Sprint 24 | [Dev][RD][Ecom] Sprint 25
Story | DEVRDECOM-242 | 53601 | [DEV][RD][Ecom][POC] New customer account type in shopify (Multipass deprecated) | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 05/May/26 9:33 AM | 29/May/26 10:22 AM |  | 5 | rr-ecommerce-shopify |  |  |  |  | 57600 | [Dev][RD][Ecom] Sprint 24 | [Dev][RD][Ecom] Sprint 25
Story | DEVRDSS-3 | 53597 | [SA][RD][Samsung][POC] Review BSS API to update card status v2 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 05/May/26 9:22 AM | 29/May/26 10:20 AM |  | 2 | [5 empty] | 14400 | [Dev][All Project] Sprint 24 | [Dev][RD][Samsung] Sprint 25
Story | DPE-507 | 53595 | [Dev][RD][PL] Enhance Check Member by Phone API to Support Terminated Users | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 05/May/26 9:02 AM | 29/May/26 12:01 PM | 08/May/26 12:00 AM | 2 | partner-loyalty |  |  |  |  | 14400 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | RDTHANA-485 | 53569 | [DEV][RD][TDM] Turtle Shopify Order event for datamart | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 30/Apr/26 2:47 PM | 02/Jun/26 9:18 AM | 15/May/26 12:00 AM | 3 | No-QA | Thana-datamart |  |  |  |  | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 25
Story | RDTHANA-484 | 53566 | [DEV][RD][TDM] Access control API on landing zone | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 30/Apr/26 2:24 PM | 02/Jun/26 9:19 AM | 11/May/26 12:00 AM | 3 | [5 empty] | 28800 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 25 | [Dev][RD][Thana] Sprint 26
Story | DEV-4 | 53559 | [Dev][RD][RRS] Optimize MongoDB Bulk Update Coupons Status to Reduce IO Wait (Batch Size Tuning) | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 30/Apr/26 1:43 PM | 02/Jun/26 10:04 AM |  | 5 | [6 empty] | [Dev][All Project] Sprint 24 | [Dev][RD][TechDebt] Sprint 25 | [Dev][RD][TechDebt] Sprint 26
Story | DEV-13 | 53553 | [Dev][RD][Tech Debt][RRS] Improve upload coupon code logic and refactor | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 30/Apr/26 9:33 AM | 02/Jun/26 11:37 AM | 15/May/26 12:00 AM | 5 | [6 empty] | [Dev][All Project] Sprint 24 | [Dev][RD][TechDebt] Sprint 25 | [Dev][RD][TechDebt] Sprint 26
Story | DPE-506 | 53505 | [Dev][RD][ORD] Enhance Pay with Point Flow to Handle CleverTap Payment Provider | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 29/Apr/26 11:30 AM | 02/Jun/26 10:19 AM | 15/May/26 12:00 AM | 2 | [5 empty] | 14400 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-505 | 53504 | [Dev][RD][PEP] Update golang version | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 29/Apr/26 11:02 AM | 27/May/26 3:05 PM | 05/May/26 12:00 AM | 5 | No-QA |  |  |  |  | 57600 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Bug | DEVRDSUP-564 | 53463 | [SUP-655][SUB][OfficerApp] BTS admin reported that 1 of the voucher couldn't be mark used, A920 displayed "Usage card is missing" 27/04/2026. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Low | Open |  | 28/Apr/26 3:20 PM | 04/Jun/26 10:29 AM | 19/May/26 12:00 AM |  | a920 | bts | OfficerApp | prod-issue | sub |  | [Dev][All Project] Sprint 24 | [Dev][All Project] Sprint 25 | [Dev][All Project] Sprint 26
Story | DPE-493 | 53456 | [Dev][RD][SSO-User] Update User Properties on Termination | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 28/Apr/26 2:15 PM | 29/May/26 12:32 PM | 15/May/26 12:00 AM | 2 | sso-user |  |  |  |  | 14400 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | DPE-492 | 53440 | Dev][RD][REM] Implement Schema Versioning for Redeemed Transaction | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 28/Apr/26 9:24 AM | 29/May/26 12:32 PM | 30/Apr/26 12:00 AM | 3 | [6 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | DPE-491 | 53439 | [Dev][RD][PE Middleware] Refactor OfferRepository: Consolidate GetOffer Methods into Generic Function | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 28/Apr/26 8:49 AM | 29/May/26 12:01 PM | 30/Apr/26 12:00 AM | 5 | point-engine-proxy | [5 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-486 | 53397 | [QA] Test execution STG | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | In Progress |  | 25/Apr/26 12:46 PM | 27/May/26 1:02 PM | [8 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-485 | 53395 | [QA] Test execution STG | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | In Progress |  | 25/Apr/26 12:46 PM | 27/May/26 1:02 PM | [8 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-484 | 53393 | [QA] Test execution STG | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | In Progress |  | 25/Apr/26 12:46 PM | 22/May/26 10:06 AM | [8 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-483 | 53391 | [QA] Create Sky Web Switch Account test cases | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | In Progress |  | 25/Apr/26 12:40 PM | 26/May/26 10:11 AM | [8 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-482 | 53389 | [QA] Create Sky API Switch account test cases | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 25/Apr/26 12:38 PM | 26/May/26 10:10 AM | [8 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-481 | 53387 | [QA] Create Sky API Reactivate test cases | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 25/Apr/26 12:38 PM | 26/May/26 10:10 AM | [8 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-480 | 53385 | [QA] Test execution STG | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 25/Apr/26 12:36 PM | 16/May/26 2:51 PM | [8 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Sub-task | DPE-479 | 53383 | [QA] Create Sky API Register Member test cases | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 25/Apr/26 12:35 PM | 30/Apr/26 11:48 AM | [8 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-478 | 53379 | [Dev][RD][BFF] Improve mapping API response message for Redemption API | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Done |  | 24/Apr/26 7:25 PM | 29/May/26 12:01 PM | 30/Apr/26 12:00 AM | 2 | [6 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-477 | 53367 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 24/Apr/26 2:10 PM | 01/Jun/26 10:23 AM | [8 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-476 | 53365 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 24/Apr/26 2:10 PM | 14/May/26 3:25 PM | [8 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-473 | 53355 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 24/Apr/26 10:57 AM | 20/May/26 2:38 PM | [8 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-472 | 53353 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 24/Apr/26 10:57 AM | 24/Apr/26 1:20 PM | [8 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Bug | DEVRDSUP-556 | 53335 | [SUP-647][NBO][SUBSCRIPTION][REWARDS] - "Draft/ Inactive/ Active Rewards" check duplicate codes with "Expired Rewards" | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Resolved |  | 23/Apr/26 3:30 PM | 04/Jun/26 10:29 AM | 07/May/26 12:00 AM |  | rem | sub |  |  |  |  | [Dev][All Project] Sprint 24 | [Dev][All Project] Sprint 25 | [Dev][All Project] Sprint 26
Story | DPE-469 | 53334 | [Dev][RD][PE Middleware] Enhance Offer Name Fields Mapping to CleverTap | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 23/Apr/26 3:25 PM | 29/May/26 12:02 PM | 30/Apr/26 12:00 AM | 2 | point-engine-proxy |  |  |  |  | 7200 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | DPE-467 | 53291 | [Dev][RD][goutil] Improve func get point history to support additional filtering | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 22/Apr/26 1:15 PM | 27/May/26 9:52 AM | 30/Apr/26 12:00 AM | 1 | No-QA | [5 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | DPE-466 | 53282 | [Dev][RD][PE Proxy Scheduler] Enhance command for importing RC retail transactions#2 | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 22/Apr/26 10:06 AM | 02/Jun/26 10:19 AM | 23/Apr/26 12:00 AM | 1 | point-engine-proxy-scheduler | [5 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-465 | 53281 | [Dev][RD][PE Proxy Scheduler] Enhance command for importing RW retail transactions#2 | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 22/Apr/26 10:06 AM | 02/Jun/26 10:19 AM | 23/Apr/26 12:00 AM | 2 | point-engine-proxy-scheduler | [5 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-464 | 53271 | Dev][RD][PE Proxy Scheduler] Enhance command to import RC BTS trip transactions | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 22/Apr/26 8:37 AM | 02/Jun/26 10:19 AM | 29/Apr/26 12:00 AM | 3 | point-engine-proxy-scheduler | [5 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-463 | 53270 | Dev][RD][PE Proxy Scheduler] Enhance command to import RW BTS trip transactions#1 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 22/Apr/26 8:35 AM | 02/Jun/26 10:19 AM | 27/Apr/26 12:00 AM | 3 | point-engine-proxy-scheduler | [5 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-462 | 53267 | [Dev][RD][PE Proxy Scheduler] Enhance Offer Import Logic for Multi Transaction Type Support | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 21/Apr/26 4:37 PM | 02/Jun/26 10:19 AM | 24/Apr/26 12:00 AM | 3 | point-engine-proxy-scheduler | [5 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DEVRDECOM-240 | 52950 | [DEV][RD][Ecom][Turtle] Custom delivery option in checkout page | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 09/Apr/26 1:56 PM | 02/Jun/26 10:01 AM |  | 5 | shopify-checkout-ui-extension |  |  |  |  | 57600 | [Dev][RD][Ecom] Sprint 23 | [Dev][RD][Ecom] Sprint 24 | [Dev][RD][Ecom] Sprint 25 | [Dev][RD][Ecom] Sprint 26
Story | RDTHANA-479 | 52945 | [DEV][RD][TDM] Enhance Lightspeed master data support pagination | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 08/Apr/26 4:46 PM | 02/Jun/26 9:17 AM | 09/Apr/26 12:00 AM | [7 empty] | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 25
Bug | DEVRDSUP-544 | 52910 | [SUP-632]Turtle plus data mismatch between clevertap and master file | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Resolved |  | 07/Apr/26 3:02 PM | 04/Jun/26 10:30 AM |  |  | CleverTap | hr-solution | turtle |  |  |  | [Dev][All Project] Sprint 23 | [Dev][All Project] Sprint 24 | [Dev][All Project] Sprint 25 | [Dev][All Project] Sprint 26
Story | DPE-430 | 52638 | [Dev][RD][PE Proxy Scheduler] Enhance command for importing RW retail transactions#1 | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 01/Apr/26 7:41 PM | 02/Jun/26 10:19 AM | 22/Apr/26 12:00 AM | 3 | point-engine-proxy-scheduler | [5 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-429 | 52629 | [Dev][RD][PE Proxy Scheduler] Enhance command for importing RC retail transactions#1 | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 01/Apr/26 4:16 PM | 02/Jun/26 10:19 AM | 21/Apr/26 12:00 AM | 3 | point-engine-proxy-scheduler | [5 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-426 | 52550 | [Dev][RD][Rewards DB] Create database view for products reporting | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 01/Apr/26 1:28 PM | 02/Jun/26 10:19 AM | 30/Apr/26 12:00 AM | 1 | DE | [5 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-415 | 52057 | [Dev][RD][Promo Code][APIs Gateway] Mapping APIs for Promo Code | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | To Do |  | 30/Mar/26 4:26 PM | 02/Jun/26 11:12 AM |  | 1 | [6 empty] | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-414 | 52056 | [Dev][RD][Promo Code][BFF] Create API to apply Promo Code | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 30/Mar/26 4:24 PM | 02/Jun/26 11:12 AM | 29/May/26 12:00 AM | 5 | BFF |  |  |  |  | 57600 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-413 | 52055 | [Dev][RD][Promo Code][PE Middleware] Create API to apply Promo Code | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 30/Mar/26 4:24 PM | 02/Jun/26 11:12 AM | 29/May/26 12:00 AM | 5 | point-engine-proxy |  |  |  |  | 57600 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-412 | 51891 | [Dev][RD][PE Middleware] Enhance get wallet history to support filtering | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 29/Mar/26 2:55 PM | 01/Jun/26 4:09 PM | 17/Apr/26 12:00 AM | 3 | point-engine-proxy | [5 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | DPE-408 | 51722 | [Dev][RD][Promo Code][BFF] Create API Spec for Promo Code | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 27/Mar/26 12:00 PM | 01/Jun/26 10:09 AM |  | 5 | No-QA | [5 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | DPE-406 | 51719 | [Dev][RD][PEP DB] Create database view for standard offer code reporting | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 27/Mar/26 11:46 AM | 02/Jun/26 10:19 AM | 30/Apr/26 12:00 AM | 3 | DE |  |  |  |  | 14400 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-402 | 51633 | [Dev][RD][PL DB] Create database view for partner reversal transactions reporting | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 26/Mar/26 4:54 PM | 02/Jun/26 10:19 AM | 14/May/26 12:00 AM | 1 | DE |  |  |  |  | 7200 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | RDTHANA-475 | 51568 | [DEV][RD][TDM] CT Event : ORDER_SUCCESS_HOOK | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Lowest | Done |  | 26/Mar/26 11:09 AM | 20/May/26 9:29 AM | 30/Apr/26 12:00 AM | 5 | [5 empty] | 57600 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 25
Story | RDTHANA-474 | 51567 | [DEV][RD][TDM] CT Event : REFUND_PAID_HOOK | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 26/Mar/26 11:09 AM | 19/May/26 5:09 PM | 07/May/26 12:00 AM | 5 | [5 empty] | 43200 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 25
Story | RDTHANA-473 | 51566 | [DEV][RD][TDM] CT Event : PAYMENT_PAID_{SHOP_NAME} | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 26/Mar/26 11:09 AM | 19/May/26 5:07 PM | 30/Apr/26 12:00 AM | 5 | [5 empty] | 43200 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 25
Story | RDTHANA-472 | 51565 | [DEV][RD][TDM] Consumer : Push to CT | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 26/Mar/26 11:08 AM | 02/Jun/26 9:18 AM | 24/Apr/26 12:00 AM | 5 | No-QA |  |  |  |  | 43200 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 25
Story | RDTHANA-468 | 51555 | [DEV][RD][TDM] Webhook Event : Fullfilment | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 26/Mar/26 11:07 AM | 19/May/26 6:08 PM | 10/Apr/26 12:00 AM | 3 | [6 empty] | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 25
Story | RDTHANA-465 | 51545 | [DEV][RD][TDM] Enhance Shopify access token flow | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 26/Mar/26 9:37 AM | 02/Jun/26 9:17 AM | 26/Mar/26 12:00 AM | 3 | No-QA | Thana-datamart |  |  |  | 28800 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 25
Story | DPE-399 | 51496 | [Dev][RD][Rewards DB] Create database view for `packages` reporting | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 25/Mar/26 4:44 PM | 02/Jun/26 10:19 AM | 30/Apr/26 12:00 AM | 3 | DE |  |  |  |  | 14400 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-389 | 51265 | [Dev][RD][REM] Add additional event perpoties to `REDEEM` event | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 24/Mar/26 3:54 PM | 29/May/26 12:32 PM |  | 3 | redemption-consumer | [5 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Epic | RDTHANA-464 | 50601 | Enhance Lightspeed txn |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 22/Mar/26 11:17 PM | 02/Jun/26 9:19 AM | 03/Apr/26 12:00 AM | [7 empty] | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 25 | [Dev][RD][Thana] Sprint 26
Story | DPE-374 | 50550 | [Dev][RD][ATN] Bulk issue point for MKT campaign | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Done |  | 22/Mar/26 10:28 AM | 01/Jun/26 2:50 PM | 03/Apr/26 12:00 AM | 5 | [5 empty] | 57600 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | RDTHANA-463 | 50163 | [DEV][RD][TDM] Enhance Data Mapping for Lightspeed Polling Transactions | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 19/Mar/26 11:10 AM | 02/Jun/26 9:18 AM | 30/Mar/26 12:00 AM | 5 | Thana-datamart |  |  |  |  | 43200 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 25
Story | DPE-363 | 50118 | [Dev][RD][SA][Sprint25] Analysis & Task Breakdown for PE Migration Execution | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 18/Mar/26 4:03 PM | 01/Jun/26 10:09 AM |  | 13 | [6 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | DEVRDSS-1 | 47383 | [SA][RD][Samsung] Impact analysis on enhance to support multiple RW card | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 10/Mar/26 11:10 AM | 29/May/26 10:20 AM |  | 3 | [5 empty] | 28800 | [Dev][All Project] Sprint 21 | [Dev][All Project] Sprint 24 | [Dev][RD][Samsung] Sprint 25
Story | DPE-319 | 47258 | [Dev][RD][REM] Improve reward redemption with 0 point | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 09/Mar/26 5:15 PM | 29/May/26 12:32 PM |  | 3 | DE | redemption-api |  |  |  | 28800 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | DPE-317 | 47023 | [Dev][RD][PE Middleware] Reversal API | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 07/Mar/26 7:44 PM | 29/May/26 12:02 PM | 30/Apr/26 12:00 AM | 5 | point-engine-proxy |  |  |  |  | 7200 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | DPE-316 | 46990 | [Dev][RD][PEP DB] Create database view for standard merchants code reporting | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 07/Mar/26 12:11 PM | 02/Jun/26 10:19 AM | 30/Apr/26 12:00 AM | 3 | DE | [5 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-315 | 46989 | [Dev][RD][LP DB] Create database view for LP card binding reporting | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 07/Mar/26 12:08 PM | 02/Jun/26 10:19 AM | 24/Apr/26 12:00 AM | 3 | DE | [5 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-314 | 46988 | [Dev][RD][SSO-User DB] Create database view for active RC cards info | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 07/Mar/26 11:36 AM | 02/Jun/26 10:19 AM | 30/Apr/26 12:00 AM | 3 | DE | [5 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-312 | 46986 | [Dev][RD][PL DB] Create database view for partner transactions reporting | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 07/Mar/26 10:57 AM | 02/Jun/26 10:19 AM | 14/May/26 12:00 AM | 1 | DE |  |  |  |  | 7200 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-311 | 46985 | [Dev][RD][PL DB] Create database view for partner unbind reporting | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 07/Mar/26 10:57 AM | 02/Jun/26 10:19 AM | 12/May/26 12:00 AM | 2 | DE |  |  |  |  | 14400 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-310 | 46952 | [Dev][RD][PL DB] Create database view for partner binding reporting | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 07/Mar/26 5:36 AM | 02/Jun/26 10:19 AM | 12/May/26 12:00 AM | 1 | DE |  |  |  |  | 7200 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Bug | DEVRDSUP-479 | 46025 | [SUP-564]ไม่สามารถดึง Available code ได้ ระบบขึ้นว่า No data found | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Pass : Waiting for deployment |  | 02/Mar/26 10:01 AM | 18/May/26 2:00 PM | 18/Mar/26 12:00 AM | 3 | rem | [5 empty] | [Dev][RD][New PE] Sprint 25 | [Dev][All Project] Sprint 20 | [Dev][All Project] Sprint 23 | [Dev][All Project] Sprint 21 | [Dev][All Project] Sprint 24
Story | DPE-303 | 45986 | Dev][RD][PE Proxy Scheduler] Implement command to import RW BTS trip transactions | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Ready To Test |  | 01/Mar/26 8:49 PM | 02/Jun/26 10:19 AM | 03/Apr/26 12:00 AM | 5 | point-engine-proxy-scheduler |  |  |  |  | 86400 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-302 | 45985 | Dev][RD][PE Proxy Scheduler] Implement command to import RC BTS trip transactions | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Ready To Test |  | 01/Mar/26 8:49 PM | 02/Jun/26 10:19 AM | 01/Apr/26 12:00 AM | 8 | point-engine-proxy-scheduler |  |  |  |  | 115200 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-301 | 45984 | [Dev][RD][PE Proxy Scheduler] Implement command for importing RW retail transactions | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 01/Mar/26 8:47 PM | 02/Jun/26 10:19 AM | 02/Apr/26 12:00 AM | 8 | point-engine-proxy-scheduler |  |  |  |  | 72000 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-296 | 45845 | [Dev][RD][PE Proxy Scheduler] Implement command for importing RC retail transactions | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 27/Feb/26 1:40 PM | 02/Jun/26 10:19 AM | 31/Mar/26 12:00 AM | 8 | point-engine-proxy-scheduler | [5 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-295 | 45844 | [Dev][RD][PE Proxy Scheduler] Implement command to import merchant codes and offers from file | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 27/Feb/26 1:39 PM | 02/Jun/26 10:19 AM | 27/Mar/26 12:00 AM | 8 | point-engine-proxy-scheduler | [5 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | RDAPS-424 | 45732 | [SA][RD] Meeting Sprint 25 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 27/Feb/26 9:43 AM | 29/May/26 3:15 PM |  | 2 | [5 empty] | 14400 | [Dev][All Project] Sprint 25
Sub-task | DPE-290 | 45375 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 28/May/26 10:49 AM | [8 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-281 | 45357 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [8 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-272 | 45339 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 28/May/26 10:49 AM | [8 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-270 | 45335 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [8 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-269 | 45333 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [8 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-268 | 45331 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [8 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-267 | 45332 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [8 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-266 | 45329 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [8 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-265 | 45330 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [8 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-262 | 45319 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [8 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-261 | 45321 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [8 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | DEVRDSUP-468 | 45126 | [SUP-552][MIXDATA][ETL] Redemption data ETL col "item_id", "using_at" and "countdown_expired_at" catch-up sync data. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 25/Feb/26 10:30 AM | 26/May/26 2:26 PM | 11/Mar/26 12:00 AM | 2 | data | [5 empty] | [Dev][All Project] Sprint 23 | [Dev][All Project] Sprint 21 | [Dev][All Project] Sprint 24 | [Dev][All Project] Sprint 25
Story | RDAPS-421 | 45103 | [SA][RD] Team Support & Management Sprint 25 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 25/Feb/26 9:32 AM | 29/May/26 3:15 PM |  | 3 | [5 empty] | 28800 | [Dev][All Project] Sprint 25
Sub-task | DPE-228 | 44837 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 23/Feb/26 5:45 PM | 16/May/26 4:27 PM | [8 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Sub-task | DPE-227 | 44835 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 23/Feb/26 5:45 PM | 12/Mar/26 11:46 AM | [8 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | DPE-207 | 44011 | [Dev][RD][SSO-User] Reward Add Card | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 18/Feb/26 3:42 PM | 29/May/26 12:02 PM |  | 1 | [6 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | RDTHANA-447 | 43072 | [DEV][RD][TDM] Sync Order Data from Shopify Stores Refund | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 11/Feb/26 6:36 PM | 02/Jun/26 9:17 AM | 18/Mar/26 12:00 AM | 5 | Thana-datamart |  |  |  |  | 57600 | [Dev][RD][Thana] Sprint 20 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 25
Story | RDTHANA-446 | 43071 | [DEV][RD][TDM] Sync Order Data from Shopify Stores to Data Mart #2 | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 11/Feb/26 6:36 PM | 02/Jun/26 9:17 AM | 20/Mar/26 12:00 AM | 5 | Thana-datamart |  |  |  |  | 57600 | [Dev][RD][Thana] Sprint 20 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 25
Story | RDTHANA-445 | 43070 | [DEV][RD][TDM] Sync Order Data from Shopify Stores to Data Mart table | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 11/Feb/26 6:35 PM | 02/Jun/26 9:17 AM | 18/Mar/26 12:00 AM | 5 | Thana-datamart |  |  |  |  | 57600 | [Dev][RD][Thana] Sprint 20 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 25
Story | RDTHANA-443 | 43068 | [DEV][RD][TDM] Create Webhook API Endpoint refunds/create | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 11/Feb/26 6:35 PM | 02/Jun/26 9:17 AM | 18/Mar/26 12:00 AM | 5 | Thana-datamart | [5 empty] | [Dev][RD][Thana] Sprint 20 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 25
Story | RDTHANA-442 | 43067 | [DEV][RD][TDM] Create Webhook API Endpoint orders | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 11/Feb/26 6:34 PM | 02/Jun/26 9:17 AM | 16/Mar/26 12:00 AM | 5 | Thana-datamart |  |  |  |  | 57600 | [Dev][RD][Thana] Sprint 20 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 25
Story | RDTHANA-441 | 43066 | [DEV][RD][TDM] Create migration | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 11/Feb/26 6:33 PM | 02/Jun/26 9:17 AM | 12/Mar/26 12:00 AM | 5 | No-QA | Thana-datamart |  |  |  | 57600 | [Dev][RD][Thana] Sprint 20 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 25
Epic | RDTHANA-431 | 42991 | Lighspeed Polling |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 11/Feb/26 3:07 PM | 02/Jun/26 9:19 AM | 06/Mar/26 12:00 AM | [7 empty] | [Dev][RD][Thana] Sprint 19 | [Dev][RD][Thana] Sprint 20 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 18 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 25 | [Dev][RD][Thana] Sprint 26
Story | RDAPS-412 | 42822 | [Dev][RD][Adhoc][Subscription][Short Distance] Est.effort enhance A920 API to support short distance subscription package | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 11/Feb/26 10:23 AM | 29/May/26 1:50 PM |  | 2 | [6 empty] | [Dev][All Project] Sprint 25
Story | DPE-167 | 42224 | [Dev][RD][RLP Web] Middleware | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 07/Feb/26 7:22 PM | 02/Jun/26 10:19 AM | 30/Apr/26 12:00 AM | 5 | [5 empty] | 7200 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-160 | 42217 | [Dev][RD][Rewards Member] Switch account | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 07/Feb/26 3:30 PM | 02/Jun/26 10:19 AM | 10/Apr/26 12:00 AM | 3 | [6 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-159 | 42216 | [Dev][RD][BFF] Get point history | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 07/Feb/26 3:24 PM | 01/Jun/26 4:10 PM | 22/Apr/69 12:00 AM | 5 | BFF | [5 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | DPE-147 | 42134 | [Dev][RD][SSO-User] WEB verify phone | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 06/Feb/26 6:37 PM | 01/Jun/26 1:34 PM |  | 1 | sso-user |  |  |  |  | 3600 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | DPE-146 | 42133 | [Dev][RD][SSO-User] WEB update avatar | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 06/Feb/26 6:37 PM | 01/Jun/26 1:34 PM |  | 1 | sso-user |  |  |  |  | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | DPE-145 | 42132 | [Dev][RD][SSO-User] WEB verify user | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 06/Feb/26 6:37 PM | 01/Jun/26 1:34 PM |  | 2 | sso-user |  |  |  |  | 10800 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | DPE-144 | 42131 | [Dev][RD][SSO-User] WEB remove card by card_id | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 06/Feb/26 6:37 PM | 01/Jun/26 1:33 PM |  | 1 | sso-user |  |  |  |  | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | DPE-143 | 42130 | [Dev][RD][SSO-User] WEB move card | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 06/Feb/26 6:36 PM | 01/Jun/26 1:33 PM | 05/Mar/26 12:00 AM | 1 | sso-user |  |  |  |  | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | DPE-142 | 42129 | [Dev][RD][SSO-User] WEB add card | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 06/Feb/26 6:36 PM | 01/Jun/26 1:33 PM |  | 1 | sso-user |  |  |  |  | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | DPE-141 | 42128 | [Dev][RD][SSO-User] WEB update profile by ID | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 06/Feb/26 6:36 PM | 01/Jun/26 1:33 PM | 12/Feb/26 12:00 AM | 2 | sso-user |  |  |  |  | 14400 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | DPE-140 | 42127 | [Dev][RD][PWP] Cancel transaction | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 6:35 PM | 02/Jun/26 10:19 AM |  | 5 | [6 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-139 | 42115 | [Dev][RD][RLP] Merchant | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Done |  | 06/Feb/26 2:53 PM | 27/May/26 2:22 PM | 28/Apr/26 12:00 AM | 3 | [5 empty] | 28800 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | DPE-138 | 42114 | [Dev][RD][RLP] Payment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Ready To Test |  | 06/Feb/26 2:53 PM | 02/Jun/26 10:19 AM | 23/Apr/26 12:00 AM | 3 | [5 empty] | 28800 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-137 | 42113 | [Dev][RD][RLP] Retrieve point balance | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 06/Feb/26 2:53 PM | 27/May/26 2:22 PM | 22/Apr/26 12:00 AM | 5 | [6 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | DPE-136 | 42112 | [Dev][RD][RLP] Command users:resend-binding | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 2:53 PM | 02/Jun/26 10:19 AM | 23/Apr/26 12:00 AM | 3 | [5 empty] | 28800 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-135 | 42111 | [Dev][RD][RLP] Bulk register by card | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 2:53 PM | 02/Jun/26 10:19 AM | 23/Apr/26 12:00 AM | 3 | [5 empty] | 28800 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-134 | 42110 | [Dev][RD][RLP] Register by card | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 2:53 PM | 02/Jun/26 10:19 AM | 28/Apr/26 12:00 AM | 2 | [5 empty] | 14400 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-133 | 42109 | [Dev][RD][RLP] Update card status is unbound by id | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 06/Feb/26 2:53 PM | 27/May/26 2:22 PM | 27/Apr/26 12:00 AM | 1 | [6 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | DPE-132 | 42108 | [Dev][RD][RLP] Update card status by id | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 06/Feb/26 2:53 PM | 27/May/26 2:22 PM | 27/Apr/26 12:00 AM | 1 | [6 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | DPE-131 | 42107 | [Dev][RD][RLP] Update card status | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 06/Feb/26 2:53 PM | 27/May/26 2:22 PM | 27/Apr/26 12:00 AM | 1 | [6 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | DPE-129 | 42104 | [Dev][RD][ATN] Realtime issue point API | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Done |  | 06/Feb/26 2:16 PM | 01/Jun/26 2:50 PM | 01/Apr/26 12:00 AM | 3 | [5 empty] | 28800 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | DPE-128 | 42103 | [Dev][RD][ATN] Request individual issue point API | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Done |  | 06/Feb/26 2:16 PM | 01/Jun/26 2:50 PM | 31/Mar/26 12:00 AM | 3 | [5 empty] | 28800 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | DPE-123 | 42098 | [Dev][RD][REMQ] Async coupon push | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 06/Feb/26 1:44 PM | 01/Jun/26 9:58 AM | 12/Mar/26 12:00 AM | 5 | redemption-consumer |  |  |  |  | 57600 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | DPE-122 | 42097 | [Dev][RD][ECS] Cancel transaction | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 1:43 PM | 02/Jun/26 11:10 AM |  | 3 | [6 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-121 | 42096 | [Dev][RD][ECS] Refund transaction | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 1:43 PM | 02/Jun/26 11:11 AM |  | 5 | [6 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-120 | 42095 | [Dev][RD][ECS] Cronjob: Daily sync issue point | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 1:43 PM | 02/Jun/26 11:11 AM | 17/Apr/26 12:00 AM | 8 | ecommerce-shopify-api |  |  |  |  | 57600 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-116 | 42091 | [Dev][RD][VLD] Add card (mark use) | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 1:43 PM | 02/Jun/26 11:22 AM | 17/Apr/26 12:00 AM | 2 | [6 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-111 | 42054 | [Dev][RD][ATN] Bulk issue point for CRM Refund via RR-Backoffice | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Done |  | 06/Feb/26 12:11 PM | 01/Jun/26 4:25 PM | 03/Apr/26 12:00 AM | 5 | [5 empty] | 57600 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | DPE-110 | 42053 | [Dev][RD][APH] Submit data enrichment | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 12:11 PM | 02/Jun/26 11:10 AM | 17/Apr/26 12:00 AM | 3 | [5 empty] | 28800 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-109 | 42052 | [Dev][RD][APH] Survey processing | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 12:11 PM | 02/Jun/26 11:10 AM | 17/Apr/26 12:00 AM | 3 | [5 empty] | 28800 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-107 | 42050 | [Dev][RD][PWP] Refund transaction | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 12:10 PM | 02/Jun/26 10:19 AM |  | 5 | [6 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-106 | 42049 | [Dev][RD][PWP] Confirm payment | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 12:10 PM | 02/Jun/26 10:19 AM | 09/Apr/26 12:00 AM | 5 | [6 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-104 | 42047 | [Dev][RD][goutil] Revert Function | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 06/Feb/26 12:10 PM | 26/May/26 4:04 PM |  | 2 | No-QA | [5 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | DPE-103 | 42046 | [Dev][RD][goutil] Implement Point Engine Client Functions | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 06/Feb/26 11:54 AM | 26/May/26 4:03 PM |  | 3 | No-QA |  |  |  |  | 28800 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | DPE-98 | 41971 | [Dev][RD][ORD] Disable sending order transaction data to DA | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:49 PM | 02/Jun/26 10:19 AM |  | 3 | [5 empty] | 28800 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-97 | 41970 | [Dev][RD][ORD] Refund order (Partial Item) | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:48 PM | 02/Jun/26 10:19 AM | 14/May/26 12:00 AM | 3 | [6 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-96 | 41969 | [Dev][RD][ORD] Refund order (Full Items) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:48 PM | 02/Jun/26 10:19 AM | 13/May/26 12:00 AM | 5 | [6 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-95 | 41968 | [Dev][RD][ORD] Place subscription order | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:48 PM | 02/Jun/26 10:19 AM | 27/Mar/26 12:00 AM | 5 | [6 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-94 | 41967 | [Dev][RD][REM] Refund coupon v2 and revert point | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 05/Feb/26 4:48 PM | 29/May/26 12:01 PM | 15/May/26 12:00 AM | 5 | redemption-api |  |  |  |  | 43200 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | DPE-93 | 41966 | [Dev][RD][REM] Improve reward redemption v2 | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 05/Feb/26 4:48 PM | 29/May/26 12:32 PM |  | 5 | redemption-api |  |  |  |  | 57600 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | DPE-92 | 41965 | [Dev][RD][Sky Web] Switch Account | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:46 PM | 02/Jun/26 10:19 AM | 19/Mar/26 12:00 AM | 5 | sky-web |  |  |  |  | 57600 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-91 | 41964 | [Dev][RD][Sky] Switch account API | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:46 PM | 02/Jun/26 10:19 AM | 19/Mar/26 12:00 AM | 3 | sky-api |  |  |  |  | 28800 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-90 | 41963 | [Dev][RD][Sky][Member] Reactivate | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:46 PM | 02/Jun/26 10:19 AM | 12/Mar/26 12:00 AM | 2 | sky-api | [5 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-89 | 41962 | [Dev][RD][Sky][Member] Register Member | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:46 PM | 02/Jun/26 10:19 AM | 13/Mar/26 12:00 AM | 3 | sky-api |  |  |  |  | 28800 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25 | [Dev][RD][New PE] Sprint 26
Story | DPE-87 | 41960 | [Dev][RD][PL][Point] Reverse transaction | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 05/Feb/26 4:46 PM | 29/May/26 12:01 PM | 08/May/26 12:00 AM | 5 | partner-loyalty | [5 empty] | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | DPE-83 | 41541 | [Dev][RD][PL][Point] Command: transaction:re-issue | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 04/Feb/26 10:27 AM | 26/May/26 4:30 PM |  | 1 | partner-loyalty | [5 empty] | [Dev][RD][New PE] Sprint 25
Story | DPE-76 | 41527 | [Dev][RD][PL][Point] Reverse redeemed transaction | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 04/Feb/26 10:23 AM | 29/May/26 12:01 PM | 07/May/26 12:00 AM | 3 | partner-loyalty |  |  |  |  | 28800 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | DPE-74 | 41523 | [Dev][RD][SSO-User] Remove SSO-Thor API Integration | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Done |  | 04/Feb/26 10:13 AM | 26/May/26 3:23 PM |  | 5 | No-QA | sso-user |  |  |  | 57600 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | DPE-68 | 41511 | [Dev][RD][SSO-User] Rewards add card | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 04/Feb/26 9:49 AM | 29/May/26 12:01 PM | 10/Feb/26 12:00 AM | 1 | sso-user |  |  |  |  | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | DPE-49 | 41435 | [Dev][RD][SSO-User] Rewards Verify phone | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 03/Feb/26 7:41 PM | 29/May/26 12:01 PM |  | 2 | sso-user |  |  |  |  | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24 | [Dev][RD][New PE] Sprint 25
Story | RDAPS-403 | 39981 | [SA][RD] Prepare task for sprint 25 - 26 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 21/Jan/26 2:13 PM | 29/May/26 3:16 PM |  | 2 | [5 empty] | 14400 | [Dev][All Project] Sprint 25
Story | DEVRDECOM-239 | 38710 | [DEV][RD][Ecom] POC Rabbit Connect x Shopify (OIDC integration) | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 12/Jan/26 2:21 PM | 29/May/26 10:22 AM | 19/May/26 12:00 AM | 1 | No-QA | RabbitConnect | rr-ecommerce-shopify |  |  | 7200 | [Dev][RD][Ecom] Sprint 25
Epic | DEVRDCT-359 | 36930 | FIX-Identity-Error |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 23/Dec/25 9:38 AM | 18/May/26 3:50 PM | [8 empty] | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15 | [Dev][RD][CT] Sprint 16 | [Dev][RD][CT] Sprint 21 | [Dev][RD][CT] Sprint 23 | [Dev][RD][CT] Sprint 24 | [Dev][RD][CT] Sprint 25
Epic | DEVRDCT-326 | 35192 | CT-POINT-ISSUE |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 01/Dec/25 9:58 AM | 18/May/26 3:50 PM | [8 empty] | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15 | [Dev][RD][CT] Sprint 16 | [Dev][RD][CT] Sprint 21 | [Dev][RD][CT] Sprint 23 | [Dev][RD][CT] Sprint 24 | [Dev][RD][CT] Sprint 25
Epic | DEVRDCT-325 | 35191 | CTxSHOPIFY |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 01/Dec/25 9:55 AM | 18/May/26 3:50 PM | [8 empty] | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15 | [Dev][RD][CT] Sprint 16 | [Dev][RD][CT] Sprint 21 | [Dev][RD][CT] Sprint 23 | [Dev][RD][CT] Sprint 24 | [Dev][RD][CT] Sprint 25
Epic | DEVRDCT-309 | 34545 | ct-member-tier |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 19/Nov/25 2:49 PM | 18/May/26 3:50 PM | [8 empty] | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15 | [Dev][RD][CT] Sprint 16 | [Dev][RD][CT] Sprint 21 | [Dev][RD][CT] Sprint 23 | [Dev][RD][CT] Sprint 24 | [Dev][RD][CT] Sprint 25
Epic | DEVRDCT-308 | 34539 | ct-campaign-type |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 19/Nov/25 10:41 AM | 18/May/26 3:50 PM |  |  | redemption-api | [5 empty] | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15 | [Dev][RD][CT] Sprint 16 | [Dev][RD][CT] Sprint 21 | [Dev][RD][CT] Sprint 23 | [Dev][RD][CT] Sprint 24 | [Dev][RD][CT] Sprint 25
Epic | DEVRDECOM-107 | 31506 | Shopify Webhook |  |  | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | To Do |  | 23/Sep/25 9:52 AM | 02/Jun/26 10:01 AM | [8 empty] | [Dev][RD][Ecom] Sprint 8 | [Dev][RD][Ecom] Sprint 9 | [Dev][RD][Ecom] Sprint 10 | [Dev][RD][Ecom] Sprint 11 | [Dev][RD][Ecom] Sprint 12 | [Dev][RD][Ecom] Sprint 13 | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15 | [Dev][RD][Ecom] Sprint 16 | [Dev][RD][Ecom] Sprint 23 | [Dev][RD][Ecom] Sprint 24 | [Dev][RD][Ecom] Sprint 25 | [Dev][RD][Ecom] Sprint 26

## Summarize Sprint 24
Column 1 | Total Stories Point | Total Manhour | Point Done | Manhour Done | Note
4 May - 15 May
Dev Resource Available | 21 | 462
Meeting Planned |  |  |  |  | Ref
Additional Meeting |  |  |  |  | Ref
Deployment |  | 2 |  |  | 2 ครั้ง 1. 1 คน 2. 2 คน
Development Sprint Total | 516 | 709.5 | 85 | 102.5
Ad-hoc Mid Sprint | 0 | 0 | 0 | 0 | 2 tasks
Requirement changes after refinement? | 0 |  | 0 | 0 | 0 tasks
Aek | 35 | 55.33 | 13 | 23.33
A | 66 | 170 | 0 | 0
Aom | 29 | 0.17 | 1 | 0.17
Zan | 22 | 0 | 21 | 0
Mai | 78 | 156 | 5 | 10
Mac | 85 | 179 | 17 | 39
Mos | 60 | 81 | 1 | 2
Jack | 0 | 0 | 0 | 0
Nim | 65 | 68 | 10 | 28
Arm | 76 | 0 | 17 | 0
| System Architech |  |  |  | Permanent Dev. |  |  | Contract | Outsource
Projects (Stories Points) | Aek | Zan | Aom | Jack | A | Mac | Mai | Arm | Mos | Nim

## Sprint 24
Issue Type | Issue key | Issue id | Summary | Assignee | Assignee Id | Reporter | Reporter Id | Priority | Status | Resolution | Created | Updated | Due date | Custom field (Story Points) | Labels | Labels | Labels | Labels | Labels | Original estimate | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint
Story | DEVRDSUP-587 | 53955 | [SUP-683][RRApp][Binding RW] RW Card not show in RR_Prod | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Thanakrit Chanthaworn | 712020:3fc982cb-c268-4f1d-9265-d3dd8fb08304 | Medium | Done |  | 15/May/26 2:12 PM | 15/May/26 3:57 PM |  | 1 | [5 empty] | 600 | [Dev][All Project] Sprint 24
Bug | DPE-545 | 53943 | [S3][BFF] The point history response is incorrect when no data matched | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 15/May/26 10:28 AM | 15/May/26 11:14 AM | [8 empty] | [Dev][RD][New PE] Sprint 24
Story | DEVRDSUP-584 | 53895 | [SUP-678]#20260300026281 [RW Binding] Binding but no TXN / No Binding got TXN ? | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 14/May/26 3:00 PM | 15/May/26 12:58 PM |  | 1 | [5 empty] | 600 | [Dev][All Project] Sprint 24
Bug | DEVRDSUP-588 | 53890 | [S3][RR-Backoffice][Rewards] Some deeplink is not displayed | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | RETESTING |  | 14/May/26 2:19 PM | 15/May/26 3:52 PM | 15/May/26 12:00 AM | [7 empty] | [Dev][All Project] Sprint 24
Bug | DPE-538 | 53888 | [S3][BFF] The point history response filtered by date and time is incorrect | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | UNDER VALIDATION |  | 14/May/26 1:41 PM | 15/May/26 10:33 AM | [8 empty] | [Dev][RD][New PE] Sprint 24
Story | DEVRDSUP-581 | 53880 | [SUP-676][SUB] Receipt is not generated after SUB transaction is made (TXN Date 13 May 2026) | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 14/May/26 11:52 AM | 15/May/26 12:58 PM | 14/May/26 12:00 AM | 1 | [5 empty] | 600 | [Dev][All Project] Sprint 24
Story | DEV-3 | 53866 | [DEV][RD][Tech Debt][HRS] : Enhance getMemberTier — Cache, Bug Fix & Cache Invalidation | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready to Staging |  | 14/May/26 9:47 AM | 15/May/26 2:58 PM |  | 3 | [6 empty] | [Dev][RD][TechDebt] Sprint 24
Story | DEV-2 | 53859 | [DEV][RD][Tech Debt][SSO] Improve performance (Relational) | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Review |  | 14/May/26 9:24 AM | 14/May/26 3:01 PM | 15/May/26 12:00 AM | 1 | [5 empty] | 7200 | [Dev][RD][TechDebt] Sprint 24
Story | DEV-1 | 53858 | [DEV][RD][Tech Debt][PL] Fix Log File Permission Issue to Prevent Root-Owned File Blocking Application Logs | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Review |  | 14/May/26 9:19 AM | 15/May/26 3:01 PM | 15/May/26 12:00 AM | 3 | [5 empty] | 28800 | [Dev][RD][TechDebt] Sprint 24
Story | RDAPS-466 | 53857 | [SA][RD][Unified App] Info Preparation | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Progress |  | 14/May/26 8:22 AM | 14/May/26 8:22 AM |  | 1 | [6 empty] | [Dev][All Project] Sprint 24
Story | RDAPS-465 | 53856 | [SA][RD][Unified App] Info Preparation | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 14/May/26 8:21 AM | 15/May/26 10:11 AM |  | 1 | [5 empty] | 7200 | [Dev][All Project] Sprint 24
Bug | DPE-537 | 53855 | [S3][RR-Backoffice][Rewards] The offer details is npt updated when the reward detail updates | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 13/May/26 5:24 PM | 14/May/26 4:43 PM | [8 empty] | [Dev][RD][New PE] Sprint 24
Bug | DPE-536 | 53854 | [S3][RR-Backoffice][Rewards] Unable to update reward information | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 13/May/26 5:20 PM | 14/May/26 4:43 PM | [8 empty] | [Dev][RD][New PE] Sprint 24
Story | RDTHANA-490 | 53844 | [DEV][RD][TDM] Enhance merchant detail to transaction without coin Event | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 13/May/26 2:46 PM | 15/May/26 11:38 AM | 14/May/26 12:00 AM | 3 | [6 empty] | [Dev][RD][Thana] Sprint 24
Sub-task | DPE-535 | 53843 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 13/May/26 2:35 PM | 13/May/26 4:10 PM | [8 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-534 | 53841 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 13/May/26 2:35 PM | 13/May/26 2:39 PM | [8 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DRST-98 | 53827 | [QA] Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 13/May/26 10:42 AM | 13/May/26 10:44 AM | [8 empty] | [Dev][All Project] Sprint 15 | [Dev][All Project] Sprint 16 | [Dev RD][VIMI Termi] Sprint 17 | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22 | [Dev RD][VIMI Termi] Sprint 23 | [Dev RD][VIMI Termi] Sprint 24
Sub-task | DRST-97 | 53814 | [QA] Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 13/May/26 1:04 AM | 13/May/26 1:09 AM | [8 empty] | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22 | [Dev RD][VIMI Termi] Sprint 23 | [Dev RD][VIMI Termi] Sprint 24
Story | DEVRDSUP-577 | 53791 | [SUP-671][Line Pay] #20260500027631 Cannot tou-up BTS Trips in Line Pay Account [User is not found in Cloud ID system] | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 11/May/26 4:23 PM | 15/May/26 12:58 PM |  | 1 | [5 empty] | 1800 | [Dev][All Project] Sprint 24
Story | DEVRDSUP-576 | 53742 | [SUP-670]Urgent [SUB] CS-#20260500027429 // หักเงิน แต่ไม่ได้รับแพ็กเกจ รบกวนออกแพ็กเกจให้ลูกค้าค่ะ | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Highest | Done |  | 08/May/26 2:43 PM | 15/May/26 12:58 PM | 08/May/26 12:00 AM | 1 | [5 empty] | 0 | [Dev][All Project] Sprint 24
Bug | RDTHANA-489 | 53730 | [DEV][RD] Refund webhook event not sync to datamart view table | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Highest | Resolved |  | 08/May/26 12:36 AM | 08/May/26 1:25 PM | [8 empty] | [Dev][RD][Thana] Sprint 24
Story | DPE-531 | 53720 | [Dev][RD][SSO-User DB] Create database view for active RC cards info | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 07/May/26 3:05 PM | 15/May/26 1:25 PM | 15/May/26 12:00 AM | 1 | DE | [5 empty] | [Dev][RD][New PE] Sprint 24
Story | DPE-530 | 53712 | [Dev][RD][IPF] Change the webhook issue point to use Point Engine Proxy | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready To Test |  | 07/May/26 2:51 PM | 14/May/26 4:15 PM | 15/May/26 12:00 AM | 3 | rr-issue-point-function |  |  |  |  | 28800 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-529 | 53708 | [QA] Test Execution - STG | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 07/May/26 2:41 PM | 07/May/26 2:41 PM | [8 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-528 | 53707 | [QA] Test Execution - STG | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 07/May/26 2:41 PM | 07/May/26 2:41 PM | [8 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-527 | 53706 | [QA] Test Execution - STG | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 07/May/26 2:41 PM | 07/May/26 2:41 PM | [8 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-526 | 53705 | [QA] Test Execution - STG | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 07/May/26 2:41 PM | 07/May/26 2:41 PM | [8 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-525 | 53704 | [QA] Test Execution - STG | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 07/May/26 2:41 PM | 07/May/26 2:41 PM | [8 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-524 | 53703 | [QA] Test Execution - STG | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 07/May/26 2:40 PM | 07/May/26 2:40 PM | [8 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-523 | 53702 | [QA] Test Execution - STG | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 07/May/26 2:39 PM | 07/May/26 2:39 PM | [8 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-522 | 53701 | [QA] Test Execution - STG | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 07/May/26 2:39 PM | 07/May/26 2:39 PM | [8 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-521 | 53700 | [QA] Test Execution - STG | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 07/May/26 2:38 PM | 07/May/26 2:39 PM | [8 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-520 | 53699 | [QA] Test Execution - STG | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 07/May/26 2:38 PM | 07/May/26 2:38 PM | [8 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-519 | 53698 | [Dev][RD][SSO-User DB] Create database view for registration_sources | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 07/May/26 2:16 PM | 15/May/26 1:25 PM | 15/May/26 12:00 AM | 1 | DE | [5 empty] | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-518 | 53689 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 07/May/26 10:23 AM | 08/May/26 11:56 AM | [8 empty] | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-517 | 53688 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 07/May/26 10:23 AM | 08/May/26 11:38 AM | [8 empty] | [Dev][RD][New PE] Sprint 24
Story | DPE-516 | 53687 | [Dev][RD][PL][Point] Improve point redeem transaction | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 07/May/26 9:37 AM | 08/May/26 12:01 PM | 07/May/26 12:00 AM | 1 | [5 empty] | 7200 | [Dev][RD][New PE] Sprint 24
Story | RDAPS-463 | 53685 | [Dev][RD][SA] Meeting | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 07/May/26 9:16 AM | 14/May/26 11:08 AM |  | 5 | [6 empty] | [Dev][All Project] Sprint 24
Sub-task | DRST-96 | 53676 | [QA] Test Execution - UAT | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 06/May/26 3:59 PM | 06/May/26 4:25 PM | [8 empty] | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22 | [Dev RD][VIMI Termi] Sprint 23 | [Dev RD][VIMI Termi] Sprint 24
Sub-task | DRST-95 | 53675 | [QA] Test Execution - STG | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 06/May/26 3:59 PM | 06/May/26 3:59 PM | [8 empty] | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22 | [Dev RD][VIMI Termi] Sprint 23 | [Dev RD][VIMI Termi] Sprint 24
Story | DPE-514 | 53674 | [Dev][RD][PE Middleware] Enhance Reversal API | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready To Test |  | 06/May/26 3:49 PM | 15/May/26 2:35 PM | 15/May/26 12:00 AM | 3 | point-engine-proxy |  |  |  |  | 28800 | [Dev][RD][New PE] Sprint 24
Story | DEVRDSUP-572 | 53659 | [SUP-637][Earning BTS Point] #20260100023991 - บัตร RW 08800450771444 -Please check Eligible Trips and Point | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | To Do |  | 06/May/26 11:19 AM | 14/May/26 2:39 PM | [8 empty] | [Dev][All Project] Sprint 24
Bug | DEVRDSUP-571 | 53655 | [SUP-664]#20260300026281 [RW Binding] Binding but no TXN / No Binding got TXN ? | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Rejected |  | 06/May/26 10:42 AM | 15/May/26 9:32 AM |  | 1 | [6 empty] | [Dev][All Project] Sprint 24
Story | DEVRDSUP-569 | 53648 | [SUP-663][SUB]CS-#20260500027382 // Request mark used[ Using] coupon - 13855211 >> RW 0880064263331 | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Highest | Done |  | 05/May/26 4:37 PM | 15/May/26 12:58 PM | 08/May/26 12:00 AM | 1 | [6 empty] | [Dev][All Project] Sprint 24
Story | DPE-512 | 53647 | [Dev][RD][REM] Implement Point Reversal if Coupon Allocation Fails After Deduction | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/May/26 3:36 PM | 08/May/26 10:26 AM | 15/May/26 12:00 AM | 2 | [5 empty] | 14400 | [Dev][RD][New PE] Sprint 24
Story | DPE-510 | 53618 | [Dev][RD][REM] Add point_provider to redeem API | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/May/26 11:42 AM | 13/May/26 11:05 AM | 15/May/26 12:00 AM | [6 empty] | 3600 | [Dev][RD][New PE] Sprint 24
Story | DPE-509 | 53616 | [Dev][RD][PL] Add point_provider to transactions and redeems table | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/May/26 11:29 AM | 14/May/26 4:23 PM | 15/May/26 12:00 AM | 1 | [5 empty] | 7200 | [Dev][RD][New PE] Sprint 24
Story | DEVRDSUP-568 | 53612 | [SUP-661][SUB] Receipt is not generate after txn is made (5/5/69) | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Highest | Done |  | 05/May/26 10:55 AM | 15/May/26 12:58 PM | 05/May/26 12:00 AM | [7 empty] | [Dev][All Project] Sprint 24
Story | DEVRDSUP-567 | 53609 | [SUP-660]ตรวจสอบไม่พบข้อมูล TXN ที่คืน Point ของ BTSG จำนวน 47 TXN | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 05/May/26 10:22 AM | 14/May/26 11:32 AM |  | 1 | [5 empty] | 1800 | [Dev][All Project] Sprint 24
Story | DPE-508 | 53606 | [Dev][RD][PWP] Refactor QR Scan API to Use Config-Based Point Provider | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/May/26 9:53 AM | 14/May/26 2:05 PM |  | 2 | [6 empty] | [Dev][RD][New PE] Sprint 24
Story | DEVRDECOM-246 | 53605 | [DEV][RD][Ecom][Turtle] Custom delivery option in email order confirmation | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 05/May/26 9:44 AM | 14/May/26 10:46 AM |  | 3 | [5 empty] | 57600 | [Dev][RD][Ecom] Sprint 24
Story | DEVRDECOM-243 | 53602 | [DEV][RD][Ecom][POC][Gustron] Banner auto login from RR app | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | To Do |  | 05/May/26 9:36 AM | 14/May/26 10:46 AM |  | 3 | [6 empty] | [Dev][RD][Ecom] Sprint 24
Story | DEVRDECOM-242 | 53601 | [DEV][RD][Ecom][POC] New customer account type in shopify (Multipass deprecated) | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Progress |  | 05/May/26 9:33 AM | 15/May/26 10:34 AM |  | 5 | [6 empty] | [Dev][RD][Ecom] Sprint 24
Story | RDAPS-462 | 53600 | [SA][RD] Prepare task for Sprint 24, 25 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 05/May/26 9:27 AM | 15/May/26 4:07 PM |  | 2 | [5 empty] | 14400 | [Dev][All Project] Sprint 24
Story | RDAPS-461 | 53599 | [SA][RD] Team Support & Management Sprint 24 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 05/May/26 9:26 AM | 14/May/26 11:34 AM |  | 3 | [5 empty] | 28800 | [Dev][All Project] Sprint 24
Story | RDAPS-460 | 53598 | [SA][RD] Meeting Sprint 24 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 05/May/26 9:26 AM | 14/May/26 11:33 AM |  | 3 | [5 empty] | 28800 | [Dev][All Project] Sprint 24
Story | RDAPS-459 | 53597 | [SA][RD][Samsung][POC] Review BSS API to update card status v2 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Review |  | 05/May/26 9:22 AM | 15/May/26 8:50 AM |  | 2 | [6 empty] | [Dev][All Project] Sprint 24
Story | DPE-507 | 53595 | [Dev][RD][PL] Enhance Check Member by Phone API to Support Terminated Users | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Review |  | 05/May/26 9:02 AM | 14/May/26 1:43 PM | 08/May/26 12:00 AM | 2 | [5 empty] | 14400 | [Dev][RD][New PE] Sprint 24
Sub-task | DRST-94 | 53577 | [QA] Test Execution - UAT | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 30/Apr/26 5:35 PM | 06/May/26 4:24 PM | [8 empty] | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22 | [Dev RD][VIMI Termi] Sprint 23 | [Dev RD][VIMI Termi] Sprint 24
Sub-task | DRST-93 | 53575 | [QA] Test Execution - STG | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 30/Apr/26 5:31 PM | 30/Apr/26 5:34 PM | [8 empty] | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22 | [Dev RD][VIMI Termi] Sprint 23 | [Dev RD][VIMI Termi] Sprint 24
Story | RDTHANA-485 | 53569 | [DEV][RD][TDM] Turtle Shopify Order event for datamart | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Review |  | 30/Apr/26 2:47 PM | 15/May/26 3:11 PM | 15/May/26 12:00 AM | 3 | No-QA | Thana-datamart |  |  |  |  | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24
Story | RDTHANA-484 | 53566 | [DEV][RD][TDM] Access control API on landing zone | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 30/Apr/26 2:24 PM | 11/May/26 5:22 PM | 11/May/26 12:00 AM | 3 | [6 empty] | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24
Story | DEV-4 | 53559 | [Dev][RD][RRS] Optimize MongoDB Bulk Update Coupons Status to Reduce IO Wait (Batch Size Tuning) | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 30/Apr/26 1:43 PM | 15/May/26 2:35 PM |  | 5 | [6 empty] | [Dev][All Project] Sprint 24
Story | RDTHANA-483 | 53558 | [DEV][RD][TDM] Setup Turtle Shopify on Production | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 30/Apr/26 10:59 AM | 13/May/26 11:45 AM |  | 3 | No-QA | [5 empty] | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24
Story | RDTHANA-482 | 53557 | [DEV][RD][TDM] Setup Dashaus shopify in Production | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 30/Apr/26 10:58 AM | 13/May/26 11:44 AM |  | 5 | No-QA | [5 empty] | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24
Story | RDAPS-456 | 53553 | [Dev][RD][RRS] Improve upload coupon code logic and refactor | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 30/Apr/26 9:33 AM | 14/May/26 2:09 PM | 15/May/26 12:00 AM | 5 | [6 empty] | [Dev][All Project] Sprint 24
Story | DPE-506 | 53505 | [Dev][RD][ORD] Enhance Pay with Point Flow to Handle CleverTap Payment Provider | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 29/Apr/26 11:30 AM | 14/May/26 4:23 PM | 15/May/26 12:00 AM | 2 | [5 empty] | 14400 | [Dev][RD][New PE] Sprint 24
Story | DPE-505 | 53504 | [Dev][RD][PEP] Update golang version | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 29/Apr/26 11:02 AM | 15/May/26 3:13 PM | 05/May/26 12:00 AM | 5 | No-QA |  |  |  |  | 57600 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-503 | 53479 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 28/Apr/26 3:44 PM | 06/May/26 2:55 PM | [8 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-502 | 53477 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 28/Apr/26 3:44 PM | 06/May/26 2:55 PM | [8 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-499 | 53471 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 28/Apr/26 3:44 PM | 13/May/26 4:12 PM | [8 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-498 | 53469 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 28/Apr/26 3:44 PM | 12/May/26 5:17 PM | [8 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-497 | 53467 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 28/Apr/26 3:44 PM | 06/May/26 10:27 AM | [8 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-496 | 53465 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 28/Apr/26 3:44 PM | 29/Apr/26 5:35 PM | [8 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Bug | DEVRDSUP-564 | 53463 | [SUP-655][SUB][OfficerApp] BTS admin reported that 1 of the voucher couldn't be mark used, A920 displayed "Usage card is missing" 27/04/2026. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Low | Open |  | 28/Apr/26 3:20 PM | 15/May/26 9:32 AM | 19/May/26 12:00 AM |  | a920 | bts | OfficerApp | prod-issue | sub |  | [Dev][All Project] Sprint 24
Story | DPE-493 | 53456 | [Dev][RD][SSO-User] Update User Properties on Termination | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 28/Apr/26 2:15 PM | 14/May/26 1:43 PM | 15/May/26 12:00 AM | 2 | sso-user |  |  |  |  | 14400 | [Dev][RD][New PE] Sprint 24
Story | DPE-492 | 53440 | Dev][RD][REM] Implement Schema Versioning for Redeemed Transaction | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 28/Apr/26 9:24 AM | 06/May/26 10:00 AM | 30/Apr/26 12:00 AM | 3 | [6 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-491 | 53439 | [Dev][RD][PE Middleware] Refactor OfferRepository: Consolidate GetOffer Methods into Generic Function | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready To Test |  | 28/Apr/26 8:49 AM | 06/May/26 10:00 AM | 30/Apr/26 12:00 AM | 5 | point-engine-proxy | [5 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-486 | 53397 | [QA] Test execution STG |  |  | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 25/Apr/26 12:46 PM | 25/Apr/26 12:46 PM | [8 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-485 | 53395 | [QA] Test execution STG |  |  | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 25/Apr/26 12:46 PM | 25/Apr/26 12:46 PM | [8 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-484 | 53393 | [QA] Test execution STG |  |  | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 25/Apr/26 12:46 PM | 25/Apr/26 12:46 PM | [8 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-483 | 53391 | [QA] Create Sky Web Switch Account test cases | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 25/Apr/26 12:40 PM | 25/Apr/26 12:44 PM | [8 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-482 | 53389 | [QA] Create Sky API Switch account test cases | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 25/Apr/26 12:38 PM | 25/Apr/26 12:43 PM | [8 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-481 | 53387 | [QA] Create Sky API Reactivate test cases | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 25/Apr/26 12:38 PM | 25/Apr/26 12:43 PM | [8 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-480 | 53385 | [QA] Test execution STG |  |  | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 25/Apr/26 12:36 PM | 25/Apr/26 12:36 PM | [8 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-479 | 53383 | [QA] Create Sky API Register Member test cases | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 25/Apr/26 12:35 PM | 30/Apr/26 11:48 AM | [8 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-478 | 53379 | [Dev][RD][BFF] Improve mapping API response message for Redemption API | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready To Test |  | 24/Apr/26 7:25 PM | 07/May/26 11:31 AM | 30/Apr/26 12:00 AM | 2 | [6 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-477 | 53367 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 24/Apr/26 2:10 PM | 14/May/26 3:25 PM | [8 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-476 | 53365 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 24/Apr/26 2:10 PM | 14/May/26 3:25 PM | [8 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-475 | 53361 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | In Progress |  | 24/Apr/26 11:39 AM | 14/May/26 5:25 PM | [8 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-474 | 53359 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 24/Apr/26 11:39 AM | 14/May/26 5:25 PM | [8 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-473 | 53355 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | In Progress |  | 24/Apr/26 10:57 AM | 24/Apr/26 3:27 PM | [8 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-472 | 53353 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 24/Apr/26 10:57 AM | 24/Apr/26 1:20 PM | [8 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-470 | 53336 | [Dev][RD][BFF] Enhance mapping detail fields from offer name to offer display name | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready To Test |  | 23/Apr/26 3:48 PM | 14/May/26 5:34 PM | 30/Apr/26 12:00 AM | 1 | BFF |  |  |  |  | 7200 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Bug | DEVRDSUP-556 | 53335 | [SUP-647][NBO][SUBSCRIPTION][REWARDS] - "Draft/ Inactive/ Active Rewards" check duplicate codes with "Expired Rewards" | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Fixing |  | 23/Apr/26 3:30 PM | 15/May/26 9:32 AM | 07/May/26 12:00 AM |  | rem | sub |  |  |  |  | [Dev][All Project] Sprint 24
Story | DPE-469 | 53334 | [Dev][RD][PE Middleware] Enhance Offer Name Fields Mapping to CleverTap | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready To Test |  | 23/Apr/26 3:25 PM | 14/May/26 3:59 PM | 30/Apr/26 12:00 AM | 2 | point-engine-proxy |  |  |  |  | 7200 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-468 | 53300 | [Dev][RD][BOF] Improve product creation logic | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 22/Apr/26 3:51 PM | 15/May/26 10:32 AM | 30/Apr/26 12:00 AM | 1 | [6 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-467 | 53291 | [Dev][RD][goutil] Improve func get point history to support additional filtering | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 22/Apr/26 1:15 PM | 13/May/26 10:42 AM | 30/Apr/26 12:00 AM | 1 | No-QA | [5 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-466 | 53282 | [Dev][RD][PE Proxy Scheduler] Enhance command for importing RC retail transactions#2 | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 22/Apr/26 10:06 AM | 08/May/26 9:42 AM | 23/Apr/26 12:00 AM | 1 | [6 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-465 | 53281 | [Dev][RD][PE Proxy Scheduler] Enhance command for importing RW retail transactions#2 | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 22/Apr/26 10:06 AM | 08/May/26 9:42 AM | 23/Apr/26 12:00 AM | 2 | [6 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-464 | 53271 | Dev][RD][PE Proxy Scheduler] Enhance command to import RC BTS trip transactions | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 22/Apr/26 8:37 AM | 08/May/26 9:42 AM | 29/Apr/26 12:00 AM | 3 | [6 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-463 | 53270 | Dev][RD][PE Proxy Scheduler] Enhance command to import RW BTS trip transactions#1 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 22/Apr/26 8:35 AM | 08/May/26 9:41 AM | 27/Apr/26 12:00 AM | 3 | [6 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-462 | 53267 | [Dev][RD][PE Proxy Scheduler] Enhance Offer Import Logic for Multi Transaction Type Support | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 21/Apr/26 4:37 PM | 06/May/26 10:00 AM | 24/Apr/26 12:00 AM | 3 | [6 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | RDTHANA-481 | 53263 | [DEV][RD][TDM] CT EVENT : POS transaction without coin spending event | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 21/Apr/26 3:11 PM | 14/May/26 9:27 AM | 28/Apr/26 12:00 AM | 5 | [5 empty] | 43200 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24
Story | DPE-447 | 53200 | [Dev][RD][PL] Update API Documentation for 401 and 422 Response Format | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 20/Apr/26 9:43 AM | 15/May/26 2:51 PM | 30/Apr/26 12:00 AM | 1 | No-QA |  |  |  |  | 7200 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DEVRDECOM-240 | 52950 | [DEV][RD][Ecom][Turtle] Custom delivery option in checkout page | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 09/Apr/26 1:56 PM | 14/May/26 10:46 AM |  | 5 | [5 empty] | 57600 | [Dev][RD][Ecom] Sprint 23 | [Dev][RD][Ecom] Sprint 24
Story | RDTHANA-479 | 52945 | [DEV][RD][TDM] Enhance Lightspeed master data support pagination | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 08/Apr/26 4:46 PM | 14/May/26 11:20 AM | 09/Apr/26 12:00 AM | [7 empty] | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24
Story | RDTHANA-478 | 52944 | [DEV][RD][TDM] Enhance lightspeed transaction mapping v2 | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 08/Apr/26 4:45 PM | 13/May/26 10:34 AM | 09/Apr/26 12:00 AM | 2 | [5 empty] | 10800 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24
Bug | DEVRDSUP-544 | 52910 | [SUP-632]Turtle plus data mismatch between clevertap and master file | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | UNDER VALIDATION |  | 07/Apr/26 3:02 PM | 15/May/26 9:32 AM |  |  | CleverTap | hr-solution | turtle |  |  |  | [Dev][All Project] Sprint 23 | [Dev][All Project] Sprint 24
Story | DPE-430 | 52638 | [Dev][RD][PE Proxy Scheduler] Enhance command for importing RW retail transactions#1 | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 01/Apr/26 7:41 PM | 06/May/26 10:00 AM | 22/Apr/26 12:00 AM | 3 | [6 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-429 | 52629 | [Dev][RD][PE Proxy Scheduler] Enhance command for importing RC retail transactions#1 | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 01/Apr/26 4:16 PM | 06/May/26 10:00 AM | 21/Apr/26 12:00 AM | 3 | [6 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-426 | 52550 | [Dev][RD][Rewards DB] Create database view for products reporting | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 01/Apr/26 1:28 PM | 15/May/26 1:25 PM | 30/Apr/26 12:00 AM | 1 | DE | [5 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-412 | 51891 | [Dev][RD][PE Middleware] Enhance get wallet history to support filtering | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 29/Mar/26 2:55 PM | 14/May/26 3:59 PM | 17/Apr/26 12:00 AM | 3 | point-engine-proxy | [5 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-408 | 51722 | [Dev][RD][Promo Code][BFF] Create API Spec for Promo Code | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 27/Mar/26 12:00 PM | 15/May/26 3:14 PM |  | 5 | No-QA | [5 empty] | [Dev][RD][New PE] Sprint 24
Story | DPE-406 | 51719 | [Dev][RD][PEP DB] Create database view for standard offer code reporting | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 27/Mar/26 11:46 AM | 15/May/26 1:25 PM | 30/Apr/26 12:00 AM | 3 | DE |  |  |  |  | 14400 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-402 | 51633 | [Dev][RD][PL DB] Create database view for partner reversal transactions reporting | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 26/Mar/26 4:54 PM | 15/May/26 1:25 PM | 14/May/26 12:00 AM | 1 | DE |  |  |  |  | 7200 | [Dev][RD][New PE] Sprint 24
Story | RDTHANA-475 | 51568 | [DEV][RD][TDM] CT Event : ORDER_SUCCESS_HOOK | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Lowest | Ready To Test |  | 26/Mar/26 11:09 AM | 15/May/26 1:36 PM | 30/Apr/26 12:00 AM | 5 | [5 empty] | 57600 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24
Story | RDTHANA-474 | 51567 | [DEV][RD][TDM] CT Event : REFUND_PAID_HOOK | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 26/Mar/26 11:09 AM | 13/May/26 3:08 PM | 07/May/26 12:00 AM | 5 | [5 empty] | 43200 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24
Story | RDTHANA-473 | 51566 | [DEV][RD][TDM] CT Event : PAYMENT_PAID_{SHOP_NAME} | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 26/Mar/26 11:09 AM | 13/May/26 3:38 PM | 30/Apr/26 12:00 AM | 5 | [5 empty] | 43200 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24
Story | RDTHANA-472 | 51565 | [DEV][RD][TDM] Consumer : Push to CT | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 26/Mar/26 11:08 AM | 13/May/26 1:10 PM | 24/Apr/26 12:00 AM | 5 | No-QA |  |  |  |  | 43200 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24
Story | RDTHANA-468 | 51555 | [DEV][RD][TDM] Webhook Event : Fullfilment | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 26/Mar/26 11:07 AM | 13/May/26 2:57 PM | 10/Apr/26 12:00 AM | 3 | [6 empty] | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24
Story | RDTHANA-465 | 51545 | [DEV][RD][TDM] Enhance Shopify access token flow | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 26/Mar/26 9:37 AM | 06/May/26 9:58 AM | 26/Mar/26 12:00 AM | 3 | No-QA | Thana-datamart |  |  |  | 28800 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24
Story | DPE-399 | 51496 | [Dev][RD][Rewards DB] Create database view for `packages` reporting | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 25/Mar/26 4:44 PM | 15/May/26 1:25 PM | 30/Apr/26 12:00 AM | 3 | DE |  |  |  |  | 14400 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-389 | 51265 | [Dev][RD][REM] Add additional event perpoties to `REDEEM` event | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 24/Mar/26 3:54 PM | 06/May/26 10:00 AM |  | 3 | [6 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | RDAPS-440 | 50959 | [SA][RD][App Handover] Review Technical Spec | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Low | Done |  | 23/Mar/26 11:27 AM | 14/May/26 1:56 PM |  | 8 | [6 empty] | [Dev][All Project] Sprint 23 | [Dev][All Project] Sprint 24
Story | RDAPS-438 | 50957 | [SA][RD][App Handover] Review Software Design and Architecture Documentation | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Low | Done |  | 23/Mar/26 11:26 AM | 14/May/26 1:57 PM |  | 5 | [6 empty] | [Dev][All Project] Sprint 21 | [Dev][All Project] Sprint 22 | [Dev][All Project] Sprint 23 | [Dev][All Project] Sprint 24
Epic | RDTHANA-464 | 50601 | Enhance Lightspeed txn |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 22/Mar/26 11:17 PM | 06/May/26 9:58 AM | 03/Apr/26 12:00 AM | [7 empty] | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24
Story | DPE-374 | 50550 | [Dev][RD][ATN] Bulk issue point for MKT campaign | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Ready To Test |  | 22/Mar/26 10:28 AM | 06/May/26 10:00 AM | 03/Apr/26 12:00 AM | 5 | [5 empty] | 57600 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DRST-78 | 50221 | Delete Report Service (wait SA -> P'Zan) | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Medium | Done |  | 19/Mar/26 1:49 PM | 25/Mar/26 11:45 AM | [8 empty] | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22 | [Dev RD][VIMI Termi] Sprint 23 | [Dev RD][VIMI Termi] Sprint 24
Sub-task | DRST-77 | 50218 | Delete-> Model ->Repository-> Service | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Medium | Done |  | 19/Mar/26 1:49 PM | 20/Mar/26 11:22 AM | [7 empty] | 28800 | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22 | [Dev RD][VIMI Termi] Sprint 23 | [Dev RD][VIMI Termi] Sprint 24
Sub-task | DRST-76 | 50206 | Delete View -> Api route -> controller | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Medium | Done |  | 19/Mar/26 1:40 PM | 20/Mar/26 11:22 AM | [7 empty] | 14400 | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22 | [Dev RD][VIMI Termi] Sprint 23 | [Dev RD][VIMI Termi] Sprint 24
Sub-task | DRST-75 | 50201 | List service,repo,model | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Medium | Done |  | 19/Mar/26 1:39 PM | 20/Mar/26 11:22 AM | [7 empty] | 43200 | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22 | [Dev RD][VIMI Termi] Sprint 23 | [Dev RD][VIMI Termi] Sprint 24
Story | RDTHANA-463 | 50163 | [DEV][RD][TDM] Enhance Data Mapping for Lightspeed Polling Transactions | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 19/Mar/26 11:10 AM | 06/May/26 9:58 AM | 30/Mar/26 12:00 AM | 5 | Thana-datamart |  |  |  |  | 43200 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24
Story | DPE-363 | 50118 | [Dev][RD][SA][Sprint25] Analysis & Task Breakdown for PE Migration Execution | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 18/Mar/26 4:03 PM | 13/May/26 10:42 AM |  | 13 | [6 empty] | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-357 | 48623 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 17/Mar/26 10:16 AM | 12/May/26 4:38 PM | [8 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-356 | 48621 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 17/Mar/26 10:16 AM | 11/May/26 4:20 PM | [8 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Bug | DEVRDSUP-499 | 48499 | [SUP-583]Issue auto push coupon campaign error number mismatch with failed event | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Mook Nicharee Boonthai | 712020:c2ed8478-f54b-4b43-92d9-b933a57493dc | Medium | Closed |  | 16/Mar/26 3:20 PM | 15/May/26 9:32 AM | [8 empty] | [Dev][All Project] Sprint 23 | [Dev][All Project] Sprint 21 | [Dev][All Project] Sprint 24
Sub-task | DPE-338 | 48464 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 16/Mar/26 2:14 PM | 15/May/26 10:08 AM | [8 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-337 | 48462 | [QA] Create test case | THUNDER(QA): PAWICH | 712020:83ff944e-9677-453f-b053-40e92520d905 | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 16/Mar/26 2:14 PM | 07/May/26 1:08 PM | [8 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-336 | 48460 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 16/Mar/26 2:14 PM | 13/May/26 4:42 PM | [8 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-335 | 48458 | [QA] Create test case | THUNDER(QA): PAWICH | 712020:83ff944e-9677-453f-b053-40e92520d905 | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 16/Mar/26 2:14 PM | 07/May/26 1:08 PM | [8 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | RDAPS-426 | 47383 | [SA][RD][Samsung] Impact analysis on enhance to support multiple RW card | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Review |  | 10/Mar/26 11:10 AM | 15/May/26 8:49 AM |  | 3 | [6 empty] | [Dev][All Project] Sprint 21 | [Dev][All Project] Sprint 24
Story | DPE-319 | 47258 | [Dev][RD][REM] Improve reward redemption with 0 point | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 09/Mar/26 5:15 PM | 15/May/26 1:25 PM |  | 3 | DE |  |  |  |  | 28800 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-318 | 47096 | [Dev][RD][PL] Create new partner | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 09/Mar/26 9:39 AM | 14/May/26 3:59 PM | 03/Apr/26 12:00 AM | 3 | [5 empty] | 28800 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-317 | 47023 | [Dev][RD][PE Middleware][CT Blocker] Reversal API | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Blocked |  | 07/Mar/26 7:44 PM | 15/May/26 3:25 PM | 30/Apr/26 12:00 AM | 5 | point-engine-proxy |  |  |  |  | 7200 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-316 | 46990 | [Dev][RD][PEP DB] Create database view for standard merchants code reporting | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 07/Mar/26 12:11 PM | 15/May/26 1:25 PM | 30/Apr/26 12:00 AM | 3 | DE | [5 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-315 | 46989 | [Dev][RD][LP DB] Create database view for LP card binding reporting | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 07/Mar/26 12:08 PM | 15/May/26 1:25 PM | 24/Apr/26 12:00 AM | 3 | DE | [5 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-314 | 46988 | [Dev][RD][SSO-User DB] Create database view for active RC cards info | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 07/Mar/26 11:36 AM | 15/May/26 1:25 PM | 30/Apr/26 12:00 AM | 3 | DE | [5 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-312 | 46986 | [Dev][RD][PL DB] Create database view for partner transactions reporting | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 07/Mar/26 10:57 AM | 15/May/26 1:25 PM | 14/May/26 12:00 AM | 1 | DE |  |  |  |  | 7200 | [Dev][RD][New PE] Sprint 24
Story | DPE-311 | 46985 | [Dev][RD][PL DB] Create database view for partner unbind reporting | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 07/Mar/26 10:57 AM | 15/May/26 1:25 PM | 12/May/26 12:00 AM | 2 | DE |  |  |  |  | 14400 | [Dev][RD][New PE] Sprint 24
Story | DPE-310 | 46952 | [Dev][RD][PL DB] Create database view for partner binding reporting | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 07/Mar/26 5:36 AM | 15/May/26 1:25 PM | 12/May/26 12:00 AM | 1 | DE |  |  |  |  | 7200 | [Dev][RD][New PE] Sprint 24
Story | DRST-61 | 46883 | [DEV][RD][BOF] Remove Subscription V1 in backoffice and database | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 06/Mar/26 5:04 PM | 15/May/26 10:11 AM | 25/Mar/26 12:00 AM | 8 | [6 empty] | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22 | [Dev RD][VIMI Termi] Sprint 23 | [Dev RD][VIMI Termi] Sprint 24
Bug | DEVRDSUP-479 | 46025 | [SUP-564]ไม่สามารถดึง Available code ได้ ระบบขึ้นว่า No data found | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Pass : Waiting for deployment |  | 02/Mar/26 10:01 AM | 05/May/26 5:03 PM | 18/Mar/26 12:00 AM | 3 | rem | [5 empty] | [Dev][All Project] Sprint 20 | [Dev][All Project] Sprint 23 | [Dev][All Project] Sprint 21 | [Dev][All Project] Sprint 24
Story | DPE-303 | 45986 | Dev][RD][PE Proxy Scheduler] Implement command to import RW BTS trip transactions | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Ready To Test |  | 01/Mar/26 8:49 PM | 06/May/26 10:00 AM | 03/Apr/26 12:00 AM | 5 | [5 empty] | 86400 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-302 | 45985 | Dev][RD][PE Proxy Scheduler] Implement command to import RC BTS trip transactions | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Ready To Test |  | 01/Mar/26 8:49 PM | 06/May/26 10:00 AM | 01/Apr/26 12:00 AM | 8 | [5 empty] | 115200 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-301 | 45984 | [Dev][RD][PE Proxy Scheduler] Implement command for importing RW retail transactions | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 01/Mar/26 8:47 PM | 06/May/26 10:00 AM | 02/Apr/26 12:00 AM | 8 | [5 empty] | 72000 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-296 | 45845 | [Dev][RD][PE Proxy Scheduler] Implement command for importing RC retail transactions | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 27/Feb/26 1:40 PM | 06/May/26 10:00 AM | 31/Mar/26 12:00 AM | 8 | [6 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-295 | 45844 | [Dev][RD][PE Proxy Scheduler] Implement command to import merchant codes and offers from file | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 27/Feb/26 1:39 PM | 06/May/26 10:00 AM | 27/Mar/26 12:00 AM | 8 | [6 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-290 | 45375 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:49 AM | [8 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-281 | 45357 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [8 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-280 | 45355 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:58 PM | [8 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-279 | 45354 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 7:01 PM | [8 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-277 | 45351 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:59 PM | [8 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-278 | 45350 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:59 PM | [8 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-276 | 45343 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:59 PM | [8 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-275 | 45348 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:59 PM | [8 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-273 | 45342 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 7:01 PM | [8 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-272 | 45339 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:50 PM | [8 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-270 | 45335 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [8 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-269 | 45333 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [8 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-268 | 45331 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [8 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-267 | 45332 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [8 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-266 | 45329 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [8 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-265 | 45330 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [8 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-262 | 45319 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [8 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-261 | 45321 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [8 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DEVRDSUP-468 | 45126 | [SUP-552][MIXDATA][ETL] Redemption data ETL col "item_id", "using_at" and "countdown_expired_at" catch-up sync data. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | In Progress |  | 25/Feb/26 10:30 AM | 05/May/26 5:03 PM | 11/Mar/26 12:00 AM | 2 | data | [5 empty] | [Dev][All Project] Sprint 23 | [Dev][All Project] Sprint 21 | [Dev][All Project] Sprint 24
Sub-task | DPE-228 | 44837 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 23/Feb/26 5:45 PM | 12/Mar/26 11:45 AM | [8 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Sub-task | DPE-227 | 44835 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 23/Feb/26 5:45 PM | 12/Mar/26 11:46 AM | [8 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-207 | 44011 | [Dev][RD][SSO-User] Reward Add Card | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 18/Feb/26 3:42 PM | 06/May/26 10:00 AM |  | 1 | [6 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DRST-21 | 43078 | [DEV][RD][BOF] Enhance Subscription Txn V2 support filter from query string | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 11/Feb/26 7:10 PM | 15/May/26 10:11 AM |  | 2 | [5 empty] | 14400 | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22 | [Dev RD][VIMI Termi] Sprint 23 | [Dev RD][VIMI Termi] Sprint 24
Story | RDTHANA-447 | 43072 | [DEV][RD][TDM] Sync Order Data from Shopify Stores Refund | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 11/Feb/26 6:36 PM | 06/May/26 9:58 AM | 18/Mar/26 12:00 AM | 5 | Thana-datamart |  |  |  |  | 57600 | [Dev][RD][Thana] Sprint 20 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24
Story | RDTHANA-446 | 43071 | [DEV][RD][TDM] Sync Order Data from Shopify Stores to Data Mart #2 | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 11/Feb/26 6:36 PM | 06/May/26 9:58 AM | 20/Mar/26 12:00 AM | 5 | Thana-datamart |  |  |  |  | 57600 | [Dev][RD][Thana] Sprint 20 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24
Story | RDTHANA-445 | 43070 | [DEV][RD][TDM] Sync Order Data from Shopify Stores to Data Mart table | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 11/Feb/26 6:35 PM | 06/May/26 9:58 AM | 18/Mar/26 12:00 AM | 5 | Thana-datamart |  |  |  |  | 57600 | [Dev][RD][Thana] Sprint 20 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24
Story | RDTHANA-443 | 43068 | [DEV][RD][TDM] Create Webhook API Endpoint refunds/create | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 11/Feb/26 6:35 PM | 06/May/26 9:58 AM | 18/Mar/26 12:00 AM | 5 | Thana-datamart | [5 empty] | [Dev][RD][Thana] Sprint 20 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24
Story | RDTHANA-442 | 43067 | [DEV][RD][TDM] Create Webhook API Endpoint orders | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 11/Feb/26 6:34 PM | 06/May/26 9:58 AM | 16/Mar/26 12:00 AM | 5 | Thana-datamart |  |  |  |  | 57600 | [Dev][RD][Thana] Sprint 20 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24
Story | RDTHANA-441 | 43066 | [DEV][RD][TDM] Create migration | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 11/Feb/26 6:33 PM | 06/May/26 9:58 AM | 12/Mar/26 12:00 AM | 5 | No-QA | Thana-datamart |  |  |  | 57600 | [Dev][RD][Thana] Sprint 20 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24
Epic | RDTHANA-431 | 42991 | Lighspeed Polling |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 11/Feb/26 3:07 PM | 06/May/26 9:58 AM | 06/Mar/26 12:00 AM | [7 empty] | [Dev][RD][Thana] Sprint 19 | [Dev][RD][Thana] Sprint 20 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 18 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24 | [Dev][RD][Thana] Sprint 24
Story | DPE-167 | 42224 | [Dev][RD][RLP Web] Middleware | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 07/Feb/26 7:22 PM | 06/May/26 2:34 PM | 30/Apr/26 12:00 AM | 5 | [5 empty] | 7200 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-160 | 42217 | [Dev][RD][Rewards Member] Switch account | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 07/Feb/26 3:30 PM | 06/May/26 10:00 AM | 10/Apr/26 12:00 AM | 3 | [6 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-159 | 42216 | [Dev][RD][BFF] Get point history | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 07/Feb/26 3:24 PM | 15/May/26 10:28 AM | 22/Apr/69 12:00 AM | 5 | [6 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-147 | 42134 | [Dev][RD][SSO-User] WEB verify phone | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 6:37 PM | 06/May/26 10:00 AM |  | 1 | sso-user |  |  |  |  | 3600 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-146 | 42133 | [Dev][RD][SSO-User] WEB update avatar | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 6:37 PM | 06/May/26 10:00 AM |  | 1 | sso-user |  |  |  |  | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-145 | 42132 | [Dev][RD][SSO-User] WEB verify user | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 6:37 PM | 06/May/26 10:00 AM |  | 2 | sso-user |  |  |  |  | 10800 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-144 | 42131 | [Dev][RD][SSO-User] WEB remove card by card_id | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 6:37 PM | 06/May/26 10:00 AM |  | 1 | sso-user |  |  |  |  | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-143 | 42130 | [Dev][RD][SSO-User] WEB move card | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 6:36 PM | 06/May/26 10:00 AM | 05/Mar/26 12:00 AM | 1 | sso-user |  |  |  |  | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-142 | 42129 | [Dev][RD][SSO-User] WEB add card | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 6:36 PM | 06/May/26 10:00 AM |  | 1 | sso-user |  |  |  |  | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-141 | 42128 | [Dev][RD][SSO-User] WEB update profile by ID | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 6:36 PM | 06/May/26 10:00 AM | 12/Feb/26 12:00 AM | 2 | sso-user |  |  |  |  | 14400 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-140 | 42127 | [Dev][RD][PWP] Cancel transaction | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 6:35 PM | 13/May/26 1:09 PM |  | 5 | [6 empty] | [Dev][RD][New PE] Sprint 24
Story | DPE-139 | 42115 | [Dev][RD][RLP] Merchant | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Ready To Test |  | 06/Feb/26 2:53 PM | 06/May/26 2:34 PM | 28/Apr/26 12:00 AM | 3 | [5 empty] | 28800 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-138 | 42114 | [Dev][RD][RLP] Payment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Ready To Test |  | 06/Feb/26 2:53 PM | 06/May/26 2:34 PM | 23/Apr/26 12:00 AM | 3 | [5 empty] | 28800 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-137 | 42113 | [Dev][RD][RLP] Retrieve point balance | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 2:53 PM | 06/May/26 2:34 PM | 22/Apr/26 12:00 AM | 5 | [6 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-136 | 42112 | [Dev][RD][RLP] Command users:resend-binding | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 2:53 PM | 06/May/26 2:34 PM | 23/Apr/26 12:00 AM | 3 | [5 empty] | 28800 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-135 | 42111 | [Dev][RD][RLP] Bulk register by card | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 2:53 PM | 06/May/26 2:34 PM | 23/Apr/26 12:00 AM | 3 | [5 empty] | 28800 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-134 | 42110 | [Dev][RD][RLP] Register by card | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 2:53 PM | 06/May/26 2:34 PM | 28/Apr/26 12:00 AM | 2 | [5 empty] | 14400 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-133 | 42109 | [Dev][RD][RLP] Update card status is unbound by id | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 2:53 PM | 06/May/26 2:34 PM | 27/Apr/26 12:00 AM | 1 | [6 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-132 | 42108 | [Dev][RD][RLP] Update card status by id | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 2:53 PM | 06/May/26 2:34 PM | 27/Apr/26 12:00 AM | 1 | [6 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-131 | 42107 | [Dev][RD][RLP] Update card status | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 2:53 PM | 13/May/26 9:40 AM | 27/Apr/26 12:00 AM | 1 | [6 empty] | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-129 | 42104 | [Dev][RD][ATN] Realtime issue point API | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Ready To Test |  | 06/Feb/26 2:16 PM | 06/May/26 10:00 AM | 01/Apr/26 12:00 AM | 3 | [5 empty] | 28800 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-128 | 42103 | [Dev][RD][ATN] Request individual issue point API | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Ready To Test |  | 06/Feb/26 2:16 PM | 06/May/26 10:00 AM | 31/Mar/26 12:00 AM | 3 | [5 empty] | 28800 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-123 | 42098 | [Dev][RD][REMQ] Async coupon push | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 1:44 PM | 06/May/26 10:00 AM | 12/Mar/26 12:00 AM | 5 | [5 empty] | 57600 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-122 | 42097 | [Dev][RD][ECS] Cancel transaction | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 1:43 PM | 14/May/26 4:23 PM |  | 3 | [6 empty] | [Dev][RD][New PE] Sprint 24
Story | DPE-121 | 42096 | [Dev][RD][ECS] Refund transaction | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 1:43 PM | 14/May/26 4:23 PM |  | 5 | [6 empty] | [Dev][RD][New PE] Sprint 24
Story | DPE-120 | 42095 | [Dev][RD][ECS] Cronjob: Daily sync issue point | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 1:43 PM | 06/May/26 10:00 AM | 17/Apr/26 12:00 AM | 8 | ecommerce-shopify-api |  |  |  |  | 57600 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-116 | 42091 | [Dev][RD][VLD] Add card (mark use) | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 1:43 PM | 06/May/26 10:00 AM | 17/Apr/26 12:00 AM | 2 | [6 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-111 | 42054 | [Dev][RD][ATN] Bulk issue point for CRM Refund via RR-Backoffice | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Ready To Test |  | 06/Feb/26 12:11 PM | 06/May/26 10:00 AM | 03/Apr/26 12:00 AM | 5 | [5 empty] | 57600 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-110 | 42053 | [Dev][RD][APH] Submit data enrichment | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 12:11 PM | 06/May/26 10:00 AM | 17/Apr/26 12:00 AM | 3 | [5 empty] | 28800 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-109 | 42052 | [Dev][RD][APH] Survey processing | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 12:11 PM | 15/May/26 2:38 PM | 17/Apr/26 12:00 AM | 3 | [5 empty] | 28800 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-107 | 42050 | [Dev][RD][PWP] Refund transaction | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 12:10 PM | 14/May/26 4:23 PM |  | 5 | [6 empty] | [Dev][RD][New PE] Sprint 24
Story | DPE-106 | 42049 | [Dev][RD][PWP] Confirm payment | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 12:10 PM | 06/May/26 10:00 AM | 09/Apr/26 12:00 AM | 5 | [6 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-104 | 42047 | [Dev][RD][goutil] Revert Function | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 06/Feb/26 12:10 PM | 14/May/26 4:23 PM |  | 2 | No-QA | [5 empty] | [Dev][RD][New PE] Sprint 24
Story | DPE-103 | 42046 | [Dev][RD][goutil] Implement Point Engine Client Functions | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 11:54 AM | 06/May/26 10:00 AM |  | 3 | No-QA |  |  |  |  | 28800 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-101 | 41974 | [Dev][RD][BOF] Create/Update Package | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 05/Feb/26 4:49 PM | 14/May/26 3:59 PM | 20/Mar/26 12:00 AM | 3 | [6 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-100 | 41973 | [Dev][RD][BOF] Update product | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 05/Feb/26 4:49 PM | 15/May/26 10:08 AM | 20/Mar/26 12:00 AM | 3 | [6 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-99 | 41972 | [Dev][RD][BOF] Create a new product | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 05/Feb/26 4:49 PM | 14/May/26 3:59 PM | 20/Mar/26 12:00 AM | 3 | [6 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-98 | 41971 | [Dev][RD][ORD] Disable sending order transaction data to DA | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:49 PM | 06/May/26 10:00 AM |  | 3 | [5 empty] | 28800 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-97 | 41970 | [Dev][RD][ORD] Refund order (Partial Item) | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:48 PM | 15/May/26 9:02 AM | 14/May/26 12:00 AM | 3 | [6 empty] | [Dev][RD][New PE] Sprint 24
Story | DPE-96 | 41969 | [Dev][RD][ORD] Refund order (Full Items) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:48 PM | 14/May/26 4:23 PM | 13/May/26 12:00 AM | 5 | [6 empty] | [Dev][RD][New PE] Sprint 24
Story | DPE-95 | 41968 | [Dev][RD][ORD] Place subscription order | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:48 PM | 06/May/26 10:00 AM | 27/Mar/26 12:00 AM | 5 | [6 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-94 | 41967 | [Dev][RD][REM] Refund coupon v2 and revert point | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:48 PM | 14/May/26 4:23 PM | 15/May/26 12:00 AM | 5 | [5 empty] | 43200 | [Dev][RD][New PE] Sprint 24
Story | DPE-93 | 41966 | [Dev][RD][REM] Improve reward redemption v2 | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:48 PM | 06/May/26 10:00 AM |  | 5 | [5 empty] | 57600 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-92 | 41965 | [Dev][RD][Sky Web] Switch Account | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:46 PM | 14/May/26 3:59 PM | 19/Mar/26 12:00 AM | 5 | sky-web |  |  |  |  | 57600 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-91 | 41964 | [Dev][RD][Sky] Switch account API | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:46 PM | 14/May/26 3:59 PM | 19/Mar/26 12:00 AM | 3 | sky-api |  |  |  |  | 28800 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-90 | 41963 | [Dev][RD][Sky][Member] Reactivate | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:46 PM | 14/May/26 3:59 PM | 12/Mar/26 12:00 AM | 2 | sky-api | [5 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-89 | 41962 | [Dev][RD][Sky][Member] Register Member | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:46 PM | 14/May/26 3:59 PM | 13/Mar/26 12:00 AM | 3 | sky-api |  |  |  |  | 28800 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-87 | 41960 | [Dev][RD][PL][Point] Reverse transaction | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:46 PM | 15/May/26 1:24 PM | 08/May/26 12:00 AM | 5 | [6 empty] | [Dev][RD][New PE] Sprint 24
Story | DPE-86 | 41959 | [Dev][RD][PL] Create transaction | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 05/Feb/26 4:46 PM | 14/May/26 3:59 PM | 03/Apr/26 12:00 AM | 5 | [6 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-76 | 41527 | [Dev][RD][PL][Point] Reverse redeemed transaction | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 04/Feb/26 10:23 AM | 14/May/26 4:23 PM | 07/May/26 12:00 AM | 3 | [5 empty] | 28800 | [Dev][RD][New PE] Sprint 24
Story | DPE-75 | 41525 | [Dev][RD][PL] Request register | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Done |  | 04/Feb/26 10:17 AM | 14/May/26 3:59 PM | 03/Apr/26 12:00 AM | 2 | partner-loyalty | [5 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-74 | 41523 | [Dev][RD][SSO-User] Remove SSO-Thor API Integration | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Ready To Test |  | 04/Feb/26 10:13 AM | 06/May/26 10:00 AM |  | 5 | No-QA | sso-user |  |  |  | 57600 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-68 | 41511 | [Dev][RD][SSO-User] Rewards add card | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 04/Feb/26 9:49 AM | 06/May/26 10:00 AM | 10/Feb/26 12:00 AM | 1 | sso-user |  |  |  |  | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DPE-49 | 41435 | [Dev][RD][SSO-User] Rewards Verify phone | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 03/Feb/26 7:41 PM | 06/May/26 10:00 AM |  | 2 | sso-user |  |  |  |  | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23 | [Dev][RD][New PE] Sprint 24
Story | DRST-6 | 38163 | [Dev][RD][Terminate VIMI][VoucherValidator] Refactor APIs to remove dependency on MVP Phase 1 source | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Done |  | 07/Jan/26 11:12 AM | 15/May/26 10:11 AM | 10/Feb/26 12:00 AM | 3 | [5 empty] | 28800 | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22 | [Dev RD][VIMI Termi] Sprint 23 | [Dev RD][VIMI Termi] Sprint 24
Story | DRST-5 | 38162 | [Dev][RD][Terminate VIMI][MerchantAPI] Refactor APIs to remove dependency on MVP Phase 1 source | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Done |  | 07/Jan/26 11:12 AM | 15/May/26 10:11 AM | 11/Feb/26 12:00 AM | 3 | [5 empty] | 28800 | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22 | [Dev RD][VIMI Termi] Sprint 23 | [Dev RD][VIMI Termi] Sprint 24
Story | DRST-7 | 36975 | [Dev][RD][Terminate VIMI] Refactor TXN Report API and Report Summary API to remove dependency on MVP Phase 1 report source | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Done |  | 23/Dec/25 12:23 PM | 15/May/26 10:11 AM | 30/Dec/25 12:00 AM | 3 | [5 empty] | 28800 | [Dev][All Project] Sprint 15 | [Dev][All Project] Sprint 16 | [Dev RD][VIMI Termi] Sprint 17 | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22 | [Dev RD][VIMI Termi] Sprint 23 | [Dev RD][VIMI Termi] Sprint 24
Epic | DEVRDECOM-107 | 31506 | Shopify Webhook |  |  | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | To Do |  | 23/Sep/25 9:52 AM | 05/May/26 4:02 PM | [8 empty] | [Dev][RD][Ecom] Sprint 8 | [Dev][RD][Ecom] Sprint 9 | [Dev][RD][Ecom] Sprint 10 | [Dev][RD][Ecom] Sprint 11 | [Dev][RD][Ecom] Sprint 12 | [Dev][RD][Ecom] Sprint 13 | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15 | [Dev][RD][Ecom] Sprint 16 | [Dev][RD][Ecom] Sprint 23 | [Dev][RD][Ecom] Sprint 24

## Summarize Sprint 23
Column 1 | Total Stories Point | Total Manhour | Point Done | Manhour Done | Note
9 Mar - 20 Mar
Dev Resource Available | 21 | 444.5
Meeting Planned |  |  |  |  | Ref
Additional Meeting |  |  |  |  | Ref
Deployment |  | 2 |  |  | 1 ครั้ง 1. 2 คน
Development Sprint Total | 507 | 775.83 | 94 | 148.83
Ad-hoc Mid Sprint | 0 | 0 | 0 | 0 | 2 tasks
Requirement changes after refinement? | 0 |  | 0 | 0 | 0 tasks
Aek | 22 | 57.67 | 17 | 41.67
A | 73 | 202 | 13 | 36
Aom | 33 | 3.17 | 5 | 3.17
Zan | 27 | 0 | 14 | 0
Mai | 75 | 150 | 9 | 8
Mac | 82 | 181 | 4 | 0
Mos | 62 | 78 | 13 | 28
Jack | 11 | 0 | 11 | 0
Nim | 59 | 104 | 3 | 32
Arm | 63 | 0 | 5 | 0
| System Architech |  |  |  | Permanent Dev. |  |  | Contract | Outsource
Projects (Stories Points) | Aek | Zan | Aom | Jack | A | Mac | Mai | Arm | Mos | Nim

## Sprint 23
Issue Type | Issue key | Issue id | Summary | Assignee | Assignee Id | Reporter | Reporter Id | Priority | Status | Resolution | Created | Updated | Due date | Custom field (Story Points) | Labels | Labels | Labels | Original estimate | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint
Sub-task | DRST-94 | 53577 | [QA] Test Execution - UAT | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 30/Apr/26 5:35 PM | 30/Apr/26 5:35 PM | [6 empty] | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22 | [Dev RD][VIMI Termi] Sprint 23
Sub-task | DRST-93 | 53575 | [QA] Test Execution - STG | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 30/Apr/26 5:31 PM | 30/Apr/26 5:34 PM | [6 empty] | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22 | [Dev RD][VIMI Termi] Sprint 23
Story | RDAPS-457 | 53555 | [SA][RD] Task preparation #24 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 30/Apr/26 9:59 AM | 30/Apr/26 9:59 AM |  | 8 |  |  |  |  | [Dev][All Project] Sprint 23
Story | RDAPS-455 | 53517 | [SA][RD] PayPoint meeting | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 29/Apr/26 2:59 PM | 30/Apr/26 9:58 AM |  | 1 |  |  |  |  | [Dev][All Project] Sprint 23
Story | DPE-505 | 53504 | [Dev][RD][PEP] Update golang version | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 29/Apr/26 11:02 AM | 30/Apr/26 10:57 AM | 05/May/26 12:00 AM | 3 |  |  |  | 28800 | [Dev][RD][New PE] Sprint 23
Story | DPE-504 | 53501 | [Dev][RD] Provide credential information | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 29/Apr/26 10:23 AM | 30/Apr/26 3:19 PM |  | 1 |  |  |  |  | [Dev][RD][New PE] Sprint 23
Sub-task | DEVRDCT-370 | 53488 | [QA] Check CT catalogs (UAT) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 28/Apr/26 6:39 PM | 28/Apr/26 8:15 PM | [6 empty] | [Dev][RD][CT] Sprint 23
Sub-task | DPE-503 | 53479 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | To Do |  | 28/Apr/26 3:44 PM | 28/Apr/26 3:44 PM | [6 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-502 | 53477 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | To Do |  | 28/Apr/26 3:44 PM | 28/Apr/26 3:44 PM | [6 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-501 | 53475 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | To Do |  | 28/Apr/26 3:44 PM | 28/Apr/26 3:44 PM | [6 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-500 | 53473 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | To Do |  | 28/Apr/26 3:44 PM | 28/Apr/26 3:44 PM | [6 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-499 | 53471 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | To Do |  | 28/Apr/26 3:44 PM | 28/Apr/26 3:44 PM | [6 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-498 | 53469 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | To Do |  | 28/Apr/26 3:44 PM | 28/Apr/26 3:44 PM | [6 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-497 | 53467 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | To Do |  | 28/Apr/26 3:44 PM | 28/Apr/26 3:44 PM | [6 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-496 | 53465 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 28/Apr/26 3:44 PM | 29/Apr/26 5:35 PM | [6 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-495 | 53462 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 28/Apr/26 2:45 PM | 28/Apr/26 2:45 PM | [6 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-494 | 53460 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 28/Apr/26 2:45 PM | 28/Apr/26 2:45 PM | [6 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DEVRDSUP-562 | 53452 | [SUP-654]SUB : Disable Credit/Debit Card Payment for BBL Package (MAY2026 Package) | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 28/Apr/26 1:43 PM | 29/Apr/26 10:39 AM | 30/Apr/26 12:00 AM | 1 | BURequest | sub |  |  | [Dev][All Project] Sprint 23
Story | DPE-492 | 53440 | Dev][RD][REM] Implement Schema Versioning for Redeemed Transaction | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 28/Apr/26 9:24 AM | 30/Apr/26 9:18 AM | 30/Apr/26 12:00 AM | 3 |  |  |  |  | [Dev][RD][New PE] Sprint 23
Story | DPE-491 | 53439 | [Dev][RD][PE Middleware] Refactor OfferRepository: Consolidate GetOffer Methods into Generic Function | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready to Staging |  | 28/Apr/26 8:49 AM | 30/Apr/26 11:18 AM | 30/Apr/26 12:00 AM | 5 | point-engine-proxy |  |  |  | [Dev][RD][New PE] Sprint 23
Bug | DPE-490 | 53437 | [S3][NPE][Offer] Unable to create offer with inactive merchant | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 27/Apr/26 5:25 PM | 29/Apr/26 10:02 AM | 28/Apr/26 12:00 AM | [5 empty] | [Dev][RD][New PE] Sprint 23
Bug | DPE-489 | 53409 | [S3][NPE][Offer] Unable to create offer with transaction type = 0 | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 27/Apr/26 3:00 PM | 27/Apr/26 5:27 PM | [6 empty] | [Dev][RD][New PE] Sprint 23
Bug | DPE-488 | 53402 | [S2][NPE][PE Proxy] Able to credit/debit point with offer that under the other wallet | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Enhancement |  | 27/Apr/26 9:45 AM | 29/Apr/26 9:44 AM | [6 empty] | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-486 | 53397 | [QA] Test execution STG |  |  | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 25/Apr/26 12:46 PM | 25/Apr/26 12:46 PM | [6 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-485 | 53395 | [QA] Test execution STG |  |  | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 25/Apr/26 12:46 PM | 25/Apr/26 12:46 PM | [6 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-484 | 53393 | [QA] Test execution STG |  |  | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 25/Apr/26 12:46 PM | 25/Apr/26 12:46 PM | [6 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-483 | 53391 | [QA] Create Sky Web Switch Account test cases | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 25/Apr/26 12:40 PM | 25/Apr/26 12:44 PM | [6 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-482 | 53389 | [QA] Create Sky API Switch account test cases | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 25/Apr/26 12:38 PM | 25/Apr/26 12:43 PM | [6 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-481 | 53387 | [QA] Create Sky API Reactivate test cases | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 25/Apr/26 12:38 PM | 25/Apr/26 12:43 PM | [6 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-480 | 53385 | [QA] Test execution STG |  |  | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 25/Apr/26 12:36 PM | 25/Apr/26 12:36 PM | [6 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-479 | 53383 | [QA] Create Sky API Register Member test cases | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 25/Apr/26 12:35 PM | 30/Apr/26 11:48 AM | [6 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-478 | 53379 | [Dev][RD][BFF] Improve mapping API response message for Redemption API | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready to Staging |  | 24/Apr/26 7:25 PM | 29/Apr/26 4:10 PM |  | 2 |  |  |  |  | [Dev][RD][New PE] Sprint 23
Story | DEVRDECOM-241 | 53374 | [DEV][RD][Eco][Log] Adjusting Log Level | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 24/Apr/26 3:59 PM | 28/Apr/26 2:37 PM | 28/Apr/26 12:00 AM | 3 | ecommerce-shopify-api |  |  | 28800 | [Dev][RD][Ecom] Sprint 23
Sub-task | DEVRDSUP-559 | 53373 | Create new fix TXNs for correct members. | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 24/Apr/26 2:46 PM | 24/Apr/26 3:53 PM | [6 empty] | [Dev][All Project] Sprint 23
Sub-task | DEVRDSUP-558 | 53371 | Reverse TXNs from UL | Game (Krittapas Tanaprasitpattana) | 712020:85e9f474-8ee8-45ba-9249-cde16fa1cd35 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 24/Apr/26 2:45 PM | 24/Apr/26 3:28 PM | [6 empty] | [Dev][All Project] Sprint 23
Sub-task | DPE-477 | 53367 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | To Do |  | 24/Apr/26 2:10 PM | 24/Apr/26 2:10 PM | [6 empty] | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-476 | 53365 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 24/Apr/26 2:10 PM | 24/Apr/26 2:10 PM | [6 empty] | [Dev][RD][New PE] Sprint 23
Story | DEVRDSUP-557 | 53362 | [SUP-652][PL][HOP] Fix 4 HOP earn TXNs where incorrect Emp ID was used. | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 24/Apr/26 11:49 AM | 24/Apr/26 3:58 PM | 27/Apr/26 12:00 AM | 1 | hop | prod-issue |  | 7200 | [Dev][All Project] Sprint 23
Sub-task | DPE-475 | 53361 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 24/Apr/26 11:39 AM | 24/Apr/26 11:39 AM | [6 empty] | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-474 | 53359 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 24/Apr/26 11:39 AM | 24/Apr/26 4:23 PM | [6 empty] | [Dev][RD][New PE] Sprint 23
Story | DEVRDCT-369 | 53357 | [Dev][RD][RRS] Change fields & filter logic | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 24/Apr/26 11:26 AM | 30/Apr/26 2:25 PM |  | 3 | CleverTap |  |  |  | [Dev][RD][CT] Sprint 23
Sub-task | DPE-473 | 53355 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | In Progress |  | 24/Apr/26 10:57 AM | 24/Apr/26 3:27 PM | [6 empty] | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-472 | 53353 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 24/Apr/26 10:57 AM | 24/Apr/26 1:20 PM | [6 empty] | [Dev][RD][New PE] Sprint 23
Story | DPE-470 | 53336 | [Dev][RD][BFF] Enhance mapping detail fields from offer name to offer display name | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready to Staging |  | 23/Apr/26 3:48 PM | 27/Apr/26 10:47 AM | 30/Apr/26 12:00 AM | 1 | BFF |  |  | 7200 | [Dev][RD][New PE] Sprint 23
Story | DPE-469 | 53334 | [Dev][RD][PE Middleware] Enhance Offer Name Fields Mapping to CleverTap | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready To Test |  | 23/Apr/26 3:25 PM | 30/Apr/26 1:22 PM | 30/Apr/26 12:00 AM | 2 | point-engine-proxy |  |  | 7200 | [Dev][RD][New PE] Sprint 23
Story | RDAPS-454 | 53333 | [SA][RD][Thana] Review Access control API - Verify QR code | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 23/Apr/26 2:35 PM | 29/Apr/26 2:54 PM | 27/Apr/26 12:00 AM | [5 empty] | [Dev][All Project] Sprint 23
Story | RDAPS-451 | 53329 | [DEV][RD][SA] Investigate Algolia Usage Spike and Verify Cost Increase | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 23/Apr/26 1:24 PM | 24/Apr/26 4:11 PM | 27/Apr/26 12:00 AM | 5 | algolia | No-QA |  |  | [Dev][All Project] Sprint 23
Story | DPE-468 | 53300 | [Dev][RD][BOF] Improve product creation logic | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 22/Apr/26 3:51 PM | 28/Apr/26 10:49 AM |  | 1 |  |  |  |  | [Dev][RD][New PE] Sprint 23
Bug | DEVRDCT-368 | 53293 | [Dev][RD][RRS] incorrect show/hidden offer catalog in clevertap | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Resolved |  | 22/Apr/26 1:45 PM | 30/Apr/26 2:25 PM | 07/May/26 12:00 AM |  | CleverTap |  |  |  | [Dev][RD][CT] Sprint 23
Story | DPE-467 | 53291 | [Dev][RD][goutil] Improve func get point history to support additional filtering | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 22/Apr/26 1:15 PM | 23/Apr/26 4:56 PM |  | 1 |  |  |  |  | [Dev][RD][New PE] Sprint 23
Story | DPE-466 | 53282 | [Dev][RD][PE Proxy Scheduler] Enhance command for importing RC retail transactions#2 | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 22/Apr/26 10:06 AM | 24/Apr/26 9:15 AM | 23/Apr/26 12:00 AM | 1 |  |  |  |  | [Dev][RD][New PE] Sprint 23
Story | DPE-465 | 53281 | [Dev][RD][PE Proxy Scheduler] Enhance command for importing RW retail transactions#2 | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 22/Apr/26 10:06 AM | 24/Apr/26 9:15 AM | 23/Apr/26 12:00 AM | 2 |  |  |  |  | [Dev][RD][New PE] Sprint 23
Story | DPE-464 | 53271 | Dev][RD][PE Proxy Scheduler] Enhance command to import RC BTS trip transactions | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 22/Apr/26 8:37 AM | 29/Apr/26 9:49 AM | 29/Apr/26 12:00 AM | 3 |  |  |  |  | [Dev][RD][New PE] Sprint 23
Story | DPE-463 | 53270 | Dev][RD][PE Proxy Scheduler] Enhance command to import RW BTS trip transactions#1 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 22/Apr/26 8:35 AM | 27/Apr/26 2:02 PM | 27/Apr/26 12:00 AM | 3 |  |  |  |  | [Dev][RD][New PE] Sprint 23
Story | DPE-462 | 53267 | [Dev][RD][PE Proxy Scheduler] Enhance Offer Import Logic for Multi Transaction Type Support | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 21/Apr/26 4:37 PM | 24/Apr/26 6:34 PM | 24/Apr/26 12:00 AM | 3 |  |  |  |  | [Dev][RD][New PE] Sprint 23
Story | DPE-461 | 53266 | [Dev][RD][RLP] Migrate Git Remote from Bitbucket to GitHub for RLP Project (Staging) | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Progress |  | 21/Apr/26 4:14 PM | 22/Apr/26 9:32 AM | 27/Apr/26 12:00 AM | 5 |  |  |  | 86400 | [Dev][RD][New PE] Sprint 23
Bug | DPE-460 | 53265 | [S3][NPE][PL MEMBER] Get 500 Internal Server Error when sync BSS member to RR profile | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 21/Apr/26 3:31 PM | 22/Apr/26 4:21 PM | [6 empty] | [Dev][RD][New PE] Sprint 23
Story | DEVRDSUP-553 | 53262 | [SUP-645]Validate info from Algolia for overquota | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 21/Apr/26 3:00 PM | 28/Apr/26 3:16 PM | 05/May/26 12:00 AM |  | RR-services |  |  |  | [Dev][All Project] Sprint 23
Bug | DEVRDSUP-552 | 53259 | [SUP-644]incorrect show/hidden offer catalog in clevertap | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Closed |  | 21/Apr/26 2:51 PM | 30/Apr/26 3:11 PM | 05/May/26 12:00 AM |  | CleverTap | rem |  |  | [Dev][All Project] Sprint 23
Story | DEVRDSUP-550 | 53249 | [SUP-646][SUB] Receipt is not generated after SUB transaction is made (TXN Date 21 APR 2026) | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Thanakrit Chanthaworn | 712020:3fc982cb-c268-4f1d-9265-d3dd8fb08304 | Highest | Done |  | 21/Apr/26 10:51 AM | 21/Apr/26 11:00 AM | 21/Apr/26 12:00 AM | 1 |  |  |  | 600 | [Dev][All Project] Sprint 23
Story | DPE-459 | 53239 | [Dev][RD][RLP] Setup Docker Environment Dev for RLP Project (Github) | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Review |  | 21/Apr/26 9:50 AM | 21/Apr/26 4:17 PM | 22/Apr/26 12:00 AM | 2 |  |  |  | 14400 | [Dev][RD][New PE] Sprint 23
Story | DPE-458 | 53231 | [Dev][RD][SA] Meeting | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 20/Apr/26 4:52 PM | 28/Apr/26 3:13 PM |  | 8 |  |  |  |  | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-457 | 53230 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 20/Apr/26 3:54 PM | 24/Apr/26 3:25 PM | [6 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-456 | 53228 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 20/Apr/26 3:54 PM | 22/Apr/26 10:40 AM | [6 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-455 | 53226 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 20/Apr/26 3:54 PM | 27/Apr/26 11:23 AM | [6 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-454 | 53224 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 20/Apr/26 3:54 PM | 22/Apr/26 3:26 PM | [6 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-453 | 53222 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 20/Apr/26 3:54 PM | 23/Apr/26 5:54 PM | [6 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-452 | 53220 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 20/Apr/26 3:54 PM | 22/Apr/26 9:44 AM | [6 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-451 | 53218 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 20/Apr/26 3:33 PM | 28/Apr/26 2:05 PM | [6 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-450 | 53216 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 20/Apr/26 3:33 PM | 20/Apr/26 3:34 PM | [6 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-449 | 53213 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 20/Apr/26 3:03 PM | 28/Apr/26 2:04 PM | [6 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-448 | 53211 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 20/Apr/26 3:03 PM | 20/Apr/26 3:04 PM | [6 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | RDAPS-450 | 53208 | [SA][RD] Prepare task for Sprint 23, 24 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 20/Apr/26 2:39 PM | 30/Apr/26 4:04 PM |  | 2 |  |  |  | 14400 | [Dev][All Project] Sprint 23
Story | RDAPS-449 | 53207 | [SA][RD] Team Support & Management Sprint 23 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 20/Apr/26 2:32 PM | 29/Apr/26 4:44 PM |  | 5 |  |  |  | 57600 | [Dev][All Project] Sprint 23
Story | RDAPS-448 | 53206 | [SA][RD] Meeting Sprint 23 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 20/Apr/26 2:32 PM | 29/Apr/26 4:43 PM |  | 5 |  |  |  | 57600 | [Dev][All Project] Sprint 23
Story | DEVRDSUP-549 | 53203 | [SUP-635][CleverTap] Re-sync user's DOB for users whos DOB is miss matching from SSO. | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Done |  | 20/Apr/26 11:37 AM | 27/Apr/26 2:47 PM | 24/Apr/26 12:00 AM |  | CleverTap |  |  |  | [Dev][All Project] Sprint 23
Story | DPE-447 | 53200 | [Dev][RD][PL] Update API Documentation for 401 and 422 Response Format | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 20/Apr/26 9:43 AM | 27/Apr/26 10:49 AM | 30/Apr/26 12:00 AM | 1 | No-QA |  |  | 7200 | [Dev][RD][New PE] Sprint 23
Bug | DPE-445 | 53155 | [S4][API Respond][Member Opt-in][by sso id] The error responses body with wrong pattern | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Closed |  | 16/Apr/26 9:31 PM | 21/Apr/26 10:47 AM | [6 empty] | [Dev][RD][New PE] Sprint 23
Bug | DPE-441 | 53146 | [S4][API Respond][Member Opt-in][by phone no.] The error responses body with wrong pattern | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Closed |  | 16/Apr/26 3:57 PM | 21/Apr/26 10:36 AM | [6 empty] | [Dev][RD][New PE] Sprint 23
Story | DEVRDSUP-547 | 53098 | [SUP-640][SUB] Receipt is not generated after SUB transaction is made (TXN Date 9 APR 2026) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Highest | Done |  | 10/Apr/26 4:41 PM | 10/Apr/26 4:56 PM | 10/Apr/26 12:00 AM | 1 |  |  |  |  | [Dev][All Project] Sprint 23
Story | DEVRDECOM-240 | 52950 | [DEV][RD][Ecom][Turtle] Custom delivery option in checkout page | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 09/Apr/26 1:56 PM | 30/Apr/26 4:04 PM |  | 5 |  |  |  | 57600 | [Dev][RD][Ecom] Sprint 23
Bug | DPE-440 | 52946 | [S3][NPE][PL MEMBER] The response is incorrect when binding a member to an already bound partner using a new member ID | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 08/Apr/26 5:06 PM | 21/Apr/26 2:14 PM | [6 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | RDTHANA-479 | 52945 | [DEV][RD][TDM] Enhance Lightspeed master data support pagination | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 08/Apr/26 4:46 PM | 21/Apr/26 10:00 AM | 09/Apr/26 12:00 AM | [5 empty] | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23
Story | RDTHANA-478 | 52944 | [DEV][RD][TDM] Enhance lightspeed transaction mapping v2 | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 08/Apr/26 4:45 PM | 21/Apr/26 10:00 AM | 09/Apr/26 12:00 AM | 2 |  |  |  | 10800 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23
Story | DEVRDSUP-546 | 52932 | [SUP-638][PL][HOP] Fix 49 failed HOP tap card TXN where the Emp ID were incorrect on 25&26 Mar 2026. | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 08/Apr/26 3:34 PM | 24/Apr/26 3:54 PM | 23/Apr/26 12:00 AM | 2 | hop |  |  | 10800 | [Dev][All Project] Sprint 23
Story | DEVRDSUP-545 | 52925 | [SUP-636][REM][BURequest] Request to change 5645 coupon to be expired by reducing expiry to near close date/time. | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Done |  | 08/Apr/26 11:27 AM | 08/Apr/26 5:25 PM | 08/Apr/26 12:00 AM | 3 | BURequest | rem |  |  | [Dev][All Project] Sprint 23
Story | DPE-439 | 52923 | [Dev][RD] Support DevOps for Provision dedicated UAT-CT environment for Point Engine migration services#2 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 08/Apr/26 10:36 AM | 21/Apr/26 11:13 AM | 17/Apr/26 12:00 AM | 3 |  |  |  | 28800 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-438 | 52921 | [Dev][RD][ECS] Get Point Balance with New Point Engine | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 08/Apr/26 10:22 AM | 21/Apr/26 10:23 AM | 17/Apr/26 12:00 AM | 1 | ecommerce-shopify-api | No-QA |  | 7200 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Bug | DEVRDSUP-544 | 52910 | [SUP-632]Turtle plus data mismatch between clevertap and master file | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | UNDER VALIDATION |  | 07/Apr/26 3:02 PM | 30/Apr/26 5:02 PM |  |  | CleverTap | hr-solution | turtle |  | [Dev][All Project] Sprint 23
Story | DPWP-58 | 52908 | [SA][RD][HOP PWP] est. effort enhance Pay With Point API to support member identification | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 07/Apr/26 2:47 PM | 22/Apr/26 9:19 AM |  | 5 |  |  |  |  | [Dev][RD][PWP] Sprint 22 | [Dev][RD][PWP] Sprint 23
Story | DEVRDSUP-543 | 52900 | [SUP-633]Reverse auto push coupon status 7 Apr 26 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Done |  | 07/Apr/26 1:45 PM | 09/Apr/26 2:06 PM | 07/Apr/26 12:00 AM | 1 | BURequest | prod-issue | rem | 7200 | [Dev][All Project] Sprint 23
Story | RDAPS-445 | 52817 | [DEV][RD][SSO-Biforst] Create cronjob to generate R Cash member report | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 07/Apr/26 9:26 AM | 27/Apr/26 11:28 AM | 17/Apr/26 12:00 AM | 5 | No-QA |  |  | 57600 | [Dev][All Project] Sprint 22 | [Dev][All Project] Sprint 23
Story | DRST-86 | 52744 | [DEV][RD][BFF] POC golangci-lint upgrade effect | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 03/Apr/26 9:13 AM | 21/Apr/26 11:07 AM |  | 1 |  |  |  |  | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22 | [Dev RD][VIMI Termi] Sprint 23
Story | DPE-434 | 52743 | [Dev][RD][SSO Backoffice] Display point info | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 03/Apr/26 8:49 AM | 30/Apr/26 1:21 PM |  | 3 |  |  |  |  | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-433 | 52688 | [Dev][RD][PE Middleware] Enhance Point History and Point Expiry API | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 02/Apr/26 12:56 PM | 30/Apr/26 1:21 PM | 17/Apr/26 12:00 AM | 1 | point-engine-proxy |  |  | 7200 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-430 | 52638 | [Dev][RD][PE Proxy Scheduler] Enhance command for importing RW retail transactions#1 | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 01/Apr/26 7:41 PM | 22/Apr/26 3:39 PM | 22/Apr/26 12:00 AM | 3 |  |  |  |  | [Dev][RD][New PE] Sprint 23
Story | DEVRDSUP-536 | 52637 | [SUP-622]Group Rewards - Lucky Draw Xiaomi | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 01/Apr/26 6:35 PM | 07/Apr/26 4:40 PM | 07/Apr/26 12:00 AM | 1 | groupReward |  |  | 3600 | [Dev][All Project] Sprint 23
Story | DPE-429 | 52629 | [Dev][RD][PE Proxy Scheduler] Enhance command for importing RC retail transactions#1 | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 01/Apr/26 4:16 PM | 22/Apr/26 3:39 PM | 21/Apr/26 12:00 AM | 3 |  |  |  |  | [Dev][RD][New PE] Sprint 23
Story | DPE-426 | 52550 | [Dev][RD][Rewards DB] Create database view for products reporting | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 01/Apr/26 1:28 PM | 28/Apr/26 9:26 AM |  | 1 |  |  |  |  | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-425 | 52509 | [Dev][RD][PE Middleware] Enhance Get Offer List & Detail API to include offer_transaction_types | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 01/Apr/26 10:42 AM | 22/Apr/26 10:09 AM | [6 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-424 | 52507 | [Dev][RD][PE Middleware] Enhance Offer Update API | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 01/Apr/26 10:42 AM | 22/Apr/26 10:09 AM | [6 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-421 | 52500 | [Dev][RD][PE Middleware] Enhance Validate Debit Point API with offer_transaction_types | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 01/Apr/26 10:21 AM | 22/Apr/26 10:09 AM |  |  | point-engine-proxy |  |  |  | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-420 | 52497 | [Dev][RD][PE Middleware] Enhance Validate Credit Point API with offer_transaction_types | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 01/Apr/26 10:21 AM | 22/Apr/26 10:09 AM | [6 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-419 | 52495 | [Dev][RD][PE Middleware] Enhance Offer Creation API to use offer_transaction_types | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 01/Apr/26 10:21 AM | 22/Apr/26 11:06 AM | [6 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-418 | 52493 | [Dev][RD][PE Middleware] Create table offer_transaction_types | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 01/Apr/26 10:20 AM | 22/Apr/26 10:09 AM |  |  | point-engine-proxy |  |  |  | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-417 | 52491 | [Dev][RD][PE Middleware] Enhance Database & Offer Transaction Validation | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 01/Apr/26 10:17 AM | 30/Apr/26 1:21 PM | 17/Apr/26 12:00 AM | 8 | point-engine-proxy |  |  | 57600 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DEVRDSUP-532 | 51925 | [SUP-611][SUB] CS-#20260300026199 // Request mark used Rabbit wallet 0888092803456 // Coupon code 11939634 | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 30/Mar/26 9:08 AM | 30/Apr/26 11:23 AM |  | 1 | bts | BURequest | sub |  | [Dev][All Project] Sprint 23
Story | DPE-412 | 51891 | [Dev][RD][PE Middleware] Enhance get wallet history to support filtering | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 29/Mar/26 2:55 PM | 30/Apr/26 1:21 PM | 17/Apr/26 12:00 AM | 3 | point-engine-proxy |  |  |  | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DRST-81 | 51769 | [DEV][RD][BFF] Enhance user me upload avatar support max file size to 5MB | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Blocked |  | 27/Mar/26 2:50 PM | 21/Apr/26 11:07 AM |  | 2 |  |  |  | 14400 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22 | [Dev RD][VIMI Termi] Sprint 23
Story | DEVRDSUP-531 | 51725 | [SUP-556][RR Account] CS-20260200025299 Kindly check 1 Rabbit Card Wallet but has 2 SSO ID [ Trader ID: 30901904/ Trader ID: 33059294] - 0880067155542 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 27/Mar/26 12:05 PM | 08/Apr/26 5:08 PM |  | 1 | RabbitWallet | sso |  | 600 | [Dev][All Project] Sprint 21 | [Dev][All Project] Sprint 23
Story | DPE-407 | 51720 | [Dev][RD][SA] POC CleverTap Promo Code | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 27/Mar/26 11:59 AM | 28/Apr/26 10:25 AM |  | 8 | No-QA |  |  |  | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-406 | 51719 | [Dev][RD][PEP DB] Create database view for standard offer code reporting | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 27/Mar/26 11:46 AM | 27/Apr/26 10:49 AM | 30/Apr/26 12:00 AM | 3 |  |  |  | 14400 | [Dev][RD][New PE] Sprint 23
Story | DPE-403 | 51703 | [Dev][RD][PE Middleware] Enhance API to get point balance | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 27/Mar/26 9:04 AM | 30/Apr/26 1:22 PM |  | 3 |  |  |  | 28800 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DEVRDSUP-529 | 51621 | [SUP-612][HRSolution] Request to remove 1 member from HR solution due to email conflict with new member. | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | To Do |  | 26/Mar/26 3:06 PM | 21/Apr/26 10:08 AM |  |  | hop | hr-solution |  |  | [Dev][All Project] Sprint 23
Story | RDTHANA-475 | 51568 | [DEV][RD][TDM] CT Event : ORDER_SUCCESS_HOOK | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Lowest | Ready to Staging |  | 26/Mar/26 11:09 AM | 30/Apr/26 3:00 PM | 30/Apr/26 12:00 AM | 5 |  |  |  | 57600 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23
Story | RDTHANA-474 | 51567 | [DEV][RD][TDM] CT Event : REFUND_PAID_HOOK | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 26/Mar/26 11:09 AM | 23/Apr/26 10:44 AM | 30/Apr/26 12:00 AM | 5 |  |  |  |  | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24
Story | RDTHANA-473 | 51566 | [DEV][RD][TDM] CT Event : PAYMENT_PAID_{SHOP_NAME} | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 26/Mar/26 11:09 AM | 30/Apr/26 2:05 PM | 30/Apr/26 12:00 AM | 5 |  |  |  | 43200 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23
Story | RDTHANA-472 | 51565 | [DEV][RD][TDM] Consumer : Push to CT | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 26/Mar/26 11:08 AM | 29/Apr/26 2:54 PM | 24/Apr/26 12:00 AM | 5 |  |  |  | 43200 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23
Story | RDTHANA-471 | 51562 | [DEV][RD][TDM] CleverTap Service setting | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 26/Mar/26 11:08 AM | 29/Apr/26 2:54 PM | 21/Apr/69 12:00 AM | 3 |  |  |  | 21600 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23
Story | RDTHANA-470 | 51559 | [DEV][RD][TDM] Fine member by multipass token | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 26/Mar/26 11:07 AM | 29/Apr/26 2:54 PM | 22/Apr/26 12:00 AM | 3 |  |  |  | 21600 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23
Story | RDTHANA-468 | 51555 | [DEV][RD][TDM] Webhook Event : Fullfilment | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 26/Mar/26 11:07 AM | 21/Apr/26 10:00 AM | 10/Apr/26 12:00 AM | 3 |  |  |  |  | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23
Story | RDTHANA-467 | 51553 | [DEV][RD][TDM] Integrate Thana City Database (Hook DB) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 26/Mar/26 11:06 AM | 21/Apr/26 10:00 AM | 08/Apr/26 12:00 AM | 3 |  |  |  | 21600 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23
Story | RDTHANA-465 | 51545 | [DEV][RD][TDM] Enhance Shopify access token flow | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 26/Mar/26 9:37 AM | 23/Apr/26 11:32 AM | 26/Mar/26 12:00 AM | 3 | No-QA | Thana-datamart |  | 28800 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23
Story | DPE-399 | 51496 | [Dev][RD][Rewards DB] Create database view for `packages` reporting | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 25/Mar/26 4:44 PM | 27/Apr/26 10:50 AM | 30/Apr/26 12:00 AM | 3 |  |  |  | 14400 | [Dev][RD][New PE] Sprint 23
Story | DPE-392 | 51392 | [Dev][RD][SSO-User] Update 'inactive' status on CT for terminated account | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 25/Mar/26 11:23 AM | 30/Apr/26 1:21 PM | 17/Apr/26 12:00 AM | 3 | sso-user |  |  | 28800 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Bug | DPE-391 | 51390 | [S3][NPE][PL MEMBER] Get 500 Internal Server Error when bind member | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 25/Mar/26 11:01 AM | 22/Apr/26 3:56 PM | [6 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-389 | 51265 | [Dev][RD][REM] Add additional event perpoties to `REDEEM` event | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 24/Mar/26 3:54 PM | 20/Apr/26 5:10 PM |  | 3 |  |  |  |  | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Bug | DEVRDSUP-510 | 51251 | [SUP-591]Urgent [CRM-Refund] CS-20260200024957 Cannot Refund at RR Back office | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Closed |  | 24/Mar/26 2:39 PM | 29/Apr/26 11:21 AM |  | 1 | bts | sub |  |  | [Dev][All Project] Sprint 21 | [Dev][All Project] Sprint 23
Bug | DEVRDSUP-509 | 51239 | [SUP-592]Urgent [CRM] CS-20260200024940 - Cannot Refund / Green Line PromptPay method | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Closed |  | 24/Mar/26 2:03 PM | 29/Apr/26 10:19 AM |  | 1 | sub |  |  |  | [Dev][All Project] Sprint 21 | [Dev][All Project] Sprint 23
Story | DEVRDSUP-508 | 51204 | [SUP-547]CS-20260100024282 รบกวนช่วยตรวจสอบ Refund Package Pay with Point สถานะที่ RR Backoffice ไม่เปลี่ยนเป็น Refunded แต่ได้ Points คืนแล้ว | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 24/Mar/26 1:19 PM | 28/Apr/26 5:24 PM |  | 2 | sub |  |  |  | [Dev][All Project] Sprint 21 | [Dev][All Project] Sprint 23
Story | RDAPS-440 | 50959 | [SA][RD][App Handover] Review Technical Spec | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Low | To Do |  | 23/Mar/26 11:27 AM | 29/Apr/26 2:54 PM | [6 empty] | [Dev][All Project] Sprint 23
Story | RDAPS-439 | 50958 | [SA][RD][App Handover] Review Source Code Documentation | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Low | Done |  | 23/Mar/26 11:27 AM | 30/Apr/26 4:00 PM |  | 1 |  |  |  | 1800 | [Dev][All Project] Sprint 23
Story | RDAPS-438 | 50957 | [SA][RD][App Handover] Review Software Design and Architecture Documentation | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Low | In Progress |  | 23/Mar/26 11:26 AM | 29/Apr/26 3:51 PM |  | 5 |  |  |  |  | [Dev][All Project] Sprint 21 | [Dev][All Project] Sprint 22 | [Dev][All Project] Sprint 23
Epic | RDNDA-35 | 50602 | Enhance Lightspeed txn |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 22/Mar/26 11:18 PM | 09/Apr/26 9:29 AM | 03/Apr/26 12:00 AM |  | Thana-datamart |  |  |  | [Dev][RD][NewDamart] Sprint 21 | [Dev][RD][Ecom] Sprint 23
Epic | RDTHANA-464 | 50601 | Enhance Lightspeed txn |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 22/Mar/26 11:17 PM | 21/Apr/26 11:12 AM | 03/Apr/26 12:00 AM | [5 empty] | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23
Story | DPE-374 | 50550 | [Dev][RD][ATN] Bulk issue point for MKT campaign | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Ready To Test |  | 22/Mar/26 10:28 AM | 21/Apr/26 10:22 AM | 03/Apr/26 12:00 AM | 5 |  |  |  | 57600 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DRST-78 | 50221 | Delete Report Service (wait SA -> P'Zan) | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Medium | Done |  | 19/Mar/26 1:49 PM | 25/Mar/26 11:45 AM | [6 empty] | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22 | [Dev RD][VIMI Termi] Sprint 23
Sub-task | DRST-77 | 50218 | Delete-> Model ->Repository-> Service | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Medium | Done |  | 19/Mar/26 1:49 PM | 20/Mar/26 11:22 AM | [5 empty] | 28800 | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22 | [Dev RD][VIMI Termi] Sprint 23
Sub-task | DRST-76 | 50206 | Delete View -> Api route -> controller | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Medium | Done |  | 19/Mar/26 1:40 PM | 20/Mar/26 11:22 AM | [5 empty] | 14400 | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22 | [Dev RD][VIMI Termi] Sprint 23
Sub-task | DRST-75 | 50201 | List service,repo,model | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Medium | Done |  | 19/Mar/26 1:39 PM | 20/Mar/26 11:22 AM | [5 empty] | 43200 | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22 | [Dev RD][VIMI Termi] Sprint 23
Story | RDNDA-33 | 50166 | [DEV][RD][TDM] Enhance Lightspeed Cronjob to Use Access Token from Hook App Service | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 19/Mar/26 11:26 AM | 09/Apr/26 11:22 AM | 25/Mar/26 12:00 AM | 2 |  |  |  | 14400 | [Dev][RD][NewDamart] Sprint 21 | [Dev][RD][Ecom] Sprint 23
Story | RDNDA-32 | 50165 | [DEV][RD][TDM] Create Hook App Service to Retrieve Lightspeed Access Token | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 19/Mar/26 11:25 AM | 09/Apr/26 11:22 AM | 25/Mar/26 12:00 AM | 2 |  |  |  | 14400 | [Dev][RD][NewDamart] Sprint 21 | [Dev][RD][Ecom] Sprint 23
Story | RDTHANA-463 | 50163 | [DEV][RD][TDM] Enhance Data Mapping for Lightspeed Polling Transactions | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 19/Mar/26 11:10 AM | 21/Apr/26 10:00 AM | 30/Mar/26 12:00 AM | 5 | Thana-datamart |  |  | 43200 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23
Story | DPE-362 | 50117 | [Dev][RD][SA][Sprint24] Analysis & Task Breakdown for PE Migration Execution | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 18/Mar/26 4:03 PM | 24/Apr/26 2:10 PM |  | 13 |  |  |  |  | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-357 | 48623 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 17/Mar/26 10:16 AM | 17/Mar/26 10:16 AM | [6 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-356 | 48621 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | In Progress |  | 17/Mar/26 10:16 AM | 20/Mar/26 4:30 PM | [6 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Bug | DEVRDSUP-501 | 48539 | [SUP-584]HOP check in notification delay | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Mook Nicharee Boonthai | 712020:c2ed8478-f54b-4b43-92d9-b933a57493dc | Medium | Rejected |  | 16/Mar/26 5:42 PM | 22/Apr/26 10:20 AM | [6 empty] | [Dev][All Project] Sprint 20 | [Dev][All Project] Sprint 21 | [Dev][All Project] Sprint 23
Bug | DEVRDSUP-499 | 48499 | [SUP-583]Issue auto push coupon campaign error number mismatch with failed event | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Mook Nicharee Boonthai | 712020:c2ed8478-f54b-4b43-92d9-b933a57493dc | Medium | UNDER VALIDATION |  | 16/Mar/26 3:20 PM | 07/Apr/26 1:55 PM | [6 empty] | [Dev][All Project] Sprint 21 | [Dev][All Project] Sprint 23
Sub-task | DPE-349 | 48488 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 16/Mar/26 2:30 PM | 22/Apr/26 4:21 PM | [6 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-348 | 48484 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 16/Mar/26 2:30 PM | 22/Apr/26 3:57 PM | [6 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-342 | 48475 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 16/Mar/26 2:30 PM | 23/Mar/26 7:44 PM | [6 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-340 | 48469 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 16/Mar/26 2:30 PM | 23/Mar/26 7:44 PM | [6 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-338 | 48464 | [QA] Test execution |  |  | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 16/Mar/26 2:14 PM | 17/Mar/26 10:16 AM | [6 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-337 | 48462 | [QA] Create test case | THUNDER(QA): PAWICH | 712020:83ff944e-9677-453f-b053-40e92520d905 | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | In Progress |  | 16/Mar/26 2:14 PM | 17/Mar/26 10:16 AM | [6 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-336 | 48460 | [QA] Test execution |  |  | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 16/Mar/26 2:14 PM | 17/Mar/26 10:15 AM | [6 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-335 | 48458 | [QA] Create test case | THUNDER(QA): PAWICH | 712020:83ff944e-9677-453f-b053-40e92520d905 | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | In Progress |  | 16/Mar/26 2:14 PM | 17/Mar/26 10:15 AM | [6 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-334 | 48391 | [Dev][RD][SSO Backoffice] Disable 'Sync Card' button | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 16/Mar/26 12:49 PM | 30/Apr/26 1:21 PM | 17/Apr/26 12:00 AM | 2 | sso-backoffice |  |  | 14400 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-319 | 47258 | [Dev][RD][REM] Improve reward redemption with 0 point | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 09/Mar/26 5:15 PM | 20/Apr/26 5:10 PM |  | 3 |  |  |  | 28800 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-318 | 47096 | [Dev][RD][PL] Create new partner | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 09/Mar/26 9:39 AM | 30/Apr/26 1:21 PM | 03/Apr/26 12:00 AM | 3 |  |  |  | 28800 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-317 | 47023 | [Dev][RD][PE Middleware][CT Blocker] Reversal API | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 07/Mar/26 7:44 PM | 29/Apr/26 10:16 AM | 30/Apr/26 12:00 AM | 5 | point-engine-proxy |  |  | 7200 | [Dev][RD][New PE] Sprint 23
Story | DPE-316 | 46990 | [Dev][RD][PEP DB] Create database view for standard merchants code reporting | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 07/Mar/26 12:11 PM | 27/Apr/26 9:51 AM |  | 3 |  |  |  |  | [Dev][RD][New PE] Sprint 23
Story | DPE-315 | 46989 | [Dev][RD][LP DB] Create database view for LP card binding reporting | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 07/Mar/26 12:08 PM | 23/Apr/26 2:23 PM | 24/Apr/26 12:00 AM | 3 |  |  |  |  | [Dev][RD][New PE] Sprint 23
Story | DPE-314 | 46988 | [Dev][RD][SSO-User DB] Create database view for active RC cards info | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 07/Mar/26 11:36 AM | 27/Apr/26 8:49 AM |  | 3 |  |  |  |  | [Dev][RD][New PE] Sprint 23
Story | DRST-61 | 46883 | [DEV][RD][BOF] Remove Subscription V1 in backoffice and database | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 06/Mar/26 5:04 PM | 21/Apr/26 9:14 AM | 25/Mar/26 12:00 AM | 8 |  |  |  |  | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22 | [Dev RD][VIMI Termi] Sprint 23
Bug | DEVRDSUP-479 | 46025 | [SUP-564]ไม่สามารถดึง Available code ได้ ระบบขึ้นว่า No data found | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Pass : Waiting for deployment |  | 02/Mar/26 10:01 AM | 17/Apr/26 11:12 AM | 18/Mar/26 12:00 AM | 3 | rem |  |  |  | [Dev][All Project] Sprint 20 | [Dev][All Project] Sprint 21 | [Dev][All Project] Sprint 23
Story | DPE-303 | 45986 | Dev][RD][PE Proxy Scheduler] Implement command to import RW BTS trip transactions | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Ready To Test |  | 01/Mar/26 8:49 PM | 22/Apr/26 12:57 PM | 03/Apr/26 12:00 AM | 5 |  |  |  | 86400 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-302 | 45985 | Dev][RD][PE Proxy Scheduler] Implement command to import RC BTS trip transactions | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Ready To Test |  | 01/Mar/26 8:49 PM | 20/Apr/26 5:10 PM | 01/Apr/26 12:00 AM | 8 |  |  |  | 115200 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-301 | 45984 | [Dev][RD][PE Proxy Scheduler] Implement command for importing RW retail transactions | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 01/Mar/26 8:47 PM | 20/Apr/26 5:10 PM | 02/Apr/26 12:00 AM | 8 |  |  |  | 72000 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-296 | 45845 | [Dev][RD][PE Proxy Scheduler] Implement command for importing RC retail transactions | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 27/Feb/26 1:40 PM | 20/Apr/26 5:10 PM | 31/Mar/26 12:00 AM | 8 |  |  |  |  | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-295 | 45844 | [Dev][RD][PE Proxy Scheduler] Implement command to import merchant codes and offers from file | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 27/Feb/26 1:39 PM | 21/Apr/26 4:45 PM | 27/Mar/26 12:00 AM | 8 |  |  |  |  | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-290 | 45375 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:49 AM | [6 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-281 | 45357 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [6 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-280 | 45355 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:58 PM | [6 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-279 | 45354 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 7:01 PM | [6 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-277 | 45351 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:59 PM | [6 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-278 | 45350 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:59 PM | [6 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-276 | 45343 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:59 PM | [6 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-275 | 45348 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:59 PM | [6 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-273 | 45342 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 7:01 PM | [6 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-272 | 45339 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:50 PM | [6 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-270 | 45335 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [6 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-269 | 45333 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [6 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-268 | 45331 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [6 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-267 | 45332 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [6 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-266 | 45329 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [6 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-265 | 45330 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [6 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-262 | 45319 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [6 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-261 | 45321 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [6 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DEVRDSUP-468 | 45126 | [SUP-552][MIXDATA][ETL] Redemption data ETL col "item_id", "using_at" and "countdown_expired_at" catch-up sync data. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | In Progress |  | 25/Feb/26 10:30 AM | 28/Apr/26 3:03 PM | 11/Mar/26 12:00 AM | 2 | data |  |  |  | [Dev][All Project] Sprint 21 | [Dev][All Project] Sprint 23
Sub-task | DPE-228 | 44837 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 23/Feb/26 5:45 PM | 12/Mar/26 11:45 AM | [6 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-227 | 44835 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 23/Feb/26 5:45 PM | 12/Mar/26 11:46 AM | [6 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-207 | 44011 | [Dev][RD][SSO-User] Reward Add Card | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 18/Feb/26 3:42 PM | 20/Apr/26 5:10 PM |  | 1 |  |  |  |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DRST-21 | 43078 | [DEV][RD][BOF] Enhance Subscription Txn V2 support filter from query string | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 11/Feb/26 7:10 PM | 21/Apr/26 9:14 AM |  | 2 |  |  |  | 14400 | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22 | [Dev RD][VIMI Termi] Sprint 23
Story | RDTHANA-447 | 43072 | [DEV][RD][TDM] Sync Order Data from Shopify Stores Refund | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 11/Feb/26 6:36 PM | 21/Apr/26 10:00 AM | 18/Mar/26 12:00 AM | 5 | Thana-datamart |  |  | 57600 | [Dev][RD][Thana] Sprint 20 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23
Story | RDTHANA-446 | 43071 | [DEV][RD][TDM] Sync Order Data from Shopify Stores to Data Mart #2 | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 11/Feb/26 6:36 PM | 21/Apr/26 10:00 AM | 20/Mar/26 12:00 AM | 5 | Thana-datamart |  |  | 57600 | [Dev][RD][Thana] Sprint 20 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23
Story | RDTHANA-445 | 43070 | [DEV][RD][TDM] Sync Order Data from Shopify Stores to Data Mart table | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 11/Feb/26 6:35 PM | 21/Apr/26 10:00 AM | 18/Mar/26 12:00 AM | 5 | Thana-datamart |  |  | 57600 | [Dev][RD][Thana] Sprint 20 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23
Story | RDTHANA-443 | 43068 | [DEV][RD][TDM] Create Webhook API Endpoint refunds/create | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 11/Feb/26 6:35 PM | 21/Apr/26 10:00 AM | 18/Mar/26 12:00 AM | 5 | Thana-datamart |  |  |  | [Dev][RD][Thana] Sprint 20 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23
Story | RDTHANA-442 | 43067 | [DEV][RD][TDM] Create Webhook API Endpoint orders | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 11/Feb/26 6:34 PM | 21/Apr/26 10:00 AM | 16/Mar/26 12:00 AM | 5 | Thana-datamart |  |  | 57600 | [Dev][RD][Thana] Sprint 20 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23
Story | RDTHANA-441 | 43066 | [DEV][RD][TDM] Create migration | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 11/Feb/26 6:33 PM | 21/Apr/26 10:00 AM | 12/Mar/26 12:00 AM | 5 | No-QA | Thana-datamart |  | 57600 | [Dev][RD][Thana] Sprint 20 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23
Epic | RDTHANA-431 | 42991 | Lighspeed Polling |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 11/Feb/26 3:07 PM | 21/Apr/26 10:00 AM | 06/Mar/26 12:00 AM | [5 empty] | [Dev][RD][Thana] Sprint 19 | [Dev][RD][Thana] Sprint 20 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 18 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 23
Story | DPE-167 | 42224 | [Dev][RD][RLP Web] Middleware | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 07/Feb/26 7:22 PM | 27/Apr/26 10:50 AM | 30/Apr/26 12:00 AM | 5 |  |  |  | 7200 | [Dev][RD][New PE] Sprint 23
Story | DPE-160 | 42217 | [Dev][RD][Rewards Member] Switch account | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 07/Feb/26 3:30 PM | 20/Apr/26 5:10 PM | 10/Apr/26 12:00 AM | 3 |  |  |  |  | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-159 | 42216 | [Dev][RD][BFF] Get point history | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 07/Feb/26 3:24 PM | 30/Apr/26 1:21 PM | 22/Apr/69 12:00 AM | 5 |  |  |  |  | [Dev][RD][New PE] Sprint 23
Story | DPE-147 | 42134 | [Dev][RD][SSO-User] WEB verify phone | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 6:37 PM | 20/Apr/26 5:10 PM |  | 1 | sso-user |  |  | 3600 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-146 | 42133 | [Dev][RD][SSO-User] WEB update avatar | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 6:37 PM | 20/Apr/26 5:10 PM |  | 1 | sso-user |  |  | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-145 | 42132 | [Dev][RD][SSO-User] WEB verify user | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 6:37 PM | 20/Apr/26 5:10 PM |  | 2 | sso-user |  |  | 10800 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-144 | 42131 | [Dev][RD][SSO-User] WEB remove card by card_id | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 6:37 PM | 20/Apr/26 5:10 PM |  | 1 | sso-user |  |  | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-143 | 42130 | [Dev][RD][SSO-User] WEB move card | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 6:36 PM | 21/Apr/26 11:11 AM | 05/Mar/26 12:00 AM | 1 | sso-user |  |  | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-142 | 42129 | [Dev][RD][SSO-User] WEB add card | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 6:36 PM | 20/Apr/26 5:10 PM |  | 1 | sso-user |  |  | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-141 | 42128 | [Dev][RD][SSO-User] WEB update profile by ID | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 6:36 PM | 20/Apr/26 5:10 PM | 12/Feb/26 12:00 AM | 2 | sso-user |  |  | 14400 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-139 | 42115 | [Dev][RD][RLP] Merchant | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Ready To Test |  | 06/Feb/26 2:53 PM | 28/Apr/26 10:51 AM | 28/Apr/26 12:00 AM | 3 |  |  |  | 28800 | [Dev][RD][New PE] Sprint 23
Story | DPE-138 | 42114 | [Dev][RD][RLP] Payment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Ready to Staging |  | 06/Feb/26 2:53 PM | 23/Apr/26 2:29 PM | 23/Apr/26 12:00 AM | 3 |  |  |  | 28800 | [Dev][RD][New PE] Sprint 23
Story | DPE-137 | 42113 | [Dev][RD][RLP] Retrieve point balance | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 2:53 PM | 28/Apr/26 10:57 AM | 22/Apr/26 12:00 AM | 5 |  |  |  |  | [Dev][RD][New PE] Sprint 23
Story | DPE-136 | 42112 | [Dev][RD][RLP] Command users:resend-binding | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 06/Feb/26 2:53 PM | 28/Apr/26 10:00 AM | 23/Apr/26 12:00 AM | 3 |  |  |  | 28800 | [Dev][RD][New PE] Sprint 23
Story | DPE-135 | 42111 | [Dev][RD][RLP] Bulk register by card | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 2:53 PM | 28/Apr/26 4:02 PM | 23/Apr/26 12:00 AM | 3 |  |  |  | 28800 | [Dev][RD][New PE] Sprint 23
Story | DPE-134 | 42110 | [Dev][RD][RLP] Register by card | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 2:53 PM | 28/Apr/26 4:50 PM | 28/Apr/26 12:00 AM | 2 |  |  |  | 14400 | [Dev][RD][New PE] Sprint 23
Story | DPE-133 | 42109 | [Dev][RD][RLP] Update card status is unbound by id | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 2:53 PM | 27/Apr/26 5:02 PM | 27/Apr/26 12:00 AM | 1 |  |  |  |  | [Dev][RD][New PE] Sprint 23
Story | DPE-132 | 42108 | [Dev][RD][RLP] Update card status by id | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 2:53 PM | 28/Apr/26 10:03 AM | 27/Apr/26 12:00 AM | 1 |  |  |  |  | [Dev][RD][New PE] Sprint 23
Story | DPE-131 | 42107 | [Dev][RD][RLP] Update card status | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 06/Feb/26 2:53 PM | 28/Apr/26 10:03 AM | 27/Apr/26 12:00 AM | 1 |  |  |  |  | [Dev][RD][New PE] Sprint 23
Story | DPE-129 | 42104 | [Dev][RD][ATN] Realtime issue point API | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Ready To Test |  | 06/Feb/26 2:16 PM | 21/Apr/26 11:12 AM | 01/Apr/26 12:00 AM | 3 |  |  |  | 28800 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-128 | 42103 | [Dev][RD][ATN] Request individual issue point API | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Ready To Test |  | 06/Feb/26 2:16 PM | 21/Apr/26 11:12 AM | 31/Mar/26 12:00 AM | 3 |  |  |  | 28800 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-123 | 42098 | [Dev][RD][REMQ] Async coupon push | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 1:44 PM | 20/Apr/26 5:10 PM | 12/Mar/26 12:00 AM | 5 |  |  |  | 57600 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-120 | 42095 | [Dev][RD][ECS] Cronjob: Daily sync issue point | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 1:43 PM | 20/Apr/26 5:10 PM | 17/Apr/26 12:00 AM | 8 | ecommerce-shopify-api |  |  | 57600 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-116 | 42091 | [Dev][RD][VLD] Add card (mark use) | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 1:43 PM | 21/Apr/26 9:46 AM | 17/Apr/26 12:00 AM | 2 |  |  |  |  | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-113 | 42088 | [Dev][RD][RRS] command: da:redemptions | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | To Do |  | 06/Feb/26 1:42 PM | 01/Apr/26 7:56 PM |  | 0 |  |  |  |  | [Dev][RD][New PE] Sprint 23
Story | DPE-111 | 42054 | [Dev][RD][ATN] Bulk issue point for CRM Refund via RR-Backoffice | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Ready To Test |  | 06/Feb/26 12:11 PM | 21/Apr/26 10:22 AM | 03/Apr/26 12:00 AM | 5 |  |  |  | 57600 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-110 | 42053 | [Dev][RD][APH] Submit data enrichment | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 12:11 PM | 21/Apr/26 10:23 AM | 17/Apr/26 12:00 AM | 3 |  |  |  | 28800 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-109 | 42052 | [Dev][RD][APH] Survey processing | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 12:11 PM | 21/Apr/26 10:23 AM | 17/Apr/26 12:00 AM | 3 |  |  |  | 28800 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-106 | 42049 | [Dev][RD][PWP] Confirm payment | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 12:10 PM | 20/Apr/26 5:10 PM | 09/Apr/26 12:00 AM | 5 |  |  |  |  | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-103 | 42046 | [Dev][RD][goutil] Implement Point Engine Client Functions | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 11:54 AM | 20/Apr/26 5:10 PM |  | 3 | No-QA |  |  | 28800 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-101 | 41974 | [Dev][RD][BOF] Create/Update Package | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:49 PM | 30/Apr/26 1:22 PM | 20/Mar/26 12:00 AM | 3 |  |  |  |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-100 | 41973 | [Dev][RD][BOF] Update product | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:49 PM | 20/Apr/26 5:10 PM | 20/Mar/26 12:00 AM | 3 |  |  |  |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-99 | 41972 | [Dev][RD][BOF] Create a new product | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:49 PM | 30/Apr/26 1:21 PM | 20/Mar/26 12:00 AM | 3 |  |  |  |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-98 | 41971 | [Dev][RD][ORD] Disable sending order transaction data to DA | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:49 PM | 20/Apr/26 5:10 PM |  | 3 |  |  |  | 28800 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-95 | 41968 | [Dev][RD][ORD] Place subscription order | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:48 PM | 23/Apr/26 4:46 PM | 27/Mar/26 12:00 AM | 5 |  |  |  |  | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-93 | 41966 | [Dev][RD][REM] Improve reward redemption v2 | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:48 PM | 20/Apr/26 5:10 PM |  | 5 |  |  |  | 57600 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-92 | 41965 | [Dev][RD][Sky Web] Switch Account | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:46 PM | 30/Apr/26 1:22 PM | 19/Mar/26 12:00 AM | 5 | sky-web |  |  | 57600 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-91 | 41964 | [Dev][RD][Sky] Switch account API | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:46 PM | 30/Apr/26 1:22 PM | 19/Mar/26 12:00 AM | 3 | sky-api |  |  | 28800 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-90 | 41963 | [Dev][RD][Sky][Member] Reactivate | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:46 PM | 30/Apr/26 1:22 PM | 12/Mar/26 12:00 AM | 2 | sky-api |  |  |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-89 | 41962 | [Dev][RD][Sky][Member] Register Member | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:46 PM | 30/Apr/26 1:21 PM | 13/Mar/26 12:00 AM | 3 | sky-api |  |  | 28800 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-86 | 41959 | [Dev][RD][PL] Create transaction | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:46 PM | 30/Apr/26 1:21 PM | 03/Apr/26 12:00 AM | 5 |  |  |  |  | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-77 | 41529 | [Dev][RD][PL] Redeem point | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 04/Feb/26 10:23 AM | 30/Apr/26 1:21 PM | 03/Apr/26 12:00 AM | 5 |  |  |  |  | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-75 | 41525 | [Dev][RD][PL] Request register | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Ready To Test |  | 04/Feb/26 10:17 AM | 30/Apr/26 1:22 PM | 03/Apr/26 12:00 AM | 2 | partner-loyalty |  |  |  | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-74 | 41523 | [Dev][RD][SSO-User] Remove SSO-Thor API Integration | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Ready To Test |  | 04/Feb/26 10:13 AM | 20/Apr/26 5:10 PM |  | 5 | No-QA | sso-user |  | 57600 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-68 | 41511 | [Dev][RD][SSO-User] Rewards add card | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 04/Feb/26 9:49 AM | 20/Apr/26 5:10 PM | 10/Feb/26 12:00 AM | 1 | sso-user |  |  | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-65 | 41499 | [Dev][RD][PL][Member] Sync RR member | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 04/Feb/26 9:18 AM | 22/Apr/26 4:21 PM | 10/Mar/26 12:00 AM | 3 | partner-loyalty |  |  | 28800 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-64 | 41497 | [Dev][RD][PL][Member] Member binding | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 04/Feb/26 9:16 AM | 22/Apr/26 3:57 PM | 13/Mar/26 12:00 AM | 5 | partner-loyalty |  |  |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-49 | 41435 | [Dev][RD][SSO-User] Rewards Verify phone | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 03/Feb/26 7:41 PM | 20/Apr/26 5:10 PM |  | 2 | sso-user |  |  | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | RDNDA-18 | 40130 | [DEV][RD][TDM] Create access control callback endpoint | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 22/Jan/26 5:03 PM | 09/Apr/26 9:29 AM |  | 3 |  |  |  | 28800 | [Dev][RD][NewDamart] Sprint 17 | [Dev][RD][NewDamart] Sprint 18 | [Dev][RD][NewDamart] Sprint 19 | [Dev][RD][NewDamart] Sprint 20 | [Dev][RD][NewDamart] Sprint 21 | [Dev][RD][Ecom] Sprint 23
Story | RDNDA-6 | 38244 | [DEV][RD][TDM] Create generic transactions endpoint | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 07/Jan/26 5:17 PM | 09/Apr/26 9:29 AM |  | 5 | Thana-datamart |  |  | 86400 | [Dev][RD][NewDamart] Sprint 16 | [Dev][RD][NewDamart] Sprint 17 | [Dev][RD][NewDamart] Sprint 18 | [Dev][RD][NewDamart] Sprint 19 | [Dev][RD][NewDamart] Sprint 20 | [Dev][RD][NewDamart] Sprint 21 | [Dev][RD][Ecom] Sprint 23
Story | DRST-6 | 38163 | [Dev][RD][Terminate VIMI][VoucherValidator] Refactor APIs to remove dependency on MVP Phase 1 source | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready To Test |  | 07/Jan/26 11:12 AM | 21/Apr/26 9:13 AM | 10/Feb/26 12:00 AM | 3 |  |  |  | 28800 | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22 | [Dev RD][VIMI Termi] Sprint 23
Story | DRST-5 | 38162 | [Dev][RD][Terminate VIMI][MerchantAPI] Refactor APIs to remove dependency on MVP Phase 1 source | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready To Test |  | 07/Jan/26 11:12 AM | 24/Apr/26 9:24 AM | 11/Feb/26 12:00 AM | 3 |  |  |  | 28800 | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22 | [Dev RD][VIMI Termi] Sprint 23
Story | DEVRRBOF-204 | 37406 | [Dev][RD][BOF][Improvement][Performance] Improve page load performance on Reward Detail page | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 28/Dec/25 8:56 PM | 23/Feb/26 10:26 AM |  | 3 | rr-backoffice |  |  |  | [Dev][RRBack] 15 | [Dev][RD][Ecom] Sprint 23
Story | DRST-7 | 36975 | [Dev][RD][Terminate VIMI] Refactor TXN Report API and Report Summary API to remove dependency on MVP Phase 1 report source | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready To Test |  | 23/Dec/25 12:23 PM | 21/Apr/26 9:14 AM | 30/Dec/25 12:00 AM | 3 |  |  |  | 28800 | [Dev][All Project] Sprint 15 | [Dev][All Project] Sprint 16 | [Dev RD][VIMI Termi] Sprint 17 | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22 | [Dev RD][VIMI Termi] Sprint 23
Epic | DEVRDCT-359 | 36930 | FIX-Identity-Error |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 23/Dec/25 9:38 AM | 07/Apr/26 10:05 AM | [6 empty] | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15 | [Dev][RD][CT] Sprint 16 | [Dev][RD][CT] Sprint 21 | [Dev][RD][CT] Sprint 23
Bug | DEVRDCT-358 | 36929 | [DEV][RD][HRS] Delay Auto CLUB_BINDING to Prevent Intermittent Identity Error | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Resolved |  | 23/Dec/25 8:59 AM | 07/Apr/26 10:05 AM |  | 2 |  |  |  |  | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15 | [Dev][RD][CT] Sprint 16 | [Dev][RD][CT] Sprint 21 | [Dev][RD][CT] Sprint 23
Epic | DEVRDCT-326 | 35192 | CT-POINT-ISSUE |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 01/Dec/25 9:58 AM | 07/Apr/26 10:05 AM | [6 empty] | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15 | [Dev][RD][CT] Sprint 16 | [Dev][RD][CT] Sprint 21 | [Dev][RD][CT] Sprint 23
Epic | DEVRDCT-325 | 35191 | CTxSHOPIFY |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 01/Dec/25 9:55 AM | 07/Apr/26 10:05 AM | [6 empty] | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15 | [Dev][RD][CT] Sprint 16 | [Dev][RD][CT] Sprint 21 | [Dev][RD][CT] Sprint 23
Epic | DEVRDCT-309 | 34545 | ct-member-tier |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 19/Nov/25 2:49 PM | 07/Apr/26 10:05 AM | [6 empty] | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15 | [Dev][RD][CT] Sprint 16 | [Dev][RD][CT] Sprint 21 | [Dev][RD][CT] Sprint 23
Epic | DEVRDCT-308 | 34539 | ct-campaign-type |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 19/Nov/25 10:41 AM | 07/Apr/26 10:05 AM |  |  | redemption-api |  |  |  | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15 | [Dev][RD][CT] Sprint 16 | [Dev][RD][CT] Sprint 21 | [Dev][RD][CT] Sprint 23
Epic | DEVRDECOM-107 | 31506 | Shopify Webhook |  |  | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | To Do |  | 23/Sep/25 9:52 AM | 28/Jan/26 10:22 AM | [6 empty] | [Dev][RD][Ecom] Sprint 8 | [Dev][RD][Ecom] Sprint 9 | [Dev][RD][Ecom] Sprint 10 | [Dev][RD][Ecom] Sprint 11 | [Dev][RD][Ecom] Sprint 12 | [Dev][RD][Ecom] Sprint 13 | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15 | [Dev][RD][Ecom] Sprint 16 | [Dev][RD][Ecom] Sprint 23

## Summarize Sprint 22
Column 1 | Total Stories Point | Total Manhour | Point Done | Manhour Done | Note
9 Mar - 20 Mar
Dev Resource Available | 21 | 444.5
Meeting Planned |  |  |  |  | Ref
Additional Meeting |  |  |  |  | Ref
Deployment |  | 2 |  |  | 1 ครั้ง 1. 2 คน
Development Sprint Total | 378 | 716 | 97 | 225
Ad-hoc Mid Sprint | 0 | 0 | 0 | 0 | 2 tasks
Requirement changes after refinement? | 0 |  | 0 | 0 | 0 tasks
Aek | 18 | 52 | 18 | 52
A | 54 | 158 | 12 | 24
Aom | 8 | 16 | 8 | 16
Zan | 13 | 0 | 5 | 0
Mai | 56 | 118 | 2 | 4
Mac | 56 | 143 | 3 | 6
Mos | 55 | 116 | 22 | 66
Jack | 14 | 0 | 6 | 0
Nim | 54 | 113 | 18 | 57
Arm | 50 | 0 | 3 | 0
| System Architech |  |  |  | Permanent Dev. |  |  | Contract | Outsource
Projects (Stories Points) | Aek | Zan | Aom | Jack | A | Mac | Mai | Arm | Mos | Nim

## Sprint 22
Issue Type | Issue key | Issue id | Summary | Assignee | Assignee Id | Reporter | Reporter Id | Priority | Status | Resolution | Created | Updated | Due date | Custom field (Story Points) | Labels | Labels | Original estimate | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint
Sub-task | DPE-457 | 53230 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 20/Apr/26 3:54 PM | 20/Apr/26 3:54 PM | [5 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-456 | 53228 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | In Progress |  | 20/Apr/26 3:54 PM | 21/Apr/26 3:56 PM | [5 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-455 | 53226 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 20/Apr/26 3:54 PM | 20/Apr/26 3:54 PM | [5 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-454 | 53224 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 20/Apr/26 3:54 PM | 20/Apr/26 3:54 PM | [5 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-453 | 53222 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 20/Apr/26 3:54 PM | 20/Apr/26 3:54 PM | [5 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-452 | 53220 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | In Progress |  | 20/Apr/26 3:54 PM | 21/Apr/26 3:56 PM | [5 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-451 | 53218 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 20/Apr/26 3:33 PM | 20/Apr/26 3:33 PM | [5 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-450 | 53216 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 20/Apr/26 3:33 PM | 20/Apr/26 3:34 PM | [5 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-449 | 53213 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 20/Apr/26 3:03 PM | 20/Apr/26 3:03 PM | [5 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-448 | 53211 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 20/Apr/26 3:03 PM | 20/Apr/26 3:04 PM | [5 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-444 | 53154 | Retest issues | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 16/Apr/26 9:23 PM | 20/Apr/26 11:48 AM | [5 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Bug | DPE-440 | 52946 | [S3][NPE][PL MEMBER] The response is incorrect when binding a member to an already bound partner using a new member ID | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 08/Apr/26 5:06 PM | 21/Apr/26 2:14 PM | [5 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | RDTHANA-479 | 52945 | [DEV][RD][TDM] Enhance Lightspeed master data support pagination | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 08/Apr/26 4:46 PM | 21/Apr/26 10:00 AM | 09/Apr/26 12:00 AM |  |  |  |  | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24
Story | RDTHANA-478 | 52944 | [DEV][RD][TDM] Enhance lightspeed transaction mapping v2 | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 08/Apr/26 4:45 PM | 21/Apr/26 10:00 AM | 09/Apr/26 12:00 AM | 2 |  |  | 10800 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24
Sub-task | DRST-92 | 52943 | [QA] Test Execution - UAT |  |  | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 08/Apr/26 4:36 PM | 09/Apr/26 2:51 PM | [5 empty] | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22
Sub-task | DRST-91 | 52941 | [QA] Test Execution - STG |  |  | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 08/Apr/26 4:35 PM | 08/Apr/26 4:43 PM | [5 empty] | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22
Sub-task | DRST-89 | 52929 | [QA] Test Execution - UAT | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 08/Apr/26 2:29 PM | 09/Apr/26 2:43 PM | [5 empty] | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22
Sub-task | DRST-88 | 52927 | [QA] Test Execution - STG | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 08/Apr/26 2:28 PM | 08/Apr/26 4:38 PM | [5 empty] | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22
Story | DPE-439 | 52923 | [Dev][RD] Support DevOps for Provision dedicated UAT-CT environment for Point Engine migration services#2 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 08/Apr/26 10:36 AM | 21/Apr/26 11:13 AM | 17/Apr/26 12:00 AM | 3 |  |  | 28800 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-438 | 52921 | [Dev][RD][ECS] Get Point Balance with New Point Engine | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 08/Apr/26 10:22 AM | 21/Apr/26 10:23 AM | 17/Apr/26 12:00 AM | 1 | ecommerce-shopify-api | No-QA | 7200 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | RDAPS-447 | 52918 | [SA][RD] Team Supoort & Management Sprint 22 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 08/Apr/26 9:43 AM | 10/Apr/26 1:22 PM |  | 3 |  |  | 28800 | [Dev][All Project] Sprint 22
Story | RDAPS-446 | 52917 | [SA][RD] Meeting Sprint 22 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 08/Apr/26 9:43 AM | 10/Apr/26 1:22 PM |  | 3 |  |  | 28800 | [Dev][All Project] Sprint 22
Story | DPWP-58 | 52908 | [SA][RD][HOP PWP] est. effort enhance Pay With Point API to support member identification | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 07/Apr/26 2:47 PM | 22/Apr/26 9:19 AM |  | 5 |  |  |  | [Dev][RD][PWP] Sprint 22 | [Dev][RD][PWP] Sprint 23
Story | DPE-437 | 52829 | [Dev][RD][RR CT] Allow Event RABBIT_CARD_TRANSACTION_OTHER to Whitelist | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 07/Apr/26 10:09 AM | 08/Apr/26 4:45 PM | 17/Apr/26 12:00 AM | 1 | CleverTap | No-QA |  | [Dev][RD][New PE] Sprint 22
Story | RDAPS-445 | 52817 | [DEV][RD][SSO-Biforst] Create cronjob to generate R Cash member report | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 07/Apr/26 9:26 AM | 21/Apr/26 10:03 AM | 17/Apr/26 12:00 AM | 5 |  |  | 57600 | [Dev][All Project] Sprint 22 | [Dev][All Project] Sprint 23
Bug | DPE-435 | 52768 | [S3][NPE][PL MEMBER] rabbit_point is null when call api check the member detail | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 03/Apr/26 3:22 PM | 07/Apr/26 5:29 PM | [5 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DRST-86 | 52744 | [DEV][RD][BFF] POC golangci-lint upgrade effect | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 03/Apr/26 9:13 AM | 21/Apr/26 11:07 AM |  | 1 |  |  |  | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22 | [Dev RD][VIMI Termi] Sprint 23
Story | DPE-434 | 52743 | [Dev][RD][SSO Backoffice] Display point info | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 03/Apr/26 8:49 AM | 20/Apr/26 5:10 PM |  | 3 |  |  |  | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DRST-85 | 52742 | [DEV][RD][BFF] Create remove card endpoint | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 02/Apr/26 11:49 PM | 17/Apr/26 10:49 AM | 03/Apr/26 12:00 AM | 3 |  |  | 21600 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22
Story | DRST-84 | 52741 | [DEV][RD][BFF] Create add card endpoint | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 02/Apr/26 11:49 PM | 17/Apr/26 10:49 AM |  | 5 |  |  |  | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22
Story | DPE-433 | 52688 | [Dev][RD][PE Middleware] Enhance Point History and Point Expiry API | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready To Test |  | 02/Apr/26 12:56 PM | 21/Apr/26 11:18 AM | 17/Apr/26 12:00 AM | 1 | point-engine-proxy |  | 7200 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-425 | 52509 | [Dev][RD][PE Middleware] Enhance Get Offer List & Detail API to include offer_transaction_types | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | In Review |  | 01/Apr/26 10:42 AM | 01/Apr/26 3:57 PM | [5 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-424 | 52507 | [Dev][RD][PE Middleware] Enhance Offer Update API | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | In Review |  | 01/Apr/26 10:42 AM | 02/Apr/26 2:53 PM | [5 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-421 | 52500 | [Dev][RD][PE Middleware] Enhance Validate Debit Point API with offer_transaction_types | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | In Review |  | 01/Apr/26 10:21 AM | 02/Apr/26 3:22 PM |  |  | point-engine-proxy |  |  | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-420 | 52497 | [Dev][RD][PE Middleware] Enhance Validate Credit Point API with offer_transaction_types | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | In Review |  | 01/Apr/26 10:21 AM | 02/Apr/26 3:22 PM | [5 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-419 | 52495 | [Dev][RD][PE Middleware] Enhance Offer Creation API to use offer_transaction_types | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | In Review |  | 01/Apr/26 10:21 AM | 02/Apr/26 2:53 PM | [5 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-418 | 52493 | [Dev][RD][PE Middleware] Create table offer_transaction_types | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | In Review |  | 01/Apr/26 10:20 AM | 01/Apr/26 3:57 PM |  |  | point-engine-proxy |  |  | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-417 | 52491 | [Dev][RD][PE Middleware] Enhance Database & Offer Transaction Validation | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready To Test |  | 01/Apr/26 10:17 AM | 21/Apr/26 11:18 AM | 17/Apr/26 12:00 AM | 8 | point-engine-proxy |  | 57600 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-416 | 52133 | [Dev][RD][PE Middleware] Integrate Swagger / API Spec Documentation | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 31/Mar/26 9:50 AM | 20/Apr/26 10:54 AM | 01/Apr/26 12:00 AM | 3 | No-QA |  | 28800 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-412 | 51891 | [Dev][RD][PE Middleware] Enhance get wallet history to support filtering | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 29/Mar/26 2:55 PM | 21/Apr/26 11:18 AM | 17/Apr/26 12:00 AM | 3 | point-engine-proxy |  |  | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DRST-81 | 51769 | [DEV][RD][BFF] Enhance user me upload avatar support max file size to 5MB | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Blocked |  | 27/Mar/26 2:50 PM | 21/Apr/26 11:07 AM |  | 2 |  |  | 14400 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22 | [Dev RD][VIMI Termi] Sprint 23
Story | DPE-407 | 51720 | [Dev][RD][SA] POC CleverTap Promo Code | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 27/Mar/26 11:59 AM | 21/Apr/26 9:40 AM |  | 8 | No-QA |  |  | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-404 | 51708 | [SA] Prepare Task description for RLP Sprint 23 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 27/Mar/26 9:57 AM | 10/Apr/26 4:23 PM |  | 2 |  |  | 14400 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-403 | 51703 | [Dev][RD][PE Middleware] Enhance API to get point balance | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 27/Mar/26 9:04 AM | 20/Apr/26 5:10 PM |  | 3 |  |  | 28800 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | RDTHANA-468 | 51555 | [DEV][RD][TDM] Webhook Event : Fullfilment | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 26/Mar/26 11:07 AM | 21/Apr/26 10:00 AM | 10/Apr/26 12:00 AM | 3 |  |  |  | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24
Story | RDTHANA-467 | 51553 | [DEV][RD][TDM] Integrate Thana City Database (Hook DB) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 26/Mar/26 11:06 AM | 21/Apr/26 10:00 AM | 08/Apr/26 12:00 AM | 3 |  |  | 21600 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24
Story | RDTHANA-465 | 51545 | [DEV][RD][TDM] Enhance Shopify access token flow | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 26/Mar/26 9:37 AM | 21/Apr/26 10:00 AM | 26/Mar/26 12:00 AM | 3 |  |  | 28800 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24
Story | DPE-393 | 51393 | [Dev][RD][SA][CT Blocker] Analyze Reversal Flow | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 25/Mar/26 11:43 AM | 19/Apr/26 11:32 AM |  | 5 | No-QA |  |  | [Dev][RD][New PE] Sprint 22
Story | DPE-392 | 51392 | [Dev][RD][SSO-User] Update 'inactive' status on CT for terminated account | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 25/Mar/26 11:23 AM | 21/Apr/26 11:18 AM | 17/Apr/26 12:00 AM | 3 | sso-user |  | 28800 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Bug | DPE-391 | 51390 | [S3][NPE][PL MEMBER] Get 500 Internal Server Error when bind member | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Reopened |  | 25/Mar/26 11:01 AM | 21/Apr/26 3:32 PM | [5 empty] | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-389 | 51265 | [Dev][RD][REM] Add additional event perpoties to `REDEEM` event | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 24/Mar/26 3:54 PM | 20/Apr/26 5:10 PM |  | 3 |  |  |  | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | RDAPS-438 | 50957 | [SA][RD][App Handover] Review Software Design and Architecture Documentation | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Low | In Progress |  | 23/Mar/26 11:26 AM | 21/Apr/26 9:20 AM |  | 8 |  |  |  | [Dev][All Project] Sprint 21 | [Dev][All Project] Sprint 22 | [Dev][All Project] Sprint 23
Story | RDAPS-437 | 50915 | [SA][RD] Team Supoort & Management Sprint 21 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 23/Mar/26 9:12 AM | 09/Apr/26 9:42 AM |  | 5 |  |  | 57600 | [Dev][All Project] Sprint 21 | [Dev][All Project] Sprint 22
Story | RDAPS-436 | 50914 | [SA][RD] Meeting Sprint 21 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 23/Mar/26 9:11 AM | 09/Apr/26 9:42 AM |  | 5 |  |  | 57600 | [Dev][All Project] Sprint 21 | [Dev][All Project] Sprint 22
Epic | RDTHANA-464 | 50601 | Enhance Lightspeed txn |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 22/Mar/26 11:17 PM | 21/Apr/26 11:12 AM | 03/Apr/26 12:00 AM |  |  |  |  | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24
Story | DPE-374 | 50550 | [Dev][RD][ATN] Bulk issue point for MKT campaign | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Ready To Test |  | 22/Mar/26 10:28 AM | 21/Apr/26 10:22 AM | 03/Apr/26 12:00 AM | 5 |  |  | 57600 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DRST-78 | 50221 | Delete Report Service (wait SA -> P'Zan) | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Medium | Done |  | 19/Mar/26 1:49 PM | 25/Mar/26 11:45 AM | [5 empty] | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22 | [Dev RD][VIMI Termi] Sprint 23
Sub-task | DRST-77 | 50218 | Delete-> Model ->Repository-> Service | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Medium | Done |  | 19/Mar/26 1:49 PM | 20/Mar/26 11:22 AM |  |  |  |  | 28800 | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22 | [Dev RD][VIMI Termi] Sprint 23
Sub-task | DRST-76 | 50206 | Delete View -> Api route -> controller | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Medium | Done |  | 19/Mar/26 1:40 PM | 20/Mar/26 11:22 AM |  |  |  |  | 14400 | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22 | [Dev RD][VIMI Termi] Sprint 23
Sub-task | DRST-75 | 50201 | List service,repo,model | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Medium | Done |  | 19/Mar/26 1:39 PM | 20/Mar/26 11:22 AM |  |  |  |  | 43200 | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22 | [Dev RD][VIMI Termi] Sprint 23
Story | RDTHANA-463 | 50163 | [DEV][RD][TDM] Enhance Data Mapping for Lightspeed Polling Transactions | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 19/Mar/26 11:10 AM | 21/Apr/26 10:00 AM | 30/Mar/26 12:00 AM | 5 | Thana-datamart |  | 43200 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24
Story | DPE-361 | 50116 | [Dev][RD][SA][Sprint23] Analysis & Task Breakdown for PE Migration Execution | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 18/Mar/26 4:02 PM | 20/Apr/26 5:40 AM |  | 8 |  |  | 57600 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-357 | 48623 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 17/Mar/26 10:16 AM | 17/Mar/26 10:16 AM | [5 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-356 | 48621 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | In Progress |  | 17/Mar/26 10:16 AM | 20/Mar/26 4:30 PM | [5 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-355 | 48538 | [Dev][RD][PE Middleware] Create Seed Data for table data_sources and transaction_types | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 16/Mar/26 5:27 PM | 20/Apr/26 2:21 PM |  | 2 | point-engine-proxy |  | 14400 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-354 | 48496 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 16/Mar/26 2:30 PM | 08/Apr/26 12:57 PM | [5 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-353 | 48494 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 16/Mar/26 2:30 PM | 08/Apr/26 2:07 PM | [5 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-352 | 48492 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 16/Mar/26 2:30 PM | 08/Apr/26 12:54 PM | [5 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-351 | 48491 | Test execution | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 16/Mar/26 2:30 PM | 20/Apr/26 11:48 AM | [5 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-350 | 48486 | Test execution | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 16/Mar/26 2:30 PM | 16/Apr/26 9:21 PM | [5 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-349 | 48488 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | In Review |  | 16/Mar/26 2:30 PM | 21/Apr/26 3:36 PM | [5 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-348 | 48484 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | In Progress |  | 16/Mar/26 2:30 PM | 02/Apr/26 3:17 PM | [5 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-347 | 48482 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 16/Mar/26 2:30 PM | 08/Apr/26 12:56 PM | [5 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-346 | 48480 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 16/Mar/26 2:30 PM | 23/Mar/26 7:27 PM | [5 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-345 | 48477 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 16/Mar/26 2:30 PM | 20/Mar/26 4:24 PM | [5 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-344 | 48478 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 16/Mar/26 2:30 PM | 23/Mar/26 7:27 PM | [5 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-343 | 48476 | Create test case | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 16/Mar/26 2:30 PM | 23/Mar/26 7:27 PM | [5 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-342 | 48475 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 16/Mar/26 2:30 PM | 23/Mar/26 7:44 PM | [5 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-341 | 48470 | Create test case | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 16/Mar/26 2:30 PM | 23/Mar/26 7:27 PM | [5 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-340 | 48469 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 16/Mar/26 2:30 PM | 23/Mar/26 7:44 PM | [5 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-339 | 48468 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 16/Mar/26 2:30 PM | 23/Mar/26 7:27 PM | [5 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-338 | 48464 | [QA] Test execution |  |  | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 16/Mar/26 2:14 PM | 17/Mar/26 10:16 AM | [5 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-337 | 48462 | [QA] Create test case | THUNDER(QA): PAWICH | 712020:83ff944e-9677-453f-b053-40e92520d905 | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | In Progress |  | 16/Mar/26 2:14 PM | 17/Mar/26 10:16 AM | [5 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-336 | 48460 | [QA] Test execution |  |  | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 16/Mar/26 2:14 PM | 17/Mar/26 10:15 AM | [5 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-335 | 48458 | [QA] Create test case | THUNDER(QA): PAWICH | 712020:83ff944e-9677-453f-b053-40e92520d905 | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | In Progress |  | 16/Mar/26 2:14 PM | 17/Mar/26 10:15 AM | [5 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-334 | 48391 | [Dev][RD][SSO Backoffice] Disable 'Sync Card' button | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 16/Mar/26 12:49 PM | 21/Apr/26 11:18 AM | 17/Apr/26 12:00 AM | 2 | sso-backoffice |  | 14400 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-326 | 48166 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 13/Mar/26 1:10 PM | 08/Apr/26 3:44 PM | [5 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-325 | 48164 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 13/Mar/26 1:10 PM | 20/Mar/26 4:25 PM | [5 empty] | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DRST-65 | 47526 | [DEV][RD][CMS API] Setup ENV | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 10/Mar/26 4:10 PM | 21/Apr/26 11:07 AM |  | 1 |  |  | 3600 | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22
Story | DPE-319 | 47258 | [Dev][RD][REM] Improve reward redemption with 0 point | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 09/Mar/26 5:15 PM | 20/Apr/26 5:10 PM |  | 3 |  |  | 28800 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-318 | 47096 | [Dev][RD][PL] Create new partner | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 09/Mar/26 9:39 AM | 20/Apr/26 5:10 PM | 03/Apr/26 12:00 AM | 3 |  |  | 28800 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DRST-61 | 46883 | [DEV][RD][BOF] Remove Subscription V1 in backoffice and database | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 06/Mar/26 5:04 PM | 21/Apr/26 9:14 AM | 25/Mar/26 12:00 AM | 8 |  |  |  | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22 | [Dev RD][VIMI Termi] Sprint 23
Story | DPE-303 | 45986 | Dev][RD][PE Proxy Scheduler] Implement command to import RW BTS trip transactions | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Ready To Test |  | 01/Mar/26 8:49 PM | 21/Apr/26 11:12 AM | 03/Apr/26 12:00 AM | 5 |  |  | 86400 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-302 | 45985 | Dev][RD][PE Proxy Scheduler] Implement command to import RC BTS trip transactions | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Ready To Test |  | 01/Mar/26 8:49 PM | 20/Apr/26 5:10 PM | 01/Apr/26 12:00 AM | 8 |  |  | 115200 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-301 | 45984 | [Dev][RD][PE Proxy Scheduler] Implement command for importing RW retail transactions | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 01/Mar/26 8:47 PM | 20/Apr/26 5:10 PM | 02/Apr/26 12:00 AM | 8 |  |  | 72000 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-296 | 45845 | [Dev][RD][PE Proxy Scheduler] Implement command for importing RC retail transactions | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 27/Feb/26 1:40 PM | 20/Apr/26 5:10 PM | 31/Mar/26 12:00 AM | 8 |  |  |  | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-295 | 45844 | [Dev][RD][PE Proxy Scheduler] Implement command to import merchant codes and offers from file | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 27/Feb/26 1:39 PM | 21/Apr/26 4:45 PM | 27/Mar/26 12:00 AM | 8 |  |  |  | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-290 | 45375 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:49 AM | [5 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-281 | 45357 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [5 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-280 | 45355 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:58 PM | [5 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-279 | 45354 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 7:01 PM | [5 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-277 | 45351 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:59 PM | [5 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-278 | 45350 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:59 PM | [5 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-276 | 45343 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:59 PM | [5 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-275 | 45348 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:59 PM | [5 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-273 | 45342 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 7:01 PM | [5 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-272 | 45339 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:50 PM | [5 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-270 | 45335 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [5 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-269 | 45333 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [5 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-268 | 45331 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [5 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-267 | 45332 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [5 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-266 | 45329 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [5 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-265 | 45330 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [5 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-262 | 45319 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [5 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-261 | 45321 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [5 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-228 | 44837 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 23/Feb/26 5:45 PM | 12/Mar/26 11:45 AM | [5 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Sub-task | DPE-227 | 44835 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 23/Feb/26 5:45 PM | 12/Mar/26 11:46 AM | [5 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-207 | 44011 | [Dev][RD][SSO-User] Reward Add Card | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 18/Feb/26 3:42 PM | 20/Apr/26 5:10 PM |  | 1 |  |  |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DRST-23 | 43648 | [DEV][RD][Rabbit CMS API] Create new endpoint for get earn by slug | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 15/Feb/26 10:50 PM | 07/Apr/26 2:44 PM |  | 2 | cms-api | No-QA | 14400 | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22
Story | DRST-22 | 43647 | [DEV][RD][Rabbit CMS API] Create new endpoint for get earn by id | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 15/Feb/26 10:46 PM | 07/Apr/26 2:44 PM |  | 2 | cms-api | No-QA | 14400 | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22
Story | DRST-21 | 43078 | [DEV][RD][BOF] Enhance Subscription Txn V2 support filter from query string | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 11/Feb/26 7:10 PM | 21/Apr/26 9:14 AM |  | 2 |  |  | 14400 | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22 | [Dev RD][VIMI Termi] Sprint 23
Story | RDTHANA-447 | 43072 | [DEV][RD][TDM] Sync Order Data from Shopify Stores Refund | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 11/Feb/26 6:36 PM | 21/Apr/26 10:00 AM | 18/Mar/26 12:00 AM | 5 | Thana-datamart |  | 57600 | [Dev][RD][Thana] Sprint 20 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24
Story | RDTHANA-446 | 43071 | [DEV][RD][TDM] Sync Order Data from Shopify Stores to Data Mart #2 | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 11/Feb/26 6:36 PM | 21/Apr/26 10:00 AM | 20/Mar/26 12:00 AM | 5 | Thana-datamart |  | 57600 | [Dev][RD][Thana] Sprint 20 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24
Story | RDTHANA-445 | 43070 | [DEV][RD][TDM] Sync Order Data from Shopify Stores to Data Mart table | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 11/Feb/26 6:35 PM | 21/Apr/26 10:00 AM | 18/Mar/26 12:00 AM | 5 | Thana-datamart |  | 57600 | [Dev][RD][Thana] Sprint 20 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24
Story | RDTHANA-443 | 43068 | [DEV][RD][TDM] Create Webhook API Endpoint refunds/create | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 11/Feb/26 6:35 PM | 21/Apr/26 10:00 AM | 18/Mar/26 12:00 AM | 5 | Thana-datamart |  |  | [Dev][RD][Thana] Sprint 20 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24
Story | RDTHANA-442 | 43067 | [DEV][RD][TDM] Create Webhook API Endpoint orders | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 11/Feb/26 6:34 PM | 21/Apr/26 10:00 AM | 16/Mar/26 12:00 AM | 5 | Thana-datamart |  | 57600 | [Dev][RD][Thana] Sprint 20 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24
Story | RDTHANA-441 | 43066 | [DEV][RD][TDM] Create migration | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 11/Feb/26 6:33 PM | 21/Apr/26 10:00 AM | 12/Mar/26 12:00 AM | 5 | No-QA | Thana-datamart | 57600 | [Dev][RD][Thana] Sprint 20 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24
Epic | RDTHANA-431 | 42991 | Lighspeed Polling |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 11/Feb/26 3:07 PM | 21/Apr/26 10:00 AM | 06/Mar/26 12:00 AM |  |  |  |  | [Dev][RD][Thana] Sprint 19 | [Dev][RD][Thana] Sprint 20 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22 | [Dev][RD][Thana] Sprint 18 | [Dev][RD][Thana] Sprint 23 | [Dev][RD][Thana] Sprint 24
Story | DRST-17 | 42821 | [DEV][RD][BOF] Create command to migrate data from VIMI database to Rabbit CMS database | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 11/Feb/26 10:17 AM | 07/Apr/26 2:42 PM |  | 8 | No-QA |  | 86400 | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22
Story | DRST-14 | 42267 | [DEV][RD][Rabbit CMS API] Create endpoint for get earn content | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 08/Feb/26 9:54 PM | 07/Apr/26 2:43 PM |  | 5 | cms-api | No-QA | 57600 | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22
Story | DPE-160 | 42217 | [Dev][RD][Rewards Member] Switch account | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 07/Feb/26 3:30 PM | 20/Apr/26 5:10 PM | 10/Apr/26 12:00 AM | 3 |  |  |  | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-158 | 42215 | [Dev][RD][BFF] Get point balance | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 07/Feb/26 3:24 PM | 08/Apr/26 3:44 PM | 16/Mar/26 12:00 AM | 5 |  |  | 57600 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-147 | 42134 | [Dev][RD][SSO-User] WEB verify phone | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 6:37 PM | 20/Apr/26 5:10 PM |  | 1 | sso-user |  | 3600 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-146 | 42133 | [Dev][RD][SSO-User] WEB update avatar | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 6:37 PM | 20/Apr/26 5:10 PM |  | 1 | sso-user |  | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-145 | 42132 | [Dev][RD][SSO-User] WEB verify user | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 6:37 PM | 20/Apr/26 5:10 PM |  | 2 | sso-user |  | 10800 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-144 | 42131 | [Dev][RD][SSO-User] WEB remove card by card_id | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 6:37 PM | 20/Apr/26 5:10 PM |  | 1 | sso-user |  | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-143 | 42130 | [Dev][RD][SSO-User] WEB move card | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 6:36 PM | 21/Apr/26 11:11 AM | 05/Mar/26 12:00 AM | 1 | sso-user |  | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-142 | 42129 | [Dev][RD][SSO-User] WEB add card | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 6:36 PM | 20/Apr/26 5:10 PM |  | 1 | sso-user |  | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-141 | 42128 | [Dev][RD][SSO-User] WEB update profile by ID | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 6:36 PM | 20/Apr/26 5:10 PM | 12/Feb/26 12:00 AM | 2 | sso-user |  | 14400 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-129 | 42104 | [Dev][RD][ATN] Realtime issue point API | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Ready To Test |  | 06/Feb/26 2:16 PM | 21/Apr/26 11:12 AM | 01/Apr/26 12:00 AM | 3 |  |  | 28800 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-128 | 42103 | [Dev][RD][ATN] Request individual issue point API | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Ready To Test |  | 06/Feb/26 2:16 PM | 21/Apr/26 11:12 AM | 31/Mar/26 12:00 AM | 3 |  |  | 28800 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-123 | 42098 | [Dev][RD][REMQ] Async coupon push | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 1:44 PM | 20/Apr/26 5:10 PM | 12/Mar/26 12:00 AM | 5 |  |  | 57600 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-120 | 42095 | [Dev][RD][ECS] Cronjob: Daily sync issue point | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 1:43 PM | 20/Apr/26 5:10 PM | 17/Apr/26 12:00 AM | 8 | ecommerce-shopify-api |  | 57600 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-116 | 42091 | [Dev][RD][VLD] Add card (mark use) | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 1:43 PM | 21/Apr/26 9:46 AM | 17/Apr/26 12:00 AM | 2 |  |  |  | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-111 | 42054 | [Dev][RD][ATN] Bulk issue point for CRM Refund via RR-Backoffice | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Ready To Test |  | 06/Feb/26 12:11 PM | 21/Apr/26 10:22 AM | 03/Apr/26 12:00 AM | 5 |  |  | 57600 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-110 | 42053 | [Dev][RD][APH] Submit data enrichment | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 12:11 PM | 21/Apr/26 10:23 AM | 17/Apr/26 12:00 AM | 3 |  |  | 28800 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-109 | 42052 | [Dev][RD][APH] Survey processing | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 12:11 PM | 21/Apr/26 10:23 AM | 17/Apr/26 12:00 AM | 3 |  |  | 28800 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-106 | 42049 | [Dev][RD][PWP] Confirm payment | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 12:10 PM | 20/Apr/26 5:10 PM | 09/Apr/26 12:00 AM | 5 |  |  |  | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-103 | 42046 | [Dev][RD][goutil] Implement Point Engine Client Functions | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 11:54 AM | 20/Apr/26 5:10 PM |  | 3 | No-QA |  | 28800 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-101 | 41974 | [Dev][RD][BOF] Create/Update Package | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:49 PM | 20/Apr/26 5:10 PM | 20/Mar/26 12:00 AM | 3 |  |  |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-100 | 41973 | [Dev][RD][BOF] Update product | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:49 PM | 20/Apr/26 5:10 PM | 20/Mar/26 12:00 AM | 3 |  |  |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-99 | 41972 | [Dev][RD][BOF] Create a new product | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:49 PM | 20/Apr/26 5:10 PM | 20/Mar/26 12:00 AM | 3 |  |  |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-98 | 41971 | [Dev][RD][ORD] Disable sending order transaction data to DA | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:49 PM | 20/Apr/26 5:10 PM |  | 3 |  |  | 28800 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-95 | 41968 | [Dev][RD][ORD] Place subscription order | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:48 PM | 20/Apr/26 5:10 PM | 27/Mar/26 12:00 AM | 5 |  |  |  | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-93 | 41966 | [Dev][RD][REM] Improve reward redemption v2 | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:48 PM | 20/Apr/26 5:10 PM |  | 5 |  |  | 57600 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-92 | 41965 | [Dev][RD][Sky Web] Switch Account | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:46 PM | 21/Apr/26 11:22 AM | 19/Mar/26 12:00 AM | 5 | sky-web |  | 57600 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-91 | 41964 | [Dev][RD][Sky] Switch account API | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:46 PM | 21/Apr/26 11:22 AM | 19/Mar/26 12:00 AM | 3 | sky-api |  | 28800 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-90 | 41963 | [Dev][RD][Sky][Member] Reactivate | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:46 PM | 21/Apr/26 11:22 AM | 12/Mar/26 12:00 AM | 2 | sky-api |  |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-89 | 41962 | [Dev][RD][Sky][Member] Register Member | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:46 PM | 21/Apr/26 11:22 AM | 13/Mar/26 12:00 AM | 3 | sky-api |  | 28800 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-86 | 41959 | [Dev][RD][PL] Create transaction | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:46 PM | 20/Apr/26 5:10 PM | 03/Apr/26 12:00 AM | 5 |  |  |  | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-81 | 41537 | [Dev][RD][PL][Member] Check RR member by Trader ID | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 04/Feb/26 10:26 AM | 08/Apr/26 12:57 PM |  | 3 |  |  |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-80 | 41535 | [Dev][RD][PL][Member] Check RR member by phone | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 04/Feb/26 10:24 AM | 08/Apr/26 12:57 PM | 16/Mar/26 12:00 AM | 3 | partner-loyalty |  | 28800 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-79 | 41533 | [Dev][RD][PL][Point] Get point | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 04/Feb/26 10:24 AM | 08/Apr/26 2:08 PM | 20/Mar/26 12:00 AM | 3 |  |  |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-78 | 41531 | [Dev][RD][PL][Member] Check Member By ID | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 04/Feb/26 10:24 AM | 08/Apr/26 12:54 PM | 12/Mar/26 12:00 AM | 3 | partner-loyalty |  | 28800 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-77 | 41529 | [Dev][RD][PL] Redeem point | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 04/Feb/26 10:23 AM | 20/Apr/26 5:10 PM | 03/Apr/26 12:00 AM | 5 |  |  |  | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-75 | 41525 | [Dev][RD][PL] Request register | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Ready To Test |  | 04/Feb/26 10:17 AM | 20/Apr/26 5:10 PM | 03/Apr/26 12:00 AM | 2 | partner-loyalty |  |  | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-74 | 41523 | [Dev][RD][SSO-User] Remove SSO-Thor API Integration | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Ready To Test |  | 04/Feb/26 10:13 AM | 20/Apr/26 5:10 PM |  | 5 | No-QA | sso-user | 57600 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-68 | 41511 | [Dev][RD][SSO-User] Rewards add card | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 04/Feb/26 9:49 AM | 20/Apr/26 5:10 PM | 10/Feb/26 12:00 AM | 1 | sso-user |  | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-67 | 41508 | [Dev][RD][PL][Member] Opt-in by SSO | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 04/Feb/26 9:43 AM | 21/Apr/26 11:25 AM | 12/Mar/26 12:00 AM | 3 | partner-loyalty |  | 28800 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-66 | 41506 | [Dev][RD][PL][Member] Opt-in | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 04/Feb/26 9:43 AM | 21/Apr/26 11:24 AM | 12/Mar/26 12:00 AM | 5 | partner-loyalty |  | 57600 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-65 | 41499 | [Dev][RD][PL][Member] Sync RR member | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 04/Feb/26 9:18 AM | 21/Apr/26 3:32 PM | 10/Mar/26 12:00 AM | 3 | partner-loyalty |  | 28800 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-64 | 41497 | [Dev][RD][PL][Member] Member binding | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 04/Feb/26 9:16 AM | 20/Apr/26 5:10 PM | 13/Mar/26 12:00 AM | 5 | partner-loyalty |  |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DPE-49 | 41435 | [Dev][RD][SSO-User] Rewards Verify phone | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 03/Feb/26 7:41 PM | 20/Apr/26 5:10 PM |  | 2 | sso-user |  | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22 | [Dev][RD][New PE] Sprint 23
Story | DRST-6 | 38163 | [Dev][RD][Terminate VIMI][VoucherValidator] Refactor APIs to remove dependency on MVP Phase 1 source | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready To Test |  | 07/Jan/26 11:12 AM | 21/Apr/26 9:13 AM | 10/Feb/26 12:00 AM | 3 |  |  | 28800 | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22 | [Dev RD][VIMI Termi] Sprint 23
Story | DRST-5 | 38162 | [Dev][RD][Terminate VIMI][MerchantAPI] Refactor APIs to remove dependency on MVP Phase 1 source | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready To Test |  | 07/Jan/26 11:12 AM | 21/Apr/26 9:13 AM | 11/Feb/26 12:00 AM | 3 |  |  | 28800 | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22 | [Dev RD][VIMI Termi] Sprint 23
Story | DRST-7 | 36975 | [Dev][RD][Terminate VIMI] Refactor TXN Report API and Report Summary API to remove dependency on MVP Phase 1 report source | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready To Test |  | 23/Dec/25 12:23 PM | 21/Apr/26 9:14 AM | 30/Dec/25 12:00 AM | 3 |  |  | 28800 | [Dev][All Project] Sprint 15 | [Dev][All Project] Sprint 16 | [Dev RD][VIMI Termi] Sprint 17 | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22 | [Dev RD][VIMI Termi] Sprint 23
Epic | DEVRDCT-359 | 36930 | FIX-Identity-Error |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 23/Dec/25 9:38 AM | 07/Apr/26 10:05 AM | [5 empty] | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15 | [Dev][RD][CT] Sprint 16 | [Dev][RD][CT] Sprint 21 | [Dev][RD][CT] Sprint 22
Bug | DEVRDCT-358 | 36929 | [DEV][RD][HRS] Delay Auto CLUB_BINDING to Prevent Intermittent Identity Error | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Resolved |  | 23/Dec/25 8:59 AM | 07/Apr/26 10:05 AM |  | 2 |  |  |  | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15 | [Dev][RD][CT] Sprint 16 | [Dev][RD][CT] Sprint 21 | [Dev][RD][CT] Sprint 22
Test Plan | DEVRDCT-342 | 35712 | [TP] Sprint #13 |  |  | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 11/Dec/25 3:26 PM | 07/Apr/26 10:05 AM | [5 empty] | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15 | [Dev][RD][CT] Sprint 16 | [Dev][RD][CT] Sprint 21 | [Dev][RD][CT] Sprint 22
Epic | DEVRDCT-326 | 35192 | CT-POINT-ISSUE |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 01/Dec/25 9:58 AM | 07/Apr/26 10:05 AM | [5 empty] | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15 | [Dev][RD][CT] Sprint 16 | [Dev][RD][CT] Sprint 21 | [Dev][RD][CT] Sprint 22
Epic | DEVRDCT-325 | 35191 | CTxSHOPIFY |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 01/Dec/25 9:55 AM | 07/Apr/26 10:05 AM | [5 empty] | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15 | [Dev][RD][CT] Sprint 16 | [Dev][RD][CT] Sprint 21 | [Dev][RD][CT] Sprint 22
Epic | DEVRDCT-309 | 34545 | ct-member-tier |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 19/Nov/25 2:49 PM | 07/Apr/26 10:05 AM | [5 empty] | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15 | [Dev][RD][CT] Sprint 16 | [Dev][RD][CT] Sprint 21 | [Dev][RD][CT] Sprint 22
Epic | DEVRDCT-308 | 34539 | ct-campaign-type |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 19/Nov/25 10:41 AM | 07/Apr/26 10:05 AM |  |  | redemption-api |  |  | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15 | [Dev][RD][CT] Sprint 16 | [Dev][RD][CT] Sprint 21 | [Dev][RD][CT] Sprint 22

## Summarize Sprint 21
Column 1 | Total Stories Point | Total Manhour | Point Done | Manhour Done | Note
9 Mar - 20 Mar
Dev Resource Available | 21 | 444.5
Meeting Planned |  |  |  |  | Ref
Additional Meeting |  |  |  |  | Ref
Deployment |  | 2 |  |  | 1 ครั้ง 1. 2 คน
Development Sprint Total | 448 | 398 | 195 | 184
Ad-hoc Mid Sprint | 0 | 0 | 0 | 0 | 2 tasks
Requirement changes after refinement? | 0 |  | 0 | 0 | 0 tasks
Aek | 17 | 34 | 11 | 34
A | 84 | 106 | 49 | 34
Aom | 30 | 76 | 30 | 76
Zan | 36 | 8 | 28 | 8
Mai | 50 | 28 | 3 | 0
Mac | 55 | 60 | 3 | 6
Mos | 68 | 34 | 40 | 26
Jack | 15 | 0 | 15 | 0
Nim | 53 | 52 | 13 | 0
Arm | 40 | 0 | 3 | 0
| System Architech |  |  |  | Permanent Dev. |  |  | Contract | Outsource
Projects (Stories Points) | Aek | Zan | Aom | Jack | A | Mac | Mai | Arm | Mos | Nim

## Sprint 21
Issue Type | Issue key | Issue id | Summary | Assignee | Assignee Id | Reporter | Reporter Id | Priority | Status | Resolution | Created | Updated | Due date | Custom field (Story Points) | Labels | Labels | Labels | Original estimate | Sprint Movement | Sprint 20 | Note | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint
Sub-task | DRST-92 | 52943 | [QA] Test Execution - UAT |  |  | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 08/Apr/26 4:36 PM | 08/Apr/26 4:36 PM | [9 empty] | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22
Sub-task | DRST-91 | 52941 | [QA] Test Execution - STG |  |  | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 08/Apr/26 4:35 PM | 08/Apr/26 4:43 PM | [9 empty] | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22
Sub-task | DRST-89 | 52929 | [QA] Test Execution - UAT | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 08/Apr/26 2:29 PM | 08/Apr/26 2:29 PM | [9 empty] | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22
Sub-task | DRST-88 | 52927 | [QA] Test Execution - STG | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 08/Apr/26 2:28 PM | 08/Apr/26 4:38 PM | [9 empty] | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22
Bug | DPE-435 | 52768 | [S3][NPE][PL MEMBER] rabbit_point is null when call api check the member detail | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 03/Apr/26 3:22 PM | 07/Apr/26 5:29 PM | [9 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DRST-86 | 52744 | [DEV][RD][BFF] POC golangci-lint upgrade effect | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 03/Apr/26 9:13 AM | 07/Apr/26 2:39 PM |  | 1 | [7 empty] | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22
Story | DPE-434 | 52743 | [Dev][RD][SSO Backoffice] Display point info | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 03/Apr/26 8:49 AM | 08/Apr/26 4:51 PM |  | 3 | [7 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DRST-85 | 52742 | [DEV][RD][BFF] Create remove card endpoint | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 02/Apr/26 11:49 PM | 08/Apr/26 4:34 PM | 03/Apr/26 12:00 AM | 3 |  |  |  | 21600 |  |  |  | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22
Story | DRST-84 | 52741 | [DEV][RD][BFF] Create add card endpoint | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 02/Apr/26 11:49 PM | 08/Apr/26 11:19 AM |  | 5 | [7 empty] | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22
Sub-task | DPE-432 | 52669 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 02/Apr/26 11:08 AM | 02/Apr/26 11:08 AM | [9 empty] | [Dev][RD][New PE] Sprint 21
Sub-task | DPE-431 | 52667 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 02/Apr/26 11:08 AM | 02/Apr/26 11:08 AM | [9 empty] | [Dev][RD][New PE] Sprint 21
Sub-task | DPE-428 | 52560 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 01/Apr/26 2:45 PM | 01/Apr/26 5:06 PM | [9 empty] | [Dev][RD][New PE] Sprint 21
Sub-task | DPE-427 | 52558 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 01/Apr/26 2:45 PM | 01/Apr/26 2:46 PM | [9 empty] | [Dev][RD][New PE] Sprint 21
Sub-task | DPE-423 | 52505 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 01/Apr/26 10:28 AM | 01/Apr/26 4:58 PM | [9 empty] | [Dev][RD][New PE] Sprint 21
Sub-task | DPE-422 | 52503 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 01/Apr/26 10:28 AM | 01/Apr/26 2:46 PM | [9 empty] | [Dev][RD][New PE] Sprint 21
Story | DPE-416 | 52133 | [Dev][RD][PE Middleware] Integrate Swagger / API Spec Documentation | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 31/Mar/26 9:50 AM | 07/Apr/26 4:01 PM | 01/Apr/26 12:00 AM | 3 | No-QA |  |  | 28800 |  |  |  | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | RDTHANA-477 | 52052 | [SA][RD][TDM] Investigate task stop or revisioning on STG/UAT | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 30/Mar/26 4:08 PM | 07/Apr/26 10:11 AM |  | 2 | [7 empty] | [Dev][RD][Thana] Sprint 21
Story | RDTHANA-476 | 52045 | [SA][RD][TDM] Support and test shopify webhook in UAT | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 30/Mar/26 4:03 PM | 07/Apr/26 10:11 AM |  | 2 | No-QA | SA-Task | [5 empty] | [Dev][RD][Thana] Sprint 21
Story | DEVRDSUP-533 | 51986 | [SUP-617]SUB : Disable Credit/Debit Card Payment for BBL Package (APR2026 Package) | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Done |  | 30/Mar/26 11:42 AM | 31/Mar/26 5:03 PM | 31/Mar/26 12:00 AM | 1 | bts | BURequest | sub |  |  |  |  | [Dev][All Project] Sprint 21
Story | DRST-81 | 51769 | [DEV][RD][BFF] Enhance user me upload avatar support max file size to 5MB | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Blocked |  | 27/Mar/26 2:50 PM | 07/Apr/26 2:39 PM |  | 2 |  |  |  | 14400 |  |  |  | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22
Bug | DPE-411 | 51735 | [S3][NPE][Offer] Get Offer List API filters not working except page size | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Closed |  | 27/Mar/26 1:20 PM | 02/Apr/26 11:03 AM | [9 empty] | [Dev][RD][New PE] Sprint 21
Bug | DPE-405 | 51710 | [S3][NPE][Offer] is_delete remains false after calling Delete API | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Closed ( Change Request) |  | 27/Mar/26 11:08 AM | 01/Apr/26 11:37 AM | [9 empty] | [Dev][RD][New PE] Sprint 21
Story | DPE-404 | 51708 | [SA] Prepare Task description for RLP Sprint 22 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Progress |  | 27/Mar/26 9:57 AM | 07/Apr/26 2:56 PM |  | 3 | [7 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-403 | 51703 | [Dev][RD][PE Middleware] Enhance API to get point balance | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 27/Mar/26 9:04 AM | 07/Apr/26 2:56 PM |  | 3 |  |  |  | 28800 |  |  |  | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Bug | DPE-401 | 51569 | [S4][NPE][Offer] Create and Update offer with incorrect date and time format API returns incorrect response | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Closed ( Change Request) |  | 26/Mar/26 11:12 AM | 07/Apr/26 1:44 PM | [9 empty] | [Dev][RD][New PE] Sprint 21
Bug | DPE-400 | 51551 | [S3][NPE][Offer] Create and Update Offer API returns unexpected type earn_special | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Closed |  | 26/Mar/26 11:02 AM | 27/Mar/26 5:35 PM | [9 empty] | [Dev][RD][New PE] Sprint 21
Story | RDTHANA-466 | 51546 | [DEV][RD][TDM] Change bullMQ to RabbitMQ | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 26/Mar/26 10:01 AM | 30/Mar/26 4:07 PM |  | 3 |  |  |  | 21600 |  |  |  | [Dev][RD][Thana] Sprint 21
Story | RDTHANA-465 | 51545 | [DEV][RD][TDM] Enhance Shopify access token flow | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 26/Mar/26 9:37 AM | 07/Apr/26 2:45 PM | 26/Mar/26 12:00 AM | 3 |  |  |  | 28800 |  |  |  | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22
Story | RDAPS-443 | 51272 | [SA][RD][Adhoc][BSS] Generate Rabbit Website Visitor Report for ETDA Submission | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 24/Mar/26 4:29 PM | 26/Mar/26 8:30 AM |  | 1 |  |  |  | 7200 |  |  |  | [Dev][All Project] Sprint 21
Bug | DPE-390 | 51270 | [S3][NPE Proxy] Credit point response is incorrect | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 24/Mar/26 4:04 PM | 01/Apr/26 11:38 AM | [9 empty] | [Dev][RD][New PE] Sprint 21
Story | DPE-388 | 51263 | [Dev][RD][SA][Sprint22] Analysis & Task Breakdown for PE Migration Execution | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 24/Mar/26 3:36 PM | 03/Apr/26 2:57 PM |  | 13 | No-QA | [6 empty] | [Dev][RD][New PE] Sprint 21
Sub-task | DPE-387 | 51260 | Test execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 24/Mar/26 3:17 PM | 31/Mar/26 3:03 PM | [9 empty] | [Dev][RD][New PE] Sprint 21
Sub-task | DPE-386 | 51258 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 24/Mar/26 3:16 PM | 24/Mar/26 3:18 PM | [9 empty] | [Dev][RD][New PE] Sprint 21
Sub-task | DPE-385 | 51256 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 24/Mar/26 3:16 PM | 26/Mar/26 5:50 PM | [9 empty] | [Dev][RD][New PE] Sprint 21
Sub-task | DPE-384 | 51254 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 24/Mar/26 3:16 PM | 24/Mar/26 3:17 PM | [9 empty] | [Dev][RD][New PE] Sprint 21
Sub-task | DPE-382 | 51245 | [NPE] CI/CD verification for CT-UAT environment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 24/Mar/26 2:17 PM | 07/Apr/26 2:54 PM | 25/Mar/26 12:00 AM | 5 |  |  |  | 57600 |  |  |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Sub-task | DPE-381 | 51243 | Test execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 24/Mar/26 2:13 PM | 26/Mar/26 5:38 PM | [9 empty] | [Dev][RD][New PE] Sprint 21
Sub-task | DPE-380 | 51241 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 24/Mar/26 2:13 PM | 24/Mar/26 2:27 PM | [9 empty] | [Dev][RD][New PE] Sprint 21
Story | RDAPS-442 | 51238 | [SA][RD] Support and invesigate | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 24/Mar/26 1:57 PM | 07/Apr/26 10:13 AM |  | 5 | [7 empty] | [Dev][All Project] Sprint 21
Story | RDAPS-441 | 51237 | [SA][RD] Meeting | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 24/Mar/26 1:50 PM | 07/Apr/26 10:13 AM |  | 5 | [7 empty] | [Dev][All Project] Sprint 21
Bug | DPE-379 | 51169 | [S3][NPE Proxy] Able to credit point with invalid transaction type | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 24/Mar/26 11:29 AM | 01/Apr/26 11:37 AM | [9 empty] | [Dev][RD][New PE] Sprint 21
Bug | DPE-378 | 51168 | [S4][NPE Proxy] Credit zero point response is incorrect | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 24/Mar/26 11:23 AM | 01/Apr/26 11:36 AM | [9 empty] | [Dev][RD][New PE] Sprint 21
Story | DPE-377 | 51059 | [Dev][RD][PE Middleware] Enhance GET List APIs to Return Standard Response Format | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Low | Done |  | 23/Mar/26 5:29 PM | 02/Apr/26 11:08 AM | 31/Mar/26 12:00 AM | 3 | point-engine-proxy |  |  | 28800 |  |  |  | [Dev][RD][New PE] Sprint 21
Story | RDAPS-438 | 50957 | [SA][RD][App Handover] Review Software Design and Architecture Documentation | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Low | In Progress |  | 23/Mar/26 11:26 AM | 27/Mar/26 4:05 PM |  | 8 | [7 empty] | [Dev][All Project] Sprint 21
Story | RDAPS-437 | 50915 | [SA][RD] Team Supoort & Management | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 23/Mar/26 9:12 AM | 27/Mar/26 8:39 AM |  | 5 |  |  |  | 57600 |  |  |  | [Dev][All Project] Sprint 21
Story | RDAPS-436 | 50914 | [SA][RD] Meeting | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 23/Mar/26 9:11 AM | 01/Apr/26 8:59 AM |  | 5 |  |  |  | 57600 |  |  |  | [Dev][All Project] Sprint 21
Story | RDAPS-435 | 50913 | [SA][RD] DailiTech Event 2026 : Make It Simple | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 23/Mar/26 9:09 AM | 01/Apr/26 8:41 AM |  | 3 |  |  |  | 28800 |  |  |  | [Dev][All Project] Sprint 21
Epic | RDNDA-35 | 50602 | Enhance Lightspeed txn |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 22/Mar/26 11:18 PM | 22/Mar/26 11:18 PM | 03/Apr/26 12:00 AM |  | Thana-datamart | [6 empty] | [Dev][RD][NewDamart] Sprint 21
Epic | RDTHANA-464 | 50601 | Enhance Lightspeed txn |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 22/Mar/26 11:17 PM | 07/Apr/26 2:45 PM | 03/Apr/26 12:00 AM | [8 empty] | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22
Story | DPE-374 | 50550 | [Dev][RD][ATN] Bulk issue point for MKT campaign | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Ready To Test |  | 22/Mar/26 10:28 AM | 07/Apr/26 2:56 PM | 03/Apr/26 12:00 AM | 5 | [7 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-373 | 50353 | [NPE] Prepare API Gateway mapping for CT env | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 20/Mar/26 4:00 PM | 25/Mar/26 2:55 PM |  | 2 |  |  |  | 7200 |  |  |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Sub-task | DPE-367 | 50330 | [NPE] Prepare env files for CT environment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 20/Mar/26 11:03 AM | 23/Mar/26 10:16 PM |  | 2 |  |  |  | 14400 | มาจาก Sprint 20 | To Do |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Story | RDNDA-34 | 50294 | [DEV][RD][TDM][SA] Prepare Prod ENV | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 20/Mar/26 10:00 AM | 07/Apr/26 10:12 AM |  | 3 |  |  |  |  | มาจาก Sprint 20 | In Progress |  | [Dev][RD][NewDamart] Sprint 20 | [Dev][RD][NewDamart] Sprint 21
Sub-task | DRST-78 | 50221 | Delete Report Service (wait SA -> P'Zan) | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Medium | Done |  | 19/Mar/26 1:49 PM | 25/Mar/26 11:45 AM | [6 empty] | มาจาก Sprint 20 | To Do |  | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22
Sub-task | DRST-77 | 50218 | Delete-> Model ->Repository-> Service | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Medium | Done |  | 19/Mar/26 1:49 PM | 20/Mar/26 11:22 AM | [5 empty] | 0 | มาจาก Sprint 20 | Done | 28800 | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22
Sub-task | DRST-76 | 50206 | Delete View -> Api route -> controller | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Medium | Done |  | 19/Mar/26 1:40 PM | 20/Mar/26 11:22 AM | [5 empty] | 0 | มาจาก Sprint 20 | Done | 14400 | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22
Sub-task | DRST-75 | 50201 | List service,repo,model | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Medium | Done |  | 19/Mar/26 1:39 PM | 20/Mar/26 11:22 AM | [5 empty] | 0 | มาจาก Sprint 20 | Done | 43200 | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22
Story | RDNDA-33 | 50166 | [DEV][RD][TDM] Enhance Lightspeed Cronjob to Use Access Token from Hook App Service | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 19/Mar/26 11:26 AM | 07/Apr/26 4:07 PM | 25/Mar/26 12:00 AM | 2 |  |  |  | 14400 |  |  |  | [Dev][RD][NewDamart] Sprint 21
Story | RDNDA-32 | 50165 | [DEV][RD][TDM] Create Hook App Service to Retrieve Lightspeed Access Token | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 19/Mar/26 11:25 AM | 07/Apr/26 4:07 PM | 25/Mar/26 12:00 AM | 2 |  |  |  | 14400 |  |  |  | [Dev][RD][NewDamart] Sprint 21
Story | RDTHANA-463 | 50163 | [DEV][RD][TDM] Enhance Data Mapping for Lightspeed Polling Transactions | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 19/Mar/26 11:10 AM | 07/Apr/26 4:07 PM | 30/Mar/26 12:00 AM | 5 | Thana-datamart |  |  | 43200 |  |  |  | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22
Story | DPE-360 | 50115 | [Dev][RD][SA][Sprint22] Analysis & Task Breakdown for PE Migration Execution | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 18/Mar/26 4:02 PM | 07/Apr/26 9:26 AM |  | 13 |  |  |  | 144000 |  |  |  | [Dev][RD][New PE] Sprint 21
Story | DPE-359 | 50114 | [SA] Meeting | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 18/Mar/26 3:54 PM | 03/Apr/26 10:29 AM |  | 8 | No-QA |  |  | 86400 |  |  |  | [Dev][RD][New PE] Sprint 21
Story | RDTHANA-462 | 49894 | [DEV][RD][SA] Analysis CT Event for Shopify webhook | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 18/Mar/26 10:00 AM | 07/Apr/26 10:11 AM | 26/Mar/26 12:00 AM | 8 | [7 empty] | [Dev][RD][Thana] Sprint 21
Sub-task | DPE-357 | 48623 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 17/Mar/26 10:16 AM | 17/Mar/26 10:16 AM | [6 empty] | มาจาก Sprint 20 | To Do |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-356 | 48621 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | In Progress |  | 17/Mar/26 10:16 AM | 20/Mar/26 4:30 PM | [6 empty] | มาจาก Sprint 20 | To Do |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-355 | 48538 | [Dev][RD][PE Middleware] Create Seed Data for table data_sources and transaction_types | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready to Staging |  | 16/Mar/26 5:27 PM | 07/Apr/26 2:56 PM |  | 2 | point-engine-proxy |  |  | 14400 |  |  |  | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-354 | 48496 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 16/Mar/26 2:30 PM | 08/Apr/26 12:57 PM | [6 empty] | มาจาก Sprint 20 | To Do |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-353 | 48494 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 16/Mar/26 2:30 PM | 08/Apr/26 2:07 PM | [6 empty] | มาจาก Sprint 20 | To Do |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-352 | 48492 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 16/Mar/26 2:30 PM | 08/Apr/26 12:54 PM | [6 empty] | มาจาก Sprint 20 | To Do |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-351 | 48491 | Test execution | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 16/Mar/26 2:30 PM | 17/Mar/26 1:43 PM | [6 empty] | มาจาก Sprint 20 | To Do |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-350 | 48486 | Test execution | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 16/Mar/26 2:30 PM | 17/Mar/26 1:43 PM | [6 empty] | มาจาก Sprint 20 | To Do |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-349 | 48488 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 16/Mar/26 2:30 PM | 16/Mar/26 2:30 PM | [6 empty] | มาจาก Sprint 20 | To Do |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-348 | 48484 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | In Progress |  | 16/Mar/26 2:30 PM | 02/Apr/26 3:17 PM | [6 empty] | มาจาก Sprint 20 | To Do |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-347 | 48482 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 16/Mar/26 2:30 PM | 08/Apr/26 12:56 PM | [6 empty] | มาจาก Sprint 20 | To Do |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-346 | 48480 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 16/Mar/26 2:30 PM | 23/Mar/26 7:27 PM | [6 empty] | มาจาก Sprint 20 | In Review |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-345 | 48477 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 16/Mar/26 2:30 PM | 20/Mar/26 4:24 PM | [6 empty] | มาจาก Sprint 20 | To Do |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-344 | 48478 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 16/Mar/26 2:30 PM | 23/Mar/26 7:27 PM | [6 empty] | มาจาก Sprint 20 | In Review |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-343 | 48476 | Create test case | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 16/Mar/26 2:30 PM | 23/Mar/26 7:27 PM | [6 empty] | มาจาก Sprint 20 | In Progress |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-342 | 48475 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 16/Mar/26 2:30 PM | 23/Mar/26 7:44 PM | [6 empty] | มาจาก Sprint 20 | In Progress |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-341 | 48470 | Create test case | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 16/Mar/26 2:30 PM | 23/Mar/26 7:27 PM | [6 empty] | มาจาก Sprint 20 | In Progress |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-340 | 48469 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 16/Mar/26 2:30 PM | 23/Mar/26 7:44 PM | [6 empty] | มาจาก Sprint 20 | In Progress |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-339 | 48468 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 16/Mar/26 2:30 PM | 23/Mar/26 7:27 PM | [6 empty] | มาจาก Sprint 20 | In Review |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-338 | 48464 | [QA] Test execution |  |  | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 16/Mar/26 2:14 PM | 17/Mar/26 10:16 AM | [6 empty] | มาจาก Sprint 20 | To Do |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-337 | 48462 | [QA] Create test case | THUNDER(QA): PAWICH | 712020:83ff944e-9677-453f-b053-40e92520d905 | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | In Progress |  | 16/Mar/26 2:14 PM | 17/Mar/26 10:16 AM | [6 empty] | มาจาก Sprint 20 | In Progress |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-336 | 48460 | [QA] Test execution |  |  | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 16/Mar/26 2:14 PM | 17/Mar/26 10:15 AM | [6 empty] | มาจาก Sprint 20 | To Do |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-335 | 48458 | [QA] Create test case | THUNDER(QA): PAWICH | 712020:83ff944e-9677-453f-b053-40e92520d905 | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | In Progress |  | 16/Mar/26 2:14 PM | 17/Mar/26 10:15 AM | [6 empty] | มาจาก Sprint 20 | In Progress |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-333 | 48213 | [Dev][RD][PE Middleware] Enhance Offer APIs – Include campaign_name in Get List and Get Detail | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 13/Mar/26 4:55 PM | 01/Apr/26 10:12 AM | 24/Mar/26 12:00 AM | 3 |  |  |  | 14400 |  |  |  | [Dev][RD][New PE] Sprint 21
Story | DPE-332 | 48212 | [Dev][RD][PE Middleware] Enhance Update Offer API – Add campaign_name | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 13/Mar/26 4:49 PM | 01/Apr/26 10:11 AM | 24/Mar/26 12:00 AM | 2 | point-engine-proxy |  |  | 7200 |  |  |  | [Dev][RD][New PE] Sprint 21
Story | DPE-330 | 48178 | [Dev][RD][PE Middleware] Enhance Offer Creation API – Add campaign_name | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 13/Mar/26 4:38 PM | 01/Apr/26 10:11 AM | 24/Mar/26 12:00 AM | 3 | point-engine-proxy |  |  | 14400 |  |  |  | [Dev][RD][New PE] Sprint 21
Story | DPE-329 | 48176 | [Dev][RD] Support DevOps for RR Service Provisioning | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 13/Mar/26 2:50 PM | 07/Apr/26 10:08 AM |  | 13 |  |  |  | 43200 | มาจาก Sprint 20 | In Progress | 86400 -> 43200 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Story | DPE-328 | 48175 | [Dev][RD][PE Middleware] Enhance Credit Point API – Add Transaction DateTime | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 13/Mar/26 2:43 PM | 02/Apr/26 10:41 AM | 25/Mar/26 12:00 AM | 2 | point-engine-proxy |  |  | 14400 |  |  |  | [Dev][RD][New PE] Sprint 21
Story | DPE-327 | 48167 | [Dev][RD][PE Middleware] Enhance Debit Point API – Add Transaction DateTime | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 13/Mar/26 1:47 PM | 02/Apr/26 10:40 AM | 25/Mar/26 12:00 AM | 2 | point-engine-proxy |  |  | 14400 |  |  |  | [Dev][RD][New PE] Sprint 21
Sub-task | DPE-326 | 48166 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 13/Mar/26 1:10 PM | 08/Apr/26 3:44 PM | [6 empty] | มาจาก Sprint 20 | To Do |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-325 | 48164 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 13/Mar/26 1:10 PM | 20/Mar/26 4:25 PM | [6 empty] | มาจาก Sprint 20 | In Review |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-320 | 47724 | [Dev][RD][RR CT] Allow Event Whitelist for Sending Data to CleverTap | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 11/Mar/26 2:17 PM | 07/Apr/26 10:10 AM |  | 2 | CleverTap | [6 empty] | [Dev][RD][New PE] Sprint 21
Story | DRST-65 | 47526 | [DEV][RD][CMS API] Setup ENV | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 10/Mar/26 4:10 PM | 07/Apr/26 2:44 PM |  | 1 |  |  |  | 0 | มาจาก Sprint 20 | Ready to Staging | 3600 | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22
Story | RDAPS-426 | 47383 | [SA][RD][Samsung] Impact analysis on enhance to support multiple RW card | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Progress |  | 10/Mar/26 11:10 AM | 26/Mar/26 3:16 PM |  | 3 | [7 empty] | [Dev][All Project] Sprint 21
Story | DPE-319 | 47258 | [Dev][RD][REM] Improve reward redemption with 0 point | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 09/Mar/26 5:15 PM | 07/Apr/26 2:56 PM |  | 3 |  |  |  | 28800 |  |  |  | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-318 | 47096 | [Dev][RD][PL] Create new partner | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 09/Mar/26 9:39 AM | 07/Apr/26 2:56 PM | 03/Apr/26 12:00 AM | 3 |  |  |  | 28800 |  |  |  | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DRST-61 | 46883 | [DEV][RD][BOF] Remove Subscription V1 in backoffice and database | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 06/Mar/26 5:04 PM | 08/Apr/26 10:02 AM | 25/Mar/26 12:00 AM | 8 |  |  |  |  | มาจาก Sprint 20 | In Progress |  | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22
Story | DPE-303 | 45986 | Dev][RD][PE Proxy Scheduler] Implement command to import RW BTS trip transactions | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Ready to Staging |  | 01/Mar/26 8:49 PM | 07/Apr/26 2:56 PM | 03/Apr/26 12:00 AM | 5 |  |  |  | 86400 |  |  |  | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-302 | 45985 | Dev][RD][PE Proxy Scheduler] Implement command to import RC BTS trip transactions | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Ready to Staging |  | 01/Mar/26 8:49 PM | 07/Apr/26 2:56 PM | 01/Apr/26 12:00 AM | 8 |  |  |  | 115200 |  |  |  | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-301 | 45984 | [Dev][RD][PE Proxy Scheduler] Implement command for importing RW retail transactions | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 01/Mar/26 8:47 PM | 07/Apr/26 3:21 PM | 02/Apr/26 12:00 AM | 8 |  |  |  | 72000 |  |  |  | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-296 | 45845 | [Dev][RD][PE Proxy Scheduler] Implement command for importing RC retail transactions | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 27/Feb/26 1:40 PM | 07/Apr/26 3:21 PM | 31/Mar/26 12:00 AM | 8 | [7 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-295 | 45844 | [Dev][RD][PE Proxy Scheduler] Implement command to import merchant codes and offers from file | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 27/Feb/26 1:39 PM | 07/Apr/26 3:21 PM | 27/Mar/26 12:00 AM | 8 | [7 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-290 | 45375 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:49 AM | [6 empty] | มาจาก Sprint 20 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-281 | 45357 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [6 empty] | มาจาก Sprint 20 | Done |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-280 | 45355 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:58 PM | [6 empty] | มาจาก Sprint 20 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-279 | 45354 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 7:01 PM | [6 empty] | มาจาก Sprint 20 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-277 | 45351 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:59 PM | [6 empty] | มาจาก Sprint 20 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-278 | 45350 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:59 PM | [6 empty] | มาจาก Sprint 20 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-276 | 45343 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:59 PM | [6 empty] | มาจาก Sprint 20 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-275 | 45348 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:59 PM | [6 empty] | มาจาก Sprint 20 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-273 | 45342 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 7:01 PM | [6 empty] | มาจาก Sprint 20 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-272 | 45339 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:50 PM | [6 empty] | มาจาก Sprint 20 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-270 | 45335 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [6 empty] | มาจาก Sprint 20 | Done |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-269 | 45333 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [6 empty] | มาจาก Sprint 20 | Done |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-268 | 45331 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [6 empty] | มาจาก Sprint 20 | Done |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-267 | 45332 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [6 empty] | มาจาก Sprint 20 | Done |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-266 | 45329 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [6 empty] | มาจาก Sprint 20 | Done |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-265 | 45330 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [6 empty] | มาจาก Sprint 20 | Done |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-262 | 45319 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [6 empty] | มาจาก Sprint 20 | Done |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-261 | 45321 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [6 empty] | มาจาก Sprint 20 | Done |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-260 | 45315 | Test execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:12 PM | 07/Apr/26 2:54 PM | [6 empty] | มาจาก Sprint 20 | To Do |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Sub-task | DPE-259 | 45313 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:12 PM | 16/Mar/26 12:42 PM | [6 empty] | มาจาก Sprint 20 | Done |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Sub-task | DPE-258 | 45311 | Test execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:12 PM | 27/Mar/26 1:34 PM | [6 empty] | มาจาก Sprint 20 | To Do |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Sub-task | DPE-257 | 45309 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:12 PM | 16/Mar/26 12:42 PM | [6 empty] | มาจาก Sprint 20 | Done |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Sub-task | DPE-250 | 45295 | Test execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:11 PM | 07/Apr/26 2:54 PM | [6 empty] | มาจาก Sprint 20 | To Do |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Sub-task | DPE-249 | 45293 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:11 PM | 16/Mar/26 12:42 PM | [6 empty] | มาจาก Sprint 20 | Done |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Sub-task | DPE-248 | 45291 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:02 PM | 31/Mar/26 5:43 PM | [6 empty] | มาจาก Sprint 20 | To Do |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Sub-task | DPE-247 | 45289 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:02 PM | 16/Mar/26 12:42 PM | [6 empty] | มาจาก Sprint 20 | Done |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Sub-task | DPE-246 | 45287 | Create test case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:01 PM | 07/Apr/26 2:54 PM | [6 empty] | มาจาก Sprint 20 | To Do |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Sub-task | DPE-245 | 45285 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:01 PM | 16/Mar/26 12:42 PM | [6 empty] | มาจาก Sprint 20 | Done |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Sub-task | DPE-240 | 45274 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 25/Feb/26 5:43 PM | 25/Mar/26 2:19 PM | [6 empty] | มาจาก Sprint 20 | To Do |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Sub-task | DPE-239 | 45272 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 25/Feb/26 5:42 PM | 16/Mar/26 12:43 PM | [6 empty] | มาจาก Sprint 20 | Done |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Sub-task | DPE-238 | 45270 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 25/Feb/26 5:42 PM | 25/Mar/26 5:12 PM | [6 empty] | มาจาก Sprint 20 | To Do |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Sub-task | DPE-237 | 45268 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 25/Feb/26 5:42 PM | 16/Mar/26 12:42 PM | [6 empty] | มาจาก Sprint 20 | Done |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Sub-task | DPE-236 | 45266 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 25/Feb/26 5:42 PM | 26/Mar/26 3:52 PM | [6 empty] | มาจาก Sprint 20 | To Do |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Sub-task | DPE-235 | 45264 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 25/Feb/26 5:41 PM | 16/Mar/26 12:42 PM | [6 empty] | มาจาก Sprint 20 | Done |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Sub-task | DPE-234 | 45262 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 25/Feb/26 5:40 PM | 25/Mar/26 4:39 PM | [6 empty] | มาจาก Sprint 20 | To Do |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Sub-task | DPE-233 | 45260 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 25/Feb/26 5:40 PM | 16/Mar/26 12:43 PM | [6 empty] | มาจาก Sprint 20 | Done |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Sub-task | DPE-232 | 45258 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 25/Feb/26 5:40 PM | 24/Mar/26 6:09 PM | [6 empty] | มาจาก Sprint 20 | To Do |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Sub-task | DPE-231 | 45256 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 25/Feb/26 5:40 PM | 16/Mar/26 12:42 PM | [6 empty] | มาจาก Sprint 20 | Done |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Sub-task | DPE-228 | 44837 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 23/Feb/26 5:45 PM | 12/Mar/26 11:45 AM | [6 empty] | มาจาก Sprint 20 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-227 | 44835 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 23/Feb/26 5:45 PM | 12/Mar/26 11:46 AM | [6 empty] | มาจาก Sprint 20 | Done |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Sub-task | DPE-226 | 44833 | [QA] Test execution | THUNDER(QA): PAWICH | 712020:83ff944e-9677-453f-b053-40e92520d905 | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 23/Feb/26 5:43 PM | 26/Mar/26 5:07 PM | [6 empty] | มาจาก Sprint 20 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Sub-task | DPE-225 | 44831 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 23/Feb/26 5:43 PM | 12/Mar/26 11:46 AM | [6 empty] | มาจาก Sprint 20 | Done |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Story | DPE-219 | 44552 | [Dev][RD][PE Middleware] Delete Offer (Soft Delete) | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 22/Feb/26 12:40 PM | 01/Apr/26 10:11 AM | 06/Mar/26 12:00 AM | 1 | point-engine-proxy |  |  | 0 | มาจาก Sprint 20 | Ready To Test | 7200 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Story | DPE-218 | 44551 | [Dev][RD][PE Middleware] Get Offer by id | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 22/Feb/26 11:42 AM | 01/Apr/26 10:12 AM | 05/Mar/26 12:00 AM | 2 | point-engine-proxy |  |  | 0 | มาจาก Sprint 20 | Ready to Staging | 14400 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Story | DPE-210 | 44188 | [Dev][RD][PE Middleware] Point expiry | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 19/Feb/26 3:22 PM | 02/Apr/26 12:57 PM |  | 3 | point-engine-proxy |  |  | 0 | มาจาก Sprint 20 | Ready To Test | 28800 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Story | DPE-208 | 44013 | [Dev][RD] API Document for MyRabbit Application to get point balance | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 18/Feb/26 3:46 PM | 03/Apr/26 10:36 AM |  | 2 | No-QA |  |  | 14400 |  |  |  | [Dev][RD][New PE] Sprint 21
Story | DPE-207 | 44011 | [Dev][RD][SSO-User] Reward Add Card | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 18/Feb/26 3:42 PM | 07/Apr/26 2:56 PM |  | 1 |  |  |  |  | มาจาก Sprint 20 | Ready To Test |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DRST-23 | 43648 | [DEV][RD][Rabbit CMS API] Create new endpoint for get earn by slug | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 15/Feb/26 10:50 PM | 07/Apr/26 2:44 PM |  | 2 | cms-api | No-QA |  | 0 | มาจาก Sprint 20 | Ready To Test | 14400 | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22
Story | DRST-22 | 43647 | [DEV][RD][Rabbit CMS API] Create new endpoint for get earn by id | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 15/Feb/26 10:46 PM | 07/Apr/26 2:44 PM |  | 2 | cms-api | No-QA |  | 0 | มาจาก Sprint 20 | Ready To Test | 14400 | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22
Story | DPE-195 | 43604 | [Dev][RD][DevOps][PE-MIGRATION] Provision dedicated UAT-CT environment for Point Engine migration services | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 15/Feb/26 1:53 PM | 25/Mar/26 3:30 PM |  | 3 | No-QA |  |  | 14400 | มาจาก Sprint 20 | In Progress | 28800 -> 14400 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Story | DPE-192 | 43566 | [Dev][RD][DevOps][RD][PE-MIGRATION] Provision uat-ct domain for CleverTap integration testing | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 13/Feb/26 9:03 PM | 25/Mar/26 3:30 PM |  | 3 |  |  |  | 14400 | มาจาก Sprint 20 | In Progress | 28800 -> 14400 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Sub-task | DPE-187 | 43123 | [QA] Test execution | THUNDER(QA): PAWICH | 712020:83ff944e-9677-453f-b053-40e92520d905 | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 12/Feb/26 10:49 AM | 26/Mar/26 5:07 PM | [6 empty] | มาจาก Sprint 20 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Sub-task | DPE-186 | 43122 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 12/Feb/26 10:49 AM | 12/Mar/26 11:46 AM | [6 empty] | มาจาก Sprint 20 | Done |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Sub-task | DPE-185 | 43121 | [QA] Test execution | THUNDER(QA): PAWICH | 712020:83ff944e-9677-453f-b053-40e92520d905 | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 12/Feb/26 10:49 AM | 26/Mar/26 5:06 PM | [6 empty] | มาจาก Sprint 20 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Sub-task | DPE-184 | 43120 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 12/Feb/26 10:49 AM | 12/Mar/26 11:46 AM | [6 empty] | มาจาก Sprint 20 | Done |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Sub-task | DPE-179 | 43115 | [QA] Test execution | THUNDER(QA): PAWICH | 712020:83ff944e-9677-453f-b053-40e92520d905 | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 12/Feb/26 10:46 AM | 26/Mar/26 5:07 PM | [6 empty] | มาจาก Sprint 20 | To Do |  | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Sub-task | DPE-178 | 43114 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 12/Feb/26 10:46 AM | 12/Mar/26 11:47 AM | [6 empty] | มาจาก Sprint 20 | Done |  | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Story | DRST-21 | 43078 | [DEV][RD][BOF] Enhance Subscription Txn V2 support filter from query string | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 11/Feb/26 7:10 PM | 08/Apr/26 10:02 AM |  | 2 |  |  |  | 0 | มาจาก Sprint 20 | Ready to Staging | 14400 | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22
Story | RDTHANA-447 | 43072 | [DEV][RD][TDM] Sync Order Data from Shopify Stores Refund | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 11/Feb/26 6:36 PM | 07/Apr/26 2:45 PM | 18/Mar/26 12:00 AM | 5 | Thana-datamart |  |  | 0 | มาจาก Sprint 20 | Ready to Staging | 57600 | [Dev][RD][Thana] Sprint 20 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22
Story | RDTHANA-446 | 43071 | [DEV][RD][TDM] Sync Order Data from Shopify Stores to Data Mart #2 | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 11/Feb/26 6:36 PM | 07/Apr/26 2:45 PM | 20/Mar/26 12:00 AM | 5 | Thana-datamart |  |  | 0 | มาจาก Sprint 20 | Ready to Staging | 57600 | [Dev][RD][Thana] Sprint 20 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22
Story | RDTHANA-445 | 43070 | [DEV][RD][TDM] Sync Order Data from Shopify Stores to Data Mart table | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 11/Feb/26 6:35 PM | 07/Apr/26 2:45 PM | 18/Mar/26 12:00 AM | 5 | Thana-datamart |  |  | 0 | มาจาก Sprint 20 | Ready to Staging | 57600 | [Dev][RD][Thana] Sprint 20 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22
Story | RDTHANA-443 | 43068 | [DEV][RD][TDM] Create Webhook API Endpoint refunds/create | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 11/Feb/26 6:35 PM | 07/Apr/26 2:45 PM | 18/Mar/26 12:00 AM | 5 | Thana-datamart |  |  |  | มาจาก Sprint 20 | Ready to Staging |  | [Dev][RD][Thana] Sprint 20 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22
Story | RDTHANA-442 | 43067 | [DEV][RD][TDM] Create Webhook API Endpoint orders | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 11/Feb/26 6:34 PM | 07/Apr/26 2:45 PM | 16/Mar/26 12:00 AM | 5 | Thana-datamart |  |  | 0 | มาจาก Sprint 20 | Ready to Staging | 57600 | [Dev][RD][Thana] Sprint 20 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22
Story | RDTHANA-441 | 43066 | [DEV][RD][TDM] Create migration | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 11/Feb/26 6:33 PM | 07/Apr/26 2:45 PM | 12/Mar/26 12:00 AM | 5 | No-QA | Thana-datamart |  | 0 | มาจาก Sprint 20 | Ready to Staging | 57600 | [Dev][RD][Thana] Sprint 20 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 22
Epic | RDTHANA-431 | 42991 | Lighspeed Polling |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 11/Feb/26 3:07 PM | 07/Apr/26 2:45 PM | 06/Mar/26 12:00 AM | [5 empty] | มาจาก Sprint 20 | To Do |  | [Dev][RD][Thana] Sprint 19 | [Dev][RD][Thana] Sprint 20 | [Dev][RD][Thana] Sprint 21 | [Dev][RD][Thana] Sprint 18 | [Dev][RD][Thana] Sprint 22
Story | DRST-17 | 42821 | [DEV][RD][BOF] Create command to migrate data from VIMI database to Rabbit CMS database | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 11/Feb/26 10:17 AM | 07/Apr/26 2:42 PM |  | 8 | No-QA |  |  | 0 | มาจาก Sprint 20 | Ready To Test | 86400 | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22
Story | DRST-14 | 42267 | [DEV][RD][Rabbit CMS API] Create endpoint for get earn content | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 08/Feb/26 9:54 PM | 07/Apr/26 2:43 PM |  | 5 | cms-api | No-QA |  | 0 | มาจาก Sprint 20 | Ready To Test | 57600 | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22
Story | DPE-171 | 42260 | [Dev][RD][PE Middleware] Update offer | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 08/Feb/26 7:59 PM | 01/Apr/26 10:11 AM | 02/Mar/26 12:00 AM | 3 | point-engine-proxy |  |  | 0 | มาจาก Sprint 20 | Ready To Test | 28800 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Story | DPE-170 | 42259 | [Dev][RD][PE Middleware] Get offer list | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 08/Feb/26 7:59 PM | 02/Apr/26 11:03 AM | 04/Mar/26 12:00 AM | 3 | point-engine-proxy |  |  | 0 | มาจาก Sprint 20 | Ready To Test | 28800 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Story | DPE-169 | 42258 | [Dev][RD][PE Middleware] Create offer | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 08/Feb/26 7:58 PM | 01/Apr/26 10:11 AM | 26/Feb/26 12:00 AM | 3 | point-engine-proxy |  |  | 0 | มาจาก Sprint 20 | Ready To Test | 28800 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Story | DPE-158 | 42215 | [Dev][RD][BFF] Get point balance | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 07/Feb/26 3:24 PM | 08/Apr/26 3:44 PM | 16/Mar/26 12:00 AM | 5 |  |  |  | 0 | มาจาก Sprint 20 | Ready To Test | 57600 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-151 | 42176 | [Dev][RD][PE Middleware] Point history | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 07/Feb/26 8:18 AM | 07/Apr/26 9:23 AM |  | 3 | point-engine-proxy |  |  | 0 | มาจาก Sprint 20 | Ready To Test | 28800 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Story | DPE-149 | 42174 | [Dev][RD][PE Middleware] Credit point | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Done |  | 07/Feb/26 8:18 AM | 01/Apr/26 10:09 AM |  | 2 | point-engine-proxy |  |  | 0 | มาจาก Sprint 20 | Ready To Test | 14400 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Story | DPE-148 | 42173 | [Dev][RD][PE Middleware] Debit point | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Done |  | 07/Feb/26 8:18 AM | 01/Apr/26 10:08 AM |  | 3 | point-engine-proxy |  |  | 0 | มาจาก Sprint 20 | Ready To Test | 43200 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Story | DPE-147 | 42134 | [Dev][RD][SSO-User] WEB verify phone | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 6:37 PM | 07/Apr/26 2:56 PM |  | 1 | sso-user |  |  | 0 | มาจาก Sprint 20 | Ready To Test | 3600 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-146 | 42133 | [Dev][RD][SSO-User] WEB update avatar | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 6:37 PM | 07/Apr/26 2:56 PM |  | 1 | sso-user |  |  | 0 | มาจาก Sprint 20 | Ready To Test | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-145 | 42132 | [Dev][RD][SSO-User] WEB verify user | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 6:37 PM | 07/Apr/26 2:56 PM |  | 2 | sso-user |  |  | 0 | มาจาก Sprint 20 | Ready To Test | 10800 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-144 | 42131 | [Dev][RD][SSO-User] WEB remove card by card_id | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 6:37 PM | 07/Apr/26 2:56 PM |  | 1 | sso-user |  |  | 0 | มาจาก Sprint 20 | Ready To Test | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-143 | 42130 | [Dev][RD][SSO-User] WEB move card | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 6:36 PM | 07/Apr/26 2:56 PM |  | 1 | sso-user |  |  |  | มาจาก Sprint 20 | Ready To Test |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-142 | 42129 | [Dev][RD][SSO-User] WEB add card | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 6:36 PM | 07/Apr/26 2:56 PM |  | 1 | sso-user |  |  | 0 | มาจาก Sprint 20 | Ready To Test | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-141 | 42128 | [Dev][RD][SSO-User] WEB update profile by ID | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 6:36 PM | 07/Apr/26 2:56 PM | 12/Feb/26 12:00 AM | 2 | sso-user |  |  | 0 | มาจาก Sprint 20 | Ready To Test | 14400 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-129 | 42104 | [Dev][RD][ATN] Realtime issue point API | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Ready To Test |  | 06/Feb/26 2:16 PM | 07/Apr/26 2:56 PM | 01/Apr/26 12:00 AM | 3 |  |  |  | 28800 |  |  |  | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-128 | 42103 | [Dev][RD][ATN] Request individual issue point API | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Ready To Test |  | 06/Feb/26 2:16 PM | 07/Apr/26 2:56 PM | 31/Mar/26 12:00 AM | 3 |  |  |  | 28800 |  |  |  | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-123 | 42098 | [Dev][RD][REMQ] Async coupon push | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 1:44 PM | 07/Apr/26 2:56 PM | 12/Mar/26 12:00 AM | 5 |  |  |  | 0 | มาจาก Sprint 20 | Ready To Test | 57600 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-111 | 42054 | [Dev][RD][ATN] Bulk issue point for CRM Refund via RR-Backoffice | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Ready To Test |  | 06/Feb/26 12:11 PM | 07/Apr/26 2:56 PM | 03/Apr/26 12:00 AM | 5 |  |  |  | 57600 |  |  |  | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-103 | 42046 | [Dev][RD][goutil] Implement Point Engine Client Functions | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 06/Feb/26 11:54 AM | 07/Apr/26 2:56 PM |  | 3 | No-QA |  |  | 28800 |  |  |  | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-101 | 41974 | [Dev][RD][BOF] Create/Update Package | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:49 PM | 07/Apr/26 2:56 PM | 20/Mar/26 12:00 AM | 3 |  |  |  |  | มาจาก Sprint 20 | Ready to Staging |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-100 | 41973 | [Dev][RD][BOF] Update product | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:49 PM | 07/Apr/26 2:56 PM | 20/Mar/26 12:00 AM | 3 |  |  |  |  | มาจาก Sprint 20 | Ready to Staging |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-99 | 41972 | [Dev][RD][BOF] Create a new product | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:49 PM | 07/Apr/26 2:56 PM | 20/Mar/26 12:00 AM | 3 |  |  |  |  | มาจาก Sprint 20 | Ready to Staging |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-98 | 41971 | [Dev][RD][ORD] Disable sending order transaction data to DA | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 05/Feb/26 4:49 PM | 07/Apr/26 2:56 PM |  | 3 |  |  |  | 28800 |  |  |  | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-95 | 41968 | [Dev][RD][ORD] Place subscription order | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 05/Feb/26 4:48 PM | 07/Apr/26 2:56 PM | 27/Mar/26 12:00 AM | 5 | [7 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-93 | 41966 | [Dev][RD][REM] Improve reward redemption v2 | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 05/Feb/26 4:48 PM | 07/Apr/26 2:56 PM |  | 5 |  |  |  | 57600 |  |  |  | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-92 | 41965 | [Dev][RD][Sky Web] Switch Account | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:46 PM | 07/Apr/26 2:56 PM | 19/Mar/26 12:00 AM | 5 | sky-web |  |  | 0 | มาจาก Sprint 20 | Ready to Staging | 57600 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-91 | 41964 | [Dev][RD][Sky] Switch account API | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:46 PM | 07/Apr/26 2:56 PM | 19/Mar/26 12:00 AM | 3 | sky-api |  |  | 0 | มาจาก Sprint 20 | Ready to Staging | 28800 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-90 | 41963 | [Dev][RD][Sky][Member] Reactivate | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:46 PM | 07/Apr/26 2:56 PM | 12/Mar/26 12:00 AM | 2 | sky-api |  |  |  | มาจาก Sprint 20 | Ready to Staging |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-89 | 41962 | [Dev][RD][Sky][Member] Register Member | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:46 PM | 07/Apr/26 2:56 PM | 13/Mar/26 12:00 AM | 3 | sky-api |  |  | 0 | มาจาก Sprint 20 | Ready to Staging | 28800 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-86 | 41959 | [Dev][RD][PL] Create transaction | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Feb/26 4:46 PM | 07/Apr/26 2:56 PM | 03/Apr/26 12:00 AM | 5 | [7 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-81 | 41537 | [Dev][RD][PL][Member] Check RR member by Trader ID | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 04/Feb/26 10:26 AM | 08/Apr/26 12:57 PM |  | 3 |  |  |  |  | มาจาก Sprint 20 | Ready to Staging |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-80 | 41535 | [Dev][RD][PL][Member] Check RR member by phone | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 04/Feb/26 10:24 AM | 08/Apr/26 12:57 PM | 16/Mar/26 12:00 AM | 3 | partner-loyalty |  |  | 0 | มาจาก Sprint 20 | Ready to Staging | 28800 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-79 | 41533 | [Dev][RD][PL][Point] Get point | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 04/Feb/26 10:24 AM | 08/Apr/26 2:08 PM | 20/Mar/26 12:00 AM | 3 |  |  |  |  | มาจาก Sprint 20 | Ready to Staging |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-78 | 41531 | [Dev][RD][PL][Member] Check Member By ID | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 04/Feb/26 10:24 AM | 08/Apr/26 12:54 PM | 12/Mar/26 12:00 AM | 3 | partner-loyalty |  |  | 0 | มาจาก Sprint 20 | Ready to Staging | 28800 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-77 | 41529 | [Dev][RD][PL] Redeem point | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 04/Feb/26 10:23 AM | 07/Apr/26 2:56 PM | 03/Apr/26 12:00 AM | 5 | [7 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-75 | 41525 | [Dev][RD][PL] Request register | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Ready To Test |  | 04/Feb/26 10:17 AM | 07/Apr/26 2:56 PM | 03/Apr/26 12:00 AM | 2 | partner-loyalty | [6 empty] | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-74 | 41523 | [Dev][RD][SSO-User] Remove SSO-Thor API Integration | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Ready To Test |  | 04/Feb/26 10:13 AM | 07/Apr/26 2:56 PM |  | 5 | No-QA | sso-user |  | 0 | มาจาก Sprint 20 | Ready To Test | 57600 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-68 | 41511 | [Dev][RD][SSO-User] Rewards add card | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 04/Feb/26 9:49 AM | 07/Apr/26 2:56 PM | 10/Feb/26 12:00 AM | 1 | sso-user |  |  | 0 | มาจาก Sprint 20 | Ready To Test | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-67 | 41508 | [Dev][RD][PL][Member] Opt-in by SSO | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 04/Feb/26 9:43 AM | 07/Apr/26 2:56 PM | 12/Mar/26 12:00 AM | 3 | partner-loyalty |  |  | 0 | มาจาก Sprint 20 | Ready to Staging | 28800 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-66 | 41506 | [Dev][RD][PL][Member] Opt-in | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 04/Feb/26 9:43 AM | 07/Apr/26 2:56 PM | 12/Mar/26 12:00 AM | 5 | partner-loyalty |  |  | 0 | มาจาก Sprint 20 | Ready to Staging | 57600 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-65 | 41499 | [Dev][RD][PL][Member] Sync RR member | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 04/Feb/26 9:18 AM | 08/Apr/26 2:09 PM | 10/Mar/26 12:00 AM | 3 | partner-loyalty |  |  | 0 | มาจาก Sprint 20 | Ready To Test | 28800 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-64 | 41497 | [Dev][RD][PL][Member] Member binding | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 04/Feb/26 9:16 AM | 08/Apr/26 5:06 PM | 13/Mar/26 12:00 AM | 5 | partner-loyalty |  |  |  | มาจาก Sprint 20 | Ready to Staging |  | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-51 | 41439 | [Dev][RD][PE Middleware] Get balance | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Done |  | 03/Feb/26 7:41 PM | 02/Apr/26 12:44 PM |  | 2 | point-engine-proxy |  |  | 0 | มาจาก Sprint 20 | Ready To Test | 28800 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Story | DPE-50 | 41437 | [Dev][RD][SSO-User] Activate user by phone | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 03/Feb/26 7:41 PM | 26/Mar/26 5:07 PM |  | 2 | sso-user |  |  | 0 | มาจาก Sprint 20 | Ready To Test | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Story | DPE-49 | 41435 | [Dev][RD][SSO-User] Rewards Verify phone | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 03/Feb/26 7:41 PM | 07/Apr/26 2:56 PM |  | 2 | sso-user |  |  | 0 | มาจาก Sprint 20 | Ready To Test | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21 | [Dev][RD][New PE] Sprint 22
Story | DPE-48 | 41433 | [Dev][RD][SSO-User] Update rewards user | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 03/Feb/26 7:40 PM | 26/Mar/26 5:07 PM | 05/Feb/26 12:00 AM | 3 | sso-user |  |  | 0 | มาจาก Sprint 20 | Ready To Test | 28800 | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Story | DPE-47 | 41431 | [Dev][RD][SSO-User] Create rewards user | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 03/Feb/26 7:40 PM | 26/Mar/26 5:07 PM | 12/Feb/26 12:00 AM | 3 | sso-user |  |  | 0 | มาจาก Sprint 20 | Ready To Test | 28800 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Story | DPE-46 | 41429 | [Dev][RD][SSO-User] Create user profile | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 03/Feb/26 7:40 PM | 26/Mar/26 5:06 PM | 11/Feb/26 12:00 AM | 3 | sso-user |  |  | 0 | มาจาก Sprint 20 | Ready To Test | 28800 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20 | [Dev][RD][New PE] Sprint 21
Story | RDNDA-18 | 40130 | [DEV][RD][TDM] Create access control callback endpoint | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 22/Jan/26 5:03 PM | 23/Mar/26 10:04 AM |  | 3 |  |  |  | 0 | มาจาก Sprint 20 | Ready to Staging | 28800 | [Dev][RD][NewDamart] Sprint 17 | [Dev][RD][NewDamart] Sprint 18 | [Dev][RD][NewDamart] Sprint 19 | [Dev][RD][NewDamart] Sprint 20 | [Dev][RD][NewDamart] Sprint 21
Story | RDNDA-6 | 38244 | [DEV][RD][TDM] Create generic transactions endpoint | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 07/Jan/26 5:17 PM | 23/Mar/26 10:04 AM |  | 5 | Thana-datamart |  |  | 0 | มาจาก Sprint 20 | Ready To Test | 86400 | [Dev][RD][NewDamart] Sprint 16 | [Dev][RD][NewDamart] Sprint 17 | [Dev][RD][NewDamart] Sprint 18 | [Dev][RD][NewDamart] Sprint 19 | [Dev][RD][NewDamart] Sprint 20 | [Dev][RD][NewDamart] Sprint 21
Story | DRST-6 | 38163 | [Dev][RD][Terminate VIMI][VoucherValidator] Refactor APIs to remove dependency on MVP Phase 1 source | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready To Test |  | 07/Jan/26 11:12 AM | 07/Apr/26 3:31 PM | 10/Feb/26 12:00 AM | 3 |  |  |  | 0 | มาจาก Sprint 20 | Ready to Staging | 28800 | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22
Story | DRST-5 | 38162 | [Dev][RD][Terminate VIMI][MerchantAPI] Refactor APIs to remove dependency on MVP Phase 1 source | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready To Test |  | 07/Jan/26 11:12 AM | 07/Apr/26 3:31 PM | 11/Feb/26 12:00 AM | 3 |  |  |  | 0 | มาจาก Sprint 20 | Ready to Staging | 28800 | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22
Story | DRST-7 | 36975 | [Dev][RD][Terminate VIMI] Refactor TXN Report API and Report Summary API to remove dependency on MVP Phase 1 report source | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready To Test |  | 23/Dec/25 12:23 PM | 07/Apr/26 3:32 PM | 30/Dec/25 12:00 AM | 3 |  |  |  | 0 | มาจาก Sprint 20 | Ready to Staging | 28800 | [Dev][All Project] Sprint 15 | [Dev][All Project] Sprint 16 | [Dev RD][VIMI Termi] Sprint 17 | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20 | [Dev RD][VIMI Termi] Sprint 21 | [Dev RD][VIMI Termi] Sprint 22

## Summarize Sprint 20
Column 1 | Total Stories Point | Total Manhour | Point Done | Manhour Done | Note
9 Mar - 20 Mar
Dev Resource Available | 21 | 444.5
Meeting Planned |  |  |  |  | Ref
Additional Meeting |  |  |  |  | Ref
Deployment |  | 2 |  |  | 1 ครั้ง 1. 2 คน
Development Sprint Total | 483 | 402.5 | 207 | 149.5
Ad-hoc Mid Sprint | 0 | 0 | 0 | 0 | 2 tasks
Requirement changes after refinement? | 0 |  | 0 | 0 | 0 tasks
Aek | 22 | 62.5 | 22 | 62.5
A | 57 | 81 | 7 | 8
Aom | 54 | 12 | 27 | 12
Zan | 27 | 0 | 24 | 0
Mai | 77 | 48 | 48 | 12
Mac | 74 | 70 | 38 | 3
Mos | 67 | 56 | 17 | 0
Jack | 10 | 0 | 5 | 0
Nim | 60 | 73 | 16 | 52
Arm | 35 | 0 | 3 | 0
Resource Plan – Sprint 20 9 Mar - 20 Mar
Capacity รวม 130.5 SP | 130.5
Allocation each project (exclude PE) | 59.5
Allocation PE | 71
New Point Engine | 66 | 4
Vimi Termination | 21 | 1
Thana | 34.5 | 2
Datamart | 0 | 0
AWS | 0 | 0
Dev Support | 1 | 1
Remaining | 5
Name | Availability | Capacity | Total Workload | Allocation PE | PE (SP) | Allocation VIMI (days) | VIMI (SP) | Allocation Thana (days) | Thana (SP) | Allocation AWS (days) | AWS (SP) | Allocation Adhoc (days) | Adhoc (SP) | Dev Support | Dev Support (SP)
A | 7 | 21 | 23.5 | 6.5 | 19.5 |  | 0 |  | 0 |  | 0 | 1 | 3 | 0 | 1
Mac | 7.5 | 22.5 | 24 | 1.5 | 4.5 |  | 0 | 6.5 | 19.5 |  | 0 |  |  | 0 | 0
Mai | 7 | 21 | 19.5 | 1.5 | 4.5 |  | 0 | 5 | 15 |  | 0 |  |  | 0 | 0
Mos | 7 | 21 | 19.5 | 6.5 | 19.5 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
Nim | 7 | 21 | 21 |  | 0 | 7 | 21 |  | 0 |  | 0 |  |  | 0 | 0
Arm | 8 | 24 | 18 | 6 | 18 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
Total |  | 130.5 | 125.5 | 22 | 66 | 7 | 21 | 11.5 | 34.5 | 0 | 0 | 1 | 3 | 0 | 1
| System Architech |  |  |  | Permanent Dev. |  |  | Outsources
Projects (Stories Points) | Aek | Zan | Aom | Jack | A | Art | Mai | Kae | Mac | Nim | Mos | Arm
| 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 47 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 2 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 20 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 3
| System Architech |  |  |  | Permanent Dev. |  |  | Outsources
Projects (Manhour) | Aek | Zan | Aom | Jack | A | Art | Mai | Kae | Mac | Nim | Mos | Arm
| 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 54 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 61.5 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 20
Issue Type | Issue key | Issue id | Summary | Assignee | Assignee Id | Reporter | Reporter Id | Priority | Status | Resolution | Created | Updated | Due date | Custom field (Story Points) | Labels | Labels | Labels | Original estimate | Sprint Movement | Sprint 19 | Note | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint
Sub-task | DPE-367 | 50330 | [NPE] Prepare env files for CT environment |  |  | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | To Do |  | 20/Mar/26 11:03 AM | 20/Mar/26 11:05 AM | [9 empty] | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-366 | 50328 | Update service to support Redis with cluster mode |  |  | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | To Do |  | 20/Mar/26 10:59 AM | 20/Mar/26 11:02 AM | [9 empty] | [Dev][RD][New PE] Sprint 20
Story | RDNDA-34 | 50294 | [DEV][RD][TDM][SA] Prepare Prod ENV | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Progress |  | 20/Mar/26 10:00 AM | 20/Mar/26 10:01 AM |  | 3 | [7 empty] | [Dev][RD][NewDamart] Sprint 20
Sub-task | DRST-78 | 50221 | Delete Report Service (wait SA -> P'Zan) | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Medium | To Do |  | 19/Mar/26 1:49 PM | 20/Mar/26 11:23 AM | [9 empty] | [Dev RD][VIMI Termi] Sprint 20
Sub-task | DRST-77 | 50218 | Delete-> Model ->Repository-> Service | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Medium | Done |  | 19/Mar/26 1:49 PM | 20/Mar/26 11:22 AM | [5 empty] | 28800 |  |  |  | [Dev RD][VIMI Termi] Sprint 20
Sub-task | DRST-76 | 50206 | Delete View -> Api route -> controller | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Medium | Done |  | 19/Mar/26 1:40 PM | 20/Mar/26 11:22 AM | [5 empty] | 14400 |  |  |  | [Dev RD][VIMI Termi] Sprint 20
Sub-task | DRST-75 | 50201 | List service,repo,model | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Medium | Done |  | 19/Mar/26 1:39 PM | 20/Mar/26 11:22 AM | [5 empty] | 43200 |  |  |  | [Dev RD][VIMI Termi] Sprint 20
Sub-task | DRST-74 | 50079 | [QA] Test Execution - UAT | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 18/Mar/26 1:59 PM | 18/Mar/26 4:15 PM | [9 empty] | [Dev RD][VIMI Termi] Sprint 20
Sub-task | DRST-73 | 50077 | [QA] Test Execution - UAT | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 18/Mar/26 1:59 PM | 18/Mar/26 3:56 PM | [9 empty] | [Dev RD][VIMI Termi] Sprint 20
Sub-task | DRST-72 | 50075 | [QA] Test Execution - UAT | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 18/Mar/26 1:59 PM | 18/Mar/26 3:36 PM | [9 empty] | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20
Sub-task | DRST-71 | 50073 | [QA] Test Execution - UAT | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 18/Mar/26 1:59 PM | 18/Mar/26 2:45 PM | [9 empty] | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20
Sub-task | DRST-70 | 50071 | [QA] Test Execution - STG | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 18/Mar/26 1:57 PM | 18/Mar/26 2:24 PM | [9 empty] | [Dev RD][VIMI Termi] Sprint 20
Bug | DEVRDSUP-504 | 49870 | [SUP-586]HOP: The Visionary card is not showing in the app. | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Mook Nicharee Boonthai | 712020:c2ed8478-f54b-4b43-92d9-b933a57493dc | Medium | UNDER VALIDATION |  | 18/Mar/26 9:44 AM | 20/Mar/26 11:29 AM | [9 empty] | [Dev][All Project] Sprint 20
Story | DPE-358 | 49771 | [Dev][RD][PE Middleware] Import Merchant and Offer Data from CSV into Database | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 17/Mar/26 4:50 PM | 19/Mar/26 9:35 AM |  | 3 | No-QA | [6 empty] | [Dev][RD][New PE] Sprint 20
Story | RDAPS-434 | 49602 | [DEV][RD][SA] Prepare task for technical dept | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 17/Mar/26 2:55 PM | 17/Mar/26 4:20 PM |  | 1 |  |  |  | 7200 |  |  |  | [Dev][All Project] Sprint 20
Story | RDAPS-433 | 48836 | [DEV][RD][SA] Incident support and investigate | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 17/Mar/26 2:04 PM | 20/Mar/26 9:45 AM |  | 1 |  |  |  | 7200 |  |  |  | [Dev][All Project] Sprint 20
Story | RDAPS-432 | 48697 | [DEV][RD][SA] Team supoort & management | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 17/Mar/26 1:56 PM | 20/Mar/26 9:53 AM |  | 8 |  |  |  | 86400 |  |  |  | [Dev][All Project] Sprint 20
Story | RDAPS-431 | 48693 | [DEV][RD][SA] Workshop AWS Transform | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 17/Mar/26 1:51 PM | 17/Mar/26 1:53 PM |  | 2 |  |  |  | 14400 |  |  |  | [Dev][All Project] Sprint 20
Story | RDAPS-430 | 48692 | [DEV][RD][SA] Meeting | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 17/Mar/26 1:42 PM | 20/Mar/26 9:51 AM |  | 8 |  |  |  | 106200 |  |  |  | [Dev][All Project] Sprint 20
Sub-task | DPE-357 | 48623 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 17/Mar/26 10:16 AM | 17/Mar/26 10:16 AM | [9 empty] | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-356 | 48621 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 17/Mar/26 10:16 AM | 17/Mar/26 10:16 AM | [9 empty] | [Dev][RD][New PE] Sprint 20
Story | DEVRDSUP-502 | 48540 | [SUP-582][Earned Points] CS-20260200024858 // Please check duplicate SSO ID with RW:0880040508640 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Mook Nicharee Boonthai | 712020:c2ed8478-f54b-4b43-92d9-b933a57493dc | Medium | Done |  | 16/Mar/26 5:46 PM | 20/Mar/26 11:29 AM |  | 1 |  |  |  | 1800 |  |  |  | [Dev][All Project] Sprint 20
Bug | DEVRDSUP-501 | 48539 | [SUP-584]HOP check in notification delay | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Mook Nicharee Boonthai | 712020:c2ed8478-f54b-4b43-92d9-b933a57493dc | Medium | UNDER VALIDATION |  | 16/Mar/26 5:42 PM | 20/Mar/26 11:29 AM | [9 empty] | [Dev][All Project] Sprint 20
Story | DEVRDSUP-500 | 48505 | [SUP-585][RR account] CS-20260100023724 // Please check duplicate SSO ID binding with RW 0880053082355 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Mook Nicharee Boonthai | 712020:c2ed8478-f54b-4b43-92d9-b933a57493dc | Medium | Done |  | 16/Mar/26 4:38 PM | 20/Mar/26 11:29 AM |  | 1 |  |  |  | 1800 |  |  |  | [Dev][All Project] Sprint 20
Sub-task | DPE-354 | 48496 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 16/Mar/26 2:30 PM | 16/Mar/26 2:30 PM | [9 empty] | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-353 | 48494 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 16/Mar/26 2:30 PM | 16/Mar/26 2:30 PM | [9 empty] | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-352 | 48492 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 16/Mar/26 2:30 PM | 16/Mar/26 2:30 PM | [9 empty] | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-351 | 48491 | Test execution | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 16/Mar/26 2:30 PM | 17/Mar/26 1:43 PM | [9 empty] | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-350 | 48486 | Test execution | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 16/Mar/26 2:30 PM | 17/Mar/26 1:43 PM | [9 empty] | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-349 | 48488 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 16/Mar/26 2:30 PM | 16/Mar/26 2:30 PM | [9 empty] | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-348 | 48484 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 16/Mar/26 2:30 PM | 16/Mar/26 2:30 PM | [9 empty] | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-347 | 48482 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 16/Mar/26 2:30 PM | 16/Mar/26 2:30 PM | [9 empty] | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-346 | 48480 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | In Review |  | 16/Mar/26 2:30 PM | 17/Mar/26 5:15 PM | [9 empty] | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-345 | 48477 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 16/Mar/26 2:30 PM | 16/Mar/26 2:30 PM | [9 empty] | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-344 | 48478 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | In Review |  | 16/Mar/26 2:30 PM | 17/Mar/26 3:09 PM | [9 empty] | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-343 | 48476 | Create test case | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | In Progress |  | 16/Mar/26 2:30 PM | 18/Mar/26 1:13 PM | [9 empty] | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-342 | 48475 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | In Progress |  | 16/Mar/26 2:30 PM | 17/Mar/26 5:16 PM | [9 empty] | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-341 | 48470 | Create test case | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | In Progress |  | 16/Mar/26 2:30 PM | 18/Mar/26 10:29 AM | [9 empty] | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-340 | 48469 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | In Progress |  | 16/Mar/26 2:30 PM | 18/Mar/26 2:53 PM | [9 empty] | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-339 | 48468 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | In Review |  | 16/Mar/26 2:30 PM | 17/Mar/26 5:08 PM | [9 empty] | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-338 | 48464 | [QA] Test execution |  |  | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 16/Mar/26 2:14 PM | 17/Mar/26 10:16 AM | [9 empty] | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-337 | 48462 | [QA] Create test case | THUNDER(QA): PAWICH | 712020:83ff944e-9677-453f-b053-40e92520d905 | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | In Progress |  | 16/Mar/26 2:14 PM | 17/Mar/26 10:16 AM | [9 empty] | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-336 | 48460 | [QA] Test execution |  |  | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 16/Mar/26 2:14 PM | 17/Mar/26 10:15 AM | [9 empty] | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-335 | 48458 | [QA] Create test case | THUNDER(QA): PAWICH | 712020:83ff944e-9677-453f-b053-40e92520d905 | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | In Progress |  | 16/Mar/26 2:14 PM | 17/Mar/26 10:15 AM | [9 empty] | [Dev][RD][New PE] Sprint 20
Sub-task | DRST-68 | 48351 | [QA] Test Execution - STG | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 16/Mar/26 9:15 AM | 16/Mar/26 1:53 PM | [9 empty] | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20
Sub-task | DRST-67 | 48349 | [QA] Test Execution - STG | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 16/Mar/26 9:15 AM | 18/Mar/26 2:05 PM | [9 empty] | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20
Sub-task | DRST-66 | 48347 | [QA] Test Execution - STG | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 16/Mar/26 9:15 AM | 18/Mar/26 10:18 AM | [9 empty] | [Dev RD][VIMI Termi] Sprint 20
Story | DPE-331 | 48211 | [Dev][RD][SSO User] Improve BSS sync member to RR API | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 13/Mar/26 4:46 PM | 20/Mar/26 10:40 AM | 20/Mar/26 12:00 AM | 2 |  |  |  | 14400 |  |  |  | [Dev][RD][New PE] Sprint 20
Story | DPE-329 | 48176 | [Dev][RD] Support DevOps for RR Service Provisioning | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 13/Mar/26 2:50 PM | 20/Mar/26 11:03 AM |  | 5 |  |  |  | 86400 |  |  |  | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-326 | 48166 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 13/Mar/26 1:10 PM | 13/Mar/26 1:10 PM | [9 empty] | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-325 | 48164 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | In Review |  | 13/Mar/26 1:10 PM | 13/Mar/26 1:51 PM | [9 empty] | [Dev][RD][New PE] Sprint 20
Bug | DPE-323 | 48023 | [S3][SSO Backoffice] Unable to create/update registration source | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | THUNDER(QA): PAWICH | 712020:83ff944e-9677-453f-b053-40e92520d905 | Medium | Rejected |  | 12/Mar/26 1:38 PM | 12/Mar/26 5:01 PM | [9 empty] | [Dev][RD][New PE] Sprint 20
Story | RDTHANA-461 | 47970 | [DEV][RD][TDM] Change master data index key csv file to lowercase | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 12/Mar/26 11:25 AM | 18/Mar/26 4:35 PM | 12/Mar/26 12:00 AM | 2 |  |  |  | 14400 |  |  |  | [Dev][RD][Thana] Sprint 20
Story | DPE-322 | 47929 | [Dev][RD][SA][Sprint21] Analysis & Task Breakdown for PE Migration Execution | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 12/Mar/26 9:42 AM | 13/Mar/26 11:36 AM |  | 13 | [7 empty] | [Dev][RD][New PE] Sprint 20
Story | DEVRDSUP-497 | 47665 | [SUP-580][SUB] Receipt is not generated after SUB transaction is made (11 MAR 2026) | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Thanakrit Chanthaworn | 712020:3fc982cb-c268-4f1d-9265-d3dd8fb08304 | Highest | Done |  | 11/Mar/26 11:29 AM | 20/Mar/26 11:30 AM | 11/Mar/26 12:00 AM | 1 | bts | BURequest | sub |  |  |  |  | [Dev][All Project] Sprint 20
Bug | RDAPS-427 | 47559 | [S3]Gen deeplink for character "Ampersand" incorrect | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Closed |  | 10/Mar/26 10:07 PM | 19/Mar/26 4:41 PM |  | 1 | [7 empty] | [Dev][All Project] Sprint 20
Story | DRST-65 | 47526 | [DEV][RD][CMS API] Setup ENV | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 10/Mar/26 4:10 PM | 10/Mar/26 5:17 PM |  | 1 |  |  |  | 3600 |  |  |  | [Dev RD][VIMI Termi] Sprint 20
Story | DEVRDSUP-495 | 47473 | [SUP-578][Sub] CS-20260300025685 // Request mark used coupon 11582937 - SN 0880063175153 Rabbit Wallet | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Thanakrit Chanthaworn | 712020:3fc982cb-c268-4f1d-9265-d3dd8fb08304 | Medium | Done |  | 10/Mar/26 2:24 PM | 20/Mar/26 11:30 AM |  |  | bts | sub | [5 empty] | [Dev][All Project] Sprint 20
Story | DEVRDSUP-494 | 47460 | [SUP-577][SUB] Receipt is not generated after SUB transaction is made (10 MAR 2026) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Thanakrit Chanthaworn | 712020:3fc982cb-c268-4f1d-9265-d3dd8fb08304 | Medium | Done |  | 10/Mar/26 1:23 PM | 10/Mar/26 3:00 PM | 10/Mar/26 12:00 AM |  | bts | BURequest | sub |  |  |  |  | [Dev][All Project] Sprint 20
Story | DEVRDSUP-493 | 47419 | [SUP-576][SUB] Mark used card fail | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Mean Pichan Suphunjitwana | 63108a0709bc6014ea8b3b58 | Medium | Done |  | 10/Mar/26 11:41 AM | 11/Mar/26 9:26 AM | [9 empty] | [Dev][All Project] Sprint 20
Bug | DEVRDSUP-492 | 47417 | [SUP-575][SSO] slow on BSS side | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Mean Pichan Suphunjitwana | 63108a0709bc6014ea8b3b58 | Medium | Resolved |  | 10/Mar/26 11:33 AM | 13/Mar/26 5:22 PM | 11/Mar/26 12:00 AM | [8 empty] | [Dev][All Project] Sprint 20
Bug | DEVRDSUP-491 | 47350 | [Subscription TXN] 'Next' button is disabled on Index page | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Pass : Waiting for deployment |  | 10/Mar/26 10:48 AM | 19/Mar/26 4:41 PM | [9 empty] | [Dev][All Project] Sprint 20
Sub-task | DRST-64 | 47309 | [QA] Test Execution STG | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 09/Mar/26 10:12 PM | 10/Mar/26 9:20 AM | [9 empty] | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20
Sub-task | DRST-63 | 47307 | [QA] Test Execution STG | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 09/Mar/26 10:11 PM | 09/Mar/26 10:56 PM | [9 empty] | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20
Sub-task | DRST-62 | 47305 | [QA] Test Execution STG | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 09/Mar/26 10:11 PM | 10/Mar/26 10:05 AM | [9 empty] | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20
Story | RDNDA-31 | 47251 | [DEV][RD][TDM][SA] Setup DEV server | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 09/Mar/26 4:25 PM | 20/Mar/26 10:00 AM |  | 8 | [7 empty] | [Dev][RD][NewDamart] Sprint 20
Story | RDAPS-425 | 47146 | [Dev][RD][SSO][Investigate] Slow API Response During Login with PIN (MyRabbit App) | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 09/Mar/26 1:21 PM | 20/Mar/26 11:22 AM |  | 3 |  |  |  | 28800 |  |  |  | [Dev][All Project] Sprint 20
Story | DPE-307 | 46949 | [Dev][RD][PE Middleware] Enhance Merchant Creation API | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 07/Mar/26 5:18 AM | 20/Mar/26 11:05 AM |  | 3 |  |  |  | 28800 |  |  |  | [Dev][RD][New PE] Sprint 20
Story | DRST-61 | 46883 | [DEV][RD][BOF] Remove Subscription V1 in backoffice and database | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Progress |  | 06/Mar/26 5:04 PM | 18/Mar/26 11:46 AM |  | 8 | [7 empty] | [Dev RD][VIMI Termi] Sprint 20
Story | DPWP-50 | 46783 | [DEV][RD][API] Create API spec for sale transaction and member identifier | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 06/Mar/26 3:39 PM | 20/Mar/26 11:24 AM |  | 8 | [7 empty] | [Dev][RD][PWP] Sprint 20
Story | DPE-305 | 46740 | [Dev][RD][SA] Design Event Properties for `RABBIT_TRANSACTION_OCCURRED ` | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 06/Mar/26 2:51 PM | 16/Mar/26 10:10 AM |  | 8 | [7 empty] | [Dev][RD][New PE] Sprint 20
Bug | DEVRDSUP-488 | 46584 | [SUP-571][HOP] Urgent: Customer Not Receiving RR Activation Email | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Closed |  | 05/Mar/26 6:38 PM | 20/Mar/26 11:29 AM | [9 empty] | [Dev][All Project] Sprint 20
Story | DRST-47 | 46144 | [DEV][RD][BFF][USER] Create update avatar endpoint | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 02/Mar/26 3:29 PM | 20/Mar/26 11:08 AM |  | 3 |  |  |  | 28800 |  |  |  | [Dev RD][VIMI Termi] Sprint 20
Story | DRST-46 | 46143 | [DEV][RD][SSO-User][Rabbit Member] Create endpoint to upload avatar | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 02/Mar/26 3:28 PM | 20/Mar/26 11:07 AM |  | 5 |  |  |  | 57600 |  |  |  | [Dev RD][VIMI Termi] Sprint 20
Story | DRST-45 | 46142 | [DEV][RD][BFF][USER] Create change password endpoint | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 02/Mar/26 3:27 PM | 20/Mar/26 11:07 AM |  | 3 |  |  |  | 28800 |  |  |  | [Dev RD][VIMI Termi] Sprint 20
Story | DRST-44 | 46141 | [DEV][RD][BFF][USER] Create confirm phone OTP | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 02/Mar/26 3:14 PM | 19/Mar/26 4:41 PM |  | 3 |  |  |  | 0 | มาจาก Sprint 19 | In Review | 28800 | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20
Story | DRST-43 | 46140 | [DEV][RD][BFF][USER] Create update user profile endpoint | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 02/Mar/26 2:55 PM | 20/Mar/26 11:08 AM | 06/Mar/26 12:00 AM | 8 |  |  |  | 43200 | มาจาก Sprint 19 | In Progress | 86400 -> 43200 | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20
Sub-task | DRST-42 | 46139 | Create API Task |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Progress |  | 02/Mar/26 2:52 PM | 02/Mar/26 2:52 PM | [6 empty] | มาจาก Sprint 19 | In Progress |  | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20
Sub-task | DRST-41 | 46137 | Update BFF API Doc | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Review |  | 02/Mar/26 2:51 PM | 20/Mar/26 9:59 AM | [6 empty] | มาจาก Sprint 19 | In Progress |  | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20
Sub-task | DRST-40 | 46135 | Mapping API VIMI to RD | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 02/Mar/26 2:51 PM | 02/Mar/26 2:52 PM | [6 empty] | มาจาก Sprint 19 | Done |  | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20
Bug | DEVRDSUP-483 | 46099 | [SUP-567]User properties birthday has changed in Clevertap | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | RETESTING |  | 02/Mar/26 1:57 PM | 20/Mar/26 11:30 AM | [9 empty] | [Dev][All Project] Sprint 20
Story | DEVRDSUP-482 | 46066 | [SUP-565][SUB] : Request to export receipt due to Incomplete Emails Received by BTSC (FEB26) | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Highest | Done |  | 02/Mar/26 12:53 PM | 20/Mar/26 11:30 AM | 05/Mar/26 12:00 AM | 1 | bts | BURequest | sub |  |  |  |  | [Dev][All Project] Sprint 20
Story | DEVRDSUP-480 | 46028 | [SUP-566][REM] Request to export available coupon codes for 1 REM SKU 02/03/2026. |  |  | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 02/Mar/26 11:02 AM | 19/Mar/26 10:34 AM | 06/Mar/26 12:00 AM |  | BURequest | rem | [5 empty] | [Dev][All Project] Sprint 20
Bug | DEVRDSUP-479 | 46025 | [SUP-564]ไม่สามารถดึง Available code ได้ ระบบขึ้นว่า No data found | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Open |  | 02/Mar/26 10:01 AM | 20/Mar/26 11:29 AM | 18/Mar/26 12:00 AM |  | rem | [6 empty] | [Dev][All Project] Sprint 20
Sub-task | DPE-299 | 45883 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | In Progress |  | 27/Feb/26 2:59 PM | 16/Mar/26 12:44 PM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-298 | 45881 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 27/Feb/26 2:59 PM | 12/Mar/26 11:46 AM | [6 empty] | มาจาก Sprint 19 | In Review |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-297 | 45879 | [Dev][RD][SSO-User] Backoffice Delete Account | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 27/Feb/26 2:54 PM | 20/Mar/26 11:07 AM | [5 empty] | 0 | มาจาก Sprint 19 | Ready to Staging | 7200 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-294 | 45383 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 13/Mar/26 11:51 AM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-293 | 45381 | Test execution | THUNDER(QA): PAWICH | 712020:83ff944e-9677-453f-b053-40e92520d905 | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 13/Mar/26 10:01 AM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-292 | 45379 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 13/Mar/26 11:18 AM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-291 | 45377 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 10:51 PM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-290 | 45375 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:49 AM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-289 | 45373 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:39 PM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-288 | 45372 | Test execution | THUNDER(QA): PAWICH | 712020:83ff944e-9677-453f-b053-40e92520d905 | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 13/Mar/26 10:01 AM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-287 | 45369 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [6 empty] | มาจาก Sprint 19 | In Review |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-286 | 45367 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [6 empty] | มาจาก Sprint 19 | In Review |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-285 | 45365 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-284 | 45363 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [6 empty] | มาจาก Sprint 19 | In Review |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-283 | 45361 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-282 | 45359 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [6 empty] | มาจาก Sprint 19 | In Review |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-281 | 45357 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [6 empty] | มาจาก Sprint 19 | In Progress |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-280 | 45355 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:58 PM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-279 | 45354 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 7:01 PM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-277 | 45351 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:59 PM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-278 | 45350 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:59 PM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-276 | 45343 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:59 PM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-275 | 45348 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:59 PM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-274 | 45345 | TO BE DELETED |  |  | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 27/Feb/26 3:08 PM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-273 | 45342 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 7:01 PM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-272 | 45339 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:50 PM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-271 | 45337 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 16/Mar/26 3:12 PM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-270 | 45335 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-269 | 45333 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-268 | 45331 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-267 | 45332 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-266 | 45329 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-265 | 45330 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-264 | 45324 | TO BE DELETED |  |  | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-263 | 45326 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-262 | 45319 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-261 | 45321 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:48 PM | 12/Mar/26 11:46 AM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-260 | 45315 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:12 PM | 25/Feb/26 6:12 PM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-259 | 45313 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:12 PM | 16/Mar/26 12:42 PM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-258 | 45311 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:12 PM | 25/Feb/26 6:12 PM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-257 | 45309 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:12 PM | 16/Mar/26 12:42 PM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-256 | 45307 | Test execution | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | In Progress |  | 25/Feb/26 6:12 PM | 19/Mar/26 12:37 PM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-255 | 45305 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:12 PM | 16/Mar/26 12:42 PM | [6 empty] | มาจาก Sprint 19 | In Review |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-254 | 45303 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:12 PM | 25/Feb/26 6:12 PM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-253 | 45301 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:12 PM | 16/Mar/26 12:42 PM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-252 | 45299 | Test execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:12 PM | 19/Mar/26 12:37 PM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-251 | 45297 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:12 PM | 16/Mar/26 12:42 PM | [6 empty] | มาจาก Sprint 19 | In Review |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-250 | 45295 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:11 PM | 25/Feb/26 6:11 PM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-249 | 45293 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:11 PM | 16/Mar/26 12:42 PM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-248 | 45291 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:02 PM | 25/Feb/26 6:03 PM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-247 | 45289 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:02 PM | 16/Mar/26 12:42 PM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-246 | 45287 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:01 PM | 25/Feb/26 6:01 PM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-245 | 45285 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 6:01 PM | 16/Mar/26 12:42 PM | [6 empty] | มาจาก Sprint 19 | In Progress |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-244 | 45282 | Test execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 5:56 PM | 19/Mar/26 12:37 PM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-243 | 45280 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 5:56 PM | 18/Mar/26 11:22 AM | [6 empty] | มาจาก Sprint 19 | In Review |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-242 | 45278 | Test execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | In Progress |  | 25/Feb/26 5:56 PM | 19/Mar/26 12:37 PM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-241 | 45276 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | Done |  | 25/Feb/26 5:56 PM | 16/Mar/26 12:42 PM | [6 empty] | มาจาก Sprint 19 | In Review |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-240 | 45274 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 25/Feb/26 5:43 PM | 25/Feb/26 5:43 PM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-239 | 45272 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 25/Feb/26 5:42 PM | 16/Mar/26 12:43 PM | [6 empty] | มาจาก Sprint 19 | In Review |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-238 | 45270 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 25/Feb/26 5:42 PM | 25/Feb/26 5:42 PM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-237 | 45268 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 25/Feb/26 5:42 PM | 16/Mar/26 12:42 PM | [6 empty] | มาจาก Sprint 19 | In Review |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-236 | 45266 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 25/Feb/26 5:42 PM | 25/Feb/26 5:42 PM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-235 | 45264 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 25/Feb/26 5:41 PM | 16/Mar/26 12:42 PM | [6 empty] | มาจาก Sprint 19 | In Review |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-234 | 45262 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 25/Feb/26 5:40 PM | 25/Feb/26 5:40 PM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-233 | 45260 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 25/Feb/26 5:40 PM | 16/Mar/26 12:43 PM | [6 empty] | มาจาก Sprint 19 | In Review |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-232 | 45258 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 25/Feb/26 5:40 PM | 12/Mar/26 11:45 AM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-231 | 45256 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 25/Feb/26 5:40 PM | 16/Mar/26 12:42 PM | [6 empty] | มาจาก Sprint 19 | In Review |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-230 | 44981 | [Dev][RD][SA] Retail Transaction Flow | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 24/Feb/26 2:10 PM | 16/Mar/26 11:11 AM |  | 13 | No-QA |  |  | 43200 | มาจาก Sprint 19 | In Progress | 86400 -> 43200 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-229 | 44980 | [Dev][RD][PE Proxy Scheduler] Request Github Repository | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 24/Feb/26 2:10 PM | 19/Mar/26 2:02 PM |  | 2 | [7 empty] | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-228 | 44837 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 23/Feb/26 5:45 PM | 12/Mar/26 11:45 AM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-227 | 44835 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 23/Feb/26 5:45 PM | 12/Mar/26 11:46 AM | [6 empty] | มาจาก Sprint 19 | In Review |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-226 | 44833 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 23/Feb/26 5:43 PM | 23/Feb/26 5:43 PM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-225 | 44831 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 23/Feb/26 5:43 PM | 12/Mar/26 11:46 AM | [6 empty] | มาจาก Sprint 19 | In Review |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-224 | 44784 | [Dev][RD][PE Middleware] Database Migration | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Highest | Done |  | 23/Feb/26 3:39 PM | 17/Mar/26 4:32 PM |  | 3 | No-QA | point-engine-proxy |  | 0 | มาจาก Sprint 19 | Ready to Staging | 28800 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-223 | 44711 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 23/Feb/26 1:29 PM | 13/Mar/26 9:31 AM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-222 | 44709 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 23/Feb/26 1:29 PM | 12/Mar/26 11:46 AM | [6 empty] | มาจาก Sprint 19 | In Review |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-221 | 44707 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 23/Feb/26 1:29 PM | 13/Mar/26 9:32 AM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-220 | 44705 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 23/Feb/26 1:29 PM | 12/Mar/26 11:46 AM | [6 empty] | มาจาก Sprint 19 | In Review |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-219 | 44552 | [Dev][RD][PE Middleware] Delete Offer (Soft Delete) | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready To Test |  | 22/Feb/26 12:40 PM | 18/Mar/26 1:42 PM | 06/Mar/26 12:00 AM | 1 | point-engine-proxy |  |  | 3600 | มาจาก Sprint 19 | In Progress | 7200 -> 3600 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-218 | 44551 | [Dev][RD][PE Middleware] Get Offer by id | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready to Staging |  | 22/Feb/26 11:42 AM | 18/Mar/26 1:43 PM | 05/Mar/26 12:00 AM | 2 | point-engine-proxy |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 14400 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-217 | 44550 | [Dev][RD][PE Middleware] Get Merchant by id | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready To Test |  | 22/Feb/26 11:17 AM | 18/Mar/26 1:17 PM |  | 3 | point-engine-proxy |  |  |  | มาจาก Sprint 19 | Ready to Staging |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-216 | 44549 | [Dev][RD][PE Middleware] Centralized Code Generation Function | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | High | Done |  | 22/Feb/26 10:19 AM | 17/Mar/26 4:32 PM |  | 3 | No-QA | point-engine-proxy |  |  | มาจาก Sprint 19 | Ready to Staging |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | RDTHANA-460 | 44483 | CSV Generate |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 20/Feb/26 3:45 PM | 20/Feb/26 3:45 PM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][Thana] Sprint 19 | [Dev][RD][Thana] Sprint 20
Sub-task | RDTHANA-459 | 44481 | CSV Template |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Progress |  | 20/Feb/26 3:45 PM | 05/Mar/26 10:24 AM | [6 empty] | มาจาก Sprint 19 | In Progress |  | [Dev][RD][Thana] Sprint 19 | [Dev][RD][Thana] Sprint 20
Sub-task | RDTHANA-458 | 44479 | CSV Generate |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 20/Feb/26 3:45 PM | 20/Feb/26 3:45 PM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][Thana] Sprint 19 | [Dev][RD][Thana] Sprint 20
Sub-task | RDTHANA-457 | 44477 | CSV Template |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Review |  | 20/Feb/26 3:44 PM | 04/Mar/26 1:34 PM | [6 empty] | มาจาก Sprint 19 | In Review |  | [Dev][RD][Thana] Sprint 19 | [Dev][RD][Thana] Sprint 20
Sub-task | RDTHANA-456 | 44475 | CSV Generate |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 20/Feb/26 3:44 PM | 02/Mar/26 4:41 PM | [6 empty] | มาจาก Sprint 19 | Done |  | [Dev][RD][Thana] Sprint 19 | [Dev][RD][Thana] Sprint 20
Sub-task | RDTHANA-455 | 44473 | CSV Template |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 20/Feb/26 3:44 PM | 02/Mar/26 1:28 PM | [6 empty] | มาจาก Sprint 19 | Done |  | [Dev][RD][Thana] Sprint 19 | [Dev][RD][Thana] Sprint 20
Sub-task | RDTHANA-454 | 44471 | CSV Generate | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 20/Feb/26 3:44 PM | 06/Mar/26 10:03 AM | [6 empty] | มาจาก Sprint 19 | In Review |  | [Dev][RD][Thana] Sprint 19 | [Dev][RD][Thana] Sprint 20
Sub-task | RDTHANA-453 | 44469 | CSV Template | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 20/Feb/26 3:44 PM | 06/Mar/26 10:03 AM | [6 empty] | มาจาก Sprint 19 | In Review |  | [Dev][RD][Thana] Sprint 19 | [Dev][RD][Thana] Sprint 20
Sub-task | RDTHANA-452 | 44467 | CSV Generate | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 20/Feb/26 3:43 PM | 02/Mar/26 4:27 PM | [6 empty] | มาจาก Sprint 19 | Done |  | [Dev][RD][Thana] Sprint 19 | [Dev][RD][Thana] Sprint 20
Sub-task | RDTHANA-451 | 44465 | CSV Template | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 20/Feb/26 3:43 PM | 02/Mar/26 1:28 PM | [6 empty] | มาจาก Sprint 19 | Done |  | [Dev][RD][Thana] Sprint 19 | [Dev][RD][Thana] Sprint 20
Story | RDTHANA-450 | 44430 | [DEV][RD][TDM] Create cronjob for polling master data - customer | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 20/Feb/26 2:38 PM | 18/Mar/26 4:35 PM | 06/Mar/26 12:00 AM | 5 |  |  |  | 28800 | มาจาก Sprint 19 | In Progress | 57600 -> 28800 | [Dev][RD][Thana] Sprint 19 | [Dev][RD][Thana] Sprint 20
Story | DPE-215 | 44364 | [Dev][RD][PE Middleware] Update Merchant by id | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 20/Feb/26 11:16 AM | 18/Mar/26 1:17 PM |  | 3 | point-engine-proxy |  |  |  | มาจาก Sprint 19 | Ready to Staging |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Bug | DEVRDSUP-462 | 44263 | [SUP-520][Rabbit connect] Unable to login to RR app with Facebook account or Apple ID | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Resolved |  | 19/Feb/26 6:42 PM | 20/Mar/26 11:00 AM | 13/Mar/26 12:00 AM | 2 | prod-issue | RabbitConnect | sso |  | มาจาก Sprint 19 | UNDER VALIDATION |  | [Dev][All Project] Sprint 19 | [Dev][All Project] Sprint 20
Sub-task | DPE-214 | 44196 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 19/Feb/26 3:40 PM | 13/Mar/26 9:32 AM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-213 | 44194 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 19/Feb/26 3:40 PM | 12/Mar/26 11:46 AM | [6 empty] | มาจาก Sprint 19 | In Review |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-212 | 44192 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 19/Feb/26 3:40 PM | 13/Mar/26 9:32 AM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-211 | 44190 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 19/Feb/26 3:40 PM | 12/Mar/26 11:46 AM | [6 empty] | มาจาก Sprint 19 | In Review |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-210 | 44188 | [Dev][RD][PE Middleware] Point expiry | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 19/Feb/26 3:22 PM | 18/Mar/26 1:40 PM |  | 3 | point-engine-proxy |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 28800 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DRST-26 | 44053 | [DEV][RD][API][SA] Find and replace VIMI API by RD API | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 19/Feb/26 9:21 AM | 20/Mar/26 9:59 AM |  | 8 |  |  |  |  | มาจาก Sprint 19 | In Progress |  | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20
Story | DRST-25 | 44052 | [DEV][RD][BFF] Create new endpoint to get earn by slug | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 19/Feb/26 9:16 AM | 19/Mar/26 4:09 PM |  | 3 |  |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 28800 | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20
Story | DRST-24 | 44051 | [DEV][RD][BFF] Create new endpoint to get earn by id | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 19/Feb/26 9:15 AM | 19/Mar/26 4:09 PM |  | 2 |  |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 14400 | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20
Story | DPE-207 | 44011 | [Dev][RD][SSO-User] Reward Add Card | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 18/Feb/26 3:42 PM | 12/Mar/26 3:21 PM |  | 1 |  |  |  |  | มาจาก Sprint 19 | Ready to Staging |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-206 | 44010 | [Dev][RD][SSO-User] Backoffice Sync Cards | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 18/Feb/26 3:42 PM | 16/Mar/26 3:40 PM |  | 1 |  |  |  |  | มาจาก Sprint 19 | Ready to Staging |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DRST-23 | 43648 | [DEV][RD][Rabbit CMS API] Create new endpoint for get earn by slug | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 15/Feb/26 10:50 PM | 10/Mar/26 4:05 PM |  | 2 |  |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 14400 | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20
Story | DRST-22 | 43647 | [DEV][RD][Rabbit CMS API] Create new endpoint for get earn by id | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 15/Feb/26 10:46 PM | 10/Mar/26 4:05 PM |  | 2 |  |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 14400 | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20
Story | DPE-195 | 43604 | [Dev][RD][DevOps][PE-MIGRATION] Provision dedicated UAT-CT environment for Point Engine migration services | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 15/Feb/26 1:53 PM | 18/Mar/26 8:55 AM |  | 3 | No-QA |  |  |  | มาจาก Sprint 19 | In Progress |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-192 | 43566 | [Dev][RD][DevOps][RD][PE-MIGRATION] Provision uat-ct domain for CleverTap integration testing | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 13/Feb/26 9:03 PM | 18/Mar/26 8:55 AM |  | 3 |  |  |  |  | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-190 | 43427 | [Dev][RD][SSO-User] Offline register | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 13/Feb/26 1:03 PM | 20/Mar/26 11:07 AM |  | 2 |  |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Bug | DEVRDSUP-453 | 43426 | [SUP-525]SUB : Refunded txn report Search result shows “No Data Found” even though data exists | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Thanakrit Chanthaworn | 712020:3fc982cb-c268-4f1d-9265-d3dd8fb08304 | Medium | Pass : Waiting for deployment |  | 13/Feb/26 1:02 PM | 19/Mar/26 4:41 PM | 03/Mar/26 12:00 AM | 3 |  |  |  |  | มาจาก Sprint 19 | Fixing |  | [Dev][All Project] Sprint 19 | [Dev][All Project] Sprint 20
Sub-task | DPE-189 | 43275 | [QA] Test execution | THUNDER(QA): PAWICH | 712020:83ff944e-9677-453f-b053-40e92520d905 | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 12/Feb/26 2:47 PM | 13/Mar/26 9:33 AM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-188 | 43273 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 12/Feb/26 2:46 PM | 12/Mar/26 11:46 AM | [6 empty] | มาจาก Sprint 19 | In Review |  | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-187 | 43123 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 12/Feb/26 10:49 AM | 23/Feb/26 4:10 PM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-186 | 43122 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 12/Feb/26 10:49 AM | 12/Mar/26 11:46 AM | [6 empty] | มาจาก Sprint 19 | In Review |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-185 | 43121 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 12/Feb/26 10:49 AM | 23/Feb/26 4:10 PM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-184 | 43120 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 12/Feb/26 10:49 AM | 12/Mar/26 11:46 AM | [6 empty] | มาจาก Sprint 19 | In Review |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-183 | 43119 | [QA] Test execution | THUNDER(QA): PAWICH | 712020:83ff944e-9677-453f-b053-40e92520d905 | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 12/Feb/26 10:48 AM | 13/Mar/26 9:33 AM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-182 | 43118 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 12/Feb/26 10:48 AM | 12/Mar/26 11:46 AM | [6 empty] | มาจาก Sprint 19 | In Review |  | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-181 | 43117 | [QA] Test execution | THUNDER(QA): PAWICH | 712020:83ff944e-9677-453f-b053-40e92520d905 | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 12/Feb/26 10:47 AM | 16/Mar/26 12:43 PM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-180 | 43116 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 12/Feb/26 10:47 AM | 12/Mar/26 11:46 AM | [6 empty] | มาจาก Sprint 19 | In Progress |  | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-179 | 43115 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 12/Feb/26 10:46 AM | 23/Feb/26 4:10 PM | [6 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Sub-task | DPE-178 | 43114 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 12/Feb/26 10:46 AM | 12/Mar/26 11:47 AM | [6 empty] | มาจาก Sprint 19 | In Review |  | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DRST-21 | 43078 | [DEV][RD][BOF] Enhance Subscription Txn V2 support filter from query string | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 11/Feb/26 7:10 PM | 11/Mar/26 10:00 AM |  | 2 |  |  |  | 14400 |  |  |  | [Dev RD][VIMI Termi] Sprint 20
Story | RDTHANA-447 | 43072 | [DEV][RD][TDM] Sync Order Data from Shopify Stores Refund | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 11/Feb/26 6:36 PM | 20/Mar/26 9:17 AM | 18/Mar/26 12:00 AM | 5 |  |  |  | 57600 |  |  |  | [Dev][RD][Thana] Sprint 20
Story | RDTHANA-446 | 43071 | [DEV][RD][TDM] Sync Order Data from Shopify Stores to Data Mart #2 | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 11/Feb/26 6:36 PM | 20/Mar/26 11:19 AM | 20/Mar/26 12:00 AM | 5 |  |  |  | 57600 |  |  |  | [Dev][RD][Thana] Sprint 20
Story | RDTHANA-445 | 43070 | [DEV][RD][TDM] Sync Order Data from Shopify Stores to Data Mart table | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 11/Feb/26 6:35 PM | 19/Mar/26 11:16 AM | 18/Mar/26 12:00 AM | 5 |  |  |  | 57600 |  |  |  | [Dev][RD][Thana] Sprint 20
Story | RDTHANA-443 | 43068 | [DEV][RD][TDM] Create Webhook API Endpoint refunds/create | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 11/Feb/26 6:35 PM | 18/Mar/26 9:24 AM | 18/Mar/26 12:00 AM | 5 | [7 empty] | [Dev][RD][Thana] Sprint 20
Story | RDTHANA-442 | 43067 | [DEV][RD][TDM] Create Webhook API Endpoint orders | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 11/Feb/26 6:34 PM | 17/Mar/26 11:50 AM | 16/Mar/26 12:00 AM | 5 |  |  |  | 57600 |  |  |  | [Dev][RD][Thana] Sprint 20
Story | RDTHANA-441 | 43066 | [DEV][RD][TDM] Create migration | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 11/Feb/26 6:33 PM | 13/Mar/26 3:09 PM | 12/Mar/26 12:00 AM | 5 |  |  |  | 57600 |  |  |  | [Dev][RD][Thana] Sprint 20
Story | RDTHANA-440 | 43065 | [DEV][RD][TDM] Setup Dynamo config support Application ENV | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 11/Feb/26 6:33 PM | 18/Mar/26 4:23 PM | 10/Mar/26 12:00 AM | 2 |  |  |  | 10800 |  |  |  | [Dev][RD][Thana] Sprint 20
Story | RDTHANA-439 | 43064 | [DEV][RD][TDM] Add Hook App database connection | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 11/Feb/26 6:33 PM | 10/Mar/26 3:30 PM | 10/Mar/26 12:00 AM | 2 |  |  |  | 10800 |  |  |  | [Dev][RD][Thana] Sprint 20
Story | RDTHANA-437 | 43029 | [DEV][RD][TDM] Create cronjob for polling master data - category | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 11/Feb/26 4:31 PM | 18/Mar/26 4:29 PM | 05/Mar/26 12:00 AM | 5 | No-QA | Thana-datamart |  | 0 | มาจาก Sprint 19 | In Review | 57600 | [Dev][RD][Thana] Sprint 19 | [Dev][RD][Thana] Sprint 20
Story | RDTHANA-436 | 43028 | [DEV][RD][TDM] Create cronjob for polling master data - shop | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 11/Feb/26 4:31 PM | 18/Mar/26 4:28 PM | 02/Mar/26 12:00 AM | 5 | No-QA | Thana-datamart |  | 0 | มาจาก Sprint 19 | Ready to Staging | 57600 | [Dev][RD][Thana] Sprint 19 | [Dev][RD][Thana] Sprint 20
Story | RDTHANA-435 | 43027 | [DEV][RD][TDM] Create cronjob for polling master data - employee | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 11/Feb/26 4:31 PM | 18/Mar/26 4:29 PM | 05/Mar/26 12:00 AM | 5 | No-QA | Thana-datamart |  | 0 | มาจาก Sprint 19 | In Review | 43200 | [Dev][RD][Thana] Sprint 19 | [Dev][RD][Thana] Sprint 20
Story | RDTHANA-434 | 43026 | [DEV][RD][TDM] Create cronjob for polling master data - item | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 11/Feb/26 4:12 PM | 18/Mar/26 4:30 PM | 04/Mar/26 12:00 AM | 8 |  |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 72000 | [Dev][RD][Thana] Sprint 19 | [Dev][RD][Thana] Sprint 20
Story | RDTHANA-433 | 43025 | [DEV][RD][TDM] Create consumer for "lightspeed-txn" | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 11/Feb/26 4:10 PM | 18/Mar/26 4:30 PM | 27/Feb/26 12:00 AM | 5 |  |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 57600 | [Dev][RD][Thana] Sprint 19 | [Dev][RD][Thana] Sprint 20
Story | RDTHANA-432 | 42992 | [DEV][RD][TDM] Create cronjob for polling sale transaction | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 11/Feb/26 3:09 PM | 18/Mar/26 4:31 PM | 19/Feb/26 12:00 AM | 5 |  |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 57600 | [Dev][RD][Thana] Sprint 19 | [Dev][RD][Thana] Sprint 18 | [Dev][RD][Thana] Sprint 20
Epic | RDTHANA-431 | 42991 | Lighspeed Polling |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 11/Feb/26 3:07 PM | 16/Mar/26 11:44 AM | 06/Mar/26 12:00 AM | [5 empty] | มาจาก Sprint 19 | To Do |  | [Dev][RD][Thana] Sprint 19 | [Dev][RD][Thana] Sprint 18 | [Dev][RD][Thana] Sprint 20
Story | RDTHANA-430 | 42990 | [DEV][RD][TDM] Create LighspeedService for getToken | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 11/Feb/26 2:57 PM | 18/Mar/26 4:33 PM | 13/Feb/26 12:00 AM | 5 |  |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 57600 | [Dev][RD][Thana] Sprint 19 | [Dev][RD][Thana] Sprint 18 | [Dev][RD][Thana] Sprint 20
Story | DRST-17 | 42821 | [DEV][RD][BOF] Create command to migrate data from VIMI database to Rabbit CMS database | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 11/Feb/26 10:17 AM | 10/Mar/26 2:55 PM |  | 8 |  |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 86400 | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20
Story | DPE-174 | 42542 | [Dev][RD] SSO new enviroment for non-prod | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Done |  | 10/Feb/26 10:29 AM | 10/Mar/26 9:39 AM |  | 3 | No-QA |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DRST-15 | 42268 | [DEV][RD][BFF] Create endpoint for get earn content | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 08/Feb/26 9:54 PM | 19/Mar/26 4:09 PM |  | 3 |  |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 28800 | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20
Story | DRST-14 | 42267 | [DEV][RD][Rabbit CMS API] Create endpoint for get earn content | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 08/Feb/26 9:54 PM | 10/Mar/26 4:05 PM |  | 5 |  |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 57600 | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20
Story | DPE-171 | 42260 | [Dev][RD][PE Middleware] Update offer | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 08/Feb/26 7:59 PM | 18/Mar/26 1:42 PM | 02/Mar/26 12:00 AM | 3 | point-engine-proxy |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 28800 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-170 | 42259 | [Dev][RD][PE Middleware] Get offer list | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 08/Feb/26 7:59 PM | 18/Mar/26 1:43 PM | 04/Mar/26 12:00 AM | 3 | point-engine-proxy |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 28800 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-169 | 42258 | [Dev][RD][PE Middleware] Create offer | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 08/Feb/26 7:58 PM | 18/Mar/26 1:42 PM | 26/Feb/26 12:00 AM | 3 | point-engine-proxy |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 28800 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-158 | 42215 | [Dev][RD][BFF] Get point balance | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 07/Feb/26 3:24 PM | 20/Mar/26 11:06 AM | 16/Mar/26 12:00 AM | 5 |  |  |  | 57600 |  |  |  | [Dev][RD][New PE] Sprint 20
Story | DPE-156 | 42181 | [Dev][RD][PE Middleware] Get Merchant list | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 07/Feb/26 11:03 AM | 18/Mar/26 3:31 PM |  | 3 | point-engine-proxy |  |  |  | มาจาก Sprint 19 | Ready to Staging |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-155 | 42180 | [Dev][RD][PE Middleware] Create Merchant | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 07/Feb/26 11:03 AM | 18/Mar/26 1:11 PM |  | 3 | point-engine-proxy |  |  |  | มาจาก Sprint 19 | Ready to Staging |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-154 | 42179 | [Dev][RD][SA][Sprint20] Analysis & Task Breakdown for PE Migration Execution | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 07/Feb/26 9:28 AM | 09/Mar/26 8:12 PM |  | 13 | No-QA |  |  |  | มาจาก Sprint 19 | In Progress |  | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-151 | 42176 | [Dev][RD][PE Middleware] Point history | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 07/Feb/26 8:18 AM | 18/Mar/26 1:40 PM |  | 3 | point-engine-proxy |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 28800 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-150 | 42175 | [Dev][RD][PE Proxy Scheduler] Initial Project | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | In Progress |  | 07/Feb/26 8:18 AM | 19/Mar/26 2:02 PM |  | 5 | [7 empty] | [Dev][RD][New PE] Sprint 20
Story | DPE-149 | 42174 | [Dev][RD][PE Middleware] Credit point | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready To Test |  | 07/Feb/26 8:18 AM | 18/Mar/26 1:40 PM |  | 2 | point-engine-proxy |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 14400 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-148 | 42173 | [Dev][RD][PE Middleware] Debit point | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready To Test |  | 07/Feb/26 8:18 AM | 18/Mar/26 1:40 PM |  | 3 | point-engine-proxy |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 43200 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-147 | 42134 | [Dev][RD][SSO-User] WEB verify phone | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 6:37 PM | 12/Mar/26 3:47 PM |  | 1 | sso-user |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 3600 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-146 | 42133 | [Dev][RD][SSO-User] WEB update avatar | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 6:37 PM | 12/Mar/26 3:47 PM |  | 1 | sso-user |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-145 | 42132 | [Dev][RD][SSO-User] WEB verify user | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 6:37 PM | 12/Mar/26 3:47 PM |  | 2 | sso-user |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 10800 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-144 | 42131 | [Dev][RD][SSO-User] WEB remove card by card_id | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 6:37 PM | 19/Mar/26 1:40 PM |  | 1 | sso-user |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-143 | 42130 | [Dev][RD][SSO-User] WEB move card | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 6:36 PM | 19/Mar/26 1:41 PM |  | 1 | sso-user |  |  |  | มาจาก Sprint 19 | Ready to Staging |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-142 | 42129 | [Dev][RD][SSO-User] WEB add card | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 6:36 PM | 19/Mar/26 1:41 PM |  | 1 | sso-user |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-141 | 42128 | [Dev][RD][SSO-User] WEB update profile by ID | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 6:36 PM | 19/Mar/26 1:42 PM | 12/Feb/26 12:00 AM | 2 | sso-user |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 14400 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-123 | 42098 | [Dev][RD][REMQ] Async coupon push | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Feb/26 1:44 PM | 17/Mar/26 10:11 AM | 12/Mar/26 12:00 AM | 5 |  |  |  | 57600 |  |  |  | [Dev][RD][New PE] Sprint 20
Bug | DEVRDSUP-421 | 42045 | [SUP-479]Link Search and link # in the pop up is not redirect | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Pass : Waiting for deployment |  | 06/Feb/26 11:33 AM | 19/Mar/26 4:09 PM | 23/Feb/26 12:00 AM | 2 | deeplink |  |  |  | มาจาก Sprint 19 | Resolved |  | [Dev][All Project] Sprint 18 | [Dev][All Project] Sprint 19 | [Dev][All Project] Sprint 20
Story | DPE-101 | 41974 | [Dev][RD][BOF] Create/Update Package | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 05/Feb/26 4:49 PM | 20/Mar/26 9:44 AM |  | 3 | [7 empty] | [Dev][RD][New PE] Sprint 20
Story | DPE-100 | 41973 | [Dev][RD][BOF] Update product | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 05/Feb/26 4:49 PM | 20/Mar/26 9:45 AM |  | 3 | [7 empty] | [Dev][RD][New PE] Sprint 20
Story | DPE-99 | 41972 | [Dev][RD][BOF] Create a new product | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 05/Feb/26 4:49 PM | 19/Mar/26 4:22 PM |  | 3 | [7 empty] | [Dev][RD][New PE] Sprint 20
Story | DPE-92 | 41965 | [Dev][RD][Sky Web] Switch Account | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 05/Feb/26 4:46 PM | 19/Mar/26 3:30 PM | 19/Mar/26 12:00 AM | 5 | sky-web |  |  | 57600 |  |  |  | [Dev][RD][New PE] Sprint 20
Story | DPE-91 | 41964 | [Dev][RD][Sky] Switch account API | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 05/Feb/26 4:46 PM | 17/Mar/26 2:23 PM |  | 3 | sky-api |  |  | 28800 |  |  |  | [Dev][RD][New PE] Sprint 20
Story | DPE-90 | 41963 | [Dev][RD][Sky][Member] Reactivate | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 05/Feb/26 4:46 PM | 13/Mar/26 11:10 AM | 12/Mar/26 12:00 AM | 2 | sky-api | [6 empty] | [Dev][RD][New PE] Sprint 20
Story | DPE-89 | 41962 | [Dev][RD][Sky][Member] Register Member | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 05/Feb/26 4:46 PM | 13/Mar/26 5:58 PM | 13/Mar/26 12:00 AM | 3 | sky-api |  |  | 28800 |  |  |  | [Dev][RD][New PE] Sprint 20
Story | RDNDA-27 | 41770 | [DEV][RD][TDM] Create script for check missing ENV | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 05/Feb/26 9:37 AM | 20/Mar/26 10:57 AM |  | 2 | No-QA | Thana-datamart |  | 0 | มาจาก Sprint 19 | Ready to Staging | 14400 | [Dev][RD][NewDamart] Sprint 17 | [Dev][RD][NewDamart] Sprint 18 | [Dev][RD][NewDamart] Sprint 19 | [Dev][RD][NewDamart] Sprint 20
Story | DPE-81 | 41537 | [Dev][RD][PL][Member] Check RR member by Trader ID | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 04/Feb/26 10:26 AM | 17/Mar/26 3:27 PM |  | 3 | [7 empty] | [Dev][RD][New PE] Sprint 20
Story | DPE-80 | 41535 | [Dev][RD][PL][Member] Check RR member by phone | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 04/Feb/26 10:24 AM | 13/Mar/26 11:43 PM | 16/Mar/26 12:00 AM | 3 | partner-loyalty |  |  | 28800 |  |  |  | [Dev][RD][New PE] Sprint 20
Story | DPE-79 | 41533 | [Dev][RD][PL][Point] Get point | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 04/Feb/26 10:24 AM | 17/Mar/26 9:51 AM |  | 3 | [7 empty] | [Dev][RD][New PE] Sprint 20
Story | DPE-78 | 41531 | [Dev][RD][PL][Member] Check Member By ID | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 04/Feb/26 10:24 AM | 17/Mar/26 10:53 AM | 12/Mar/26 12:00 AM | 3 | partner-loyalty |  |  | 28800 |  |  |  | [Dev][RD][New PE] Sprint 20
Story | DPE-74 | 41523 | [Dev][RD][SSO-User] Remove SSO-Thor API Integration | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Ready To Test |  | 04/Feb/26 10:13 AM | 12/Mar/26 3:21 PM |  | 5 | No-QA | sso-user |  | 0 | มาจาก Sprint 19 | Ready to Staging | 57600 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-73 | 41521 | [Dev][RD][SSO-User] CRM remove card | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 04/Feb/26 10:13 AM | 13/Mar/26 9:32 AM |  | 2 | sso-user |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 14400 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-72 | 41519 | [Dev][RD][SSO-User] CRM add card | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 04/Feb/26 10:13 AM | 13/Mar/26 9:32 AM |  | 2 | sso-user |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 14400 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-71 | 41517 | [Dev][RD][SSO-User] BSS Verify email | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 04/Feb/26 10:10 AM | 13/Mar/26 9:32 AM | 10/Feb/26 12:00 AM | 1 | sso-user |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-70 | 41515 | [Dev][RD][SSO-User] BSS Verify phone | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 04/Feb/26 9:49 AM | 13/Mar/26 9:31 AM |  | 1 | sso-user |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-69 | 41513 | [Dev][RD][SSO-User] BSS sync member to RR | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 04/Feb/26 9:49 AM | 16/Mar/26 3:11 PM |  | 2 | sso-user |  |  |  | มาจาก Sprint 19 | Ready to Staging |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-68 | 41511 | [Dev][RD][SSO-User] Rewards add card | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 04/Feb/26 9:49 AM | 12/Mar/26 3:18 PM | 10/Feb/26 12:00 AM | 1 | sso-user |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-67 | 41508 | [Dev][RD][PL][Member] Opt-in by SSO | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 04/Feb/26 9:43 AM | 20/Mar/26 11:06 AM | 12/Mar/26 12:00 AM | 3 | partner-loyalty |  |  | 28800 |  |  |  | [Dev][RD][New PE] Sprint 20
Story | DPE-66 | 41506 | [Dev][RD][PL][Member] Opt-in | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 04/Feb/26 9:43 AM | 20/Mar/26 11:06 AM | 12/Mar/26 12:00 AM | 5 | partner-loyalty |  |  | 57600 |  |  |  | [Dev][RD][New PE] Sprint 20
Story | DPE-65 | 41499 | [Dev][RD][PL][Member] Sync RR member | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 04/Feb/26 9:18 AM | 20/Mar/26 11:06 AM | 10/Mar/26 12:00 AM | 3 | partner-loyalty |  |  | 28800 |  |  |  | [Dev][RD][New PE] Sprint 20
Story | DPE-64 | 41497 | [Dev][RD][PL][Member] Member binding | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 04/Feb/26 9:16 AM | 18/Mar/26 2:56 PM | 13/Mar/26 12:00 AM | 5 | partner-loyalty | [6 empty] | [Dev][RD][New PE] Sprint 20
Story | DPE-62 | 41461 | [Dev][RD][SSO-User] Update a registration source | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 03/Feb/26 8:12 PM | 13/Mar/26 9:33 AM |  | 1 | sso-user |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 7200 | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-61 | 41459 | [Dev][RD][SSO-User] Backoffice Create a registration source | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 03/Feb/26 7:43 PM | 13/Mar/26 9:33 AM |  | 1 | sso-user |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 7200 | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-60 | 41457 | [Dev][RD][SSO-User] Backoffice update user | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 03/Feb/26 7:43 PM | 16/Mar/26 12:44 PM | 06/Feb/26 12:00 AM | 2 | sso-user |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 14400 | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-59 | 41455 | [Dev][RD][SSO-User] Backoffice Remove card | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 03/Feb/26 7:43 PM | 16/Mar/26 3:37 PM |  | 2 | sso-user |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 14400 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-58 | 41453 | [Dev][RD][SSO-User] Backoffice Add card | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 03/Feb/26 7:43 PM | 13/Mar/26 10:01 AM |  | 2 | sso-user |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 14400 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-56 | 41449 | [Dev][RD][SSO-User] Update email | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 03/Feb/26 7:42 PM | 13/Mar/26 9:32 AM |  | 2 | sso-user |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 14400 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-55 | 41447 | [Dev][RD][SSO-User] Verify phone | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 03/Feb/26 7:42 PM | 13/Mar/26 11:18 AM |  | 2 | sso-user |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 3600 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-54 | 41445 | [Dev][RD][SSO-User] Verify email | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 03/Feb/26 7:41 PM | 13/Mar/26 11:50 AM |  | 2 | sso-user |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 3600 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-51 | 41439 | [Dev][RD][PE Middleware] Get balance | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready To Test |  | 03/Feb/26 7:41 PM | 18/Mar/26 1:40 PM |  | 2 | point-engine-proxy |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 28800 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-50 | 41437 | [Dev][RD][SSO-User] Activate user by phone | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 03/Feb/26 7:41 PM | 12/Mar/26 3:46 PM |  | 2 | sso-user |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-49 | 41435 | [Dev][RD][SSO-User] Rewards Verify phone | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 03/Feb/26 7:41 PM | 12/Mar/26 3:46 PM |  | 2 | sso-user |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-48 | 41433 | [Dev][RD][SSO-User] Update rewards user | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 03/Feb/26 7:40 PM | 12/Mar/26 3:17 PM | 05/Feb/26 12:00 AM | 3 | sso-user |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 28800 | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-47 | 41431 | [Dev][RD][SSO-User] Create rewards user | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 03/Feb/26 7:40 PM | 19/Mar/26 1:42 PM | 12/Feb/26 12:00 AM | 3 | sso-user |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 28800 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | DPE-46 | 41429 | [Dev][RD][SSO-User] Create user profile | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 03/Feb/26 7:40 PM | 19/Mar/26 1:42 PM | 11/Feb/26 12:00 AM | 3 | sso-user |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 28800 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19 | [Dev][RD][New PE] Sprint 20
Story | RDNDA-22 | 40327 | [DEV][RD][TDM] Enhance Kinesis stream name to dynamics config | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 25/Jan/26 10:47 PM | 20/Mar/26 10:55 AM | 04/Feb/26 12:00 AM | 2 | No-QA | Thana-datamart |  | 0 | มาจาก Sprint 19 | Ready to Staging | 10800 | [Dev][RD][NewDamart] Sprint 17 | [Dev][RD][NewDamart] Sprint 18 | [Dev][RD][NewDamart] Sprint 19 | [Dev][RD][NewDamart] Sprint 20
Story | RDNDA-21 | 40326 | [DEV][RD][TDM] Enhance generic API with new data and validate with omit | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 25/Jan/26 10:31 PM | 20/Mar/26 10:55 AM | 04/Feb/26 12:00 AM | 2 |  |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 14400 | [Dev][RD][NewDamart] Sprint 17 | [Dev][RD][NewDamart] Sprint 18 | [Dev][RD][NewDamart] Sprint 19 | [Dev][RD][NewDamart] Sprint 20
Story | RDNDA-20 | 40132 | [DEV][RD][TDM] Add idempotency key for POS transaction API | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 22/Jan/26 5:10 PM | 20/Mar/26 11:30 AM |  | 3 |  |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 28800 | [Dev][RD][NewDamart] Sprint 19 | [Dev][RD][NewDamart] Sprint 20
Story | RDNDA-19 | 40131 | [DEV][RD][TDM] Create migration for access control | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 22/Jan/26 5:07 PM | 20/Mar/26 10:56 AM |  | 1 | No-QA | Thana-datamart |  | 0 | มาจาก Sprint 19 | Ready to Staging | 14400 | [Dev][RD][NewDamart] Sprint 17 | [Dev][RD][NewDamart] Sprint 18 | [Dev][RD][NewDamart] Sprint 19 | [Dev][RD][NewDamart] Sprint 20
Story | RDNDA-18 | 40130 | [DEV][RD][TDM] Create access control callback endpoint | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 22/Jan/26 5:03 PM | 20/Mar/26 10:57 AM |  | 3 |  |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 28800 | [Dev][RD][NewDamart] Sprint 17 | [Dev][RD][NewDamart] Sprint 18 | [Dev][RD][NewDamart] Sprint 19 | [Dev][RD][NewDamart] Sprint 20
Story | RDNDA-14 | 38512 | [DEV][RD][TDM] Create migration | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 09/Jan/26 1:48 PM | 20/Mar/26 10:51 AM |  | 2 | No-QA | ThanaDataMart |  | 0 | มาจาก Sprint 19 | Ready to Staging | 14400 | [Dev][RD][NewDamart] Sprint 16 | [Dev][RD][NewDamart] Sprint 17 | [Dev][RD][NewDamart] Sprint 18 | [Dev][RD][NewDamart] Sprint 19 | [Dev][RD][NewDamart] Sprint 20
Story | DPWP-18 | 38437 | [Dev][RD][PWP] Initial Project Repository for Pay with Point Scheduler appp | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 08/Jan/26 6:48 PM | 12/Mar/26 9:54 AM | 23/Jan/26 12:00 AM | 5 | No-QA |  |  | 0 | มาจาก Sprint 19 | Ready To Test | 57600 | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18 | [Dev][RD][PWP] Sprint 19 | [Dev][RD][PWP] Sprint 20
Story | RDNDA-12 | 38435 | [DEV][RD][TDM] Integrate Discord for error log | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 08/Jan/26 5:23 PM | 20/Mar/26 10:54 AM |  |  | No-QA | Thana-datamart |  |  | มาจาก Sprint 19 | Ready to Staging |  | [Dev][RD][NewDamart] Sprint 16 | [Dev][RD][NewDamart] Sprint 17 | [Dev][RD][NewDamart] Sprint 18 | [Dev][RD][NewDamart] Sprint 19 | [Dev][RD][NewDamart] Sprint 20
Story | RDNDA-11 | 38434 | [DEV][RD][TDM] Create producer function for push kinesis data | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 08/Jan/26 5:22 PM | 20/Mar/26 10:52 AM |  | 3 |  |  |  |  | มาจาก Sprint 19 | Ready to Staging |  | [Dev][RD][NewDamart] Sprint 16 | [Dev][RD][NewDamart] Sprint 17 | [Dev][RD][NewDamart] Sprint 18 | [Dev][RD][NewDamart] Sprint 19 | [Dev][RD][NewDamart] Sprint 20
Story | RDNDA-9 | 38247 | [DEV][RD][TDM] Create client middleware | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 07/Jan/26 5:19 PM | 20/Mar/26 10:52 AM |  | 3 | No-QA | Thana-datamart |  |  | มาจาก Sprint 19 | Ready to Staging |  | [Dev][RD][NewDamart] Sprint 16 | [Dev][RD][NewDamart] Sprint 17 | [Dev][RD][NewDamart] Sprint 18 | [Dev][RD][NewDamart] Sprint 19 | [Dev][RD][NewDamart] Sprint 20
Story | RDNDA-8 | 38246 | [DEV][RD][TDM] Create Push to Kinesis Consumer | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 07/Jan/26 5:19 PM | 20/Mar/26 10:54 AM | 21/Jan/26 12:00 AM | 3 | No-QA | Thana-datamart |  | 0 | มาจาก Sprint 19 | Ready to Staging | 28800 | [Dev][RD][NewDamart] Sprint 16 | [Dev][RD][NewDamart] Sprint 17 | [Dev][RD][NewDamart] Sprint 18 | [Dev][RD][NewDamart] Sprint 19 | [Dev][RD][NewDamart] Sprint 20
Story | RDNDA-6 | 38244 | [DEV][RD][TDM] Create generic transactions endpoint | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 07/Jan/26 5:17 PM | 20/Mar/26 10:52 AM |  | 5 | Thana-datamart |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 86400 | [Dev][RD][NewDamart] Sprint 16 | [Dev][RD][NewDamart] Sprint 17 | [Dev][RD][NewDamart] Sprint 18 | [Dev][RD][NewDamart] Sprint 19 | [Dev][RD][NewDamart] Sprint 20
Story | RDNDA-5 | 38243 | [DEV][RD][TDM] Initial project | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 07/Jan/26 5:16 PM | 20/Mar/26 10:51 AM |  | 5 | No-QA | ThanaDataMart |  |  | มาจาก Sprint 19 | Ready to Staging |  | [Dev][RD][NewDamart] Sprint 16 | [Dev][RD][NewDamart] Sprint 17 | [Dev][RD][NewDamart] Sprint 18 | [Dev][RD][NewDamart] Sprint 19 | [Dev][RD][NewDamart] Sprint 20
Story | DRST-6 | 38163 | [Dev][RD][Terminate VIMI][VoucherValidator] Refactor APIs to remove dependency on MVP Phase 1 source | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready to Staging |  | 07/Jan/26 11:12 AM | 10/Mar/26 10:02 AM | 10/Feb/26 12:00 AM | 3 |  |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 28800 | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20
Story | DRST-5 | 38162 | [Dev][RD][Terminate VIMI][MerchantAPI] Refactor APIs to remove dependency on MVP Phase 1 source | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready to Staging |  | 07/Jan/26 11:12 AM | 13/Mar/26 10:14 AM | 11/Feb/26 12:00 AM | 3 |  |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 28800 | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20
Story | DRST-7 | 36975 | [Dev][RD][Terminate VIMI] Refactor TXN Report API and Report Summary API to remove dependency on MVP Phase 1 report source | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready to Staging |  | 23/Dec/25 12:23 PM | 10/Mar/26 10:02 AM | 30/Dec/25 12:00 AM | 3 |  |  |  | 0 | มาจาก Sprint 19 | Ready to Staging | 28800 | [Dev][All Project] Sprint 15 | [Dev][All Project] Sprint 16 | [Dev RD][VIMI Termi] Sprint 17 | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19 | [Dev RD][VIMI Termi] Sprint 20
Epic | DEVRDCT-359 | 36930 | FIX-Identity-Error |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 23/Dec/25 9:38 AM | 19/Jan/26 2:17 PM | [9 empty] | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15 | [Dev][RD][CT] Sprint 16
Bug | DEVRDCT-358 | 36929 | [DEV][RD][HRS] Delay Auto CLUB_BINDING to Prevent Intermittent Identity Error | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Resolved |  | 23/Dec/25 8:59 AM | 19/Jan/26 2:17 PM |  | 2 | [7 empty] | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15 | [Dev][RD][CT] Sprint 16
Story | DEVRDSUP-319 | 36248 | [SUP-382][SUB] Request to make a package TXN with “allocating coupon“ to “fail“ | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 16/Dec/25 5:55 PM | 16/Mar/26 1:54 PM |  | 1 | BURequest | sub |  |  | มาจาก Sprint 19 | To Do |  | [Dev][All Project] Sprint 18 | [Dev][All Project] Sprint 19 | [Dev][All Project] Sprint 20
Test Plan | DEVRDCT-342 | 35712 | [TP] Sprint #13 |  |  | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 11/Dec/25 3:26 PM | 19/Jan/26 2:17 PM | [9 empty] | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15 | [Dev][RD][CT] Sprint 16
Epic | DEVRDCT-326 | 35192 | CT-POINT-ISSUE |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 01/Dec/25 9:58 AM | 19/Jan/26 2:17 PM | [9 empty] | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15 | [Dev][RD][CT] Sprint 16
Epic | DEVRDCT-325 | 35191 | CTxSHOPIFY |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 01/Dec/25 9:55 AM | 19/Jan/26 2:17 PM | [9 empty] | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15 | [Dev][RD][CT] Sprint 16
Epic | DEVRDCT-309 | 34545 | ct-member-tier |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 19/Nov/25 2:49 PM | 19/Jan/26 2:17 PM | [9 empty] | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15 | [Dev][RD][CT] Sprint 16
Epic | DEVRDCT-308 | 34539 | ct-campaign-type |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 19/Nov/25 10:41 AM | 19/Jan/26 2:17 PM |  |  | redemption-api | [6 empty] | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15 | [Dev][RD][CT] Sprint 16

## Summarize Sprint 19
Column 1 | Total Stories Point | Total Manhour | Point Done | Manhour Done | Note
23 Feb - 6 Mar
Dev Resource Available | 21 | 444.5
Meeting Planned |  | 43.5 |  |  | Ref
Additional Meeting |  |  |  |  | Ref
Deployment |  | 1 |  |  | 1 ครั้ง 1. 2 คน
Development Sprint Total | 364 | 214.5 | 19 | 23.5
Ad-hoc Mid Sprint | 0 | 0 | 0 | 0 | 2 tasks
Requirement changes after refinement? | 0 |  | 0 | 0 | 0 tasks
Aek | 8 | 8 | 7 | 8
A | 34 | 29 | 6 | 14
Aom | 35 | 1.5 | 3 | 1.5
Zan | 8 | 0 | 0 | 0
Mai | 61 | 64 | 0 | 0
Mac | 69 | 48 | 3 | 0
Mos | 67 | 48 | 0 | 0
Jack | 0 | 0 | 0 | 0
Nim | 59 | 16 | 0 | 0
Arm | 23 | 0 | 0 | 0
Resource Plan – Sprint 19 23 Feb - 6 Mar
Capacity รวมทั้งทีม 118.5 SP | 118.5
Allocation each project (exclude PE) | 70
Allocation PE | 48.5
New Point Engine | 45 | 3
Vimi Termination | 24 | 1
Thana | 33 | 2
Datamart | 3 | 1
AWS | 3 | 1
Dev Support | 7 | 3
Remaining | 3.5
Name | Availability | Capacity | Total Workload | Allocation PE | PE (SP) | Allocation VIMI (days) | VIMI (SP) | Allocation Thana (days) | Thana (SP) | Allocation Datamart (days) | Datamart (SP) | Allocation AWS (days) | AWS (SP) | Dev Support | Dev Support (SP)
A | 7 | 21 | 20 | 5 | 15 |  | 0 |  | 0 |  | 0 | 1 | 3 | 0 | 2
Mac | 6 | 18 | 18 |  | 0 |  | 0 | 6 | 18 |  | 0 |  | 0 | 0 | 0
Mai | 6 | 18 | 18 |  | 0 |  | 0 | 5 | 15 | 1 | 3 |  |  | 0 | 0
Mos | 7 | 21 | 18 | 5 | 15 | 1 | 3 |  |  |  | 0 |  |  | 0 | 0
Nim | 7 | 21 | 23 |  | 0 | 7 | 21 |  |  |  | 0 |  |  | 0 | 2
Arm | 6.5 | 19.5 | 18 | 5 | 15 |  | 0 |  |  |  | 0 |  |  | 0 | 3
Total |  | 118.5 | 115 | 15 | 45 | 8 | 24 | 11 | 33 | 1 | 3 | 1 | 3 | 0 | 7
| System Architech |  |  |  | Permanent Dev. |  |  | Outsources
Projects (Stories Points) | Aek | Zan | Aom | Jack | A | Art | Mai | Kae | Mac | Nim | Mos | Arm
| 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 28 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 3
| System Architech |  |  |  | Permanent Dev. |  |  | Outsources
Projects (Manhour) | Aek | Zan | Aom | Jack | A | Art | Mai | Kae | Mac | Nim | Mos | Arm
| 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 48 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 7 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 19
Issue Type | Issue key | Issue id | Summary | Assignee | Assignee Id | Reporter | Reporter Id | Priority | Status | Resolution | Created | Updated | Due date | Custom field (Story Points) | Labels | Labels | Labels | Labels | Original estimate | Sprint Movement | Sprint 18 | Note | Sprint | Sprint | Sprint | Sprint | Sprint
Sub-task | DRST-57 | 46476 | [QA] Test Execution UAT | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 05/Mar/26 1:31 PM | 05/Mar/26 1:31 PM | [10 empty] | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19
Sub-task | DRST-56 | 46474 | [QA] Test Execution UAT | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 05/Mar/26 1:31 PM | 05/Mar/26 1:31 PM | [10 empty] | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19
Sub-task | DRST-55 | 46472 | [QA] Test Execution UAT | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 05/Mar/26 1:30 PM | 05/Mar/26 1:30 PM | [10 empty] | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19
Sub-task | DRST-54 | 46470 | [QA] Test Execution UAT | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 05/Mar/26 1:30 PM | 05/Mar/26 1:30 PM | [10 empty] | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19
Sub-task | DRST-53 | 46468 | [QA] Test Execution UAT | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 05/Mar/26 1:30 PM | 05/Mar/26 1:30 PM | [10 empty] | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19
Bug | DPWP-45 | 46393 | [S3][API][PWP][Create transaction] Create transaction with API does not sent "merchant_reference" in response | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Low | UNDER VALIDATION |  | 04/Mar/26 3:13 PM | 05/Mar/26 2:09 PM | [10 empty] | [Dev][RD][PWP] Sprint 18
Test Plan | DPWP-43 | 46351 | [TP][HOP PWP] Sprint#18 API |  |  | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 04/Mar/26 2:25 PM | 04/Mar/26 2:25 PM | [10 empty] | [Dev][RD][PWP] Sprint 18
Test Set | DPWP-42 | 46350 | [TS][API] HOP Pay With Points API |  |  | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 04/Mar/26 2:23 PM | 04/Mar/26 2:26 PM | [10 empty] | [Dev][RD][PWP] Sprint 18
Story | DEVRDSUP-486 | 46243 | [SUP-570][SUB] Receipt is not generated after SUB transaction is made (2-3 MAR 2026) | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Highest | Done |  | 04/Mar/26 10:47 AM | 04/Mar/26 11:03 AM | 04/Mar/26 12:00 AM |  | BURequest |  |  |  | 1800 |  |  |  | [Dev][All Project] Sprint 19
Story | DRST-44 | 46141 | [DEV][RD][BFF][USER] Create confirm phone OTP | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Review |  | 02/Mar/26 3:14 PM | 05/Mar/26 2:31 PM |  | 3 | [8 empty] | [Dev RD][VIMI Termi] Sprint 19
Story | DRST-43 | 46140 | [DEV][RD][BFF][USER] Create update user profile endpoint | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Progress |  | 02/Mar/26 2:55 PM | 04/Mar/26 12:00 PM | 06/Mar/26 12:00 AM | 8 | [8 empty] | [Dev RD][VIMI Termi] Sprint 19
Sub-task | DRST-42 | 46139 | Create API Task |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Progress |  | 02/Mar/26 2:52 PM | 02/Mar/26 2:52 PM | [10 empty] | [Dev RD][VIMI Termi] Sprint 19
Sub-task | DRST-41 | 46137 | Update BFF API Doc | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Progress |  | 02/Mar/26 2:51 PM | 02/Mar/26 2:52 PM | [10 empty] | [Dev RD][VIMI Termi] Sprint 19
Sub-task | DRST-40 | 46135 | Mapping API VIMI to RD | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 02/Mar/26 2:51 PM | 02/Mar/26 2:52 PM | [10 empty] | [Dev RD][VIMI Termi] Sprint 19
Sub-task | DPE-299 | 45883 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 27/Feb/26 2:59 PM | 01/Mar/26 8:41 PM | [10 empty] | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-298 | 45881 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | In Review |  | 27/Feb/26 2:59 PM | 04/Mar/26 11:18 AM | [10 empty] | [Dev][RD][New PE] Sprint 19
Story | DPE-297 | 45879 | [Dev][RD][SSO-User] Backoffice Delete Account | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 27/Feb/26 2:54 PM | 05/Mar/26 4:51 PM | [10 empty] | [Dev][RD][New PE] Sprint 19
Story | DEVRDSUP-477 | 45778 | [SUP-562][SUB] Receipt is not generated after SUB transaction is made (27 FEB 2026) | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Done |  | 27/Feb/26 12:11 PM | 27/Feb/26 4:39 PM | 27/Feb/26 12:00 AM |  | bts | sub |  |  | 1800 |  |  |  | [Dev][All Project] Sprint 19
Story | DEVRDSUP-472 | 45699 | [SUP-557]Get list of customer who still have ticket in his/her account | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 26/Feb/26 8:44 PM | 06/Mar/26 9:00 AM |  | 2 | BURequest | challenge | vimi |  | 14400 |  |  |  | [Dev][All Project] Sprint 19
Story | RDAPS-423 | 45632 | [DEV][RD][Investigate] Check RLPxCleverTap binding Dec 2025 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Progress |  | 26/Feb/26 6:08 PM | 26/Feb/26 6:10 PM |  | 1 | [8 empty] | [Dev][All Project] Sprint 19
Story | DRST-39 | 45528 | [DEV][RD][SA][UAT] Partners & benefit manual operation testing | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 26/Feb/26 2:06 PM | 06/Mar/26 9:00 AM |  | 1 |  |  |  |  | 3600 |  |  |  | [Dev RD][VIMI Termi] Sprint 19
Sub-task | DRST-38 | 45495 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 26/Feb/26 1:21 PM | 26/Feb/26 2:01 PM | [10 empty] | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19
Story | DEVRDSUP-470 | 45424 | [SUP-554][SUB] Request to disable credit card payment method for BBL flow verification prior to launch 26/02/2026 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Done |  | 26/Feb/26 10:38 AM | 06/Mar/26 9:00 AM | 26/Feb/26 12:00 AM | 1 | sub |  |  |  | 1800 |  |  |  | [Dev][All Project] Sprint 19
Sub-task | DPE-294 | 45383 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 7:02 PM | [10 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-293 | 45381 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 7:02 PM | [10 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-292 | 45379 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 7:02 PM | [10 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-291 | 45377 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 7:02 PM | [10 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-290 | 45375 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 7:02 PM | [10 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-289 | 45373 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 7:01 PM | [10 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-288 | 45372 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 7:02 PM | [10 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-287 | 45369 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | In Review |  | 25/Feb/26 6:48 PM | 04/Mar/26 10:20 AM | [10 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-286 | 45367 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | In Review |  | 25/Feb/26 6:48 PM | 04/Mar/26 10:21 AM | [10 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-285 | 45365 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 7:02 PM | [10 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-284 | 45363 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | In Review |  | 25/Feb/26 6:48 PM | 04/Mar/26 10:20 AM | [10 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-283 | 45361 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 7:02 PM | [10 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-282 | 45359 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | In Review |  | 25/Feb/26 6:48 PM | 04/Mar/26 10:21 AM | [10 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-281 | 45357 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | In Progress |  | 25/Feb/26 6:48 PM | 04/Mar/26 11:14 AM | [10 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-280 | 45355 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:58 PM | [10 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-279 | 45354 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 7:01 PM | [10 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-277 | 45351 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:59 PM | [10 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-278 | 45350 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:59 PM | [10 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-276 | 45343 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:59 PM | [10 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-275 | 45348 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:59 PM | [10 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-274 | 45345 | TO BE DELETED |  |  | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 27/Feb/26 3:08 PM | [10 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-273 | 45342 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 7:01 PM | [10 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-272 | 45339 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:50 PM | [10 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-271 | 45337 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:50 PM | [10 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-270 | 45335 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:59 PM | [10 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-269 | 45333 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:59 PM | [10 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-268 | 45331 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 7:01 PM | [10 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-267 | 45332 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:59 PM | [10 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-266 | 45329 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:58 PM | [10 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-265 | 45330 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 7:01 PM | [10 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-264 | 45324 | TO BE DELETED |  |  | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 27/Feb/26 3:08 PM | [10 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-263 | 45326 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:50 PM | [10 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-262 | 45319 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:50 PM | [10 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-261 | 45321 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:48 PM | 25/Feb/26 6:59 PM | [10 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-260 | 45315 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:12 PM | 25/Feb/26 6:12 PM | [10 empty] | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-259 | 45313 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:12 PM | 25/Feb/26 6:12 PM | [10 empty] | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-258 | 45311 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:12 PM | 25/Feb/26 6:12 PM | [10 empty] | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-257 | 45309 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:12 PM | 25/Feb/26 6:12 PM | [10 empty] | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-256 | 45307 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:12 PM | 25/Feb/26 6:12 PM | [10 empty] | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-255 | 45305 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | In Review |  | 25/Feb/26 6:12 PM | 04/Mar/26 9:22 PM | [10 empty] | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-254 | 45303 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:12 PM | 25/Feb/26 6:12 PM | [10 empty] | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-253 | 45301 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:12 PM | 25/Feb/26 6:12 PM | [10 empty] | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-252 | 45299 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:12 PM | 25/Feb/26 6:12 PM | [10 empty] | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-251 | 45297 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | In Review |  | 25/Feb/26 6:12 PM | 04/Mar/26 5:49 PM | [10 empty] | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-250 | 45295 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:11 PM | 25/Feb/26 6:11 PM | [10 empty] | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-249 | 45293 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:11 PM | 25/Feb/26 6:11 PM | [10 empty] | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-248 | 45291 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:02 PM | 25/Feb/26 6:03 PM | [10 empty] | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-247 | 45289 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:02 PM | 25/Feb/26 6:02 PM | [10 empty] | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-246 | 45287 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 6:01 PM | 25/Feb/26 6:01 PM | [10 empty] | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-245 | 45285 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | In Progress |  | 25/Feb/26 6:01 PM | 04/Mar/26 9:32 PM | [10 empty] | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-244 | 45282 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 5:56 PM | 25/Feb/26 5:58 PM | [10 empty] | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-243 | 45280 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | In Review |  | 25/Feb/26 5:56 PM | 04/Mar/26 9:05 PM | [10 empty] | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-242 | 45278 | Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | To Do |  | 25/Feb/26 5:56 PM | 25/Feb/26 5:58 PM | [10 empty] | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-241 | 45276 | Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Automation for Jira | 557058:f58131cb-b67d-43c7-b30d-6b58d40bd077 | Medium | In Review |  | 25/Feb/26 5:56 PM | 04/Mar/26 4:44 PM | [10 empty] | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-240 | 45274 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 25/Feb/26 5:43 PM | 25/Feb/26 5:43 PM | [10 empty] | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-239 | 45272 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Review |  | 25/Feb/26 5:42 PM | 27/Feb/26 6:19 PM | [10 empty] | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-238 | 45270 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 25/Feb/26 5:42 PM | 25/Feb/26 5:42 PM | [10 empty] | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-237 | 45268 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Review |  | 25/Feb/26 5:42 PM | 04/Mar/26 4:20 PM | [10 empty] | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-236 | 45266 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 25/Feb/26 5:42 PM | 25/Feb/26 5:42 PM | [10 empty] | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-235 | 45264 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Review |  | 25/Feb/26 5:41 PM | 04/Mar/26 4:09 PM | [10 empty] | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-234 | 45262 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 25/Feb/26 5:40 PM | 25/Feb/26 5:40 PM | [10 empty] | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-233 | 45260 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Review |  | 25/Feb/26 5:40 PM | 25/Feb/26 5:41 PM | [10 empty] | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-232 | 45258 | [QA] Test execution |  |  | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 25/Feb/26 5:40 PM | 25/Feb/26 5:40 PM | [10 empty] | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-231 | 45256 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Review |  | 25/Feb/26 5:40 PM | 25/Feb/26 5:40 PM | [10 empty] | [Dev][RD][New PE] Sprint 19
Story | DEVRDSUP-469 | 45210 | [SUP-548]Turtle Shop Deal Extension | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 25/Feb/26 2:35 PM | 27/Feb/26 5:52 PM | 27/Feb/26 12:00 AM | 2 | BURequest | turtle | [6 empty] | [Dev][All Project] Sprint 19
Sub-task | DRST-37 | 45167 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 25/Feb/26 1:36 PM | 25/Feb/26 4:47 PM | [10 empty] | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19
Sub-task | DRST-36 | 45165 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 25/Feb/26 1:35 PM | 05/Mar/26 1:30 PM | [10 empty] | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19
Sub-task | DRST-35 | 45163 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 25/Feb/26 1:26 PM | 25/Feb/26 1:26 PM | [10 empty] | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19
Sub-task | DRST-34 | 45129 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 25/Feb/26 11:34 AM | 25/Feb/26 11:51 AM | [10 empty] | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19
Sub-task | DRST-33 | 45125 | [QA] Test Execution STG | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 25/Feb/26 10:04 AM | 04/Mar/26 3:27 PM | [10 empty] | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19
Sub-task | DRST-32 | 45123 | [QA] Test Execution STG | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 25/Feb/26 10:04 AM | 04/Mar/26 3:27 PM | [10 empty] | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19
Sub-task | DRST-31 | 45121 | [QA] Test Execution STG | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 25/Feb/26 10:03 AM | 04/Mar/26 3:27 PM | [10 empty] | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19
Sub-task | DRST-30 | 45119 | [QA] Test Execution STG | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 25/Feb/26 10:03 AM | 04/Mar/26 3:27 PM | [10 empty] | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19
Sub-task | DRST-29 | 45117 | [QA] Test Execution STG | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 25/Feb/26 10:03 AM | 04/Mar/26 3:27 PM | [10 empty] | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19
Story | DEVRDSUP-467 | 45058 | [SUP-550]SUB : Disable Credit/Debit Card Payment for BBL Package | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 24/Feb/26 5:07 PM | 25/Feb/26 1:57 PM | 25/Feb/26 12:00 AM | 1 | bts | BURequest | sub |  | 1800 |  |  |  | [Dev][All Project] Sprint 19
Story | DEVRDSUP-466 | 44991 | [SUP-551][BUReq][SSO][UAT] Request from BSS to unbind wallet cards from SSO on UAT 24/02/2026 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 24/Feb/26 3:40 PM | 26/Feb/26 2:03 PM | 24/Feb/26 12:00 AM | 1 | BURequest |  |  |  | 7200 |  |  |  | [Dev][All Project] Sprint 19
Story | DPE-230 | 44981 | [Dev][RD][SA] Retail Transaction Flow | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 24/Feb/26 2:10 PM | 27/Feb/26 11:11 AM |  | 13 | No-QA | [7 empty] | [Dev][RD][New PE] Sprint 19
Task | DM-189 | 44936 | [DEV][RD][AWSTH] Verify Database replication for RR Member Acquisition and RR Athena | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Low | Done |  | 24/Feb/26 11:37 AM | 05/Mar/26 6:05 PM | 25/Feb/26 12:00 AM | 1 | No-QA |  |  |  | 7200 |  |  |  | [Dev][RD][AWS] Sprint 19
Sub-task | DPE-228 | 44837 | [QA] Test execution |  |  | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 23/Feb/26 5:45 PM | 23/Feb/26 5:45 PM | [10 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-227 | 44835 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Review |  | 23/Feb/26 5:45 PM | 23/Feb/26 5:45 PM | [10 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-226 | 44833 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 23/Feb/26 5:43 PM | 23/Feb/26 5:43 PM | [10 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-225 | 44831 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Review |  | 23/Feb/26 5:43 PM | 23/Feb/26 5:43 PM | [10 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Story | DPE-224 | 44784 | [Dev][RD][PE Middleware] Database Migration | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Highest | Ready to Staging |  | 23/Feb/26 3:39 PM | 04/Mar/26 10:31 AM |  | 3 | No-QA | point-engine-proxy |  |  | 28800 |  |  |  | [Dev][RD][New PE] Sprint 19
Sub-task | DPWP-41 | 44782 | [QA] (On STG) Test execution API to cancel transaction | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 23/Feb/26 3:24 PM | 23/Feb/26 3:31 PM | [10 empty] | [Dev][RD][PWP] Sprint 18
Sub-task | DPWP-40 | 44778 | [QA] Create test case API to cancel transaction | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | In Progress |  | 23/Feb/26 3:23 PM | 27/Feb/26 3:15 PM | [10 empty] | [Dev][RD][PWP] Sprint 18
Sub-task | DPE-223 | 44711 | [QA] Test execution |  |  | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 23/Feb/26 1:29 PM | 23/Feb/26 4:10 PM | [10 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-222 | 44709 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Review |  | 23/Feb/26 1:29 PM | 23/Feb/26 4:10 PM | [10 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-221 | 44707 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 23/Feb/26 1:29 PM | 23/Feb/26 4:10 PM | [10 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-220 | 44705 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Review |  | 23/Feb/26 1:29 PM | 23/Feb/26 4:10 PM | [10 empty] | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Story | DPE-219 | 44552 | [Dev][RD][PE Middleware] Delete Offer (Soft Delete) | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | In Progress |  | 22/Feb/26 12:40 PM | 05/Mar/26 1:40 PM | 06/Mar/26 12:00 AM | 1 | point-engine-proxy |  |  |  | 7200 |  |  |  | [Dev][RD][New PE] Sprint 19
Story | DPE-218 | 44551 | [Dev][RD][PE Middleware] Get Offer by id | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready to Staging |  | 22/Feb/26 11:42 AM | 04/Mar/26 3:43 PM | 05/Mar/26 12:00 AM | 2 | point-engine-proxy |  |  |  | 14400 |  |  |  | [Dev][RD][New PE] Sprint 19
Story | DPE-217 | 44550 | [Dev][RD][PE Middleware] Get Merchant by id | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready to Staging |  | 22/Feb/26 11:17 AM | 05/Mar/26 10:08 AM |  | 3 | point-engine-proxy | [7 empty] | [Dev][RD][New PE] Sprint 19
Story | DPE-216 | 44549 | [Dev][RD][PE Middleware] Centralized Code Generation Function | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | High | Ready to Staging |  | 22/Feb/26 10:19 AM | 04/Mar/26 10:31 AM |  | 3 | No-QA | point-engine-proxy | [6 empty] | [Dev][RD][New PE] Sprint 19
Sub-task | RDTHANA-460 | 44483 | CSV Generate |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 20/Feb/26 3:45 PM | 20/Feb/26 3:45 PM | [10 empty] | [Dev][RD][Thana] Sprint 19
Sub-task | RDTHANA-459 | 44481 | CSV Template |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Progress |  | 20/Feb/26 3:45 PM | 05/Mar/26 10:24 AM | [10 empty] | [Dev][RD][Thana] Sprint 19
Sub-task | RDTHANA-458 | 44479 | CSV Generate |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 20/Feb/26 3:45 PM | 20/Feb/26 3:45 PM | [10 empty] | [Dev][RD][Thana] Sprint 19
Sub-task | RDTHANA-457 | 44477 | CSV Template |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Review |  | 20/Feb/26 3:44 PM | 04/Mar/26 1:34 PM | [10 empty] | [Dev][RD][Thana] Sprint 19
Sub-task | RDTHANA-456 | 44475 | CSV Generate |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 20/Feb/26 3:44 PM | 02/Mar/26 4:41 PM | [10 empty] | [Dev][RD][Thana] Sprint 19
Sub-task | RDTHANA-455 | 44473 | CSV Template |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 20/Feb/26 3:44 PM | 02/Mar/26 1:28 PM | [10 empty] | [Dev][RD][Thana] Sprint 19
Sub-task | RDTHANA-454 | 44471 | CSV Generate | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Review |  | 20/Feb/26 3:44 PM | 05/Mar/26 11:14 AM | [10 empty] | [Dev][RD][Thana] Sprint 19
Sub-task | RDTHANA-453 | 44469 | CSV Template | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Review |  | 20/Feb/26 3:44 PM | 05/Mar/26 11:14 AM | [10 empty] | [Dev][RD][Thana] Sprint 19
Sub-task | RDTHANA-452 | 44467 | CSV Generate | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 20/Feb/26 3:43 PM | 02/Mar/26 4:27 PM | [10 empty] | [Dev][RD][Thana] Sprint 19
Sub-task | RDTHANA-451 | 44465 | CSV Template | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 20/Feb/26 3:43 PM | 02/Mar/26 1:28 PM | [10 empty] | [Dev][RD][Thana] Sprint 19
Story | RDTHANA-450 | 44430 | [DEV][RD][TDM] Create cronjob for polling master data - customer | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Progress |  | 20/Feb/26 2:38 PM | 05/Mar/26 9:56 AM | 06/Mar/26 12:00 AM | 5 |  |  |  |  | 57600 |  |  |  | [Dev][RD][Thana] Sprint 19
Story | DEVRDSUP-463 | 44397 | [SUP-544][Member Account] Cannot terminate/delete account ID: 32123252 please check | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 20/Feb/26 11:38 AM | 06/Mar/26 8:59 AM |  | 2 | BURequest | sso |  |  | 1800 |  |  |  | [Dev][All Project] Sprint 19
Story | DPE-215 | 44364 | [Dev][RD][PE Middleware] Update Merchant by id | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 20/Feb/26 11:16 AM | 05/Mar/26 2:20 PM |  | 3 | point-engine-proxy | [7 empty] | [Dev][RD][New PE] Sprint 19
Bug | DEVRDSUP-462 | 44263 | [SUP-520][Rabbit connect] Unable to login to RR app with Facebook account or Apple ID | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | UNDER VALIDATION |  | 19/Feb/26 6:42 PM | 25/Feb/26 2:09 PM | 13/Mar/26 12:00 AM | 2 | prod-issue | RabbitConnect | sso | [5 empty] | [Dev][All Project] Sprint 19
Sub-task | DPE-214 | 44196 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 19/Feb/26 3:40 PM | 23/Feb/26 4:10 PM | [7 empty] | มาจาก Sprint 18 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-213 | 44194 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Review |  | 19/Feb/26 3:40 PM | 23/Feb/26 4:10 PM | [7 empty] | มาจาก Sprint 18 | In Review |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-212 | 44192 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 19/Feb/26 3:40 PM | 23/Feb/26 4:10 PM | [7 empty] | มาจาก Sprint 18 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-211 | 44190 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Review |  | 19/Feb/26 3:40 PM | 23/Feb/26 4:10 PM | [7 empty] | มาจาก Sprint 18 | In Review |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Story | DPE-210 | 44188 | [Dev][RD][PE Middleware] Point expiry | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 19/Feb/26 3:22 PM | 05/Mar/26 2:31 PM |  | 3 | point-engine-proxy |  |  |  | 28800 |  |  |  | [Dev][RD][New PE] Sprint 19
Story | DRST-26 | 44053 | [DEV][RD][API][SA] Find and replace VIMI API by RD API | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Progress |  | 19/Feb/26 9:21 AM | 02/Mar/26 2:51 PM |  | 8 | [8 empty] | [Dev RD][VIMI Termi] Sprint 19
Story | DRST-25 | 44052 | [DEV][RD][BFF] Create new endpoint to get earn by slug | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 19/Feb/26 9:16 AM | 04/Mar/26 9:15 AM |  | 3 |  |  |  |  | 28800 |  |  |  | [Dev RD][VIMI Termi] Sprint 19
Story | DRST-24 | 44051 | [DEV][RD][BFF] Create new endpoint to get earn by id | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 19/Feb/26 9:15 AM | 04/Mar/26 9:15 AM |  | 2 |  |  |  |  | 14400 |  |  |  | [Dev RD][VIMI Termi] Sprint 19
Story | DEVRDSUP-460 | 44014 | [SUP-540]SUB : TXN Report – Some Columns Have Missing Data | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 18/Feb/26 3:50 PM | 05/Mar/26 2:14 PM | 25/Feb/26 12:00 AM | 3 | bts | BURequest | sub | [5 empty] | [Dev][All Project] Sprint 18 | [Dev][All Project] Sprint 19
Story | DPE-207 | 44011 | [Dev][RD][SSO-User] Reward Add Card | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 18/Feb/26 3:42 PM | 05/Mar/26 3:33 PM |  | 1 | [5 empty] | มาจาก Sprint 18 | In Review |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Story | DPE-206 | 44010 | [Dev][RD][SSO-User] Backoffice Sync Cards | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 18/Feb/26 3:42 PM | 05/Mar/26 3:32 PM |  | 1 | [5 empty] | มาจาก Sprint 18 | In Review |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Story | DRST-23 | 43648 | [DEV][RD][Rabbit CMS API] Create new endpoint for get earn by slug | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 15/Feb/26 10:50 PM | 04/Mar/26 9:15 AM |  | 2 |  |  |  |  | 14400 |  |  |  | [Dev RD][VIMI Termi] Sprint 19
Story | DRST-22 | 43647 | [DEV][RD][Rabbit CMS API] Create new endpoint for get earn by id | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 15/Feb/26 10:46 PM | 25/Feb/26 4:11 PM |  | 2 | [8 empty] | [Dev RD][VIMI Termi] Sprint 19
Story | DPE-195 | 43604 | [Dev][RD][DevOps][PE-MIGRATION] Provision dedicated UAT-CT environment for Point Engine migration services | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 15/Feb/26 1:53 PM | 04/Mar/26 9:35 AM |  | 3 | No-QA | [7 empty] | [Dev][RD][New PE] Sprint 19
Story | DPE-192 | 43566 | [Dev][RD][DevOps][RD][PE-MIGRATION] Provision uat-ct domain for CleverTap integration testing | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | To Do |  | 13/Feb/26 9:03 PM | 24/Feb/26 11:09 AM |  | 3 | [8 empty] | [Dev][RD][New PE] Sprint 19
Story | DPE-190 | 43427 | [Dev][RD][SSO-User] Offline register | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 13/Feb/26 1:03 PM | 05/Mar/26 4:51 PM |  | 2 | [5 empty] | มาจาก Sprint 18 | Ready to Staging |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Bug | DEVRDSUP-453 | 43426 | [SUP-525]SUB : Refunded txn report Search result shows “No Data Found” even though data exists | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Thanakrit Chanthaworn | 712020:3fc982cb-c268-4f1d-9265-d3dd8fb08304 | Medium | Fixing |  | 13/Feb/26 1:02 PM | 04/Mar/26 1:25 PM | 03/Mar/26 12:00 AM | 3 | [8 empty] | [Dev][All Project] Sprint 19
Bug | DEVRDSUP-450 | 43352 | [SUP-531][HRSolution] HR solution Reward distribution feature, import col mismatched with template. | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Pass : Waiting for deployment |  | 13/Feb/26 9:51 AM | 05/Mar/26 3:08 PM | 03/Mar/26 12:00 AM | [6 empty] | มาจาก Sprint 18 | Fixing |  | [Dev][All Project] Sprint 18 | [Dev][All Project] Sprint 19
Sub-task | DPE-189 | 43275 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 12/Feb/26 2:47 PM | 25/Feb/26 7:02 PM | [7 empty] | มาจาก Sprint 18 | To Do |  | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-188 | 43273 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Review |  | 12/Feb/26 2:46 PM | 23/Feb/26 4:10 PM | [7 empty] | มาจาก Sprint 18 | In Review |  | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-187 | 43123 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 12/Feb/26 10:49 AM | 23/Feb/26 4:10 PM | [7 empty] | มาจาก Sprint 18 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-186 | 43122 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Review |  | 12/Feb/26 10:49 AM | 23/Feb/26 5:43 PM | [7 empty] | มาจาก Sprint 18 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-185 | 43121 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 12/Feb/26 10:49 AM | 23/Feb/26 4:10 PM | [7 empty] | มาจาก Sprint 18 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-184 | 43120 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Review |  | 12/Feb/26 10:49 AM | 23/Feb/26 5:43 PM | [7 empty] | มาจาก Sprint 18 | To Do |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-183 | 43119 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 12/Feb/26 10:48 AM | 25/Feb/26 7:02 PM | [7 empty] | มาจาก Sprint 18 | To Do |  | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-182 | 43118 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Review |  | 12/Feb/26 10:48 AM | 23/Feb/26 4:10 PM | [7 empty] | มาจาก Sprint 18 | In Review |  | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-181 | 43117 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 12/Feb/26 10:47 AM | 23/Feb/26 4:10 PM | [7 empty] | มาจาก Sprint 18 | To Do |  | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-180 | 43116 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Progress |  | 12/Feb/26 10:47 AM | 23/Feb/26 4:10 PM | [7 empty] | มาจาก Sprint 18 | In Progress |  | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-179 | 43115 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 12/Feb/26 10:46 AM | 23/Feb/26 4:10 PM | [7 empty] | มาจาก Sprint 18 | To Do |  | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Sub-task | DPE-178 | 43114 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Review |  | 12/Feb/26 10:46 AM | 23/Feb/26 5:45 PM | [7 empty] | มาจาก Sprint 18 | In Progress |  | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Story | RDTHANA-437 | 43029 | [DEV][RD][TDM] Create cronjob for polling master data - category | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Review |  | 11/Feb/26 4:31 PM | 05/Mar/26 9:56 AM | 05/Mar/26 12:00 AM | 5 |  |  |  |  | 57600 |  |  |  | [Dev][RD][Thana] Sprint 19
Story | RDTHANA-436 | 43028 | [DEV][RD][TDM] Create cronjob for polling master data - shop | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 11/Feb/26 4:31 PM | 04/Mar/26 9:45 AM | 02/Mar/26 12:00 AM | 5 |  |  |  |  | 57600 |  |  |  | [Dev][RD][Thana] Sprint 19
Story | RDTHANA-435 | 43027 | [DEV][RD][TDM] Create cronjob for polling master data - employee | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Review |  | 11/Feb/26 4:31 PM | 05/Mar/26 1:12 PM | 05/Mar/26 12:00 AM | 5 |  |  |  |  | 43200 |  |  |  | [Dev][RD][Thana] Sprint 19
Story | RDTHANA-434 | 43026 | [DEV][RD][TDM] Create cronjob for polling master data - item | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 11/Feb/26 4:12 PM | 04/Mar/26 9:33 AM | 04/Mar/26 12:00 AM | 8 |  |  |  |  | 72000 |  |  |  | [Dev][RD][Thana] Sprint 19
Story | RDTHANA-433 | 43025 | [DEV][RD][TDM] Create consumer for "lightspeed-txn" | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 11/Feb/26 4:10 PM | 27/Feb/26 3:03 PM | 27/Feb/26 12:00 AM | 5 |  |  |  |  | 57600 |  |  |  | [Dev][RD][Thana] Sprint 19
Story | RDTHANA-432 | 42992 | [DEV][RD][TDM] Create cronjob for polling sale transaction | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 11/Feb/26 3:09 PM | 05/Mar/26 2:14 PM | 19/Feb/26 12:00 AM | 5 |  |  |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 57600 | [Dev][RD][Thana] Sprint 18 | [Dev][RD][Thana] Sprint 19
Epic | RDTHANA-431 | 42991 | Lighspeed Polling |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 11/Feb/26 3:07 PM | 24/Feb/26 1:40 PM | 06/Mar/26 12:00 AM | [6 empty] | มาจาก Sprint 18 | To Do |  | [Dev][RD][Thana] Sprint 18 | [Dev][RD][Thana] Sprint 19
Story | RDTHANA-430 | 42990 | [DEV][RD][TDM] Create LighspeedService for getToken | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 11/Feb/26 2:57 PM | 05/Mar/26 2:14 PM | 13/Feb/26 12:00 AM | 5 |  |  |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 57600 | [Dev][RD][Thana] Sprint 18 | [Dev][RD][Thana] Sprint 19
Story | DRST-17 | 42821 | [DEV][RD][BOF] Create command to migrate data from VIMI database to Rabbit CMS database | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 11/Feb/26 10:17 AM | 05/Mar/26 2:14 PM |  | 8 |  |  |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 86400 | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19
Story | DPE-174 | 42542 | [Dev][RD] SSO new enviroment for non-prod | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready to Staging |  | 10/Feb/26 10:29 AM | 04/Mar/26 10:09 AM |  | 3 | No-QA |  |  |  | 3600 | มาจาก Sprint 18 | In Progress | 7200 -> 3600 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Story | DRST-15 | 42268 | [DEV][RD][BFF] Create endpoint for get earn content | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 08/Feb/26 9:54 PM | 02/Mar/26 11:41 AM |  | 3 | [8 empty] | [Dev RD][VIMI Termi] Sprint 19
Story | DRST-14 | 42267 | [DEV][RD][Rabbit CMS API] Create endpoint for get earn content | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 08/Feb/26 9:54 PM | 05/Mar/26 2:14 PM |  | 5 |  |  |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 57600 | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19
Story | DRST-13 | 42266 | [DEV][RD][BOF] Create feature structure for earn content management | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 08/Feb/26 9:28 PM | 05/Mar/26 10:47 AM | 27/Feb/26 12:00 AM | 3 |  |  |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 28800 | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19
Story | DRST-12 | 42265 | [DEV][RD][BOF] Create edit earn form page | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 08/Feb/26 9:26 PM | 05/Mar/26 10:47 AM | 27/Feb/26 12:00 AM | 3 |  |  |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 28800 | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19
Story | DRST-11 | 42264 | [DEV][RD][BOF] Implement create form for earn content | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 08/Feb/26 9:25 PM | 05/Mar/26 10:47 AM | 27/Feb/26 12:00 AM | 3 |  |  |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 28800 | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19
Story | DRST-10 | 42263 | [DEV][RD][BOF] Create earn content index page | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 08/Feb/26 9:25 PM | 05/Mar/26 10:47 AM | 27/Feb/26 12:00 AM | 3 |  |  |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 28800 | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19
Story | DRST-8 | 42261 | [DEV][RD][CMS API] Create migration for earn contents | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 08/Feb/26 9:01 PM | 05/Mar/26 10:47 AM | 09/Feb/26 12:00 AM | 1 |  |  |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 7200 | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19
Story | DPE-171 | 42260 | [Dev][RD][PE Middleware] Update offer | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 08/Feb/26 7:59 PM | 04/Mar/26 3:43 PM | 02/Mar/26 12:00 AM | 3 | point-engine-proxy |  |  |  | 28800 |  |  |  | [Dev][RD][New PE] Sprint 19
Story | DPE-170 | 42259 | [Dev][RD][PE Middleware] Get offer list | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 08/Feb/26 7:59 PM | 04/Mar/26 3:43 PM | 04/Mar/26 12:00 AM | 3 | point-engine-proxy | [7 empty] | [Dev][RD][New PE] Sprint 19
Story | DPE-169 | 42258 | [Dev][RD][PE Middleware] Create offer | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 08/Feb/26 7:58 PM | 04/Mar/26 3:43 PM | 26/Feb/26 12:00 AM | 3 | point-engine-proxy | [7 empty] | [Dev][RD][New PE] Sprint 19
Story | DPE-156 | 42181 | [Dev][RD][PE Middleware] Get Merchant list | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 07/Feb/26 11:03 AM | 05/Mar/26 2:27 PM |  | 3 | point-engine-proxy | [7 empty] | [Dev][RD][New PE] Sprint 19
Story | DPE-155 | 42180 | [Dev][RD][PE Middleware] Create Merchant | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 07/Feb/26 11:03 AM | 04/Mar/26 5:11 PM |  | 3 | point-engine-proxy | [7 empty] | [Dev][RD][New PE] Sprint 19
Story | DPE-154 | 42179 | [Dev][RD][SA][Sprint20] Analysis & Task Breakdown for PE Migration Execution | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 07/Feb/26 9:28 AM | 25/Feb/26 8:07 AM |  | 13 | No-QA | [7 empty] | [Dev][RD][New PE] Sprint 19
Story | DPE-151 | 42176 | [Dev][RD][PE Middleware] Point history | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 07/Feb/26 8:18 AM | 04/Mar/26 3:43 PM |  | 3 | point-engine-proxy |  |  |  | 28800 |  |  |  | [Dev][RD][New PE] Sprint 19
Story | DPE-149 | 42174 | [Dev][RD][PE Middleware] Credit point | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready to Staging |  | 07/Feb/26 8:18 AM | 04/Mar/26 3:42 PM |  | 2 | point-engine-proxy |  |  |  | 14400 |  |  |  | [Dev][RD][New PE] Sprint 19
Story | DPE-148 | 42173 | [Dev][RD][PE Middleware] Debit point | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready to Staging |  | 07/Feb/26 8:18 AM | 04/Mar/26 3:42 PM |  | 3 | point-engine-proxy |  |  |  | 43200 |  |  |  | [Dev][RD][New PE] Sprint 19
Story | DPE-147 | 42134 | [Dev][RD][SSO-User] WEB verify phone | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 06/Feb/26 6:37 PM | 05/Mar/26 4:41 PM |  | 1 | sso-user |  |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 3600 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Story | DPE-146 | 42133 | [Dev][RD][SSO-User] WEB update avatar | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 06/Feb/26 6:37 PM | 05/Mar/26 4:38 PM |  | 1 | sso-user |  |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Story | DPE-145 | 42132 | [Dev][RD][SSO-User] WEB verify user | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 06/Feb/26 6:37 PM | 05/Mar/26 4:36 PM |  | 2 | sso-user |  |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 10800 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Story | DPE-144 | 42131 | [Dev][RD][SSO-User] WEB remove card by card_id | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 06/Feb/26 6:37 PM | 05/Mar/26 3:18 PM |  | 1 | sso-user |  |  |  | 0 | มาจาก Sprint 18 | In Review | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Story | DPE-143 | 42130 | [Dev][RD][SSO-User] WEB move card | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 06/Feb/26 6:36 PM | 05/Mar/26 3:19 PM |  | 1 | sso-user |  |  |  |  | มาจาก Sprint 18 | In Progress |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Story | DPE-142 | 42129 | [Dev][RD][SSO-User] WEB add card | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 06/Feb/26 6:36 PM | 05/Mar/26 3:18 PM |  | 1 | sso-user |  |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Story | DPE-141 | 42128 | [Dev][RD][SSO-User] WEB update profile by ID | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 06/Feb/26 6:36 PM | 05/Mar/26 3:18 PM | 12/Feb/26 12:00 AM | 2 | sso-user |  |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 14400 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Bug | DEVRDSUP-421 | 42045 | [SUP-479]Link Search and link # in the pop up is not redirect | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Resolved |  | 06/Feb/26 11:33 AM | 05/Mar/26 3:08 PM | 23/Feb/26 12:00 AM | 2 | deeplink |  |  |  |  | มาจาก Sprint 18 | Open |  | [Dev][All Project] Sprint 18 | [Dev][All Project] Sprint 19
Story | RDNDA-27 | 41770 | [DEV][RD][TDM] Create script for check missing ENV | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 05/Feb/26 9:37 AM | 24/Feb/26 9:59 AM |  | 2 |  |  |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 14400 | [Dev][RD][NewDamart] Sprint 17 | [Dev][RD][NewDamart] Sprint 18 | [Dev][RD][NewDamart] Sprint 19
Story | DPE-74 | 41523 | [Dev][RD][SSO-User] Remove SSO-Thor API Integration | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Ready to Staging |  | 04/Feb/26 10:13 AM | 24/Feb/26 11:09 AM |  | 5 | No-QA | sso-user |  |  | 28800 | มาจาก Sprint 18 | In Progress | 57600 -> 28800 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Story | DPE-73 | 41521 | [Dev][RD][SSO-User] CRM remove card | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 04/Feb/26 10:13 AM | 05/Mar/26 10:47 AM |  | 2 | sso-user |  |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 14400 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Story | DPE-72 | 41519 | [Dev][RD][SSO-User] CRM add card | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 04/Feb/26 10:13 AM | 05/Mar/26 10:47 AM |  | 2 | sso-user |  |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 14400 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Story | DPE-71 | 41517 | [Dev][RD][SSO-User] BSS Verify email | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 04/Feb/26 10:10 AM | 05/Mar/26 10:47 AM | 10/Feb/26 12:00 AM | 1 | sso-user |  |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Story | DPE-70 | 41515 | [Dev][RD][SSO-User] BSS Verify phone | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 04/Feb/26 9:49 AM | 05/Mar/26 10:47 AM |  | 1 | sso-user |  |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Story | DPE-69 | 41513 | [Dev][RD][SSO-User] BSS sync member to RR | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 04/Feb/26 9:49 AM | 05/Mar/26 3:29 PM |  | 2 | sso-user |  |  |  |  | มาจาก Sprint 18 | In Review |  | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Story | DPE-68 | 41511 | [Dev][RD][SSO-User] Rewards add card | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 04/Feb/26 9:49 AM | 05/Mar/26 3:29 PM | 10/Feb/26 12:00 AM | 1 | sso-user |  |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Story | DPE-62 | 41461 | [Dev][RD][SSO-User] Update a registration source | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 03/Feb/26 8:12 PM | 05/Mar/26 5:11 PM |  | 1 | sso-user |  |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 7200 | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Story | DPE-61 | 41459 | [Dev][RD][SSO-User] Backoffice Create a registration source | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 03/Feb/26 7:43 PM | 05/Mar/26 5:11 PM |  | 1 | sso-user |  |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 7200 | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Story | DPE-60 | 41457 | [Dev][RD][SSO-User] Backoffice update user | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 03/Feb/26 7:43 PM | 05/Mar/26 3:28 PM | 06/Feb/26 12:00 AM | 2 | sso-user |  |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 14400 | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Story | DPE-59 | 41455 | [Dev][RD][SSO-User] Backoffice Remove card | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 03/Feb/26 7:43 PM | 05/Mar/26 3:32 PM |  | 2 | sso-user |  |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 14400 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Story | DPE-58 | 41453 | [Dev][RD][SSO-User] Backoffice Add card | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 03/Feb/26 7:43 PM | 05/Mar/26 3:31 PM |  | 2 | sso-user |  |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 14400 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Story | DPE-56 | 41449 | [Dev][RD][SSO-User] Update email | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 03/Feb/26 7:42 PM | 05/Mar/26 3:30 PM |  | 2 | sso-user |  |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 14400 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Story | DPE-55 | 41447 | [Dev][RD][SSO-User] Verify phone | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 03/Feb/26 7:42 PM | 05/Mar/26 4:33 PM |  | 2 | sso-user |  |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 3600 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Story | DPE-54 | 41445 | [Dev][RD][SSO-User] Verify email | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 03/Feb/26 7:41 PM | 05/Mar/26 4:33 PM |  | 2 | sso-user |  |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 3600 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Story | DPE-51 | 41439 | [Dev][RD][PE Middleware] Get balance | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready to Staging |  | 03/Feb/26 7:41 PM | 04/Mar/26 11:22 AM |  | 2 | point-engine-proxy |  |  |  | 28800 |  |  |  | [Dev][RD][New PE] Sprint 19
Story | DPE-50 | 41437 | [Dev][RD][SSO-User] Activate user by phone | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 03/Feb/26 7:41 PM | 05/Mar/26 3:54 PM |  | 2 | sso-user |  |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Story | DPE-49 | 41435 | [Dev][RD][SSO-User] Rewards Verify phone | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 03/Feb/26 7:41 PM | 05/Mar/26 3:13 PM |  | 2 | sso-user |  |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 7200 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Story | DPE-48 | 41433 | [Dev][RD][SSO-User] Update rewards user | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 03/Feb/26 7:40 PM | 05/Mar/26 3:28 PM | 05/Feb/26 12:00 AM | 3 | sso-user |  |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 28800 | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Story | DPE-47 | 41431 | [Dev][RD][SSO-User] Create rewards user | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 03/Feb/26 7:40 PM | 05/Mar/26 3:18 PM | 12/Feb/26 12:00 AM | 3 | sso-user |  |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 28800 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Story | DPE-46 | 41429 | [Dev][RD][SSO-User] Create user profile | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 03/Feb/26 7:40 PM | 05/Mar/26 3:18 PM | 11/Feb/26 12:00 AM | 3 | sso-user |  |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 28800 | [Dev][RD][New PE] Sprint 18 | [Dev][RD][New PE] Sprint 19
Bug | DEVRDSUP-406 | 41284 | [SUP-481][Urgent] Turtle Auto push coupon failed | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Low | Closed |  | 03/Feb/26 11:08 AM | 24/Feb/26 2:09 PM | 25/Feb/26 12:00 AM |  | CleverTap | prod-issue |  |  |  | มาจาก Sprint 18 | Resolved |  | [Dev][All Project] Sprint 18 | [Dev][All Project] Sprint 19
Sub-task | DPWP-39 | 40985 | [QA] (On STG) Test execution process payment expiration (transaction status = 'expired') | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 29/Jan/26 7:53 PM | 23/Feb/26 3:31 PM | [7 empty] | มาจาก Sprint 18 | To Do |  | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Sub-task | DPWP-38 | 40983 | [QA] (On STG) Test execution process payment after customer confirm payment with [BFF] API | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 29/Jan/26 7:52 PM | 23/Feb/26 3:31 PM | [7 empty] | มาจาก Sprint 18 | To Do |  | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Sub-task | DPWP-37 | 40981 | [QA] (On STG) Test execution process payment after customer scans QR with [BFF] API | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 29/Jan/26 7:50 PM | 23/Feb/26 3:29 PM | [7 empty] | มาจาก Sprint 18 | To Do |  | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Sub-task | DPWP-36 | 40979 | [QA] (On STG) Test execution refund transaction and reverse points with API | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 29/Jan/26 7:49 PM | 23/Feb/26 3:29 PM | [7 empty] | มาจาก Sprint 18 | To Do |  | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Sub-task | DPWP-35 | 40977 | [QA] Test execution mark transaction as completed after merchant confirms order with API (On Staging) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 29/Jan/26 7:47 PM | 29/Jan/26 7:48 PM | [7 empty] | มาจาก Sprint 18 | To Do |  | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Sub-task | DPWP-34 | 40975 | [QA] (On STG) Test execution process payment after customer confirm payment with API | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 29/Jan/26 7:46 PM | 23/Feb/26 3:28 PM | [7 empty] | มาจาก Sprint 18 | To Do |  | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Sub-task | DPWP-33 | 40662 | [QA] Create test case process payment expiration (transaction status = 'expired') | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 28/Jan/26 10:36 AM | 28/Jan/26 10:36 AM | [7 empty] | มาจาก Sprint 18 | To Do |  | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Sub-task | DPWP-32 | 40660 | [QA] Create test case [BFF] API to process payment after customer confirm payment | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 28/Jan/26 10:34 AM | 29/Jan/26 7:52 PM | [7 empty] | มาจาก Sprint 18 | To Do |  | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Sub-task | DPWP-31 | 40657 | [QA] Create test case [BFF] API to process payment after customer scans QR | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 28/Jan/26 10:22 AM | 26/Feb/26 3:39 PM | [7 empty] | มาจาก Sprint 18 | To Do |  | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Sub-task | DPWP-30 | 40620 | [QA] (On STG) Test execution retrieve a transaction information with API | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 27/Jan/26 5:15 PM | 23/Feb/26 3:29 PM | [7 empty] | มาจาก Sprint 18 | To Do |  | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Sub-task | DPWP-29 | 40618 | [QA] (On STG) Test execution process payment after customer scans QR with API | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | In Progress |  | 27/Jan/26 5:03 PM | 05/Mar/26 3:52 PM | [7 empty] | มาจาก Sprint 18 | To Do |  | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Sub-task | DPWP-28 | 40616 | [QA] (On STG) Test execution create a new Point Payment transaction with API | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 27/Jan/26 5:01 PM | 05/Mar/26 3:48 PM | [7 empty] | มาจาก Sprint 18 | To Do |  | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Story | DM-182 | 40478 | [DEV][RD][AWSTH] Verify API Gateway on dev environment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Lowest | Done |  | 27/Jan/26 10:08 AM | 05/Mar/26 6:05 PM |  | 5 | No-QA |  |  |  | 43200 | มาจาก Sprint 18 | In Progress | 86400 -> 43200 | [Dev][RD][AWS] Sprint 17 | [Dev][RD][AWS] Sprint 18 | [Dev][RD][AWS] Sprint 19
Story | RDNDA-22 | 40327 | [DEV][RD][TDM] Enhance Kinesis stream name to dynamics config | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 25/Jan/26 10:47 PM | 24/Feb/26 9:59 AM | 04/Feb/26 12:00 AM | 2 |  |  |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 10800 | [Dev][RD][NewDamart] Sprint 17 | [Dev][RD][NewDamart] Sprint 18 | [Dev][RD][NewDamart] Sprint 19
Story | RDNDA-21 | 40326 | [DEV][RD][TDM] Enhance generic API with new data and validate with omit | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 25/Jan/26 10:31 PM | 24/Feb/26 9:59 AM | 04/Feb/26 12:00 AM | 2 |  |  |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 14400 | [Dev][RD][NewDamart] Sprint 17 | [Dev][RD][NewDamart] Sprint 18 | [Dev][RD][NewDamart] Sprint 19
Story | RDNDA-20 | 40132 | [DEV][RD][TDM] Add idempotency key for POS transaction API | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 22/Jan/26 5:10 PM | 27/Feb/26 9:25 AM |  | 3 |  |  |  |  | 28800 |  |  |  | [Dev][RD][NewDamart] Sprint 19
Story | RDNDA-19 | 40131 | [DEV][RD][TDM] Create migration for access control | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 22/Jan/26 5:07 PM | 24/Feb/26 9:59 AM |  | 1 |  |  |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 14400 | [Dev][RD][NewDamart] Sprint 17 | [Dev][RD][NewDamart] Sprint 18 | [Dev][RD][NewDamart] Sprint 19
Story | RDNDA-18 | 40130 | [DEV][RD][TDM] Create access control callback endpoint | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 22/Jan/26 5:03 PM | 24/Feb/26 9:59 AM |  | 3 |  |  |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 28800 | [Dev][RD][NewDamart] Sprint 17 | [Dev][RD][NewDamart] Sprint 18 | [Dev][RD][NewDamart] Sprint 19
Sub-task | DPWP-27 | 39934 | [QA] Create test case refund transaction and reverse points API | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 21/Jan/26 10:09 AM | 26/Feb/26 12:46 AM | [7 empty] | มาจาก Sprint 18 | To Do |  | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Sub-task | DPWP-26 | 39932 | [QA] Create test case mark transaction as completed after merchant confirms order API | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 21/Jan/26 10:09 AM | 19/Feb/26 4:53 PM | [7 empty] | มาจาก Sprint 18 | Done |  | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Sub-task | DPWP-25 | 39930 | [QA] Create test case process payment after customer confirm payment API | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 21/Jan/26 10:08 AM | 12/Feb/26 4:37 PM | [7 empty] | มาจาก Sprint 18 | Done |  | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Sub-task | DPWP-24 | 39928 | [QA] Create test case retrieve a transaction information API | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 21/Jan/26 10:07 AM | 23/Feb/26 3:19 PM | [7 empty] | มาจาก Sprint 18 | In Progress |  | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Sub-task | DPWP-23 | 39926 | [QA] Create test case process payment after customer scans QR API | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 21/Jan/26 10:06 AM | 23/Feb/26 3:19 PM | [7 empty] | มาจาก Sprint 18 | In Progress |  | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Sub-task | DPWP-22 | 39924 | [QA] Create test case create a new Point Payment transaction API | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 21/Jan/26 10:06 AM | 23/Feb/26 3:19 PM | [7 empty] | มาจาก Sprint 18 | In Progress |  | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Story | RDNDA-14 | 38512 | [DEV][RD][TDM] Create migration | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 09/Jan/26 1:48 PM | 24/Feb/26 9:59 AM |  | 2 | No-QA | ThanaDataMart |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 14400 | [Dev][RD][NewDamart] Sprint 16 | [Dev][RD][NewDamart] Sprint 17 | [Dev][RD][NewDamart] Sprint 18 | [Dev][RD][NewDamart] Sprint 19
Story | DPWP-21 | 38478 | [Dev][RD][PWP] Create API to cancel transaction to support point reservation rule | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 09/Jan/26 11:32 AM | 04/Mar/26 11:40 AM |  | 8 |  |  |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 43200 | [Dev][RD][PWP] Sprint 18
Story | DPWP-18 | 38437 | [Dev][RD][PWP] Initial Project Repository for Pay with Point Scheduler appp | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 08/Jan/26 6:48 PM | 09/Feb/26 11:04 AM | 23/Jan/26 12:00 AM | 5 | No-QA |  |  |  | 0 | มาจาก Sprint 18 | Ready To Test | 57600 | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Story | RDNDA-12 | 38435 | [DEV][RD][TDM] Integrate Discord for error log | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 08/Jan/26 5:23 PM | 24/Feb/26 9:59 AM | [7 empty] | มาจาก Sprint 18 | Ready to Staging |  | [Dev][RD][NewDamart] Sprint 16 | [Dev][RD][NewDamart] Sprint 17 | [Dev][RD][NewDamart] Sprint 18 | [Dev][RD][NewDamart] Sprint 19
Story | RDNDA-11 | 38434 | [DEV][RD][TDM] Create producer function for push kinesis data | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 08/Jan/26 5:22 PM | 24/Feb/26 9:59 AM |  | 3 | [5 empty] | มาจาก Sprint 18 | Ready to Staging |  | [Dev][RD][NewDamart] Sprint 16 | [Dev][RD][NewDamart] Sprint 17 | [Dev][RD][NewDamart] Sprint 18 | [Dev][RD][NewDamart] Sprint 19
Story | RDNDA-9 | 38247 | [DEV][RD][TDM] Create client middleware | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 07/Jan/26 5:19 PM | 24/Feb/26 9:59 AM |  | 3 | [5 empty] | มาจาก Sprint 18 | Ready to Staging |  | [Dev][RD][NewDamart] Sprint 16 | [Dev][RD][NewDamart] Sprint 17 | [Dev][RD][NewDamart] Sprint 18 | [Dev][RD][NewDamart] Sprint 19
Story | RDNDA-8 | 38246 | [DEV][RD][TDM] Create Push to Kinesis Consumer | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 07/Jan/26 5:19 PM | 05/Mar/26 3:14 PM | 21/Jan/26 12:00 AM | 3 |  |  |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 28800 | [Dev][RD][NewDamart] Sprint 16 | [Dev][RD][NewDamart] Sprint 17 | [Dev][RD][NewDamart] Sprint 18 | [Dev][RD][NewDamart] Sprint 19
Story | RDNDA-6 | 38244 | [DEV][RD][TDM] Create generic transactions endpoint | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 07/Jan/26 5:17 PM | 24/Feb/26 9:59 AM |  | 5 |  |  |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 86400 | [Dev][RD][NewDamart] Sprint 16 | [Dev][RD][NewDamart] Sprint 17 | [Dev][RD][NewDamart] Sprint 18 | [Dev][RD][NewDamart] Sprint 19
Story | RDNDA-5 | 38243 | [DEV][RD][TDM] Initial project | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 07/Jan/26 5:16 PM | 24/Feb/26 9:59 AM |  | 5 | No-QA | ThanaDataMart |  |  |  | มาจาก Sprint 18 | Ready to Staging |  | [Dev][RD][NewDamart] Sprint 16 | [Dev][RD][NewDamart] Sprint 17 | [Dev][RD][NewDamart] Sprint 18 | [Dev][RD][NewDamart] Sprint 19
Story | DPWP-16 | 38207 | [Dev][RD][PWP] Implement cronjob to process payment expiration | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 07/Jan/26 3:26 PM | 20/Feb/26 11:19 AM |  | 5 | [5 empty] | มาจาก Sprint 18 | Ready to Staging |  | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Story | DRST-6 | 38163 | [Dev][RD][Terminate VIMI][VoucherValidator] Refactor APIs to remove dependency on MVP Phase 1 source | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready to Staging |  | 07/Jan/26 11:12 AM | 05/Mar/26 2:14 PM | 10/Feb/26 12:00 AM | 3 |  |  |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 28800 | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19
Story | DRST-5 | 38162 | [Dev][RD][Terminate VIMI][MerchantAPI] Refactor APIs to remove dependency on MVP Phase 1 source | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready to Staging |  | 07/Jan/26 11:12 AM | 05/Mar/26 2:14 PM | 11/Feb/26 12:00 AM | 3 |  |  |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 28800 | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19
Story | DPWP-15 | 38057 | [Dev][RD][BFF] Create API to process payment after customer confirm payment | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Jan/26 6:58 PM | 04/Mar/26 11:32 AM | 03/Feb/26 12:00 AM | 5 |  |  |  |  | 0 | มาจาก Sprint 18 | Ready To Test | 43200 | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Story | DPWP-14 | 38056 | [Dev][RD][BFF] Create API to process payment after customer scans QR | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Jan/26 6:57 PM | 04/Mar/26 11:24 AM |  | 5 |  |  |  |  | 0 | มาจาก Sprint 18 | Ready To Test | 72000 | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Story | DPWP-13 | 38055 | [Dev][RD][PWP] Create API to refund transaction and reverse points | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Jan/26 6:55 PM | 04/Mar/26 11:35 AM |  | 5 |  |  |  |  | 0 | มาจาก Sprint 18 | Ready To Test | 57600 | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Story | DPWP-12 | 38054 | [Dev][RD][PWP] Create API to mark transaction as completed after merchant confirms order | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Jan/26 6:52 PM | 04/Mar/26 11:34 AM |  | 5 |  |  |  |  | 0 | มาจาก Sprint 18 | Ready To Test | 86400 | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Story | DPWP-11 | 38053 | [Dev][RD][PWP] Create API to process payment after customer confirm payment | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Jan/26 6:47 PM | 04/Mar/26 11:31 AM |  | 8 |  |  |  |  | 0 | มาจาก Sprint 18 | Ready To Test | 86400 | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Story | DPWP-10 | 37976 | [Dev][RD][PWP] Create API to retrieve a transaction information | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Jan/26 11:10 AM | 04/Mar/26 11:26 AM | 20/Jan/26 12:00 AM | 3 |  |  |  |  | 0 | มาจาก Sprint 18 | Ready To Test | 21600 | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Story | DPWP-9 | 37926 | [Dev][RD][PWP] Create API to process payment after customer scans QR | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Jan/26 6:06 PM | 04/Mar/26 11:22 AM |  | 5 | [5 empty] | มาจาก Sprint 18 | Ready to Staging |  | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Story | DPWP-8 | 37906 | [Dev][RD][PWP] Create API to create a new Point Payment transaction | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 05/Jan/26 1:25 PM | 05/Mar/26 3:48 PM | 19/Jan/26 12:00 AM | 8 | pay-with-point-api |  |  |  | 0 | มาจาก Sprint 18 | Ready To Test | 86400 | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Story | DRST-7 | 36975 | [Dev][RD][Terminate VIMI] Refactor TXN Report API and Report Summary API to remove dependency on MVP Phase 1 report source | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready to Staging |  | 23/Dec/25 12:23 PM | 05/Mar/26 2:14 PM | 30/Dec/25 12:00 AM | 3 |  |  |  |  | 0 | มาจาก Sprint 18 | Ready to Staging | 28800 | [Dev][All Project] Sprint 15 | [Dev][All Project] Sprint 16 | [Dev RD][VIMI Termi] Sprint 17 | [Dev RD][VIMI Termi] Sprint 18 | [Dev RD][VIMI Termi] Sprint 19
Story | DEVRDSUP-319 | 36248 | [SUP-382][SUB] Request to make a package TXN with “allocating coupon“ to “fail“ | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | To Do |  | 16/Dec/25 5:55 PM | 23/Feb/26 4:25 PM |  |  | BURequest | sub |  |  |  | มาจาก Sprint 18 | To Do |  | [Dev][All Project] Sprint 18 | [Dev][All Project] Sprint 19
Bug | DEVRDSUP-300 | 35666 | [SUP-363][Club][HR Solution] Club tier order can't be updated | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Closed |  | 11/Dec/25 12:23 AM | 24/Feb/26 12:59 PM | 25/Dec/25 12:00 AM |  | hr-solution | mid-sprint |  |  |  | มาจาก Sprint 18 | Resolved |  | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 18 | [Dev][All Project] Sprint 19
Bug | DEVRDSUP-299 | 35664 | [SUP-362][SUB] Package TXNs is "Expired" and payment was completed but SUB TXN report shows payment fail and last TXN update was change on Nov while TXN was expired since Aug. | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Low | Closed |  | 10/Dec/25 5:36 PM | 24/Feb/26 1:08 PM | 08/Jan/26 12:00 AM |  | data | mid-sprint | prod-issue | sub |  | มาจาก Sprint 18 | Resolved |  | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15 | [Dev][All Project] Sprint 18 | [Dev][All Project] Sprint 19

## Summarize Sprint 18
Column 1 | Total Stories Point | Total Manhour | Point Done | Manhour Done | Note
9 Feb - 20 Feb
Dev Resource Available | 12 | 406
Meeting Planned |  |  |  |  | Ref
Additional Meeting |  |  |  |  | Ref
Deployment |  | 2 |  |  | 2 ครั้ง 1. 3 คน 2. 2 คน
Development Sprint Total | 321 | 260.92 | 87 | 23.92
Ad-hoc Mid Sprint | 0 | 0 | 0 | 2 | 0 tasks
Requirement changes after refinement? | 0 |  | 0 | 0 | 0 tasks
Aek | 8 | 3.75 | 7 | 3.75
A | 27 | 56 | 6 | 10
Aom | 34 | 0.17 | 14 | 0.17
Zan | 21 | 0 | 11 | 0
Mai | 44 | 46 | 2 | 0
Mac | 54 | 81 | 6 | 8
Mos | 49 | 48 | 1 | 0
Jack | 39 | 0 | 39 | 0
Nim | 37 | 26 | 1 | 2
Arm | 5 | 0 | 0 | 0
| System Architech |  |  |  | Permanent Dev. |  |  | Outsources
Projects (Stories Points) | Aek | Zan | Aom | Jack | A | Art | Mai | Kae | Mac | Nim | Mos | Arm
Das Haus - Thana City & Das Haus | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0
E-commerce 1.1. E-Commerce x Shopify Plus 1.2. Shopify:Snackmaker 1.3. Shopify: Turtle Delivery 1.4. Shopify: Turtle Delivery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CleverTap - MKT Automation Tool | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Adjust Integration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Adhoc - Non-Epics - Turtle Display club tier on POS - Data Mart Migration | 1 | 5 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
Support Incidents | 4 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0
| System Architech |  |  |  | Permanent Dev. |  |  | Outsources
Projects (Manhour) | Aek | Zan | Aom | Jack | A | Art | Mai | Kae | Mac | Nim | Mos | Arm
Das Haus - Thana City & Das Haus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0
E-commerce 1.1. E-Commerce x Shopify Plus 1.2. Shopify:Snackmaker 1.3. Shopify: Turtle Delivery 1.4. Shopify: Turtle Delivery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CleverTap - MKT Automation Tool | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Adjust Integration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Adhoc - Non-Epics - Turtle Display club tier on POS - Data Mart Migration | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Support Incidents | 1.5 | 0 | 0.17 | 0 | 0 | 0 | 0 | 0 | 8 | 2 | 0 | 0

## Sprint 18
Issue Type | Issue key | Issue id | Summary | Assignee | Assignee Id | Reporter | Reporter Id | Priority | Status | Resolution | Created | Updated | Due date | Custom field (Story Points) | Labels | Labels | Labels | Labels | Original estimate | Sprint Movement | Sprint 17 | Note | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint
Story | RDAPS-420 | 44296 | [DEV][RD][SSO Backoffice] Request access to SSO back office for Support My Rabbit project | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 20/Feb/26 9:04 AM | 20/Feb/26 9:05 AM |  | 1 |  |  |  |  | 900 |  |  |  | [Dev][All Project] Sprint 18
Sub-task | DPE-214 | 44196 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 19/Feb/26 3:40 PM | 19/Feb/26 3:40 PM | [10 empty] | [Dev][RD][New PE] Sprint 18
Sub-task | DPE-213 | 44194 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Review |  | 19/Feb/26 3:40 PM | 19/Feb/26 3:41 PM | [10 empty] | [Dev][RD][New PE] Sprint 18
Sub-task | DPE-212 | 44192 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 19/Feb/26 3:40 PM | 19/Feb/26 3:40 PM | [10 empty] | [Dev][RD][New PE] Sprint 18
Sub-task | DPE-211 | 44190 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Review |  | 19/Feb/26 3:40 PM | 19/Feb/26 3:41 PM | [10 empty] | [Dev][RD][New PE] Sprint 18
Story | DPE-207 | 44011 | [Dev][RD][SSO-User] Reward Add Card | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 18/Feb/26 3:42 PM | 19/Feb/26 10:38 AM | [10 empty] | [Dev][RD][New PE] Sprint 18
Story | DPE-206 | 44010 | [Dev][RD][SSO-User] Backoffice Sync Cards | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 18/Feb/26 3:42 PM | 19/Feb/26 10:38 AM | [10 empty] | [Dev][RD][New PE] Sprint 18
Task | DM-188 | 44007 | [AWS][RD][DEV] RR BackOffice Update query lat,lon with compatible with MySQL | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 18/Feb/26 2:28 PM | 18/Feb/26 2:29 PM | 19/Feb/26 12:00 AM | 1 | No-QA |  |  |  | 7200 |  |  |  | [Dev][RD][New PE] Sprint 18
Story | DEVRDSUP-458 | 43840 | [SUP-538][Turtle] Request to export logs for SMS delay case analysis for super turtle. | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 16/Feb/26 7:20 PM | 20/Feb/26 9:09 AM |  | 1 | turtle |  |  |  | 1800 |  |  |  | [Dev][All Project] Sprint 18
Task | DM-186 | 43600 | [DEV][RD][AWSTH] Merchant API Cleanup Unused Code After Migration #2 | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 15/Feb/26 11:55 AM | 15/Feb/26 12:36 PM | 20/Feb/26 12:00 AM | 1 | No-QA | [7 empty] | [Dev][RD][AWS] Sprint 18
Story | DPE-190 | 43427 | [Dev][RD][SSO-User] Offline register | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 13/Feb/26 1:03 PM | 19/Feb/26 2:28 PM |  | 2 | [8 empty] | [Dev][RD][New PE] Sprint 18
Story | DEVRDSUP-451 | 43388 | [SUP-533][SUB] Receipt is not generated after SUB transaction is made (13 FEB 2026) | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Thanakrit Chanthaworn | 712020:3fc982cb-c268-4f1d-9265-d3dd8fb08304 | Medium | Done |  | 13/Feb/26 11:08 AM | 13/Feb/26 11:17 AM | 13/Feb/26 12:00 AM | 1 | bts | BURequest | sub |  | 600 |  |  |  | [Dev][All Project] Sprint 18
Bug | RDAPS-418 | 43353 | [DEV][RD][HRS] Import member status not change when completed both of instant and scheduled | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Pass : Waiting for deployment |  | 13/Feb/26 10:02 AM | 19/Feb/26 4:29 PM | [10 empty] | [Dev][All Project] Sprint 18
Bug | DEVRDSUP-450 | 43352 | [SUP-531][HRSolution] HR solution Reward distribution feature, import col mismatched with template. | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Fixing |  | 13/Feb/26 9:51 AM | 20/Feb/26 10:09 AM | 03/Mar/26 12:00 AM | [9 empty] | [Dev][All Project] Sprint 18
Story | DEVRDSUP-445 | 43312 | [SUP-526]Urgent! [SUB] CS- 20260200024941/ PromptPay// ซื้อแล้วไม่ได้รับแพ็กเกจ สถานะ Payment Gateway Dashboard เป็น Cancelled | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 12/Feb/26 4:58 PM | 13/Feb/26 11:21 AM |  |  | init-pack | sub | [6 empty] | [Dev][All Project] Sprint 18
Sub-task | DPE-189 | 43275 | [QA] Test execution | THUNDER(QA): PAWICH | 712020:83ff944e-9677-453f-b053-40e92520d905 | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 12/Feb/26 2:47 PM | 12/Feb/26 2:47 PM | [10 empty] | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18
Sub-task | DPE-188 | 43273 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Review |  | 12/Feb/26 2:46 PM | 12/Feb/26 2:47 PM | [10 empty] | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18
Sub-task | DPE-187 | 43123 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 12/Feb/26 10:49 AM | 12/Feb/26 10:49 AM | [10 empty] | [Dev][RD][New PE] Sprint 18
Sub-task | DPE-186 | 43122 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 12/Feb/26 10:49 AM | 12/Feb/26 10:49 AM | [10 empty] | [Dev][RD][New PE] Sprint 18
Sub-task | DPE-185 | 43121 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 12/Feb/26 10:49 AM | 12/Feb/26 10:49 AM | [10 empty] | [Dev][RD][New PE] Sprint 18
Sub-task | DPE-184 | 43120 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 12/Feb/26 10:49 AM | 12/Feb/26 10:49 AM | [10 empty] | [Dev][RD][New PE] Sprint 18
Sub-task | DPE-183 | 43119 | [QA] Test execution | THUNDER(QA): PAWICH | 712020:83ff944e-9677-453f-b053-40e92520d905 | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 12/Feb/26 10:48 AM | 12/Feb/26 2:47 PM | [10 empty] | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18
Sub-task | DPE-182 | 43118 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Review |  | 12/Feb/26 10:48 AM | 12/Feb/26 2:46 PM | [10 empty] | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18
Sub-task | DPE-181 | 43117 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 12/Feb/26 10:47 AM | 12/Feb/26 10:47 AM | [10 empty] | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18
Sub-task | DPE-180 | 43116 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Progress |  | 12/Feb/26 10:47 AM | 12/Feb/26 2:49 PM | [10 empty] | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18
Sub-task | DPE-179 | 43115 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 12/Feb/26 10:46 AM | 12/Feb/26 10:47 AM | [10 empty] | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18
Sub-task | DPE-178 | 43114 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Progress |  | 12/Feb/26 10:46 AM | 12/Feb/26 10:47 AM | [10 empty] | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18
Story | RDNDA-30 | 43076 | [DEV][RD][TDM][SA] Update API doc for support idempotency | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 11/Feb/26 6:53 PM | 11/Feb/26 6:53 PM |  | 1 | [8 empty] | [Dev][RD][NewDamart] Sprint 18
Story | DRST-19 | 43074 | [DEV][RD][SA] Partner instruction manual | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 11/Feb/26 6:49 PM | 18/Feb/26 4:27 PM |  | 1 |  |  |  |  | 7200 |  |  |  | [Dev RD][VIMI Termi] Sprint 18
Story | RDTHANA-432 | 42992 | [DEV][RD][TDM] Create cronjob for polling sale transaction | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 11/Feb/26 3:09 PM | 19/Feb/26 9:09 PM | 19/Feb/26 12:00 AM | 5 |  |  |  |  | 57600 |  |  |  | [Dev][RD][Thana] Sprint 18
Epic | RDTHANA-431 | 42991 | Lighspeed Polling |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 11/Feb/26 3:07 PM | 11/Feb/26 7:00 PM | [10 empty] | [Dev][RD][Thana] Sprint 18
Story | RDTHANA-430 | 42990 | [DEV][RD][TDM] Create LighspeedService for getToken | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 11/Feb/26 2:57 PM | 19/Feb/26 9:09 PM | 13/Feb/26 12:00 AM | 5 |  |  |  |  | 57600 |  |  |  | [Dev][RD][Thana] Sprint 18
Story | DRST-17 | 42821 | [DEV][RD][BOF] Create command to migrate data from VIMI database to Rabbit CMS database | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 11/Feb/26 10:17 AM | 20/Feb/26 9:29 AM |  | 8 | [8 empty] | [Dev RD][VIMI Termi] Sprint 18
Story | RDAPS-408 | 42576 | [DEV][RD][HRS] Increase maximum and response time for API | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 10/Feb/26 11:08 AM | 19/Feb/26 9:30 PM |  | 3 | [8 empty] | [Dev][All Project] Sprint 18
Story | DPE-174 | 42542 | [Dev][RD] SSO new enviroment for non-prod | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | In Progress |  | 10/Feb/26 10:29 AM | 19/Feb/26 11:24 AM |  | 2 | No-QA |  |  |  | 7200 |  |  |  | [Dev][RD][New PE] Sprint 18
Story | DRST-16 | 42509 | [DEV][RD][SA] Design and mapping earn content api | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Progress |  | 10/Feb/26 10:04 AM | 20/Feb/26 9:41 AM |  | 5 | [8 empty] | [Dev RD][VIMI Termi] Sprint 18
Story | DRST-14 | 42267 | [DEV][RD][Rabbit CMS API] Create endpoint for get earn content | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 08/Feb/26 9:54 PM | 20/Feb/26 9:22 AM |  | 5 | [8 empty] | [Dev RD][VIMI Termi] Sprint 18
Story | DRST-13 | 42266 | [DEV][RD][BOF] Create feature structure for earn content management | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 08/Feb/26 9:28 PM | 19/Feb/26 2:07 PM | 27/Feb/26 12:00 AM | 3 | [8 empty] | [Dev RD][VIMI Termi] Sprint 18
Story | DRST-12 | 42265 | [DEV][RD][BOF] Create edit earn form page | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 08/Feb/26 9:26 PM | 19/Feb/26 2:07 PM | 27/Feb/26 12:00 AM | 3 | [8 empty] | [Dev RD][VIMI Termi] Sprint 18
Story | DRST-11 | 42264 | [DEV][RD][BOF] Implement create form for earn content | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 08/Feb/26 9:25 PM | 19/Feb/26 2:07 PM | 27/Feb/26 12:00 AM | 3 | [8 empty] | [Dev RD][VIMI Termi] Sprint 18
Story | DRST-10 | 42263 | [DEV][RD][BOF] Create earn content index page | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 08/Feb/26 9:25 PM | 19/Feb/26 2:07 PM | 27/Feb/26 12:00 AM | 3 | [8 empty] | [Dev RD][VIMI Termi] Sprint 18
Story | DRST-8 | 42261 | [DEV][RD][CMS API] Create migration for earn contents | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 08/Feb/26 9:01 PM | 19/Feb/26 2:07 PM | 09/Feb/26 12:00 AM | 1 |  |  |  |  | 7200 |  |  |  | [Dev RD][VIMI Termi] Sprint 18
Story | DPE-168 | 42225 | [Dev][RD][PE Middleware] APIs Specification | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Done |  | 07/Feb/26 7:26 PM | 20/Feb/26 10:08 AM |  | 13 | Document | No-QA | [6 empty] | [Dev][RD][New PE] Sprint 18
Story | DPE-164 | 42221 | [Dev][RD][Blocker] Pending final solution – awaiting alignment with DA and CleverTap technical teams |  |  | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Highest | Done |  | 07/Feb/26 4:05 PM | 18/Feb/26 2:59 PM | [10 empty] | [Dev][RD][New PE] Sprint 18
Story | DPE-163 | 42220 | [Dev][RD][Blocker] Business dependency: CleverTap sandbox required for POC & integration testing | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Highest | Done |  | 07/Feb/26 4:00 PM | 13/Feb/26 1:16 PM | 11/Feb/26 12:00 AM | [9 empty] | [Dev][RD][New PE] Sprint 18
Story | DPE-161 | 42218 | [Dev][RD][Blocker] Final solution for PE |  |  | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Highest | Done |  | 07/Feb/26 3:43 PM | 18/Feb/26 2:59 PM |  |  | No-QA | [7 empty] | [Dev][RD][New PE] Sprint 18
Story | DPE-153 | 42178 | [Dev][RD][SSO-User] [POC]POC – Internal Trader ID generation without creating member in Point Engine | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 07/Feb/26 8:25 AM | 12/Feb/26 10:51 AM | 10/Feb/26 12:00 AM | 2 | Document | No-QA |  |  | 14400 |  |  |  | [Dev][RD][New PE] Sprint 18
Story | DPE-147 | 42134 | [Dev][RD][SSO-User] WEB verify phone | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 06/Feb/26 6:37 PM | 19/Feb/26 4:29 PM |  | 1 | sso-user |  |  |  | 3600 |  |  |  | [Dev][RD][New PE] Sprint 18
Story | DPE-146 | 42133 | [Dev][RD][SSO-User] WEB update avatar | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 06/Feb/26 6:37 PM | 19/Feb/26 4:29 PM |  | 1 | sso-user |  |  |  | 7200 |  |  |  | [Dev][RD][New PE] Sprint 18
Story | DPE-145 | 42132 | [Dev][RD][SSO-User] WEB verify user | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 06/Feb/26 6:37 PM | 19/Feb/26 4:29 PM |  | 2 | sso-user |  |  |  | 10800 |  |  |  | [Dev][RD][New PE] Sprint 18
Story | DPE-144 | 42131 | [Dev][RD][SSO-User] WEB remove card by card_id | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 06/Feb/26 6:37 PM | 19/Feb/26 4:28 PM |  | 1 | sso-user |  |  |  | 7200 |  |  |  | [Dev][RD][New PE] Sprint 18
Story | DPE-143 | 42130 | [Dev][RD][SSO-User] WEB move card | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 06/Feb/26 6:36 PM | 19/Feb/26 4:28 PM |  | 1 | sso-user | [7 empty] | [Dev][RD][New PE] Sprint 18
Story | DPE-142 | 42129 | [Dev][RD][SSO-User] WEB add card | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 06/Feb/26 6:36 PM | 19/Feb/26 4:28 PM |  | 1 | sso-user |  |  |  | 7200 |  |  |  | [Dev][RD][New PE] Sprint 18
Story | DPE-141 | 42128 | [Dev][RD][SSO-User] WEB update profile by ID | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 06/Feb/26 6:36 PM | 19/Feb/26 4:29 PM | 12/Feb/26 12:00 AM | 2 | sso-user |  |  |  | 14400 |  |  |  | [Dev][RD][New PE] Sprint 18
Bug | DEVRDSUP-423 | 42124 | [SUP-497][Binding] #20251200022494 Binding RRxLP ข้อมูลเวลาไม่ตรงกัน | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Enhancement |  | 06/Feb/26 6:10 PM | 19/Feb/26 10:44 AM |  | 1 | lp | pdpa | [6 empty] | [Dev][All Project] Sprint 18
Story | DEVRDSUP-422 | 42116 | [SUP-495][RR Account] CS- 20260200024747 Kindly check 1 Rabbit Card Wallet but has 2 SSO ID [Member ID: 32834438, Member ID 32834826] SN 0884013063815 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 06/Feb/26 3:20 PM | 18/Feb/26 3:56 PM |  | 1 |  |  |  |  | 1800 |  |  |  | [Dev][All Project] Sprint 18
Bug | DEVRDSUP-421 | 42045 | [SUP-479]Link Search and link # in the pop up is not redirect | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Open |  | 06/Feb/26 11:33 AM | 09/Feb/26 9:40 AM | 23/Feb/26 12:00 AM |  | deeplink | [7 empty] | [Dev][All Project] Sprint 18
Story | DEVRDSUP-417 | 41823 | [SUP-492][RR Account] CS- 20260200024576 Kindly check 1 Rabbit Card Wallet but has 2 SSO ID | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Thanakrit Chanthaworn | 712020:3fc982cb-c268-4f1d-9265-d3dd8fb08304 | Medium | Done |  | 05/Feb/26 11:36 AM | 18/Feb/26 3:56 PM |  | 1 |  |  |  |  | 1800 |  |  |  | [Dev][All Project] Sprint 18
Story | RDNDA-27 | 41770 | [DEV][RD][TDM] Create script for check missing ENV | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 05/Feb/26 9:37 AM | 09/Feb/26 11:37 AM | [10 empty] | [Dev][RD][NewDamart] Sprint 17 | [Dev][RD][NewDamart] Sprint 18
Story | DPE-74 | 41523 | [Dev][RD][SSO-User] Remove SSO-Thor API Integration | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | In Progress |  | 04/Feb/26 10:13 AM | 19/Feb/26 4:30 PM |  | 5 | No-QA | sso-user |  |  | 57600 |  |  |  | [Dev][RD][New PE] Sprint 18
Story | DPE-73 | 41521 | [Dev][RD][SSO-User] CRM remove card | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 04/Feb/26 10:13 AM | 19/Feb/26 4:29 PM |  | 2 | sso-user |  |  |  | 14400 |  |  |  | [Dev][RD][New PE] Sprint 18
Story | DPE-72 | 41519 | [Dev][RD][SSO-User] CRM add card | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 04/Feb/26 10:13 AM | 19/Feb/26 4:29 PM |  | 2 | sso-user |  |  |  | 14400 |  |  |  | [Dev][RD][New PE] Sprint 18
Story | DPE-71 | 41517 | [Dev][RD][SSO-User] BSS Verify email | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 04/Feb/26 10:10 AM | 19/Feb/26 4:29 PM | 10/Feb/26 12:00 AM | 1 | sso-user |  |  |  | 7200 |  |  |  | [Dev][RD][New PE] Sprint 18
Story | DPE-70 | 41515 | [Dev][RD][SSO-User] BSS Verify phone | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 04/Feb/26 9:49 AM | 19/Feb/26 4:29 PM |  | 1 | sso-user |  |  |  | 7200 |  |  |  | [Dev][RD][New PE] Sprint 18
Story | DPE-69 | 41513 | [Dev][RD][SSO-User] BSS sync member to RR | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 04/Feb/26 9:49 AM | 19/Feb/26 4:28 PM |  | 2 | sso-user | [7 empty] | [Dev][RD][New PE] Sprint 18
Story | DPE-68 | 41511 | [Dev][RD][SSO-User] Rewards add card | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 04/Feb/26 9:49 AM | 19/Feb/26 4:29 PM | 10/Feb/26 12:00 AM | 1 | sso-user |  |  |  | 7200 |  |  |  | [Dev][RD][New PE] Sprint 18
Story | DPE-62 | 41461 | [Dev][RD][SSO-User] Update a registration source | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 03/Feb/26 8:12 PM | 19/Feb/26 4:29 PM |  | 1 | sso-user |  |  |  | 0 | มาจาก Sprint 17 | Ready to Staging | 7200 | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18
Story | DPE-61 | 41459 | [Dev][RD][SSO-User] Backoffice Create a registration source | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 03/Feb/26 7:43 PM | 19/Feb/26 4:29 PM |  | 1 | sso-user |  |  |  | 0 | มาจาก Sprint 17 | Ready to Staging | 7200 | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18
Story | DPE-60 | 41457 | [Dev][RD][SSO-User] Backoffice update user | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 03/Feb/26 7:43 PM | 19/Feb/26 4:29 PM | 06/Feb/26 12:00 AM | 2 | sso-user |  |  |  | 14400 | มาจาก Sprint 17 | To Do |  | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18
Story | DPE-59 | 41455 | [Dev][RD][SSO-User] Backoffice Remove card | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 03/Feb/26 7:43 PM | 19/Feb/26 4:29 PM |  | 2 | sso-user |  |  |  | 14400 |  |  |  | [Dev][RD][New PE] Sprint 18
Story | DPE-58 | 41453 | [Dev][RD][SSO-User] Backoffice Add card | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 03/Feb/26 7:43 PM | 19/Feb/26 4:29 PM |  | 2 | sso-user |  |  |  | 14400 |  |  |  | [Dev][RD][New PE] Sprint 18
Story | DPE-56 | 41449 | [Dev][RD][SSO-User] Update email | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 03/Feb/26 7:42 PM | 19/Feb/26 4:29 PM |  | 2 | sso-user |  |  |  | 14400 |  |  |  | [Dev][RD][New PE] Sprint 18
Story | DPE-55 | 41447 | [Dev][RD][SSO-User] Verify phone | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 03/Feb/26 7:42 PM | 19/Feb/26 4:29 PM |  | 2 | sso-user |  |  |  | 3600 |  |  |  | [Dev][RD][New PE] Sprint 18
Story | DPE-54 | 41445 | [Dev][RD][SSO-User] Verify email | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 03/Feb/26 7:41 PM | 19/Feb/26 4:29 PM |  | 2 | sso-user |  |  |  | 3600 |  |  |  | [Dev][RD][New PE] Sprint 18
Story | DPE-53 | 41443 | [Dev][RD][PE Middleware][Infra] Request new project for point-engine-middleware | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Highest | Done |  | 03/Feb/26 7:41 PM | 20/Feb/26 9:11 AM |  | 5 | [8 empty] | [Dev][RD][New PE] Sprint 18
Story | DPE-52 | 41441 | [Dev][RD][PE Middleware] Database Design | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Highest | Done |  | 03/Feb/26 7:41 PM | 20/Feb/26 10:08 AM |  | 8 | Document | No-QA | [6 empty] | [Dev][RD][New PE] Sprint 18
Story | DPE-50 | 41437 | [Dev][RD][SSO-User] Activate user by phone | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 03/Feb/26 7:41 PM | 19/Feb/26 4:29 PM |  | 2 | sso-user |  |  |  | 7200 |  |  |  | [Dev][RD][New PE] Sprint 18
Story | DPE-49 | 41435 | [Dev][RD][SSO-User] Rewards Verify phone | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 03/Feb/26 7:41 PM | 19/Feb/26 4:28 PM |  | 2 | sso-user |  |  |  | 7200 |  |  |  | [Dev][RD][New PE] Sprint 18
Story | DPE-48 | 41433 | [Dev][RD][SSO-User] Update rewards user | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 03/Feb/26 7:40 PM | 19/Feb/26 4:28 PM | 05/Feb/26 12:00 AM | 3 | sso-user |  |  |  | 0 | มาจาก Sprint 17 | In Review | 28800 | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18
Story | DPE-47 | 41431 | [Dev][RD][SSO-User] Create rewards user | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 03/Feb/26 7:40 PM | 19/Feb/26 4:28 PM | 12/Feb/26 12:00 AM | 3 | sso-user |  |  |  | 28800 |  |  |  | [Dev][RD][New PE] Sprint 18
Story | DPE-46 | 41429 | [Dev][RD][SSO-User] Create user profile | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 03/Feb/26 7:40 PM | 19/Feb/26 4:28 PM | 11/Feb/26 12:00 AM | 3 | sso-user |  |  |  | 28800 |  |  |  | [Dev][RD][New PE] Sprint 18
Bug | DEVRDSUP-406 | 41284 | [SUP-481][Urgent] Turtle Auto push coupon failed | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Low | Resolved |  | 03/Feb/26 11:08 AM | 09/Feb/26 10:05 AM | 25/Feb/26 12:00 AM |  | CleverTap | prod-issue | [6 empty] | [Dev][All Project] Sprint 18
Story | RDNDA-23 | 41019 | [DEV][RD][TDM][POC] connect and record data to DynamoDB | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 30/Jan/26 9:25 AM | 09/Feb/26 11:37 AM | [6 empty] | 28800 |  |  |  | [Dev][RD][NewDamart] Sprint 17 | [Dev][RD][NewDamart] Sprint 18
Sub-task | DPWP-39 | 40985 | [QA] Test execution process payment expiration (transaction status = 'expired') | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 29/Jan/26 7:53 PM | 29/Jan/26 7:56 PM | [7 empty] | มาจาก Sprint 17 | To Do |  | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Sub-task | DPWP-38 | 40983 | [QA] Test execution process payment after customer confirm payment with [BFF] API | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 29/Jan/26 7:52 PM | 29/Jan/26 7:52 PM | [7 empty] | มาจาก Sprint 17 | To Do |  | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Sub-task | DPWP-37 | 40981 | [QA] Test execution process payment after customer scans QR with [BFF] API (On Staging) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 29/Jan/26 7:50 PM | 29/Jan/26 7:56 PM | [7 empty] | มาจาก Sprint 17 | To Do |  | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Sub-task | DPWP-36 | 40979 | [QA] Test execution refund transaction and reverse points with API (On Staging) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 29/Jan/26 7:49 PM | 29/Jan/26 7:55 PM | [7 empty] | มาจาก Sprint 17 | To Do |  | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Sub-task | DPWP-35 | 40977 | [QA] Test execution mark transaction as completed after merchant confirms order with API (On Staging) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 29/Jan/26 7:47 PM | 29/Jan/26 7:48 PM | [7 empty] | มาจาก Sprint 17 | To Do |  | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Sub-task | DPWP-34 | 40975 | [QA] Test execution process payment after customer confirm payment with API (On Staging) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 29/Jan/26 7:46 PM | 29/Jan/26 7:48 PM | [7 empty] | มาจาก Sprint 17 | To Do |  | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Sub-task | DPWP-33 | 40662 | [QA] Create test case process payment expiration (transaction status = 'expired') | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 28/Jan/26 10:36 AM | 28/Jan/26 10:36 AM | [7 empty] | มาจาก Sprint 17 | To Do |  | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Sub-task | DPWP-32 | 40660 | [QA] Create test case [BFF] API to process payment after customer confirm payment | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 28/Jan/26 10:34 AM | 29/Jan/26 7:52 PM | [7 empty] | มาจาก Sprint 17 | To Do |  | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Sub-task | DPWP-31 | 40657 | [QA] Create test case [BFF] API to process payment after customer scans QR | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 28/Jan/26 10:22 AM | 29/Jan/26 7:50 PM | [7 empty] | มาจาก Sprint 17 | To Do |  | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Story | DPE-45 | 40623 | [Dev][RD] Define target architecture for New Point Engine | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Highest | In Progress |  | 27/Jan/26 7:43 PM | 11/Feb/26 1:38 PM |  | 13 | No-QA | [7 empty] | [Dev][RD][New PE] Sprint 18
Sub-task | DPWP-30 | 40620 | [QA] Test execution retrieve a transaction information with API (On Staging) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 27/Jan/26 5:15 PM | 29/Jan/26 7:44 PM | [7 empty] | มาจาก Sprint 17 | To Do |  | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Sub-task | DPWP-29 | 40618 | [QA] Test execution process payment after customer scans QR with API (On Staging) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 27/Jan/26 5:03 PM | 29/Jan/26 7:42 PM | [7 empty] | มาจาก Sprint 17 | To Do |  | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Sub-task | DPWP-28 | 40616 | [QA] Test execution create a new Point Payment transaction with API (On staging) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 27/Jan/26 5:01 PM | 29/Jan/26 4:39 PM | [7 empty] | มาจาก Sprint 17 | To Do |  | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Story | DM-182 | 40478 | [DEV][RD][AWSTH] Verify API Gateway on dev environment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Lowest | In Progress |  | 27/Jan/26 10:08 AM | 19/Feb/26 10:06 PM |  | 5 | No-QA |  |  |  | 43200 | มาจาก Sprint 17 | In Progress | 86400 -> 43200 | [Dev][RD][AWS] Sprint 17 | [Dev][RD][AWS] Sprint 18
Story | DPE-43 | 40420 | [Dev][RD][PE-MIGRATION][POC] Debit Loyalty Wallet (Redeem Points) | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 26/Jan/26 2:32 PM | 20/Feb/26 10:07 AM |  | 3 | No-QA | POC | [6 empty] | [Dev][RD][New PE] Sprint 18
Story | DPE-42 | 40419 | [Dev][RD][PE-MIGRATION][POC] Credit Loyalty Wallet (Earn Points) | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 26/Jan/26 2:31 PM | 20/Feb/26 10:07 AM |  | 5 | No-QA | POC | [6 empty] | [Dev][RD][New PE] Sprint 18
Story | DPE-41 | 40417 | [Dev][RD][PE-MIGRATION][POC] Get Wallet Transactions | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 26/Jan/26 2:30 PM | 20/Feb/26 10:06 AM |  | 5 | No-QA | POC | [6 empty] | [Dev][RD][New PE] Sprint 18
Story | DPE-40 | 40416 | [Dev][RD][PE-MIGRATION][POC] Get Loyalty Wallet Details | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 26/Jan/26 2:29 PM | 20/Feb/26 10:06 AM |  | 5 | No-QA | POC | [6 empty] | [Dev][RD][New PE] Sprint 18
Story | RDNDA-22 | 40327 | [DEV][RD][TDM] Enhance Kinesis stream name to dynamics config | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 25/Jan/26 10:47 PM | 09/Feb/26 11:37 AM | 04/Feb/26 12:00 AM | 2 |  |  |  |  | 10800 |  |  |  | [Dev][RD][NewDamart] Sprint 17 | [Dev][RD][NewDamart] Sprint 18
Story | RDNDA-21 | 40326 | [DEV][RD][TDM] Enhance generic API with new data and validate with omit | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 25/Jan/26 10:31 PM | 09/Feb/26 11:37 AM | 04/Feb/26 12:00 AM | 2 |  |  |  |  | 14400 |  |  |  | [Dev][RD][NewDamart] Sprint 17 | [Dev][RD][NewDamart] Sprint 18
Story | DPE-16 | 40269 | [Dev][RD][PE-MIGRATION][IMPACT] Assess impact for Point Engine Proxy | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 25/Jan/26 8:48 AM | 11/Feb/26 1:40 PM |  | 1 | No-QA |  |  |  |  | มาจาก Sprint 17 | In Review |  | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18
Story | DPE-12 | 40265 | [Dev][RD][PE-MIGRATION][IMPACT] Assess impact for RR Backoffice | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 25/Jan/26 8:48 AM | 13/Feb/26 1:16 PM |  | 1 | No-QA |  |  |  | 0 | มาจาก Sprint 17 | In Review | 28800 | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18
Story | DPE-10 | 40263 | [Dev][RD][PE-MIGRATION][IMPACT] Assess impact for RR Athena | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 25/Jan/26 8:48 AM | 11/Feb/26 11:07 PM |  | 1 | No-QA |  |  |  |  | มาจาก Sprint 17 | In Review |  | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18
Story | DPE-7 | 40259 | [Dev][RD][PE-MIGRATION][IMPACT] Assess impact for LP | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 25/Jan/26 8:37 AM | 18/Feb/26 3:55 PM |  | 2 | No-QA |  |  |  | 0 | มาจาก Sprint 17 | In Review | 10800 | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18
Story | RDNDA-19 | 40131 | [DEV][RD][TDM] Create migration for access control | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 22/Jan/26 5:07 PM | 19/Feb/26 6:39 PM |  | 1 |  |  |  |  | 14400 |  |  |  | [Dev][RD][NewDamart] Sprint 17 | [Dev][RD][NewDamart] Sprint 18
Story | RDNDA-18 | 40130 | [DEV][RD][TDM] Create access control callback endpoint | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 22/Jan/26 5:03 PM | 09/Feb/26 11:37 AM |  | 3 |  |  |  |  | 28800 |  |  |  | [Dev][RD][NewDamart] Sprint 17 | [Dev][RD][NewDamart] Sprint 18
Story | RDNDA-17 | 40129 | [DEV][RD][SA] Design callback API | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Review |  | 22/Jan/26 5:02 PM | 11/Feb/26 6:54 PM |  | 3 | [8 empty] | [Dev][RD][NewDamart] Sprint 17 | [Dev][RD][NewDamart] Sprint 18
Story | DPE-5 | 40122 | [Dev][RD][PE-MIGRATION][IMPACT] Assess impact for Partner Loyalty API | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 22/Jan/26 2:50 PM | 11/Feb/26 1:38 PM |  | 2 | No-QA |  |  |  |  | มาจาก Sprint 17 | In Review |  | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18
Story | DPE-4 | 40121 | [Dev][RD][PE-MIGRATION][IMPACT] Assess impact for HR Solution | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 22/Jan/26 2:45 PM | 09/Feb/26 7:19 PM |  | 1 | No-QA |  |  |  |  | มาจาก Sprint 17 | In Review |  | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18
Story | DPE-2 | 40113 | [Dev][RD][PE-MIGRATION][IMPACT] Assess impact for SSO | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 22/Jan/26 1:14 PM | 11/Feb/26 1:38 PM |  | 3 | No-QA |  |  |  |  | มาจาก Sprint 17 | In Review |  | [Dev][RD][New PE] Sprint 17 | [Dev][RD][New PE] Sprint 18
Story | DEVRDSUP-389 | 39980 | [SUP-462]SUB : Request to remove rr_finance@rabbit.co.th from the auto email loop when refunds are processed. | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Thanakrit Chanthaworn | 712020:3fc982cb-c268-4f1d-9265-d3dd8fb08304 | Medium | Done |  | 21/Jan/26 2:10 PM | 10/Feb/26 8:36 AM |  | 1 | mid-sprint | sub |  |  | 7200 |  |  |  | [Dev][All Project] Sprint 16 | [Dev][All Project] Sprint 18
Sub-task | DPWP-27 | 39934 | [QA] Create test case refund transaction and reverse points API | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 21/Jan/26 10:09 AM | 28/Jan/26 10:21 AM | [7 empty] | มาจาก Sprint 17 | To Do |  | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Sub-task | DPWP-26 | 39932 | [QA] Create test case mark transaction as completed after merchant confirms order API | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 21/Jan/26 10:09 AM | 19/Feb/26 4:53 PM | [7 empty] | มาจาก Sprint 17 | To Do |  | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Sub-task | DPWP-25 | 39930 | [QA] Create test case process payment after customer confirm payment API | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 21/Jan/26 10:08 AM | 12/Feb/26 4:37 PM | [7 empty] | มาจาก Sprint 17 | In Progress |  | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Sub-task | DPWP-24 | 39928 | [QA] Create test case retrieve a transaction information API | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | In Progress |  | 21/Jan/26 10:07 AM | 21/Jan/26 10:12 AM | [7 empty] | มาจาก Sprint 17 | In Progress |  | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Sub-task | DPWP-23 | 39926 | [QA] Create test case process payment after customer scans QR API | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | In Progress |  | 21/Jan/26 10:06 AM | 27/Jan/26 5:03 PM | [7 empty] | มาจาก Sprint 17 | In Progress |  | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Sub-task | DPWP-22 | 39924 | [QA] Create test case create a new Point Payment transaction API | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | In Progress |  | 21/Jan/26 10:06 AM | 27/Jan/26 5:03 PM | [7 empty] | มาจาก Sprint 17 | In Progress |  | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Epic | RDAPS-398 | 39575 | HR-MEMBER-REFACTOR |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 19/Jan/26 10:59 AM | 09/Feb/26 10:10 AM | [7 empty] | มาจาก Sprint 17 | To Do |  | [Dev][All Project] Sprint 16 | [Dev][All Project] Sprint 17 | [Dev][All Project] Sprint 18
Story | RDNDA-14 | 38512 | [DEV][RD][TDM] Create migration | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 09/Jan/26 1:48 PM | 09/Feb/26 11:37 AM |  | 2 | No-QA | ThanaDataMart |  |  | 14400 |  |  |  | [Dev][RD][NewDamart] Sprint 16 | [Dev][RD][NewDamart] Sprint 17 | [Dev][RD][NewDamart] Sprint 18
Story | DPWP-21 | 38478 | [Dev][RD][PWP] Create API to cancel transaction to support point reservation rule | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 09/Jan/26 11:32 AM | 11/Feb/26 3:26 PM |  | 8 |  |  |  |  | 43200 |  |  |  | [Dev][RD][PWP] Sprint 18
Story | DPWP-18 | 38437 | [Dev][RD][PWP] Initial Project Repository for Pay with Point Scheduler appp | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 08/Jan/26 6:48 PM | 09/Feb/26 11:04 AM | 23/Jan/26 12:00 AM | 5 | No-QA |  |  |  | 0 | มาจาก Sprint 17 | Ready To Test | 57600 | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Story | RDNDA-12 | 38435 | [DEV][RD][TDM] Integrate Discord for error log | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 08/Jan/26 5:23 PM | 09/Feb/26 11:37 AM | [10 empty] | [Dev][RD][NewDamart] Sprint 16 | [Dev][RD][NewDamart] Sprint 17 | [Dev][RD][NewDamart] Sprint 18
Story | RDNDA-11 | 38434 | [DEV][RD][TDM] Create producer function for push kinesis data | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 08/Jan/26 5:22 PM | 09/Feb/26 11:37 AM |  | 3 | [8 empty] | [Dev][RD][NewDamart] Sprint 16 | [Dev][RD][NewDamart] Sprint 17 | [Dev][RD][NewDamart] Sprint 18
Story | RDNDA-9 | 38247 | [DEV][RD][TDM] Create client middleware | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 07/Jan/26 5:19 PM | 09/Feb/26 11:37 AM |  | 3 | [8 empty] | [Dev][RD][NewDamart] Sprint 16 | [Dev][RD][NewDamart] Sprint 17 | [Dev][RD][NewDamart] Sprint 18
Story | RDNDA-8 | 38246 | [DEV][RD][TDM] Create Push to Kinesis Consumer | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 07/Jan/26 5:19 PM | 09/Feb/26 11:37 AM | 21/Jan/26 12:00 AM | 3 |  |  |  |  | 28800 |  |  |  | [Dev][RD][NewDamart] Sprint 16 | [Dev][RD][NewDamart] Sprint 17 | [Dev][RD][NewDamart] Sprint 18
Story | RDNDA-6 | 38244 | [DEV][RD][TDM] Create generic transactions endpoint | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 07/Jan/26 5:17 PM | 09/Feb/26 11:37 AM |  | 5 |  |  |  |  | 86400 |  |  |  | [Dev][RD][NewDamart] Sprint 16 | [Dev][RD][NewDamart] Sprint 17 | [Dev][RD][NewDamart] Sprint 18
Story | RDNDA-5 | 38243 | [DEV][RD][TDM] Initial project | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 07/Jan/26 5:16 PM | 09/Feb/26 11:37 AM |  | 5 | No-QA | ThanaDataMart | [6 empty] | [Dev][RD][NewDamart] Sprint 16 | [Dev][RD][NewDamart] Sprint 17 | [Dev][RD][NewDamart] Sprint 18
Story | DPWP-16 | 38207 | [Dev][RD][PWP] Implement cronjob to process payment expiration | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 07/Jan/26 3:26 PM | 09/Feb/26 11:04 AM |  | 5 | [5 empty] | มาจาก Sprint 17 | Ready to Staging |  | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Story | DRST-6 | 38163 | [Dev][RD][Terminate VIMI][VoucherValidator] Refactor APIs to remove dependency on MVP Phase 1 source | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready to Staging |  | 07/Jan/26 11:12 AM | 11/Feb/26 11:03 AM | 10/Feb/26 12:00 AM | 3 |  |  |  |  | 28800 |  |  |  | [Dev RD][VIMI Termi] Sprint 18
Story | DRST-5 | 38162 | [Dev][RD][Terminate VIMI][MerchantAPI] Refactor APIs to remove dependency on MVP Phase 1 source | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready to Staging |  | 07/Jan/26 11:12 AM | 19/Feb/26 9:30 PM | 11/Feb/26 12:00 AM | 3 |  |  |  |  | 28800 |  |  |  | [Dev RD][VIMI Termi] Sprint 18
Story | DPWP-15 | 38057 | [Dev][RD][BFF] Create API to process payment after customer confirm payment | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Jan/26 6:58 PM | 09/Feb/26 3:55 PM | 03/Feb/26 12:00 AM | 5 |  |  |  |  | 0 | มาจาก Sprint 17 | Ready to Staging | 43200 | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Story | DPWP-14 | 38056 | [Dev][RD][BFF] Create API to process payment after customer scans QR | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Jan/26 6:57 PM | 09/Feb/26 11:04 AM |  | 5 |  |  |  |  | 0 | มาจาก Sprint 17 | Ready To Test | 72000 | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Story | DPWP-13 | 38055 | [Dev][RD][PWP] Create API to refund transaction and reverse points | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Jan/26 6:55 PM | 10/Feb/26 6:11 PM |  | 5 |  |  |  |  | 0 | มาจาก Sprint 17 | Ready To Test | 57600 | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Story | DPWP-12 | 38054 | [Dev][RD][PWP] Create API to mark transaction as completed after merchant confirms order | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Jan/26 6:52 PM | 09/Feb/26 11:04 AM |  | 5 |  |  |  |  | 0 | มาจาก Sprint 17 | Ready To Test | 86400 | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Story | DPWP-11 | 38053 | [Dev][RD][PWP] Create API to process payment after customer confirm payment | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Jan/26 6:47 PM | 09/Feb/26 11:04 AM |  | 8 |  |  |  |  | 0 | มาจาก Sprint 17 | Ready To Test | 86400 | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Bug | DEVRDSUP-365 | 38051 | [SUP-435][HRSolution] HR solution's login page doesn't change the display language | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Low | Pass : Waiting for deployment |  | 06/Jan/26 5:41 PM | 19/Feb/26 9:30 PM | 04/Feb/26 12:00 AM | 1 | hr-solution | [7 empty] | [Dev][All Project] Sprint 15 | [Dev][All Project] Sprint 18
Story | RDAPS-382 | 37978 | [Dev][RD][SSO-User] Improve query strategies for card type and card range retrieval | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready to Staging |  | 06/Jan/26 11:23 AM | 09/Feb/26 10:10 AM | [7 empty] | มาจาก Sprint 17 | Ready to Staging |  | [Dev][All Project] Sprint 15 | [Dev][All Project] Sprint 16 | [Dev][All Project] Sprint 17 | [Dev][All Project] Sprint 18
Story | DPWP-10 | 37976 | [Dev][RD][PWP] Create API to retrieve a transaction information | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Jan/26 11:10 AM | 09/Feb/26 11:04 AM | 20/Jan/26 12:00 AM | 3 |  |  |  |  | 0 | มาจาก Sprint 17 | Ready To Test | 21600 | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Story | DPWP-9 | 37926 | [Dev][RD][PWP] Create API to process payment after customer scans QR | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 05/Jan/26 6:06 PM | 09/Feb/26 11:04 AM |  | 5 | [5 empty] | มาจาก Sprint 17 | Ready to Staging |  | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Story | DPWP-8 | 37906 | [Dev][RD][PWP] Create API to create a new Point Payment transaction | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Jan/26 1:25 PM | 09/Feb/26 11:04 AM | 19/Jan/26 12:00 AM | 8 | pay-with-point-api |  |  |  | 0 | มาจาก Sprint 17 | Ready To Test | 86400 | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17 | [Dev][RD][PWP] Sprint 18
Story | DRST-7 | 36975 | [Dev][RD][Terminate VIMI] Refactor TXN Report API and Report Summary API to remove dependency on MVP Phase 1 report source | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready to Staging |  | 23/Dec/25 12:23 PM | 19/Feb/26 9:30 PM | 30/Dec/25 12:00 AM | 3 |  |  |  |  | 28800 |  |  |  | [Dev][All Project] Sprint 15 | [Dev][All Project] Sprint 16 | [Dev RD][VIMI Termi] Sprint 17 | [Dev RD][VIMI Termi] Sprint 18
Story | DEVRDSUP-328 | 36862 | [SUP-390]CRM Request - CS-20251200022091 Request to Revert RR Backoffice Status from Refunded to Active (Wrong Refund Action) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 22/Dec/25 4:42 PM | 09/Feb/26 7:23 PM |  | 3 |  |  |  |  | 28800 |  |  |  | [Dev][All Project] Sprint 15 | [Dev][All Project] Sprint 18
Story | DEVRDSUP-319 | 36248 | [SUP-382][SUB] Request to make a package TXN with “allocating coupon“ to “fail“ | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | To Do |  | 16/Dec/25 5:55 PM | 09/Feb/26 9:40 AM |  |  | BURequest | sub | [6 empty] | [Dev][All Project] Sprint 18
Story | RDTHANA-426 | 35904 | [DEV][API DOC][SA] Design get access token | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 14/Dec/25 3:04 PM | 19/Feb/26 9:09 PM |  | 3 | [8 empty] | [Dev][RD][Thana] Sprint 18
Bug | DEVRDSUP-301 | 35668 | [SUP-364][Club][HR Solution] Club tier get removed entirely when user deletes the Tier name (EN), Tier name (TH) text string. | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Low | Resolved |  | 11/Dec/25 12:41 AM | 09/Feb/26 9:40 AM | 08/Jan/26 12:00 AM |  | hr-solution | mid-sprint | [6 empty] | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 18
Bug | DEVRDSUP-300 | 35666 | [SUP-363][Club][HR Solution] Club tier order can't be updated | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Resolved |  | 11/Dec/25 12:23 AM | 09/Feb/26 9:40 AM | 25/Dec/25 12:00 AM |  | hr-solution | mid-sprint | [6 empty] | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 18
Bug | DEVRDSUP-299 | 35664 | [SUP-362][SUB] Package TXNs is "Expired" and payment was completed but SUB TXN report shows payment fail and last TXN update was change on Nov while TXN was expired since Aug. | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Low | Resolved |  | 10/Dec/25 5:36 PM | 09/Feb/26 9:40 AM | 08/Jan/26 12:00 AM |  | data | mid-sprint | prod-issue | sub |  |  |  |  | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15 | [Dev][All Project] Sprint 18
Bug | RDAPS-316 | 35558 | [Dev][RD][RRS] Fix datetime filter logic to support millisecond precision for redemption ETL | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Pass : Waiting for deployment |  | 08/Dec/25 5:57 PM | 09/Feb/26 10:10 AM |  | 2 | [5 empty] | มาจาก Sprint 17 | Pass : Waiting for deployment |  | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15 | [Dev][All Project] Sprint 16 | [Dev][All Project] Sprint 17 | [Dev][All Project] Sprint 18
Story | DEVRDSUP-252 | 34528 | [SUP-312][SUB] Skipped Receipt GR Offline (Ticket 6 Nov) | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 18/Nov/25 3:37 PM | 20/Feb/26 10:10 AM | 26/Dec/25 12:00 AM | 8 | [8 empty] | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 16 | [Dev][All Project] Sprint 18
Story | DM-31 | 34302 | [DEV][RD][AWSTH] RR Scheduler pre-validation for dev environment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Low | Done |  | 14/Nov/25 4:53 PM | 19/Feb/26 6:39 PM |  | 1 | No-QA |  |  |  | 7200 | มาจาก Sprint 17 | To Do |  | [Dev][RD][AWS] Sprint 17 | [Dev][RD][AWS] Sprint 18
Story | DM-28 | 34299 | [DEV][RD][AWSTH] RR Link Notify API pre-validation for dev environment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 14/Nov/25 4:52 PM | 19/Feb/26 6:39 PM | 13/Feb/26 12:00 AM | 2 | No-QA |  |  |  | 7200 | มาจาก Sprint 17 | In Progress | 14400 -> 7200 | [Dev][RD][AWS] Sprint 17 | [Dev][RD][AWS] Sprint 18
Story | DM-22 | 34293 | [DEV][RD][AWSTH] RR BackOffice pre-validation for dev environment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Low | In Progress |  | 14/Nov/25 4:49 PM | 19/Feb/26 10:06 PM |  | 3 | No-QA |  |  |  | 28800 | มาจาก Sprint 17 | To Do |  | [Dev][RD][AWS] Sprint 17 | [Dev][RD][AWS] Sprint 18
Story | DM-6 | 34277 | [DEV][RD][AWSTH] HR Solution pre-validation for dev environment |  |  | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Low | To Do |  | 14/Nov/25 4:40 PM | 19/Feb/26 6:39 PM |  | 3 | No-QA |  |  |  |  | มาจาก Sprint 17 | To Do |  | [Dev][RD][AWS] Sprint 17 | [Dev][RD][AWS] Sprint 18
Improvement | DEVRDSUP-242 | 34266 | [DEVRDSUP-93][REM] POC - solution finding on how to sync reward stock count to algolia tp prevent stock missmatch | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | In Review |  | 14/Nov/25 2:01 PM | 09/Feb/26 9:40 AM | 12/Dec/25 12:00 AM |  | rem | [7 empty] | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 18
Bug | RDAPS-269 | 34036 | [DEV][RD][Cron-job][Merchant Ranking] Enhance get merchant with active store only | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Pass : Waiting for deployment |  | 11/Nov/25 1:09 PM | 09/Feb/26 10:10 AM |  | 2 | No-QA |  |  |  |  | มาจาก Sprint 17 | Pass : Waiting for deployment |  | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15 | [Dev][All Project] Sprint 16 | [Dev][All Project] Sprint 17 | [Dev][All Project] Sprint 18
Task | DEVRDSUP-153 | 31856 | Find and remove double bound 1 wallet card to multiple SSO to resolve DEVRDSUP-146 error for other users. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Blocked |  | 30/Sep/25 1:40 PM | 09/Feb/26 9:40 AM | 01/Dec/25 12:00 AM | 5 | [8 empty] | [Dev][All Project] Sprint 9 | [Dev][All Project] Sprint 10 | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 18
Story | RDAPS-160 | 29972 | [DEV][RD][SSO-Backoffice] Disable SEO tracking | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 20/Aug/25 11:21 AM | 09/Feb/26 10:10 AM | 04/Sep/25 12:00 AM | 1 |  |  |  |  | 0 | มาจาก Sprint 17 | Ready To Test | 7200 | [Dev][All project]Sprint 6 | [Dev][All project]Sprint 7 | [Dev][All Project] Sprint 9 | [Dev][All Project] Sprint 10 | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15 | [Dev][All Project] Sprint 16 | [Dev][All Project] Sprint 17 | [Dev][All Project] Sprint 18

## Summarize Sprint 17
Column 1 | Total Stories Point | Total Manhour | Point Done | Manhour Done | Note
26 Jan - 6 Feb
Dev Resource Available | 12 | 338
Meeting Planned |  |  |  |  | Ref
Additional Meeting |  |  |  |  | Ref
Deployment |  | 3 |  |  | 1 ครั้ง 1. 3 คน
Development Sprint Total | 182 | 250.17 | 72 | 142.17
Ad-hoc Mid Sprint | 0 | 0 | 1 | 0 | 0 tasks
Requirement changes after refinement? | 0 |  | 0 | 0 | 0 tasks
Aek | 1 | 0 | 0 | 0
A | 62 | 150 | 52 | 122
Aom | 22 | 16.17 | 10 | 16.17
Zan | 6 | 0 | 0 | 0
Mai | 13 | 8 | 1 | 0
Mac | 29 | 20 | 4 | 0
Mos | 19 | 24 | 0 | 0
Jack | 1 | 0 | 1 | 0
Nim | 13 | 32 | 2 | 4
Arm | 10 | 0 | 2 | 0
| System Architech |  |  |  | Permanent Dev. |  |  | Outsources
Projects (Stories Points) | Aek | Zan | Aom | Jack | A | Art | Mai | Kae | Mac | Nim | Mos | Arm
Das Haus - Thana City & Das Haus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E-commerce 1.1. E-Commerce x Shopify Plus 1.2. Shopify:Snackmaker 1.3. Shopify: Turtle Delivery 1.4. Shopify: Turtle Delivery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CleverTap - MKT Automation Tool | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 2 | 0
Adjust Integration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Adhoc - Non-Epics - Turtle Display club tier on POS - Data Mart Migration | 0 | 2 | 9 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
Support Incidents | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| System Architech |  |  |  | Permanent Dev. |  |  | Outsources
Projects (Manhour) | Aek | Zan | Aom | Jack | A | Art | Mai | Kae | Mac | Nim | Mos | Arm
Das Haus - Thana City & Das Haus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E-commerce 1.1. E-Commerce x Shopify Plus 1.2. Shopify:Snackmaker 1.3. Shopify: Turtle Delivery 1.4. Shopify: Turtle Delivery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CleverTap - MKT Automation Tool | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Adjust Integration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Adhoc - Non-Epics - Turtle Display club tier on POS - Data Mart Migration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Support Incidents | 0 | 0 | 0.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 17
Issue Type | Issue key | Issue id | Summary | Assignee | Assignee Id | Reporter | Reporter Id | Priority | Status | Resolution | Created | Updated | Due date | Custom field (Story Points) | Labels | Labels | Labels | Original estimate | Sprint Movement | Sprint 16 | Note | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint
Story | RDAPS-406 | 41542 | [Dev][RD][Adhoc][Short-distance] est.effort for subscription enhancement | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 04/Feb/26 10:30 AM | 04/Feb/26 3:52 PM |  | 2 | mid-sprint | [6 empty] | [Dev][All Project] Sprint 17
Story | DPE-62 | 41461 | [Dev][RD][SSO-User] Update a registration source Update a registration source | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 03/Feb/26 8:12 PM | 05/Feb/26 1:44 PM | [5 empty] | 7200 |  |  |  | [Dev][RD][New PE] Sprint 17
Story | DPE-61 | 41459 | [Dev][RD][SSO-User] Backoffice Create a registration source | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 03/Feb/26 7:43 PM | 05/Feb/26 5:13 PM | [5 empty] | 7200 |  |  |  | [Dev][RD][New PE] Sprint 17
Story | DPE-60 | 41457 | [Dev][RD][SSO-User] Backoffice update user | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | To Do |  | 03/Feb/26 7:43 PM | 05/Feb/26 4:39 PM | [9 empty] | [Dev][RD][New PE] Sprint 17
Story | DPE-48 | 41433 | [Dev][RD][SSO-User] Update rewards user | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 03/Feb/26 7:40 PM | 05/Feb/26 2:21 PM | 05/Feb/26 12:00 AM |  |  |  |  | 28800 |  |  |  | [Dev][RD][New PE] Sprint 17
Task | DM-185 | 41379 | [DEV][RD][AWSTH] Update Query Lat, Long compatible with MySQL | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 03/Feb/26 3:11 PM | 05/Feb/26 3:52 PM | 04/Feb/26 12:00 AM | 1 | No-QA |  |  | 7200 |  |  |  | [Dev][RD][AWS] Sprint 17
Sub-task | DPWP-39 | 40985 | [QA] Test execution process payment expiration (transaction status = 'expired') | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 29/Jan/26 7:53 PM | 29/Jan/26 7:56 PM | [9 empty] | [Dev][RD][PWP] Sprint 17
Sub-task | DPWP-38 | 40983 | [QA] Test execution process payment after customer confirm payment with [BFF] API | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 29/Jan/26 7:52 PM | 29/Jan/26 7:52 PM | [9 empty] | [Dev][RD][PWP] Sprint 17
Sub-task | DPWP-37 | 40981 | [QA] Test execution process payment after customer scans QR with [BFF] API (On Staging) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 29/Jan/26 7:50 PM | 29/Jan/26 7:56 PM | [9 empty] | [Dev][RD][PWP] Sprint 17
Sub-task | DPWP-36 | 40979 | [QA] Test execution refund transaction and reverse points with API (On Staging) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 29/Jan/26 7:49 PM | 29/Jan/26 7:55 PM | [9 empty] | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17
Sub-task | DPWP-35 | 40977 | [QA] Test execution mark transaction as completed after merchant confirms order with API (On Staging) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 29/Jan/26 7:47 PM | 29/Jan/26 7:48 PM | [9 empty] | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17
Sub-task | DPWP-34 | 40975 | [QA] Test execution process payment after customer confirm payment with API (On Staging) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 29/Jan/26 7:46 PM | 29/Jan/26 7:48 PM | [9 empty] | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17
Story | DEVRDSUP-402 | 40838 | [SUP-476]Group Rewards - Lucky Draw iPhone 17 Jan26 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 29/Jan/26 11:16 AM | 04/Feb/26 4:42 PM | 04/Feb/26 12:00 AM | 1 | BURequest | mid-sprint | rem |  |  |  |  | [Dev][All Project] Sprint 17
Story | DEVRDSUP-401 | 40798 | [SUP-475]Urgent #20260100024374 - Didn't get the package รบกวน Drop Package ให้ลูกค้าค่ะ | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 28/Jan/26 7:14 PM | 28/Jan/26 7:20 PM |  |  | BURequest | sub |  | 600 |  |  |  | [Dev][All Project] Sprint 17
Task | DM-184 | 40762 | [DEV][RD][AWSTH] Fix PostgreSQL incompatible with timestamp | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | High | Done |  | 28/Jan/26 4:27 PM | 05/Feb/26 3:47 PM | 30/Jan/26 12:00 AM | 1 | No-QA | partner-loyalty |  | 7200 |  |  |  | [Dev][RD][AWS] Sprint 17
Sub-task | DPWP-33 | 40662 | [QA] Create test case process payment expiration (transaction status = 'expired') | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 28/Jan/26 10:36 AM | 28/Jan/26 10:36 AM | [9 empty] | [Dev][RD][PWP] Sprint 17
Sub-task | DPWP-32 | 40660 | [QA] Create test case [BFF] API to process payment after customer confirm payment | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 28/Jan/26 10:34 AM | 29/Jan/26 7:52 PM | [9 empty] | [Dev][RD][PWP] Sprint 17
Sub-task | DPWP-31 | 40657 | [QA] Create test case [BFF] API to process payment after customer scans QR | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 28/Jan/26 10:22 AM | 29/Jan/26 7:50 PM | [9 empty] | [Dev][RD][PWP] Sprint 17
Sub-task | DPWP-30 | 40620 | [QA] Test execution retrieve a transaction information with API (On Staging) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 27/Jan/26 5:15 PM | 29/Jan/26 7:44 PM | [9 empty] | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17
Sub-task | DPWP-29 | 40618 | [QA] Test execution process payment after customer scans QR with API (On Staging) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 27/Jan/26 5:03 PM | 29/Jan/26 7:42 PM | [9 empty] | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17
Sub-task | DPWP-28 | 40616 | [QA] Test execution create a new Point Payment transaction with API (On staging) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 27/Jan/26 5:01 PM | 29/Jan/26 4:39 PM | [9 empty] | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17
Story | DM-183 | 40512 | [DEV][RD][AWSTH] Verify database replicate for rr-ecommerce shopify at Dev environment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 27/Jan/26 11:52 AM | 27/Jan/26 10:51 PM | 28/Jan/26 12:00 AM | 1 | No-QA |  |  | 7200 |  |  |  | [Dev][RD][AWS] Sprint 17
Story | DM-182 | 40478 | [DEV][RD][AWSTH] Verify API Gateway on dev environment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | In Progress |  | 27/Jan/26 10:08 AM | 29/Jan/26 5:48 PM | 03/Feb/26 12:00 AM | 5 | No-QA |  |  | 86400 |  |  |  | [Dev][RD][AWS] Sprint 17
Story | DPE-44 | 40432 | [Dev][RD][PE-MIGRATION][IMPACT] Assess impact for 'goutil' | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 26/Jan/26 3:34 PM | 03/Feb/26 9:57 AM |  | 2 | No-QA | [6 empty] | [Dev][RD][New PE] Sprint 17
Story | RDAPS-405 | 40426 | [Dev][RD][Technical][DB][Performance] Analyze and Tune Coupon Allocation Performance | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | To Do |  | 26/Jan/26 2:48 PM | 26/Jan/26 2:52 PM |  | 5 | [7 empty] | [Dev][All Project] Sprint 17
Story | DPE-37 | 40290 | [Dev][RD][PE-MIGRATION][IMPACT] Assess impact for Rabbit CMS API | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 25/Jan/26 9:03 AM | 05/Feb/26 10:00 AM |  | 1 |  |  |  | 14400 |  |  |  | [Dev][RD][New PE] Sprint 17
Story | DPE-36 | 40289 | [Dev][RD][PE-MIGRATION][IMPACT] Assess impact for Notification API | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 25/Jan/26 9:03 AM | 05/Feb/26 10:55 AM |  | 1 | [7 empty] | [Dev][RD][New PE] Sprint 17
Story | DPE-35 | 40288 | [Dev][RD][PE-MIGRATION][IMPACT] Assess impact for Merchant API | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 25/Jan/26 9:03 AM | 05/Feb/26 10:55 AM |  | 1 | [7 empty] | [Dev][RD][New PE] Sprint 17
Story | DPE-34 | 40287 | [Dev][RD][PE-MIGRATION][IMPACT] Assess impact for Exclusive Store API | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 25/Jan/26 9:03 AM | 29/Jan/26 2:00 PM |  | 1 | [7 empty] | [Dev][RD][New PE] Sprint 17
Story | DPE-33 | 40286 | [Dev][RD][PE-MIGRATION][IMPACT] Assess impact for Deeplink API | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 25/Jan/26 9:03 AM | 05/Feb/26 10:52 AM |  | 1 |  |  |  | 7200 |  |  |  | [Dev][RD][New PE] Sprint 17
Story | DPE-32 | 40285 | [Dev][RD][PE-MIGRATION][IMPACT] Assess impact for RR Voucher validator | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 25/Jan/26 9:03 AM | 29/Jan/26 10:53 AM |  | 1 | [7 empty] | [Dev][RD][New PE] Sprint 17
Story | DPE-31 | 40284 | [Dev][RD][PE-MIGRATION][IMPACT] Assess impact for RR Member | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 25/Jan/26 9:03 AM | 29/Jan/26 11:44 AM |  | 1 | [7 empty] | [Dev][RD][New PE] Sprint 17
Story | DPE-30 | 40283 | [Dev][RD][PE-MIGRATION][IMPACT] Assess impact for RR Member Acquisition | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 25/Jan/26 9:03 AM | 05/Feb/26 9:59 AM |  | 1 |  |  |  | 28800 |  |  |  | [Dev][RD][New PE] Sprint 17
Story | DPE-29 | 40282 | [Dev][RD][PE-MIGRATION][IMPACT] Assess impact for RR Link Notify | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 25/Jan/26 9:03 AM | 05/Feb/26 10:52 AM |  | 1 |  |  |  | 7200 |  |  |  | [Dev][RD][New PE] Sprint 17
Story | DPE-28 | 40281 | [Dev][RD][PE-MIGRATION][IMPACT] Assess impact for RR Thana datamart | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 25/Jan/26 9:03 AM | 05/Feb/26 10:54 AM |  | 1 | [7 empty] | [Dev][RD][New PE] Sprint 17
Story | DPE-27 | 40280 | [Dev][RD][PE-MIGRATION][IMPACT] Assess impact for RR Pay with Point API | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 25/Jan/26 8:49 AM | 29/Jan/26 11:44 AM |  | 1 | [7 empty] | [Dev][RD][New PE] Sprint 17
Story | DPE-26 | 40279 | [Dev][RD][PE-MIGRATION][IMPACT] Assess impact for RR Ecommerce Shopify | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 25/Jan/26 8:49 AM | 05/Feb/26 9:59 AM |  | 1 |  |  |  | 14400 |  |  |  | [Dev][RD][New PE] Sprint 17
Story | DPE-25 | 40278 | [Dev][RD][PE-MIGRATION][IMPACT] Assess impact for RR DatahubGQL | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 25/Jan/26 8:49 AM | 03/Feb/26 10:54 AM |  | 1 | [7 empty] | [Dev][RD][New PE] Sprint 17
Story | DPE-24 | 40277 | [Dev][RD][PE-MIGRATION][IMPACT] Assess impact for RR Cronjob | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 25/Jan/26 8:49 AM | 05/Feb/26 9:59 AM |  | 1 | No-QA |  |  | 14400 |  |  |  | [Dev][RD][New PE] Sprint 17
Story | DPE-23 | 40276 | [Dev][RD][PE-MIGRATION][IMPACT] Assess impact for RR CloudID API | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 25/Jan/26 8:48 AM | 05/Feb/26 10:54 AM |  | 1 | No-QA | [6 empty] | [Dev][RD][New PE] Sprint 17
Story | DPE-22 | 40275 | [Dev][RD][PE-MIGRATION][IMPACT] Assess impact for RR CleverTap | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 25/Jan/26 8:48 AM | 05/Feb/26 10:54 AM |  | 1 | No-QA | [6 empty] | [Dev][RD][New PE] Sprint 17
Story | DPE-21 | 40274 | [Dev][RD][PE-MIGRATION][IMPACT] Assess impact for Rewards Consumer | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 25/Jan/26 8:48 AM | 27/Jan/26 7:22 PM |  | 1 | No-QA | [6 empty] | [Dev][RD][New PE] Sprint 17
Story | DPE-20 | 40273 | [Dev][RD][PE-MIGRATION][IMPACT] Assess impact for Rewards API | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 25/Jan/26 8:48 AM | 27/Jan/26 7:22 PM |  | 1 | No-QA | [6 empty] | [Dev][RD][New PE] Sprint 17
Story | DPE-19 | 40272 | [Dev][RD][PE-MIGRATION][IMPACT] Assess impact for Offline Subscription BFF | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 25/Jan/26 8:48 AM | 05/Feb/26 10:53 AM |  | 1 | No-QA | [6 empty] | [Dev][RD][New PE] Sprint 17
Story | DPE-18 | 40271 | [Dev][RD][PE-MIGRATION][IMPACT] Assess impact for RR Cart API | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 25/Jan/26 8:48 AM | 05/Feb/26 10:53 AM |  | 1 | No-QA | [6 empty] | [Dev][RD][New PE] Sprint 17
Story | DPE-17 | 40270 | [Dev][RD][PE-MIGRATION][IMPACT] Assess impact for Rabbit App BFF | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 25/Jan/26 8:48 AM | 30/Jan/26 10:28 AM |  | 1 | No-QA | [6 empty] | [Dev][RD][New PE] Sprint 17
Story | DPE-16 | 40269 | [Dev][RD][PE-MIGRATION][IMPACT] Assess impact for Point Engine Proxy | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 25/Jan/26 8:48 AM | 29/Jan/26 11:50 AM |  | 1 | No-QA | [6 empty] | [Dev][RD][New PE] Sprint 17
Story | DPE-15 | 40268 | [Dev][RD][PE-MIGRATION][IMPACT] Assess impact for Redemption API | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 25/Jan/26 8:48 AM | 29/Jan/26 1:06 PM |  | 1 | No-QA | [6 empty] | [Dev][RD][New PE] Sprint 17
Story | DPE-14 | 40267 | [Dev][RD][PE-MIGRATION][IMPACT] Assess impact for Redemption Consumer | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 25/Jan/26 8:48 AM | 29/Jan/26 1:06 PM |  | 1 | No-QA | [6 empty] | [Dev][RD][New PE] Sprint 17
Story | DPE-13 | 40266 | [Dev][RD][PE-MIGRATION][IMPACT] Assess impact for RR Order Service | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 25/Jan/26 8:48 AM | 28/Jan/26 8:13 PM |  | 1 | No-QA | [6 empty] | [Dev][RD][New PE] Sprint 17
Story | DPE-12 | 40265 | [Dev][RD][PE-MIGRATION][IMPACT] Assess impact for RR Backoffice | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 25/Jan/26 8:48 AM | 05/Feb/26 9:59 AM |  | 1 | No-QA |  |  | 28800 |  |  |  | [Dev][RD][New PE] Sprint 17
Story | DPE-11 | 40264 | [Dev][RD][PE-MIGRATION][IMPACT] Assess impact for RR Scheduler | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 25/Jan/26 8:48 AM | 27/Jan/26 4:13 PM |  | 1 | No-QA | [6 empty] | [Dev][RD][New PE] Sprint 17
Story | DPE-10 | 40263 | [Dev][RD][PE-MIGRATION][IMPACT] Assess impact for RR Athena | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 25/Jan/26 8:48 AM | 29/Jan/26 10:19 AM |  | 1 | No-QA | [6 empty] | [Dev][RD][New PE] Sprint 17
Story | DPE-9 | 40262 | [Dev][RD][PE-MIGRATION][IMPACT] Assess impact for RR Aphrodite | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 25/Jan/26 8:48 AM | 28/Jan/26 11:29 AM |  | 1 | No-QA | [6 empty] | [Dev][RD][New PE] Sprint 17
Story | DPE-8 | 40261 | [Dev][RD][PE-MIGRATION][IMPACT] Assess impact for Sky | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 25/Jan/26 8:48 AM | 28/Jan/26 11:14 AM |  | 2 | No-QA | [6 empty] | [Dev][RD][New PE] Sprint 17
Story | DPE-7 | 40259 | [Dev][RD][PE-MIGRATION][IMPACT] Assess impact for LP | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 25/Jan/26 8:37 AM | 02/Feb/26 4:00 PM |  | 1 | No-QA | [6 empty] | [Dev][RD][New PE] Sprint 17
Story | DPE-5 | 40122 | [Dev][RD][PE-MIGRATION][IMPACT] Assess impact for Partner Loyalty API | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 22/Jan/26 2:50 PM | 28/Jan/26 2:04 PM |  | 2 | No-QA | [6 empty] | [Dev][RD][New PE] Sprint 17
Story | DPE-4 | 40121 | [Dev][RD][PE-MIGRATION][IMPACT] Assess impact for HR Solution | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 22/Jan/26 2:45 PM | 29/Jan/26 5:25 PM |  | 1 | No-QA | [6 empty] | [Dev][RD][New PE] Sprint 17
Story | DPE-3 | 40120 | [Dev][RD][PE-MIGRATION][IMPACT][SA] Analysis and Breakdown Task | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 22/Jan/26 1:44 PM | 05/Feb/26 10:55 AM |  | 5 |  |  |  | 57600 |  |  |  | [Dev][RD][New PE] Sprint 17
Story | DPE-2 | 40113 | [Dev][RD][PE-MIGRATION][IMPACT] Assess impact for SSO | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 22/Jan/26 1:14 PM | 05/Feb/26 10:09 AM |  | 3 | No-QA | [6 empty] | [Dev][RD][New PE] Sprint 17
Sub-task | DPWP-27 | 39934 | [QA] Create test case refund transaction and reverse points API | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 21/Jan/26 10:09 AM | 28/Jan/26 10:21 AM | [6 empty] | มาจาก Sprint 16 | To Do |  | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17
Sub-task | DPWP-26 | 39932 | [QA] Create test case mark transaction as completed after merchant confirms order API | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 21/Jan/26 10:09 AM | 29/Jan/26 7:44 PM | [6 empty] | มาจาก Sprint 16 | To Do |  | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17
Sub-task | DPWP-25 | 39930 | [QA] Create test case process payment after customer confirm payment API | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | In Progress |  | 21/Jan/26 10:08 AM | 29/Jan/26 7:45 PM | [6 empty] | มาจาก Sprint 16 | To Do |  | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17
Sub-task | DPWP-24 | 39928 | [QA] Create test case retrieve a transaction information API | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | In Progress |  | 21/Jan/26 10:07 AM | 21/Jan/26 10:12 AM | [6 empty] | มาจาก Sprint 16 | In Progress |  | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17
Sub-task | DPWP-23 | 39926 | [QA] Create test case process payment after customer scans QR API | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | In Progress |  | 21/Jan/26 10:06 AM | 27/Jan/26 5:03 PM | [6 empty] | มาจาก Sprint 16 | In Progress |  | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17
Sub-task | DPWP-22 | 39924 | [QA] Create test case create a new Point Payment transaction API | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | In Progress |  | 21/Jan/26 10:06 AM | 27/Jan/26 5:03 PM | [6 empty] | มาจาก Sprint 16 | In Progress |  | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17
Epic | RDAPS-398 | 39575 | HR-MEMBER-REFACTOR |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 19/Jan/26 10:59 AM | 26/Jan/26 2:39 PM | [6 empty] | มาจาก Sprint 16 | To Do |  | [Dev][All Project] Sprint 16 | [Dev][All Project] Sprint 17
Story | DPWP-18 | 38437 | [Dev][RD][PWP] Initial Project Repository for Pay with Point Scheduler appp | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 08/Jan/26 6:48 PM | 05/Feb/26 10:01 AM | 23/Jan/26 12:00 AM | 5 | No-QA |  |  | 28800 | มาจาก Sprint 16 | In Progress | 57600 -> 28,800 | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17
Story | DPWP-16 | 38207 | [Dev][RD][PWP] Implement cronjob to process payment expiration | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 07/Jan/26 3:26 PM | 03/Feb/26 5:01 PM |  | 5 | [7 empty] | [Dev][RD][PWP] Sprint 17
Story | DPWP-15 | 38057 | [Dev][RD][BFF] Create API to process payment after customer confirm payment | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 06/Jan/26 6:58 PM | 04/Feb/26 11:07 AM | 03/Feb/26 12:00 AM | 5 |  |  |  | 43200 |  |  |  | [Dev][RD][PWP] Sprint 17
Story | DPWP-14 | 38056 | [Dev][RD][BFF] Create API to process payment after customer scans QR | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Jan/26 6:57 PM | 05/Feb/26 11:14 AM |  | 5 |  |  |  | 72000 |  |  |  | [Dev][RD][PWP] Sprint 17
Story | DPWP-13 | 38055 | [Dev][RD][PWP] Create API to refund transaction and reverse points | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Jan/26 6:55 PM | 05/Feb/26 9:47 AM |  | 5 |  |  |  | 0 | มาจาก Sprint 16 | Ready to Staging | 57600 | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17
Story | DPWP-12 | 38054 | [Dev][RD][PWP] Create API to mark transaction as completed after merchant confirms order | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Jan/26 6:52 PM | 04/Feb/26 9:40 AM |  | 5 |  |  |  | 0 | มาจาก Sprint 16 | Ready to Staging | 86400 | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17
Story | DPWP-11 | 38053 | [Dev][RD][PWP] Create API to process payment after customer confirm payment | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Jan/26 6:47 PM | 05/Feb/26 9:59 AM |  | 8 |  |  |  | 0 | มาจาก Sprint 16 | Ready to Staging | 86400 | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17
Story | RDAPS-382 | 37978 | [Dev][RD][SSO-User] Improve query strategies for card type and card range retrieval | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready to Staging |  | 06/Jan/26 11:23 AM | 26/Jan/26 5:01 PM | [6 empty] | มาจาก Sprint 16 | Ready to Staging |  | [Dev][All Project] Sprint 15 | [Dev][All Project] Sprint 16 | [Dev][All Project] Sprint 17
Story | DPWP-10 | 37976 | [Dev][RD][PWP] Create API to retrieve a transaction information | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 06/Jan/26 11:10 AM | 04/Feb/26 11:09 AM | 20/Jan/26 12:00 AM | 3 |  |  |  | 0 | มาจาก Sprint 16 | Ready to Staging | 21600 | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17
Story | DPWP-9 | 37926 | [Dev][RD][PWP] Create API to process payment after customer scans QR | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 05/Jan/26 6:06 PM | 03/Feb/26 3:49 PM |  | 5 |  |  |  |  | มาจาก Sprint 16 | Ready to Staging |  | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17
Story | DPWP-8 | 37906 | [Dev][RD][PWP] Create API to create a new Point Payment transaction | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Jan/26 1:25 PM | 04/Feb/26 11:08 AM | 19/Jan/26 12:00 AM | 8 | pay-with-point-api |  |  | 0 | มาจาก Sprint 16 | Ready to Staging | 86400 | [Dev][RD][PWP] Sprint 16 | [Dev][RD][PWP] Sprint 17
Epic | DEVRDCT-359 | 36930 | FIX-Identity-Error |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 23/Dec/25 9:38 AM | 19/Jan/26 2:17 PM | [6 empty] | มาจาก Sprint 16 | To Do |  | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15 | [Dev][RD][CT] Sprint 16
Bug | DEVRDCT-358 | 36929 | [DEV][RD][HRS] Delay Auto CLUB_BINDING to Prevent Intermittent Identity Error | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Resolved |  | 23/Dec/25 8:59 AM | 19/Jan/26 2:17 PM |  | 2 |  |  |  |  | มาจาก Sprint 16 | Resolved |  | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15 | [Dev][RD][CT] Sprint 16
Test Plan | DEVRDCT-342 | 35712 | [TP] Sprint #13 |  |  | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 11/Dec/25 3:26 PM | 19/Jan/26 2:17 PM | [6 empty] | มาจาก Sprint 16 | To Do |  | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15 | [Dev][RD][CT] Sprint 16
Bug | RDAPS-316 | 35558 | [Dev][RD][RRS] Fix datetime filter logic to support millisecond precision for redemption ETL | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Pass : Waiting for deployment |  | 08/Dec/25 5:57 PM | 26/Jan/26 2:39 PM |  | 2 |  |  |  |  | มาจาก Sprint 16 | Pass : Waiting for deployment |  | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15 | [Dev][All Project] Sprint 16 | [Dev][All Project] Sprint 17
Epic | DEVRDCT-326 | 35192 | CT-POINT-ISSUE |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 01/Dec/25 9:58 AM | 19/Jan/26 2:17 PM | [6 empty] | มาจาก Sprint 16 | To Do |  | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15 | [Dev][RD][CT] Sprint 16
Epic | DEVRDCT-325 | 35191 | CTxSHOPIFY |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 01/Dec/25 9:55 AM | 19/Jan/26 2:17 PM | [6 empty] | มาจาก Sprint 16 | To Do |  | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15 | [Dev][RD][CT] Sprint 16
Epic | DEVRDCT-309 | 34545 | ct-member-tier |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 19/Nov/25 2:49 PM | 19/Jan/26 2:17 PM | [6 empty] | มาจาก Sprint 16 | To Do |  | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15 | [Dev][RD][CT] Sprint 16
Epic | DEVRDCT-308 | 34539 | ct-campaign-type |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 19/Nov/25 10:41 AM | 19/Jan/26 2:17 PM |  |  | redemption-api |  |  |  | มาจาก Sprint 16 | To Do |  | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15 | [Dev][RD][CT] Sprint 16
Story | DM-92 | 34424 | [DEV][RD][AWSTH] Partner Loyalty API pre-validation for dev environment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 17/Nov/25 11:10 AM | 05/Feb/26 3:47 PM | 29/Jan/26 12:00 AM | 2 | No-QA | partner-loyalty |  | 7200 | มาจาก Sprint 16 | In Progress | 7200 -> 3600 | [Dev][RD][AWS] Sprint 16 | [Dev][RD][AWS] Sprint 17
Story | DM-61 | 34340 | [DEV][RD][AWSTH] RR Member Acquisition pre-validation for dev environment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 14/Nov/25 6:29 PM | 05/Feb/26 3:47 PM | 02/Feb/26 12:00 AM | 2 | No-QA |  |  | 14400 | มาจาก Sprint 16 | To Do |  | [Dev][RD][AWS] Sprint 17
Story | DM-59 | 34337 | [DEV][RD][AWSTH] BTS Officer app pre-validation for dev environment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 14/Nov/25 6:24 PM | 05/Feb/26 3:47 PM | 06/Feb/26 12:00 AM | 2 | No-QA |  |  | 14400 | มาจาก Sprint 16 | To Do |  | [Dev][RD][AWS] Sprint 17
Story | DM-31 | 34302 | [DEV][RD][AWSTH] RR Scheduler pre-validation for dev environment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | To Do |  | 14/Nov/25 4:53 PM | 05/Feb/26 3:47 PM |  | 3 | No-QA |  |  |  | มาจาก Sprint 16 | To Do |  | [Dev][RD][AWS] Sprint 17
Story | DM-30 | 34301 | [DEV][RD][AWSTH] RR Member Web pre-validation for dev environment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 14/Nov/25 4:53 PM | 05/Feb/26 3:47 PM | 02/Feb/26 12:00 AM | 1 | No-QA |  |  | 7200 | มาจาก Sprint 16 | To Do |  | [Dev][RD][AWS] Sprint 17
Story | DM-29 | 34300 | [DEV][RD][AWSTH] RR Order API pre-validation for dev environment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 14/Nov/25 4:52 PM | 05/Feb/26 3:47 PM | 02/Feb/26 12:00 AM | 3 | No-QA |  |  | 28800 | มาจาก Sprint 16 | To Do |  | [Dev][RD][AWS] Sprint 17
Story | DM-28 | 34299 | [DEV][RD][AWSTH] RR Link Notify API pre-validation for dev environment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | In Progress |  | 14/Nov/25 4:52 PM | 05/Feb/26 3:58 PM | 06/Feb/26 12:00 AM | 2 | No-QA |  |  | 14400 | มาจาก Sprint 16 | To Do |  | [Dev][RD][AWS] Sprint 17
Story | DM-27 | 34298 | [DEV][RD][AWSTH] RR CronJob pre-validation for dev environment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 14/Nov/25 4:52 PM | 05/Feb/26 3:47 PM | 04/Feb/26 12:00 AM | 1 | No-QA |  |  | 7200 | มาจาก Sprint 16 | To Do |  | [Dev][RD][AWS] Sprint 17
Story | DM-26 | 34297 | [DEV][RD][AWSTH] RR CloudID API pre-validation for dev environment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 14/Nov/25 4:51 PM | 05/Feb/26 3:47 PM | 05/Feb/26 12:00 AM | 3 | No-QA |  |  | 28800 | มาจาก Sprint 16 | To Do |  | [Dev][RD][AWS] Sprint 17
Story | DM-25 | 34296 | [DEV][RD][AWSTH] RR Datahub GQL pre-validation for dev environment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 14/Nov/25 4:51 PM | 05/Feb/26 3:47 PM | 03/Feb/26 12:00 AM | 1 | No-QA |  |  | 7200 | มาจาก Sprint 16 | To Do |  | [Dev][RD][AWS] Sprint 17
Story | DM-24 | 34295 | [DEV][RD][AWSTH] RR CleverTap pre-validation for dev environment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 14/Nov/25 4:51 PM | 05/Feb/26 3:47 PM | 04/Feb/26 12:00 AM | 1 | No-QA |  |  | 7200 | มาจาก Sprint 16 | To Do |  | [Dev][RD][AWS] Sprint 17
Story | DM-23 | 34294 | [DEV][RD][AWSTH] RR Cart API pre-validation for dev environment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 14/Nov/25 4:50 PM | 05/Feb/26 3:47 PM |  | 2 | No-QA |  |  | 7200 | มาจาก Sprint 16 | To Do |  | [Dev][RD][AWS] Sprint 17
Story | DM-22 | 34293 | [DEV][RD][AWSTH] RR BackOffice pre-validation for dev environment |  |  | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | To Do |  | 14/Nov/25 4:49 PM | 05/Feb/26 3:47 PM |  | 3 | No-QA |  |  |  | มาจาก Sprint 16 | To Do |  | [Dev][RD][AWS] Sprint 17
Story | DM-21 | 34292 | [DEV][RD][AWSTH] RR Athena API pre-validation for dev environment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 14/Nov/25 4:49 PM | 05/Feb/26 3:47 PM | 03/Feb/26 12:00 AM | 1 | No-QA |  |  | 7200 | มาจาก Sprint 16 | To Do |  | [Dev][RD][AWS] Sprint 17
Story | DM-20 | 34291 | [DEV][RD][AWSTH] RR Aphrodite pre-validation for dev environment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 14/Nov/25 4:49 PM | 05/Feb/26 5:11 PM | 06/Feb/26 12:00 AM | 2 | No-QA |  |  | 14400 | มาจาก Sprint 16 | To Do |  | [Dev][RD][AWS] Sprint 17
Story | DM-19 | 34290 | [DEV][RD][AWSTH] Rewards Consumer pre-validation for dev environment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 14/Nov/25 4:48 PM | 05/Feb/26 3:47 PM | 06/Feb/26 12:00 AM | 3 | No-QA |  |  | 28800 | มาจาก Sprint 16 | To Do |  | [Dev][RD][AWS] Sprint 17
Story | DM-18 | 34289 | [DEV][RD][AWSTH] Rewards API pre-validation for dev environment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 14/Nov/25 4:48 PM | 05/Feb/26 3:47 PM | 02/Feb/26 12:00 AM | 1 | No-QA |  |  | 28800 | มาจาก Sprint 16 | To Do |  | [Dev][RD][AWS] Sprint 17
Story | DM-17 | 34288 | [DEV][RD][AWSTH] Redemption Consumer pre-validation for dev environment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 14/Nov/25 4:48 PM | 05/Feb/26 3:47 PM | 04/Feb/26 12:00 AM | 3 | No-QA |  |  | 28800 | มาจาก Sprint 16 | To Do |  | [Dev][RD][AWS] Sprint 17
Story | DM-16 | 34287 | [DEV][RD][AWSTH] Redemption API pre-validation for dev environment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 14/Nov/25 4:48 PM | 05/Feb/26 3:47 PM | 02/Feb/26 12:00 AM | 3 | No-QA |  |  | 28800 | มาจาก Sprint 16 | To Do |  | [Dev][RD][AWS] Sprint 17
Story | DM-15 | 34286 | [DEV][RD][AWSTH] Rabbit Sky Web pre-validation for dev environment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 14/Nov/25 4:47 PM | 05/Feb/26 3:47 PM | 02/Feb/26 12:00 AM | 3 | No-QA |  |  | 28800 | มาจาก Sprint 16 | To Do |  | [Dev][RD][AWS] Sprint 17
Story | DM-14 | 34285 | [DEV][RD][AWSTH] Rabbit Sky API pre-validation for dev environment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 14/Nov/25 4:47 PM | 05/Feb/26 3:47 PM | 30/Jan/26 12:00 AM | 1 |  |  |  | 7200 | มาจาก Sprint 16 | To Do |  | [Dev][RD][AWS] Sprint 17
Story | DM-13 | 34284 | [DEV][RD][AWSTH] Rabbit CMS API pre-validation for dev environment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 14/Nov/25 4:46 PM | 05/Feb/26 3:47 PM | 03/Feb/26 12:00 AM | 3 | No-QA |  |  | 28800 | มาจาก Sprint 16 | To Do |  | [Dev][RD][AWS] Sprint 17
Story | DM-12 | 34283 | [DEV][RD][AWSTH] Rabbit App BFF pre-validation for dev environment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 14/Nov/25 4:46 PM | 05/Feb/26 3:47 PM | 04/Feb/26 12:00 AM | 3 | No-QA |  |  | 28800 | มาจาก Sprint 16 | To Do |  | [Dev][RD][AWS] Sprint 17
Story | DM-11 | 34282 | [DEV][RD][AWSTH] Point Engine Proxy pre-validation for dev environment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 14/Nov/25 4:46 PM | 05/Feb/26 3:47 PM |  | 1 | No-QA |  |  | 7200 | มาจาก Sprint 16 | To Do |  | [Dev][RD][AWS] Sprint 17
Story | DM-10 | 34281 | [DEV][RD][AWSTH] Offline Subscription BFF pre-validation for dev environment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 14/Nov/25 4:46 PM | 05/Feb/26 3:47 PM | 04/Feb/26 12:00 AM | 3 | No-QA |  |  | 28800 | มาจาก Sprint 16 | To Do |  | [Dev][RD][AWS] Sprint 17
Story | DM-9 | 34280 | [DEV][RD][AWSTH] Notification API pre-validation for dev environment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 14/Nov/25 4:42 PM | 05/Feb/26 3:47 PM | 02/Feb/26 12:00 AM | 1 | No-QA |  |  | 0 | มาจาก Sprint 16 | To Do |  | [Dev][RD][AWS] Sprint 17
Story | DM-7 | 34278 | [DEV][RD][AWSTH] Merchant API pre-validation for dev environment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 14/Nov/25 4:41 PM | 05/Feb/26 3:47 PM | 02/Feb/26 12:00 AM | 1 | No-QA |  |  | 7200 | มาจาก Sprint 16 | To Do |  | [Dev][RD][AWS] Sprint 17
Story | DM-6 | 34277 | [DEV][RD][AWSTH] HR Solution pre-validation for dev environment |  |  | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | To Do |  | 14/Nov/25 4:40 PM | 05/Feb/26 3:47 PM |  | 3 | No-QA |  |  |  | มาจาก Sprint 16 | To Do |  | [Dev][RD][AWS] Sprint 17
Story | DM-5 | 34276 | [DEV][RD][AWSTH] Exclusive Store API pre-validation for dev environment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 14/Nov/25 4:39 PM | 05/Feb/26 3:47 PM | 02/Feb/26 12:00 AM | 1 | No-QA |  |  | 7200 | มาจาก Sprint 16 | To Do |  | [Dev][RD][AWS] Sprint 17
Story | DM-4 | 34274 | [DEV][RD][AWSTH] DeepLink API pre-validation for dev environment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 14/Nov/25 4:37 PM | 05/Feb/26 3:47 PM | 30/Jan/26 12:00 AM | 1 | No-QA |  |  | 7200 | มาจาก Sprint 16 | To Do |  | [Dev][RD][AWS] Sprint 17
Bug | RDAPS-269 | 34036 | [DEV][RD][Cron-job][Merchant Ranking] Enhance get merchant with active store only | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Pass : Waiting for deployment |  | 11/Nov/25 1:09 PM | 26/Jan/26 2:39 PM |  | 2 | No-QA |  |  |  | มาจาก Sprint 16 | Pass : Waiting for deployment |  | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15 | [Dev][All Project] Sprint 16 | [Dev][All Project] Sprint 17
Story | RDAPS-160 | 29972 | [DEV][RD][SSO-Backoffice] Disable SEO tracking | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 20/Aug/25 11:21 AM | 26/Jan/26 2:39 PM | 04/Sep/25 12:00 AM | 1 |  |  |  | 0 | มาจาก Sprint 16 | Ready To Test | 7200 | [Dev][All project]Sprint 6 | [Dev][All project]Sprint 7 | [Dev][All Project] Sprint 9 | [Dev][All Project] Sprint 10 | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15 | [Dev][All Project] Sprint 16 | [Dev][All Project] Sprint 17

## Summarize Sprint 16
Column 1 | Total Stories Point | Total Manhour | Point Done | Manhour Done | Note
12 Jan - 23 Jan
Dev Resource Available | 15 | 416
Meeting Planned |  |  |  |  | Ref
Additional Meeting |  |  |  |  | Ref
Deployment |  | 6 |  |  | 4 ครั้ง 1. 2 คน 2. 2 คน 3. 1 คน 4. 1 คน
Development Sprint Total | 297 | 163 | 124 | 61
Ad-hoc Mid Sprint | 0 | 0 | 0 | 0 | 0 tasks
Requirement changes after refinement? | 0 |  | 0 | 0 | 0 tasks
Aek | 5 | 3 | 2 | 3
A | 11 | 24 | 7 | 24
Aom | 47 | 34 | 24 | 34
Zan | 27 | 0 | 25 | 0
Mai | 31 | 0 | 12 | 0
Mac | 22 | 38 | 0 | 0
Mos | 35 | 0 | 18 | 0
Jack | 0 | 0 | 0 | 0
Nim | 29 | 48 | 17 | 0
Arm | 29 | 16 | 19 | 0
| System Architech |  |  |  | Permanent Dev. |  |  | Outsources
Projects (Stories Points) | Aek | Zan | Aom | Jack | A | Art | Mai | Kae | Mac | Nim | Mos | Arm
Das Haus - Thana City & Das Haus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E-commerce 1.1. E-Commerce x Shopify Plus 1.2. Shopify:Snackmaker 1.3. Shopify: Turtle Delivery 1.4. Shopify: Turtle Delivery | 5 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 5 | 12 | 11
CleverTap - MKT Automation Tool | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 2 | 0
Adjust Integration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Adhoc - Non-Epics - Turtle Display club tier on POS - Data Mart Migration | 0 | 27 | 15 | 0 | 0 | 0 | 10 | 0 | 3 | 0 | 6 | 8
Support Incidents | 0 | 0 | 9 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 | 0
| System Architech |  |  |  | Permanent Dev. |  |  | Outsources
Projects (Manhour) | Aek | Zan | Aom | Jack | A | Art | Mai | Kae | Mac | Nim | Mos | Arm
Das Haus - Thana City & Das Haus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E-commerce 1.1. E-Commerce x Shopify Plus 1.2. Shopify:Snackmaker 1.3. Shopify: Turtle Delivery 1.4. Shopify: Turtle Delivery | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CleverTap - MKT Automation Tool | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Adjust Integration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Adhoc - Non-Epics - Turtle Display club tier on POS - Data Mart Migration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Support Incidents | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 16
Issue Type | Issue key | Issue id | Summary | Assignee | Assignee Id | Reporter | Reporter Id | Priority | Status | Resolution | Created | Updated | Due date | Custom field (Story Points) | Labels | Labels | Labels | Original estimate | Sprint Movement | Sprint 15 | Note | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint
Story | RDAPS-404 | 40133 | [DEV][RD][HRS] Run bulk inactive member | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 22/Jan/26 7:34 PM | 23/Jan/26 3:01 AM |  | 1 | [7 empty] | [Dev][All Project] Sprint 16
Story | DEVRDSUP-389 | 39980 | [SUP-462]SUB : Request to remove rr_finance@rabbit.co.th from the auto email loop when refunds are processed. | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Thanakrit Chanthaworn | 712020:3fc982cb-c268-4f1d-9265-d3dd8fb08304 | Medium | Ready to Staging |  | 21/Jan/26 2:10 PM | 22/Jan/26 11:57 AM |  | 1 | mid-sprint | sub | [5 empty] | [Dev][All Project] Sprint 16
Sub-task | DPWP-27 | 39934 | [QA] Create test case refund transaction and reverse points API |  |  | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 21/Jan/26 10:09 AM | 21/Jan/26 10:09 AM | [9 empty] | [Dev][RD][PWP] Sprint 16
Sub-task | DPWP-26 | 39932 | [QA] Create test case mark transaction as completed after merchant confirms order API | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 21/Jan/26 10:09 AM | 21/Jan/26 10:09 AM | [9 empty] | [Dev][RD][PWP] Sprint 16
Sub-task | DPWP-25 | 39930 | [QA] Create test case process payment after customer confirm payment API | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 21/Jan/26 10:08 AM | 21/Jan/26 10:08 AM | [9 empty] | [Dev][RD][PWP] Sprint 16
Sub-task | DPWP-24 | 39928 | [QA] Create test case retrieve a transaction information API | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | In Progress |  | 21/Jan/26 10:07 AM | 21/Jan/26 10:12 AM | [9 empty] | [Dev][RD][PWP] Sprint 16
Sub-task | DPWP-23 | 39926 | [QA] Create test case process payment after customer scans QR API | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | In Progress |  | 21/Jan/26 10:06 AM | 21/Jan/26 10:06 AM | [9 empty] | [Dev][RD][PWP] Sprint 16
Sub-task | DPWP-22 | 39924 | [QA] Create test case create a new Point Payment transaction API | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | In Progress |  | 21/Jan/26 10:06 AM | 21/Jan/26 10:06 AM | [9 empty] | [Dev][RD][PWP] Sprint 16
Sub-task | RDAPS-402 | 39885 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 20/Jan/26 9:41 PM | 20/Jan/26 9:45 PM | [9 empty] | [Dev][All Project] Sprint 16
Sub-task | RDAPS-401 | 39817 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 20/Jan/26 1:32 PM | 20/Jan/26 1:33 PM | [9 empty] | [Dev][All Project] Sprint 16
Story | RDAPS-400 | 39745 | [Dev][RD][ORD] Prevent Receipt Number Skipping & Ensure Sequential Generation | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 20/Jan/26 9:17 AM | 22/Jan/26 4:47 PM |  | 13 | [7 empty] | [Dev][All Project] Sprint 16
Bug | RDAPS-399 | 39656 | [DEV][RD][HRS] Background API sill woking on scheduled upload import | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Closed |  | 19/Jan/26 2:06 PM | 20/Jan/26 5:00 PM |  | 1 | No-QA | [6 empty] | [Dev][All Project] Sprint 16
Epic | RDAPS-398 | 39575 | HR-MEMBER-REFACTOR |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 19/Jan/26 10:59 AM | 19/Jan/26 10:59 AM | [9 empty] | [Dev][All Project] Sprint 16
Story | RDAPS-397 | 39574 | [DEV][RD][HRS] Disable to select BU when BU was inactive for import member | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 19/Jan/26 10:53 AM | 20/Jan/26 9:41 PM | 19/Jan/26 12:00 AM | 1 | [7 empty] | [Dev][All Project] Sprint 16
Story | RDAPS-396 | 39572 | [DEV][RD][HRS] Separate loading import page | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Done |  | 19/Jan/26 10:37 AM | 20/Jan/26 9:45 PM | 19/Jan/26 12:00 AM | 2 | [7 empty] | [Dev][All Project] Sprint 16
Story | DEVRDECOM-238 | 39538 | [DEV][RD][Ecom][Ecommercd-Shopify] Enhance Warehouse Status Cronjob: Add Request Delay and Exclude Cancelled Orders | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 19/Jan/26 9:19 AM | 22/Jan/26 4:47 PM |  | 1 | [7 empty] | [Dev][RD][Ecom] Sprint 16
Story | RDNDA-15 | 39177 | [DEV][RD][TDM] Consult shopify webhook and view tables for OM | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 15/Jan/26 10:15 AM | 21/Jan/26 11:33 AM |  |  | No-QA | rr-ecommerce-shopify | [5 empty] | [Dev][RD][NewDamart] Sprint 16
Story | RDAPS-395 | 39174 | [DEV][RD][HR] Check and optimize Import member support more than 2000+ record | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 15/Jan/26 9:56 AM | 23/Jan/26 12:12 PM |  | 8 | [7 empty] | [Dev][All Project] Sprint 16
Story | DM-179 | 39009 | [DEV][RD][AWSTH] Update app to read env from OS | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 14/Jan/26 11:13 AM | 23/Jan/26 10:02 AM | 15/Jan/26 12:00 AM | 3 | No-QA |  |  | 28800 |  |  |  | [Dev][RD][AWS] Sprint 16
Story | DM-178 | 38944 | [DEV][RD][AWSTH] Update application port following with DevOps concept | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Highest | Done |  | 14/Jan/26 10:21 AM | 23/Jan/26 10:03 AM | 15/Jan/26 12:00 AM | 3 | No-QA |  |  | 28800 |  |  |  | [Dev][RD][AWS] Sprint 16
Sub-task | RDAPS-394 | 38903 | [QA] Test check API route using through DA (UAT) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 13/Jan/26 8:37 PM | 14/Jan/26 4:46 PM | [9 empty] | [Dev][All Project] Sprint 15 | [Dev][All Project] Sprint 16
Sub-task | RDAPS-393 | 38834 | [QA] Check log from 8x8 SMS OTP | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 13/Jan/26 12:03 PM | 13/Jan/26 12:07 PM | [9 empty] | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15 | [Dev][All Project] Sprint 16
Bug | DEVRDSUP-373 | 38766 | [SUP-443][Issue from MIX team] Subscription Voucher Issue of Dec 25 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Rejected |  | 13/Jan/26 10:11 AM | 19/Jan/26 3:22 PM | 13/Jan/26 12:00 AM |  | etl | mid-sprint | prod-issue |  |  |  |  | [Dev][All Project] Sprint 16
Story | DEVRDSUP-372 | 38731 | [SUP-446]Request to export reward TXN report data due to issue on RR backoffice where data can't be exported. (Turtle shop) | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Done |  | 12/Jan/26 5:51 PM | 23/Jan/26 12:28 PM | 13/Jan/26 12:00 AM | 1 | BURequest | rem | turtle |  |  |  |  | [Dev][All Project] Sprint 16
Sub-task | DEVRDECOM-237 | 38717 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 12/Jan/26 3:15 PM | 21/Jan/26 1:25 PM | [9 empty] | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15 | [Dev][RD][Ecom] Sprint 16
Sub-task | DEVRDECOM-236 | 38715 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 12/Jan/26 3:15 PM | 19/Jan/26 1:35 PM | [9 empty] | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15 | [Dev][RD][Ecom] Sprint 16
Sub-task | DEVRDECOM-235 | 38713 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 12/Jan/26 3:14 PM | 19/Jan/26 1:35 PM | [9 empty] | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15 | [Dev][RD][Ecom] Sprint 16
Story | DEVRDECOM-231 | 38597 | [DEV][RD][Estimate] Est. mandays & timeline Sync Customer Data from Shopify Event to Data Mart | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 11/Jan/26 7:34 PM | 19/Jan/26 11:20 AM |  | 1 |  |  |  | 3600 |  |  |  | [Dev][RD][Ecom] Sprint 16
Story | RDNDA-14 | 38512 | [DEV][RD][TDM] Create migration | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 09/Jan/26 1:48 PM | 15/Jan/26 9:36 AM |  | 2 | No-QA | ThanaDataMart | [5 empty] | [Dev][RD][NewDamart] Sprint 16
Test Plan | DEVRDECOM-230 | 38511 | [TP][RR-Backoffice][Ecommerce Shopify] Sprint15 | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 09/Jan/26 1:29 PM | 20/Jan/26 11:21 AM | [9 empty] | [Dev][RD][Ecom] Sprint 15 | [Dev][RD][Ecom] Sprint 16
Story | RDAPS-390 | 38471 | [DEV][RD][HRS] Handle wrong Date format in precheck import process | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 09/Jan/26 9:57 AM | 13/Jan/26 3:33 PM | [5 empty] | 0 | มาจาก Sprint 15 | Ready to Staging | 7200 | [Dev][All Project] Sprint 15 | [Dev][All Project] Sprint 16
Story | DPWP-18 | 38437 | [Dev][RD][PWP] Initial Project Repository for Pay with Point Scheduler appp | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 08/Jan/26 6:48 PM | 23/Jan/26 10:07 AM |  | 5 | No-QA | [6 empty] | [Dev][RD][PWP] Sprint 16
Story | RDNDA-12 | 38435 | [DEV][RD][TDM] Integrate Discord for error log | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 08/Jan/26 5:23 PM | 22/Jan/26 11:23 AM | [9 empty] | [Dev][RD][NewDamart] Sprint 16
Story | RDNDA-11 | 38434 | [DEV][RD][TDM] Create producer function for push kinesis data | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 08/Jan/26 5:22 PM | 20/Jan/26 3:27 PM |  | 3 | [7 empty] | [Dev][RD][NewDamart] Sprint 16
Sub-task | DEVRDECOM-229 | 38428 | [QA] Test execution UAT | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 08/Jan/26 4:23 PM | 14/Jan/26 3:43 PM | [6 empty] | มาจาก Sprint 15 | To Do |  | [Dev][RD][Ecom] Sprint 15 | [Dev][RD][Ecom] Sprint 16
Story | DM-160 | 38317 | [DEV][RD][AWSTH] Update DB connection to support primary/replica architecture for Partner Loyalty API | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 08/Jan/26 11:41 AM | 23/Jan/26 11:54 AM |  | 1 | No-QA | partner-loyalty |  | 28800 |  |  |  | [Dev][RD][AWS] Sprint 16
Story | RDAPS-388 | 38313 | [SA][RD][Thana City Datamart] Create task for sprint 16 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 08/Jan/26 10:17 AM | 15/Jan/26 9:54 AM |  | 8 |  |  |  |  | มาจาก Sprint 15 | In Progress |  | [Dev][All Project] Sprint 15 | [Dev][All Project] Sprint 16
Sub-task | DEVRDECOM-228 | 38276 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 07/Jan/26 6:18 PM | 16/Jan/26 2:43 PM | [6 empty] | มาจาก Sprint 15 | To Do |  | [Dev][RD][Ecom] Sprint 15 | [Dev][RD][Ecom] Sprint 16
Sub-task | DEVRDECOM-227 | 38274 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 07/Jan/26 6:18 PM | 16/Jan/26 2:43 PM | [6 empty] | มาจาก Sprint 15 | To Do |  | [Dev][RD][Ecom] Sprint 15 | [Dev][RD][Ecom] Sprint 16
Sub-task | DEVRDECOM-224 | 38268 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Progress |  | 07/Jan/26 6:18 PM | 09/Jan/26 4:59 PM | [6 empty] | มาจาก Sprint 15 | To Do |  | [Dev][RD][Ecom] Sprint 15 | [Dev][RD][Ecom] Sprint 16
Sub-task | DEVRDECOM-223 | 38266 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Progress |  | 07/Jan/26 6:18 PM | 09/Jan/26 4:59 PM | [6 empty] | มาจาก Sprint 15 | To Do |  | [Dev][RD][Ecom] Sprint 15 | [Dev][RD][Ecom] Sprint 16
Story | RDNDA-9 | 38247 | [DEV][RD][TDM] Create client middleware | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 07/Jan/26 5:19 PM | 19/Jan/26 9:57 AM |  | 3 | [7 empty] | [Dev][RD][NewDamart] Sprint 16
Story | RDNDA-8 | 38246 | [DEV][RD][TDM] Create Push to Kinesis Consumer | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 07/Jan/26 5:19 PM | 21/Jan/26 4:00 PM | 21/Jan/26 12:00 AM | 3 |  |  |  | 28800 |  |  |  | [Dev][RD][NewDamart] Sprint 16
Story | RDNDA-7 | 38245 | [DEV][RD][TDM][POC] Push data to kinesis | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 07/Jan/26 5:18 PM | 20/Jan/26 9:10 AM | 16/Jan/26 12:00 AM | 5 | No-QA | ThanaDataMart |  | 57600 |  |  |  | [Dev][RD][NewDamart] Sprint 16
Story | RDNDA-6 | 38244 | [DEV][RD][TDM] Create generic transactions endpoint | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 07/Jan/26 5:17 PM | 21/Jan/26 4:32 PM |  | 5 |  |  |  | 86400 |  |  |  | [Dev][RD][NewDamart] Sprint 16
Story | RDNDA-5 | 38243 | [DEV][RD][TDM] Initial project | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 07/Jan/26 5:16 PM | 15/Jan/26 2:30 PM |  | 5 | No-QA | ThanaDataMart | [5 empty] | [Dev][RD][NewDamart] Sprint 16
Sub-task | DEVRDECOM-214 | 38206 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 07/Jan/26 2:13 PM | 12/Jan/26 3:14 PM | [6 empty] | มาจาก Sprint 15 | To Do |  | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15 | [Dev][RD][Ecom] Sprint 16
Sub-task | DEVRDECOM-213 | 38204 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 07/Jan/26 2:13 PM | 12/Jan/26 2:15 PM | [6 empty] | มาจาก Sprint 15 | In Progress |  | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15 | [Dev][RD][Ecom] Sprint 16
Sub-task | DEVRDECOM-212 | 38202 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 07/Jan/26 2:12 PM | 12/Jan/26 10:26 AM | [6 empty] | มาจาก Sprint 15 | In Progress |  | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15 | [Dev][RD][Ecom] Sprint 16
Story | DEVRDECOM-211 | 38128 | [DEV][RD][POC] Member data for datamart | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 07/Jan/26 9:30 AM | 19/Jan/26 11:19 AM |  | 1 |  |  |  | 7200 |  |  |  | [Dev][RD][Ecom] Sprint 16
Story | RDAPS-384 | 38127 | [Dev][RD][Enhancement][REM Consumer] Add x-request-id header for outbound API calls to DA | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 07/Jan/26 9:15 AM | 14/Jan/26 4:46 PM |  | 3 |  |  |  | 0 | มาจาก Sprint 15 | Ready to Staging | 28800 | [Dev][All Project] Sprint 15 | [Dev][All Project] Sprint 16
Story | DPWP-13 | 38055 | [Dev][RD][PWP] Create API to refund transaction and reverse points | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 06/Jan/26 6:55 PM | 23/Jan/26 9:10 AM |  | 5 | [7 empty] | [Dev][RD][PWP] Sprint 16
Story | DPWP-12 | 38054 | [Dev][RD][PWP] Create API to mark transaction as completed after merchant confirms order | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 06/Jan/26 6:52 PM | 21/Jan/26 4:32 PM |  | 5 |  |  |  | 86400 |  |  |  | [Dev][RD][PWP] Sprint 16
Story | DPWP-11 | 38053 | [Dev][RD][PWP] Create API to process payment after customer confirm payment | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 06/Jan/26 6:47 PM | 20/Jan/26 5:15 PM |  | 8 | [7 empty] | [Dev][RD][PWP] Sprint 16
Story | RDAPS-382 | 37978 | [Dev][RD][SSO-User] Improve query strategies for card type and card range retrieval | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready to Staging |  | 06/Jan/26 11:23 AM | 13/Jan/26 1:51 PM | [6 empty] | มาจาก Sprint 15 | Ready to Staging |  | [Dev][All Project] Sprint 15 | [Dev][All Project] Sprint 16
Story | DPWP-10 | 37976 | [Dev][RD][PWP] Create API to retrieve a transaction information | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 06/Jan/26 11:10 AM | 20/Jan/26 2:57 PM | 20/Jan/26 12:00 AM | 3 |  |  |  | 21600 |  |  |  | [Dev][RD][PWP] Sprint 16
Story | DPWP-9 | 37926 | [Dev][RD][PWP] Create API to process payment after customer scans QR | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 05/Jan/26 6:06 PM | 22/Jan/26 5:57 PM |  | 5 | [7 empty] | [Dev][RD][PWP] Sprint 16
Story | DPWP-8 | 37906 | [Dev][RD][PWP] Create API to create a new Point Payment transaction | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 05/Jan/26 1:25 PM | 20/Jan/26 9:09 AM | 19/Jan/26 12:00 AM | 8 | pay-with-point-api |  |  | 86400 |  |  |  | [Dev][RD][PWP] Sprint 16
Story | DPWP-7 | 37865 | [Dev][RD][PWP] Create database migration for new schemas | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Done |  | 05/Jan/26 12:05 PM | 15/Jan/26 3:47 PM |  | 3 | No-QA |  |  | 28800 |  |  |  | [Dev][RD][PWP] Sprint 16
Story | DPWP-6 | 37864 | [Dev][RD][SA] Request Github Repository for Pay with Point | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 05/Jan/26 12:04 PM | 15/Jan/26 3:47 PM |  | 1 |  |  |  | 3600 |  |  |  | [Dev][RD][PWP] Sprint 15 | [Dev][RD][PWP] Sprint 16
Story | DPWP-4 | 37469 | [Dev][RD][SA] Request Database for Pay with Point | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 29/Dec/25 1:39 PM | 15/Jan/26 3:47 PM |  | 1 |  |  |  | 3600 |  |  |  | [Dev][RD][PWP] Sprint 15 | [Dev][RD][PWP] Sprint 16
Story | DPWP-3 | 37468 | [Dev][RD][PWP] Initial Project Repository for Pay with Point APIs | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Done |  | 29/Dec/25 1:39 PM | 15/Jan/26 3:46 PM |  | 5 |  |  |  | 86400 |  |  |  | [Dev][RD][PWP] Sprint 16
Story | DPWP-2 | 37467 | [Dev][RD][SA] Analyze and breakdown task for implementation phasee | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 29/Dec/25 1:38 PM | 14/Jan/26 10:15 AM |  | 13 | [7 empty] | [Dev][RD][PWP] Sprint 15 | [Dev][RD][PWP] Sprint 16
Story | DEVRDECOM-210 | 37465 | [DEV][RD][Ecom][Ecommerce-Shopify] Enhance Shopify Order Paid & Refund Payment Mapping and CleverTap Transaction Sync | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 29/Dec/25 10:46 AM | 19/Jan/26 2:21 PM |  | 3 |  |  |  | 0 | มาจาก Sprint 15 | Ready to Staging | 28800 | [Dev][RD][Ecom] Sprint 15 | [Dev][RD][Ecom] Sprint 16
Story | RDAPS-379 | 37463 | [DEV][RD][SA] Design system for Thana City Datamart API | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 29/Dec/25 10:12 AM | 15/Jan/26 9:54 AM |  | 8 |  |  |  |  | มาจาก Sprint 15 | In Progress |  | [Dev][All Project] Sprint 15 | [Dev][All Project] Sprint 16
Story | DEVRDECOM-209 | 37450 | [DEV][RD][Ecom][RR-Backoffice] Implement Backoffice for Shopify Member enhancement to support tag management | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 29/Dec/25 9:37 AM | 19/Jan/26 2:20 PM |  | 5 |  |  |  | 0 | มาจาก Sprint 15 | Ready To Test | 57600 | [Dev][RD][Ecom] Sprint 15 | [Dev][RD][Ecom] Sprint 16
Story | DEVRDECOM-208 | 36982 | [DEV][RD][Ecom][Ecommerce-Shopify] Add created_by and updated_by columns to shopify_shops and shopify_credentials table | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 23/Dec/25 2:44 PM | 22/Jan/26 4:47 PM | 24/Dec/25 12:00 AM | 1 |  |  |  | 0 | มาจาก Sprint 15 | Ready To Test | 7200 | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15 | [Dev][RD][Ecom] Sprint 16
Story | RDAPS-372 | 36975 | [Dev][RD][Technical] Refactor TXN Report API and Report Summary API to remove dependency on MVP Phase 1 report source | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready to Staging |  | 23/Dec/25 12:23 PM | 22/Jan/26 5:11 PM | 30/Dec/25 12:00 AM | 3 |  |  |  | 0 | มาจาก Sprint 15 | Ready to Staging | 28800 | [Dev][All Project] Sprint 15 | [Dev][All Project] Sprint 16
Story | RDAPS-371 | 36968 | [DEV][RD][HRS] Create cancel button for schedule upload | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 23/Dec/25 11:16 AM | 13/Jan/26 3:35 PM |  | 3 |  |  |  | 0 | มาจาก Sprint 15 | Ready To Test | 28800 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15 | [Dev][All Project] Sprint 16
Epic | DEVRDCT-359 | 36930 | FIX-Identity-Error |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 23/Dec/25 9:38 AM | 19/Jan/26 2:17 PM | [6 empty] | มาจาก Sprint 15 | To Do |  | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15 | [Dev][RD][CT] Sprint 16
Bug | DEVRDCT-358 | 36929 | [DEV][RD][HRS] Delay Auto CLUB_BINDING to Prevent Intermittent Identity Error | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Resolved |  | 23/Dec/25 8:59 AM | 19/Jan/26 2:17 PM |  | 2 |  |  |  |  | มาจาก Sprint 15 | Resolved |  | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15 | [Dev][RD][CT] Sprint 16
Story | RDAPS-370 | 36861 | [DEV][RD][HRS] Enhance update import data log when empty employee id | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 22/Dec/25 3:49 PM | 13/Jan/26 3:38 PM |  | 3 |  |  |  | 0 | มาจาก Sprint 15 | Ready To Test | 28800 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15 | [Dev][All Project] Sprint 16
Test Plan | RDAPS-368 | 36821 | [TP] MEMBER-ENHANCEMENT |  |  | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 22/Dec/25 10:48 AM | 19/Jan/26 2:01 PM | [6 empty] | มาจาก Sprint 15 | To Do |  | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15 | [Dev][All Project] Sprint 16
Sub-task | DEVRDECOM-207 | 36760 | Integrate frontend with Shopify shops API endpoints | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Medium | Done |  | 22/Dec/25 10:30 AM | 24/Dec/25 9:06 AM | [6 empty] | มาจาก Sprint 15 | Done |  | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15 | [Dev][RD][Ecom] Sprint 16
Sub-task | DEVRDECOM-206 | 36758 | Develop frontend create/edit form with validation for Shopify shops | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Medium | Done |  | 22/Dec/25 10:30 AM | 24/Dec/25 9:06 AM | [6 empty] | มาจาก Sprint 15 | Done |  | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15 | [Dev][RD][Ecom] Sprint 16
Sub-task | DEVRDECOM-205 | 36757 | Implement API endpoint for Shopify shops datatable | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Medium | Done |  | 22/Dec/25 10:29 AM | 22/Dec/25 10:31 AM | [6 empty] | มาจาก Sprint 15 | Done |  | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15 | [Dev][RD][Ecom] Sprint 16
Sub-task | DEVRDECOM-204 | 36756 | Implement API endpoints for Create, Read, and Update Shopify shops | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Medium | Done |  | 22/Dec/25 10:29 AM | 24/Dec/25 9:06 AM | [6 empty] | มาจาก Sprint 15 | Done |  | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15 | [Dev][RD][Ecom] Sprint 16
Sub-task | DEVRDECOM-202 | 36755 | Create frontend template for Backoffice Shopify shops | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Medium | Done |  | 22/Dec/25 10:29 AM | 24/Dec/25 9:06 AM | [6 empty] | มาจาก Sprint 15 | Done |  | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15 | [Dev][RD][Ecom] Sprint 16
Sub-task | DEVRDECOM-203 | 36753 | Create API template for Shopify shops module | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Medium | Done |  | 22/Dec/25 10:29 AM | 22/Dec/25 10:31 AM | [6 empty] | มาจาก Sprint 15 | Done |  | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15 | [Dev][RD][Ecom] Sprint 16
Story | RDAPS-349 | 36428 | [Dev][RD][PL] Add 8x8 SMS Logging for RequestOtp Function | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 18/Dec/25 9:54 AM | 23/Jan/26 12:18 PM | 19/Dec/25 12:00 AM | 2 |  |  |  | 0 | มาจาก Sprint 15 | Ready To Test | 115200 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15 | [Dev][All Project] Sprint 16
Story | DEVRDECOM-201 | 36281 | [DEV][RD][Ecom][Ecommerce-Shopify] Enhance Shopify Webhook Processing: Add Delay for Refund Update Flow | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 17/Dec/25 9:16 AM | 22/Jan/26 4:47 PM |  | 3 |  |  |  | 0 | มาจาก Sprint 15 | Ready To Test | 43200 | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15 | [Dev][RD][Ecom] Sprint 16
Story | RDAPS-347 | 36157 | [Dev][RD][Enhancement][REM] Add x-request-id header for outbound API calls to DA | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 16/Dec/25 11:06 AM | 14/Jan/26 4:46 PM |  | 3 |  |  |  | 0 | มาจาก Sprint 15 | Ready To Test | 28800 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15 | [Dev][All Project] Sprint 16
Story | RDAPS-346 | 36156 | [Dev][RD][Enhancement][ORD] Add x-request-id header for outbound API calls to DA | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 16/Dec/25 11:06 AM | 14/Jan/26 4:46 PM |  | 3 |  |  |  | 0 | มาจาก Sprint 15 | Ready To Test | 28800 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15 | [Dev][All Project] Sprint 16
Story | DEVRDECOM-199 | 35956 | [DEV][RD][Ecom][RR-Backoffice] Implement Backoffice for Shopify Refunds | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 15/Dec/25 10:38 AM | 19/Jan/26 2:20 PM |  | 5 |  |  |  |  | มาจาก Sprint 15 | Ready to Staging |  | [Dev][RD][Ecom] Sprint 15 | [Dev][RD][Ecom] Sprint 16
Story | DEVRDECOM-194 | 35943 | [DEV][RD][Ecom][RR-Backoffice] Implement Backoffice for Shopify Members | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 15/Dec/25 9:48 AM | 19/Jan/26 2:20 PM |  | 5 |  |  |  | 0 | มาจาก Sprint 15 | Ready To Test | 57600 | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15 | [Dev][RD][Ecom] Sprint 16
Story | DEVRDECOM-193 | 35941 | [DEV][RD][Ecom][RR-Backoffice] Implement Backoffice for Shopify Credentials | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 15/Dec/25 9:24 AM | 19/Jan/26 2:20 PM |  | 5 |  |  |  | 0 | มาจาก Sprint 15 | Ready To Test | 57600 | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15 | [Dev][RD][Ecom] Sprint 16
Story | DEVRDECOM-192 | 35940 | [DEV][RD][Ecom][RR-Backoffice] Implement Backoffice for Shopify Shops | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 15/Dec/25 9:14 AM | 19/Jan/26 2:20 PM | 22/Dec/25 12:00 AM | 5 |  |  |  | 0 | มาจาก Sprint 15 | Ready To Test | 57600 | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15 | [Dev][RD][Ecom] Sprint 16
Story | RDAPS-337 | 35903 | [DEV][RD][APH] Add survey request log | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 14/Dec/25 2:39 PM | 13/Jan/26 2:57 PM | 17/Dec/25 12:00 AM | 3 | Aphrodire | No-QA |  | 0 | มาจาก Sprint 15 | Ready To Test | 28800 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15 | [Dev][All Project] Sprint 16
Story | RDAPS-336 | 35902 | [DEV][RD][APH] Change bug log to discord noti | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 14/Dec/25 2:36 PM | 13/Jan/26 2:57 PM | 19/Dec/25 12:00 AM | 3 | Aphrodire | No-QA |  | 0 | มาจาก Sprint 15 | Ready To Test | 28800 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15 | [Dev][All Project] Sprint 16
Story | RDAPS-335 | 35901 | [DEV][RD][APH] Integrate bug notification to discord | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 14/Dec/25 2:36 PM | 13/Jan/26 2:57 PM |  | 3 | Aphrodire | No-QA |  | 0 | มาจาก Sprint 15 | Ready To Test | 28800 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15 | [Dev][All Project] Sprint 16
Test Plan | DEVRDCT-342 | 35712 | [TP] Sprint #13 |  |  | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 11/Dec/25 3:26 PM | 19/Jan/26 2:17 PM | [6 empty] | มาจาก Sprint 15 | To Do |  | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15 | [Dev][RD][CT] Sprint 16
Story | RDAPS-322 | 35656 | [DEV][RD][MSG] Change support email | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 10/Dec/25 1:27 PM | 13/Jan/26 2:28 PM |  | 2 | No-QA | sso-messenger |  |  | มาจาก Sprint 15 | Ready To Test |  | [Dev][All Project] Sprint 15 | [Dev][All Project] Sprint 16
Bug | RDAPS-316 | 35558 | [Dev][RD][RRS] Fix datetime filter logic to support millisecond precision for redemption ETL | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Pass : Waiting for deployment |  | 08/Dec/25 5:57 PM | 13/Jan/26 1:51 PM |  | 2 |  |  |  |  | มาจาก Sprint 15 | Pass : Waiting for deployment |  | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15 | [Dev][All Project] Sprint 16
Story | RDAPS-305 | 35378 | [DEV][RD][SRS] Change support email | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 03/Dec/25 2:08 PM | 23/Jan/26 12:12 PM |  | 2 | No-QA | rr-scheduler |  |  | มาจาก Sprint 15 | Ready To Test |  | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 15 | [Dev][All Project] Sprint 16
Epic | DEVRDCT-326 | 35192 | CT-POINT-ISSUE |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 01/Dec/25 9:58 AM | 19/Jan/26 2:17 PM | [6 empty] | มาจาก Sprint 15 | To Do |  | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15 | [Dev][RD][CT] Sprint 16
Epic | DEVRDCT-325 | 35191 | CTxSHOPIFY |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 01/Dec/25 9:55 AM | 19/Jan/26 2:17 PM | [6 empty] | มาจาก Sprint 15 | To Do |  | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15 | [Dev][RD][CT] Sprint 16
Epic | DEVRDCT-309 | 34545 | ct-member-tier |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 19/Nov/25 2:49 PM | 19/Jan/26 2:17 PM | [6 empty] | มาจาก Sprint 15 | To Do |  | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15 | [Dev][RD][CT] Sprint 16
Epic | DEVRDCT-308 | 34539 | ct-campaign-type |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 19/Nov/25 10:41 AM | 19/Jan/26 2:17 PM |  |  | redemption-api |  |  |  | มาจาก Sprint 15 | To Do |  | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15 | [Dev][RD][CT] Sprint 16
Story | DEVRDSUP-252 | 34528 | [SUP-312][SUB] Skipped Receipt GR Offline (Ticket 6 Nov) | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Ready to Staging |  | 18/Nov/25 3:37 PM | 21/Jan/26 2:06 PM | 26/Dec/25 12:00 AM | 8 | [7 empty] | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 16
Story | DM-92 | 34424 | [DEV][RD][AWSTH] Partner Loyalty API pre-validation for dev environment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | In Progress |  | 17/Nov/25 11:10 AM | 19/Jan/26 9:48 AM |  | 2 | No-QA | partner-loyalty | [5 empty] | [Dev][RD][AWS] Sprint 16
Story | DEVRDECOM-173 | 34379 | [DEV][RD][Eco][security/risk] Check list | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Low | In Review |  | 16/Nov/25 5:08 PM | 14/Jan/26 9:28 AM |  | 3 | No-QA |  |  | 0 | มาจาก Sprint 15 | In Review | 28800 | [Dev][RD][Ecom] Sprint 12 | [Dev][RD][Ecom] Sprint 13 | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15 | [Dev][RD][Ecom] Sprint 16
Story | DM-61 | 34340 | [DEV][RD][AWSTH] RR Member Acquisition pre-validation for dev environment |  |  | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | To Do |  | 14/Nov/25 6:29 PM | 13/Jan/26 4:07 PM |  | 2 | [7 empty] | [Dev][RD][AWS] Sprint 16
Story | DM-59 | 34337 | [DEV][RD][AWSTH] BTS Officer app pre-validation for dev environment |  |  | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | To Do |  | 14/Nov/25 6:24 PM | 22/Jan/26 4:56 PM |  | 2 | No-QA | [6 empty] | [Dev][RD][AWS] Sprint 16
Story | DM-31 | 34302 | [DEV][RD][AWSTH] RR Scheduler pre-validation for dev environment |  |  | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | To Do |  | 14/Nov/25 4:53 PM | 13/Jan/26 4:07 PM |  | 3 | [7 empty] | [Dev][RD][AWS] Sprint 16
Story | DM-30 | 34301 | [DEV][RD][AWSTH] RR Member Web pre-validation for dev environment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | To Do |  | 14/Nov/25 4:53 PM | 13/Jan/26 4:07 PM |  | 1 | [7 empty] | [Dev][RD][AWS] Sprint 16
Story | DM-29 | 34300 | [DEV][RD][AWSTH] RR Order API pre-validation for dev environment |  |  | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | To Do |  | 14/Nov/25 4:52 PM | 22/Jan/26 5:07 PM |  | 3 | No-QA | [6 empty] | [Dev][RD][AWS] Sprint 16
Story | DM-28 | 34299 | [DEV][RD][AWSTH] RR Link Notify API pre-validation for dev environment |  |  | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | To Do |  | 14/Nov/25 4:52 PM | 22/Jan/26 4:55 PM |  | 2 | [7 empty] | [Dev][RD][AWS] Sprint 16
Story | DM-27 | 34298 | [DEV][RD][AWSTH] RR CronJob pre-validation for dev environment |  |  | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | To Do |  | 14/Nov/25 4:52 PM | 22/Jan/26 5:07 PM |  | 1 | No-QA | [6 empty] | [Dev][RD][AWS] Sprint 16
Story | DM-26 | 34297 | [DEV][RD][AWSTH] RR CloudID API pre-validation for dev environment |  |  | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | To Do |  | 14/Nov/25 4:51 PM | 22/Jan/26 5:06 PM |  | 3 | No-QA | [6 empty] | [Dev][RD][AWS] Sprint 16
Story | DM-25 | 34296 | [DEV][RD][AWSTH] RR Datahub GQL pre-validation for dev environment |  |  | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | To Do |  | 14/Nov/25 4:51 PM | 22/Jan/26 5:06 PM |  | 1 | No-QA | [6 empty] | [Dev][RD][AWS] Sprint 16
Story | DM-24 | 34295 | [DEV][RD][AWSTH] RR CleverTap pre-validation for dev environment |  |  | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | To Do |  | 14/Nov/25 4:51 PM | 22/Jan/26 5:06 PM |  | 1 | No-QA | [6 empty] | [Dev][RD][AWS] Sprint 16
Story | DM-23 | 34294 | [DEV][RD][AWSTH] RR Cart API pre-validation for dev environment |  |  | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | To Do |  | 14/Nov/25 4:50 PM | 22/Jan/26 5:06 PM |  | 3 | No-QA | [6 empty] | [Dev][RD][AWS] Sprint 16
Story | DM-22 | 34293 | [DEV][RD][AWSTH] RR BackOffice pre-validation for dev environment |  |  | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | To Do |  | 14/Nov/25 4:49 PM | 22/Jan/26 5:02 PM |  | 3 | No-QA | [6 empty] | [Dev][RD][AWS] Sprint 16
Story | DM-21 | 34292 | [DEV][RD][AWSTH] RR Athena API pre-validation for dev environment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | To Do |  | 14/Nov/25 4:49 PM | 13/Jan/26 4:07 PM |  | 1 | [7 empty] | [Dev][RD][AWS] Sprint 16
Story | DM-20 | 34291 | [DEV][RD][AWSTH] RR Aphrodite pre-validation for dev environment |  |  | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | To Do |  | 14/Nov/25 4:49 PM | 13/Jan/26 4:07 PM |  | 2 | [7 empty] | [Dev][RD][AWS] Sprint 16
Story | DM-19 | 34290 | [DEV][RD][AWSTH] Rewards Consumer pre-validation for dev environment |  |  | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | To Do |  | 14/Nov/25 4:48 PM | 22/Jan/26 5:06 PM |  | 3 | No-QA | [6 empty] | [Dev][RD][AWS] Sprint 16
Story | DM-18 | 34289 | [DEV][RD][AWSTH] Rewards API pre-validation for dev environment |  |  | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | To Do |  | 14/Nov/25 4:48 PM | 22/Jan/26 5:06 PM |  | 3 | No-QA | [6 empty] | [Dev][RD][AWS] Sprint 16
Story | DM-17 | 34288 | [DEV][RD][AWSTH] Redemption Consumer pre-validation for dev environment |  |  | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | To Do |  | 14/Nov/25 4:48 PM | 22/Jan/26 5:05 PM |  | 3 | No-QA | [6 empty] | [Dev][RD][AWS] Sprint 16
Story | DM-16 | 34287 | [DEV][RD][AWSTH] Redemption API pre-validation for dev environment |  |  | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | To Do |  | 14/Nov/25 4:48 PM | 22/Jan/26 5:03 PM |  | 3 | No-QA | [6 empty] | [Dev][RD][AWS] Sprint 16
Story | DM-15 | 34286 | [DEV][RD][AWSTH] Rabbit Sky Web pre-validation for dev environment |  |  | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | To Do |  | 14/Nov/25 4:47 PM | 12/Jan/26 4:11 PM |  | 2 | [7 empty] | [Dev][RD][AWS] Sprint 16
Story | DM-14 | 34285 | [DEV][RD][AWSTH] Rabbit Sky API pre-validation for dev environment |  |  | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | To Do |  | 14/Nov/25 4:47 PM | 12/Jan/26 4:11 PM |  | 2 | [7 empty] | [Dev][RD][AWS] Sprint 16
Story | DM-13 | 34284 | [DEV][RD][AWSTH] Rabbit CMS API pre-validation for dev environment |  |  | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | To Do |  | 14/Nov/25 4:46 PM | 22/Jan/26 5:03 PM |  | 3 | No-QA | [6 empty] | [Dev][RD][AWS] Sprint 16
Story | DM-12 | 34283 | [DEV][RD][AWSTH] Rabbit App BFF pre-validation for dev environment |  |  | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | To Do |  | 14/Nov/25 4:46 PM | 22/Jan/26 5:03 PM |  | 3 | No-QA | [6 empty] | [Dev][RD][AWS] Sprint 16
Story | DM-11 | 34282 | [DEV][RD][AWSTH] Point Engine Proxy pre-validation for dev environment |  |  | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | To Do |  | 14/Nov/25 4:46 PM | 22/Jan/26 5:03 PM |  | 1 | No-QA | [6 empty] | [Dev][RD][AWS] Sprint 16
Story | DM-10 | 34281 | [DEV][RD][AWSTH] Offline Subscription BFF pre-validation for dev environment |  |  | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | To Do |  | 14/Nov/25 4:46 PM | 22/Jan/26 5:04 PM |  | 3 | No-QA | [6 empty] | [Dev][RD][AWS] Sprint 16
Story | DM-9 | 34280 | [DEV][RD][AWSTH] Notification API pre-validation for dev environment |  |  | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | To Do |  | 14/Nov/25 4:42 PM | 22/Jan/26 5:04 PM |  | 1 | No-QA | [6 empty] | [Dev][RD][AWS] Sprint 16
Story | DM-7 | 34278 | [DEV][RD][AWSTH] Merchant API pre-validation for dev environment |  |  | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | To Do |  | 14/Nov/25 4:41 PM | 22/Jan/26 5:04 PM |  | 2 | No-QA | [6 empty] | [Dev][RD][AWS] Sprint 16
Story | DM-6 | 34277 | [DEV][RD][AWSTH] HR Solution pre-validation for dev environment |  |  | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | To Do |  | 14/Nov/25 4:40 PM | 22/Jan/26 5:04 PM |  | 3 | No-QA | [6 empty] | [Dev][RD][AWS] Sprint 16
Story | DM-5 | 34276 | [DEV][RD][AWSTH] Exclusive Store API pre-validation for dev environment |  |  | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | To Do |  | 14/Nov/25 4:39 PM | 22/Jan/26 5:04 PM |  | 2 | No-QA | [6 empty] | [Dev][RD][AWS] Sprint 16
Story | DM-4 | 34274 | [DEV][RD][AWSTH] DeepLink API pre-validation for dev environment |  |  | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | To Do |  | 14/Nov/25 4:37 PM | 22/Jan/26 5:04 PM |  | 1 | No-QA | [6 empty] | [Dev][RD][AWS] Sprint 16
Bug | RDAPS-269 | 34036 | [DEV][RD][Cron-job][Merchant Ranking] Enhance get merchant with active store only | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Pass : Waiting for deployment |  | 11/Nov/25 1:09 PM | 13/Jan/26 1:51 PM |  | 2 | No-QA |  |  |  | มาจาก Sprint 15 | Pass : Waiting for deployment |  | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15 | [Dev][All Project] Sprint 16
Story | RDAPS-233 | 32777 | [Dev][RD][RRS] Enhance Redemption ETL to add fields 'USING_AT' and 'COUNTDOWN_EXPIRED_AT' | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 19/Oct/25 3:24 PM | 21/Jan/26 2:05 PM | 21/Oct/25 12:00 AM | 2 | rr-scheduler |  |  | 0 | มาจาก Sprint 15 | Blocked | 14400 | [Dev][All Project] Sprint 10 | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15 | [Dev][All Project] Sprint 16
Story | DEVRDSUP-175 | 32272 | [SUP-239][ETL] Catch-up redemption data (item_id, using_at, and countdown_expired_at) | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Ready To Test |  | 14/Oct/25 4:34 PM | 21/Jan/26 1:59 PM | 30/Oct/25 12:00 AM | 5 | etl | [6 empty] | [Dev][All Project] Sprint 10 | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 16
Epic | DEVRDECOM-107 | 31506 | Shopify Webhook |  |  | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | To Do |  | 23/Sep/25 9:52 AM | 14/Jan/26 9:28 AM | [6 empty] | มาจาก Sprint 15 | To Do |  | [Dev][RD][Ecom] Sprint 8 | [Dev][RD][Ecom] Sprint 9 | [Dev][RD][Ecom] Sprint 10 | [Dev][RD][Ecom] Sprint 11 | [Dev][RD][Ecom] Sprint 12 | [Dev][RD][Ecom] Sprint 13 | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15 | [Dev][RD][Ecom] Sprint 16
Story | RDAPS-160 | 29972 | [DEV][RD][SSO-Backoffice] Disable SEO tracking | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 20/Aug/25 11:21 AM | 13/Jan/26 1:51 PM | 04/Sep/25 12:00 AM | 1 |  |  |  | 0 | มาจาก Sprint 15 | Ready To Test | 7200 | [Dev][All project]Sprint 6 | [Dev][All project]Sprint 7 | [Dev][All Project] Sprint 9 | [Dev][All Project] Sprint 10 | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15 | [Dev][All Project] Sprint 16

## Summarize Sprint 15
Column 1 | Total Stories Point | Total Manhour | Point Done | Manhour Done | Note
1 Dec - 12 Dec
Dev Resource Available | 12 | 328.25
Meeting Planned |  |  |  |  | Ref
Additional Meeting |  |  |  |  | Ref
Deployment |  | 3.5 |  |  | 2 ครั้ง 1. 2 คน 2. 1 คน 3. 1 คน
Development Sprint Total | 238 | 119.5 | 57 | 31.5
Ad-hoc Mid Sprint | 0 | 4 | 2 | 0 | 0 tasks
Requirement changes after refinement? | 0 |  | 0 | 0 | 0 tasks
Aek | 4 | 0 | 0 | 0
A | 21 | 15 | 8 | 7
Aom | 32 | 4.5 | 4 | 4.5
Zan | 29 | 0 | 11 | 0
Mai | 29 | 0 | 2 | 0
Mac | 26 | 30 | 5 | 0
Mos | 33 | 34 | 14 | 8
Jack | 0 | 0 | 0 | 0
Art | 0 | 0 | 0 | 0
Kae | 0 | 0 | 0 | 0
Nim | 38 | 32 | 6 | 8
Arm | 26 | 4 | 7 | 4
| System Architech |  |  |  | Permanent Dev. |  |  | Outsources
Projects (Stories Points) | Aek | Zan | Aom | Jack | A | Art | Mai | Kae | Mac | Nim | Mos | Arm
Das Haus - Thana City & Das Haus | 0 | 0 | 0 | 0 | 6 | 0 | 4 | 0 | 3 | 5 | 0 | 0
E-commerce 1.1. E-Commerce x Shopify Plus 1.2. Shopify:Snackmaker 1.3. Shopify: Turtle Delivery 1.4. Shopify: Turtle Delivery | 3 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 8 | 8 | 11 | 14
CleverTap - MKT Automation Tool | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 2 | 0
Adjust Integration | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 3 | 0 | 0
Adhoc - Non-Epics - Turtle Display club tier on POS - Data Mart Migration | 0 | 29 | 28 | 0 | 0 | 0 | 10 | 0 | 11 | 0 | 20 | 10
Support Incidents | 1 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0
| System Architech |  |  |  | Permanent Dev. |  |  | Outsources
Projects (Manhour) | Aek | Zan | Aom | Jack | A | Art | Mai | Kae | Mac | Nim | Mos | Arm
Das Haus - Thana City & Das Haus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E-commerce 1.1. E-Commerce x Shopify Plus 1.2. Shopify:Snackmaker 1.3. Shopify: Turtle Delivery 1.4. Shopify: Turtle Delivery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 24 | 0
CleverTap - MKT Automation Tool | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Adjust Integration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Adhoc - Non-Epics - Turtle Display club tier on POS - Data Mart Migration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 16 | 10 | 0
Support Incidents | 0 | 0 | 4.5 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0

## Sprint 15
Issue Type | Issue key | Issue id | Summary | Assignee | Assignee Id | Reporter | Reporter Id | Priority | Status | Resolution | Created | Updated | Due date | Custom field (Story Points) | Labels | Labels | Labels | Labels | Original estimate | Sprint Movement | Sprint 14 | Note | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint
Story | RDAPS-390 | 38471 | [DEV][RD][HRS] Handle wrong Date format in precheck import process | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 09/Jan/26 9:57 AM | 09/Jan/26 10:01 AM | [6 empty] | 7200 |  |  |  | [Dev][All Project] Sprint 15
Sub-task | DEVRDECOM-229 | 38428 | [QA] Test execution |  |  | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 08/Jan/26 4:23 PM | 08/Jan/26 4:23 PM | [10 empty] | [Dev][RD][Ecom] Sprint 15
Sub-task | RDAPS-389 | 38426 | [QA] Test execution on PROD | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | In Progress |  | 08/Jan/26 4:09 PM | 08/Jan/26 4:10 PM | [10 empty] | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Bug | DEVRDSUP-368 | 38389 | [SUP-440][SUB][NBO] SUB package TXN detail are showing many values incorrectly and HOLD, REFUND doesn't work anymore. | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Fixing |  | 08/Jan/26 2:41 PM | 09/Jan/26 9:39 AM | 12/Jan/26 12:00 AM |  | mid-sprint | prod-issue | rr-backoffice | sub |  |  |  |  | [Dev][All Project] Sprint 15
Story | RDAPS-388 | 38313 | [SA][RD][Thana City Datamart] Create task for sprint 16 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Progress |  | 08/Jan/26 10:17 AM | 08/Jan/26 10:18 AM |  | 8 | [8 empty] | [Dev][All Project] Sprint 15
Sub-task | RDAPS-387 | 38312 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 08/Jan/26 10:08 AM | 08/Jan/26 10:09 AM | [10 empty] | [Dev][All Project] Sprint 15
Sub-task | DEVRDECOM-228 | 38276 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 07/Jan/26 6:18 PM | 07/Jan/26 6:19 PM | [10 empty] | [Dev][RD][Ecom] Sprint 15
Sub-task | DEVRDECOM-227 | 38274 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 07/Jan/26 6:18 PM | 07/Jan/26 6:18 PM | [10 empty] | [Dev][RD][Ecom] Sprint 15
Sub-task | DEVRDECOM-226 | 38272 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 07/Jan/26 6:18 PM | 07/Jan/26 6:18 PM | [10 empty] | [Dev][RD][Ecom] Sprint 15
Sub-task | DEVRDECOM-225 | 38270 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 07/Jan/26 6:18 PM | 07/Jan/26 6:18 PM | [10 empty] | [Dev][RD][Ecom] Sprint 15
Sub-task | DEVRDECOM-224 | 38268 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 07/Jan/26 6:18 PM | 07/Jan/26 6:18 PM | [10 empty] | [Dev][RD][Ecom] Sprint 15
Sub-task | DEVRDECOM-223 | 38266 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 07/Jan/26 6:18 PM | 07/Jan/26 6:18 PM | [10 empty] | [Dev][RD][Ecom] Sprint 15
Sub-task | DEVRDECOM-222 | 38264 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Review |  | 07/Jan/26 6:17 PM | 08/Jan/26 3:39 PM | [10 empty] | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Sub-task | DEVRDECOM-221 | 38262 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Review |  | 07/Jan/26 6:17 PM | 08/Jan/26 3:39 PM | [10 empty] | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Sub-task | DEVRDECOM-220 | 38260 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Progress |  | 07/Jan/26 6:17 PM | 08/Jan/26 3:54 PM | [10 empty] | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Sub-task | DEVRDECOM-219 | 38258 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Progress |  | 07/Jan/26 6:17 PM | 08/Jan/26 3:54 PM | [10 empty] | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Sub-task | DEVRDECOM-218 | 38256 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Review |  | 07/Jan/26 6:16 PM | 08/Jan/26 3:28 PM | [10 empty] | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Sub-task | DEVRDECOM-217 | 38254 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Review |  | 07/Jan/26 6:16 PM | 08/Jan/26 3:28 PM | [10 empty] | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Sub-task | DEVRDECOM-216 | 38252 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Progress |  | 07/Jan/26 5:58 PM | 08/Jan/26 11:29 AM | [10 empty] | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Sub-task | DEVRDECOM-215 | 38250 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Review |  | 07/Jan/26 5:58 PM | 08/Jan/26 11:29 AM | [10 empty] | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Sub-task | DEVRDECOM-214 | 38206 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | To Do |  | 07/Jan/26 2:13 PM | 07/Jan/26 2:13 PM | [10 empty] | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Sub-task | DEVRDECOM-213 | 38204 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | In Progress |  | 07/Jan/26 2:13 PM | 09/Jan/26 10:02 AM | [10 empty] | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Sub-task | DEVRDECOM-212 | 38202 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | In Progress |  | 07/Jan/26 2:12 PM | 09/Jan/26 10:02 AM | [10 empty] | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Task | DM-159 | 38164 | [DEV][RD][AWSTH] Update RLP information to support DevOps team | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 07/Jan/26 11:28 AM | 08/Jan/26 3:19 PM | 09/Jan/26 12:00 AM | 1 | infra | No-QA |  |  | 3600 |  |  |  | [Dev][RD][AWS] Sprint 15
Story | RDAPS-384 | 38127 | [Dev][RD][Enhancement][REM Consumer] Add x-request-id header for outbound API calls to DA | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 07/Jan/26 9:15 AM | 07/Jan/26 4:48 PM |  | 3 |  |  |  |  | 28800 |  |  |  | [Dev][All Project] Sprint 15
Bug | DEVRDSUP-365 | 38051 | [SUP-435][HRSolution] HR solution's login page doesn't change the display language | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Low | Fixing |  | 06/Jan/26 5:41 PM | 09/Jan/26 7:27 AM | 04/Feb/26 12:00 AM | 1 | hr-solution | [7 empty] | [Dev][All Project] Sprint 15
Story | DEVRDSUP-364 | 38017 | [SUP-430][SUB] : Request to export receipt due to Incomplete Emails Received by BTSC (December2025) | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 06/Jan/26 4:56 PM | 08/Jan/26 1:53 PM | 09/Jan/26 12:00 AM | 1 | bts | BURequest | sub | [5 empty] | [Dev][All Project] Sprint 15
Story | RDAPS-383 | 37983 | [DEV][RD][HRS] Create command to bulk inactive member | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 06/Jan/26 11:47 AM | 07/Jan/26 11:43 AM |  | 3 | [8 empty] | [Dev][All Project] Sprint 15
Story | RDAPS-382 | 37978 | [Dev][RD][SSO-User] Improve query strategies for card type and card range retrieval | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready to Staging |  | 06/Jan/26 11:23 AM | 08/Jan/26 9:59 AM | [10 empty] | [Dev][All Project] Sprint 15
Bug | DEVRDSUP-359 | 37918 | [SUP-394][BTS Trips] #20251200022178 can't get points NBO with the status ““Fail – 500 Internal Server Error.” | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Low | Rejected |  | 05/Jan/26 4:12 PM | 07/Jan/26 2:56 PM | 02/Feb/26 12:00 AM | 1 | bts | challenge | mid-sprint | prod-issue |  |  |  |  | [Dev][All Project] Sprint 15
Sub-task | RDAPS-381 | 37914 | [QA] Create Test Case & Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 05/Jan/26 2:33 PM | 07/Jan/26 9:41 AM | [10 empty] | [Dev][All Project] Sprint 15
Sub-task | DEVRRBOF-206 | 37856 | [QA] Test execution | GIFT : Netnapa Sarawan | 712020:de8942b7-86cb-492b-95e7-5475add8a3f1 | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 05/Jan/26 10:57 AM | 05/Jan/26 11:50 AM | [10 empty] | [Dev][RRBack] 15
Bug | DEVRDSUP-357 | 37754 | [SUP-405][RDxDA][ETL] Missing BSS_SSO_CHG_SSOMEMBERPROFILE from 20251224074502 batch | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Resolved |  | 02/Jan/26 3:48 PM | 07/Jan/26 3:53 PM | 07/Jan/26 12:00 AM | 1 | data | etl | prod-issue | [5 empty] | [Dev][All Project] Sprint 15
Story | DM-158 | 37687 | [DEV][RD][AWS] Prepare document for List services using S3 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 02/Jan/26 11:33 AM | 06/Jan/26 9:13 AM |  | 2 | No-QA |  |  |  | 14400 |  |  |  | [Dev][RD][AWS] Sprint 15
Story | DM-157 | 37651 | [DEV][RD][AWS][PL] Change column client id to varchar for oauth client table | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 02/Jan/26 9:35 AM | 08/Jan/26 4:34 PM | 05/Jan/26 12:00 AM | 1 | No-QA | partner-loyalty |  |  | 7200 |  |  |  | [Dev][RD][AWS] Sprint 15
Sub-task | RDAPS-380 | 37548 | [QA] Retest coupon expiry date logic when restate a coupon to Redeemed | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 30/Dec/25 10:35 AM | 30/Dec/25 5:08 PM | [7 empty] | มาจาก Sprint 14 | In Progress |  | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Story | DEVRDSUP-353 | 37512 | [SUP-423][Turtle] Reuquest to batch update 2 auto-pushed reward SKUs to expire on 31/12/2025 23:59:59 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Done |  | 29/Dec/25 9:56 PM | 30/Dec/25 5:23 PM | 30/Dec/25 12:00 AM | 2 | BURequest | mid-sprint | turtle |  | 14400 |  |  |  | [Dev][All Project] Sprint 15
Story | DEVRRBOF-205 | 37478 | [Dev][RD][BOF] Update Default Info for Rewards Setting | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 29/Dec/25 4:17 PM | 08/Jan/26 4:44 PM |  | 2 | rr-backoffice | [7 empty] | [Dev][RRBack] 15
Story | DEVRDSUP-351 | 37475 | [SUP-422][BU][Dev] MKT ขอดูจำนวนคนเข้า Campaign Donation | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 29/Dec/25 2:37 PM | 30/Dec/25 10:22 AM |  | 1 |  |  |  |  | 1800 |  |  |  | [Dev][All Project] Sprint 15
Story | DEVRDSUP-350 | 37472 | [SUP-421]Query Point expire 2025 - Donation [29 Dec] | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 29/Dec/25 1:59 PM | 02/Jan/26 9:22 AM |  | 1 | [8 empty] | [Dev][All Project] Sprint 15
Story | DEVRDECOM-210 | 37465 | [DEV][RD][Ecom][Ecommerce-Shopify] Enhance Shopify Order Paid & Refund Payment Mapping and CleverTap Transaction Sync | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready to Staging |  | 29/Dec/25 10:46 AM | 09/Jan/26 9:25 AM | [6 empty] | 28800 |  |  |  | [Dev][RD][Ecom] Sprint 15
Story | DEVRDADJ-74 | 37464 | [DEV][RD][BOF] Enhance deeplink update function support internal name changed | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 29/Dec/25 10:22 AM | 08/Jan/26 9:23 AM | 30/Dec/25 12:00 AM | 3 |  |  |  |  | 28800 |  |  |  | [Dev][RDAdjust] Sprint 15
Story | RDAPS-379 | 37463 | [DEV][RD][SA] Design system for Thana City Datamart API | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Progress |  | 29/Dec/25 10:12 AM | 30/Dec/25 9:59 AM |  | 8 | [8 empty] | [Dev][All Project] Sprint 15
Story | DEVRDECOM-209 | 37450 | [DEV][RD][Ecom][RR-Backoffice] Implement Backoffice for Shopify Member enhancement to support tag management | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 29/Dec/25 9:37 AM | 09/Jan/26 9:34 AM |  | 5 |  |  |  |  | 57600 |  |  |  | [Dev][RD][Ecom] Sprint 15
Story | RDAPS-378 | 37448 | [DEV][RD][HRS] Create cronjob to auto sync member data with SSO detail | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 29/Dec/25 9:34 AM | 08/Jan/26 10:08 AM |  | 3 |  |  |  |  | 28800 |  |  |  | [Dev][All Project] Sprint 15
Story | RDAPS-377 | 37444 | [Dev][RD][HRS] Create script to generate registration_data | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 29/Dec/25 9:23 AM | 09/Jan/26 9:13 AM |  | 3 |  |  |  |  | 28800 |  |  |  | [Dev][All Project] Sprint 15
Story | DEVRRBOF-204 | 37406 | [Dev][RD][BOF][Improvement][Performance] Improve page load performance on Reward Detail page | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 28/Dec/25 8:56 PM | 08/Jan/26 10:04 AM |  | 3 | rr-backoffice | [7 empty] | [Dev][RRBack] 15
Bug | DEVRDSUP-339 | 37296 | [SUP-407][SUB] Can't active any category. | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Low | Resolved |  | 25/Dec/25 3:01 PM | 08/Jan/26 9:48 AM | 15/Jan/26 12:00 AM | 1 | mid-sprint | rr-backoffice | [6 empty] | [Dev][All Project] Sprint 15
Story | DM-156 | 37228 | [DEV][RD][AWS][POC] Partner Loyalty Compatibility Check After Database Migration from MariaDB to PostgreSQL | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 25/Dec/25 10:04 AM | 08/Jan/26 4:34 PM |  | 3 | No-QA | [7 empty] | [Dev][RD][AWS] Sprint 15
Story | RDAPS-375 | 37123 | [Dev][RD][Redemption] Migrate data for `allocation_type` in coupon_codes collection | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | To Do |  | 24/Dec/25 12:21 PM | 28/Dec/25 8:54 PM | 07/Jan/26 12:00 AM | [9 empty] | [Dev][All Project] Sprint 15
Story | DEVRRBOF-202 | 36985 | [RR-Backoffice] Enhance displaying 'Display rule' | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 23/Dec/25 4:06 PM | 07/Jan/26 11:29 PM | 30/Dec/25 12:00 AM | 2 |  |  |  |  | 14400 |  |  |  | [Dev][RRBack] 15
Story | DEVRDECOM-208 | 36982 | [DEV][RD][Ecom][Ecommerce-Shopify] Add created_by and updated_by columns to shopify_shops and shopify_credentials table | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 23/Dec/25 2:44 PM | 07/Jan/26 11:08 AM | 24/Dec/25 12:00 AM | 1 |  |  |  |  | 0 | มาจาก Sprint 14 | Ready To Test | 7200 | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Story | RDAPS-372 | 36975 | [Dev][RD][Technical] Refactor TXN Report API and Report Summary API to remove dependency on MVP Phase 1 report source | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready to Staging |  | 23/Dec/25 12:23 PM | 07/Jan/26 11:12 AM | 30/Dec/25 12:00 AM | 3 |  |  |  |  | 28800 |  |  |  | [Dev][All Project] Sprint 15
Story | RDAPS-371 | 36968 | [DEV][RD][HRS] Create cancel button for schedule upload | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 23/Dec/25 11:16 AM | 30/Dec/25 10:04 AM |  | 3 |  |  |  |  | 0 | มาจาก Sprint 14 | Ready To Test | 28800 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Epic | DEVRDCT-359 | 36930 | FIX-Identity-Error |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 23/Dec/25 9:38 AM | 08/Jan/26 4:39 PM | [7 empty] | มาจาก Sprint 14 | To Do |  | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15
Bug | DEVRDCT-358 | 36929 | [DEV][RD][HRS] Delay Auto CLUB_BINDING to Prevent Intermittent Identity Error | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Resolved |  | 23/Dec/25 8:59 AM | 08/Jan/26 4:39 PM |  | 2 | [5 empty] | มาจาก Sprint 14 | Resolved |  | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15
Bug | DEVRDSUP-330 | 36896 | [SUP-391][REM] Reward can be created twice if user click submit button twice quickly. | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Low | Closed |  | 22/Dec/25 5:57 PM | 08/Jan/26 4:44 PM | 22/Jan/26 12:00 AM | 1 | mid-sprint | prod-issue | rem | rr-backoffice |  | มาจาก Sprint 14 | Resolved |  | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Story | DEVRDSUP-328 | 36862 | [SUP-390]CRM Request - CS-20251200022091 Request to Revert RR Backoffice Status from Refunded to Active (Wrong Refund Action) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Ready to Staging |  | 22/Dec/25 4:42 PM | 09/Jan/26 10:16 AM |  | 3 |  |  |  |  | 28800 |  |  |  | [Dev][All Project] Sprint 15
Story | RDAPS-370 | 36861 | [DEV][RD][HRS] Enhance update import data log when empty employee id | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 22/Dec/25 3:49 PM | 30/Dec/25 10:04 AM |  | 3 |  |  |  |  | 0 | มาจาก Sprint 14 | Ready To Test | 28800 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Test Plan | RDAPS-368 | 36821 | [TP] MEMBER-ENHANCEMENT |  |  | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | To Do |  | 22/Dec/25 10:48 AM | 30/Dec/25 10:04 AM | [7 empty] | มาจาก Sprint 14 | To Do |  | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Sub-task | DEVRDECOM-207 | 36760 | Integrate frontend with Shopify shops API endpoints | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Medium | Done |  | 22/Dec/25 10:30 AM | 24/Dec/25 9:06 AM | [7 empty] | มาจาก Sprint 14 | Done |  | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Sub-task | DEVRDECOM-206 | 36758 | Develop frontend create/edit form with validation for Shopify shops | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Medium | Done |  | 22/Dec/25 10:30 AM | 24/Dec/25 9:06 AM | [7 empty] | มาจาก Sprint 14 | Done |  | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Sub-task | DEVRDECOM-205 | 36757 | Implement API endpoint for Shopify shops datatable | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Medium | Done |  | 22/Dec/25 10:29 AM | 22/Dec/25 10:31 AM | [7 empty] | มาจาก Sprint 14 | Done |  | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Sub-task | DEVRDECOM-204 | 36756 | Implement API endpoints for Create, Read, and Update Shopify shops | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Medium | Done |  | 22/Dec/25 10:29 AM | 24/Dec/25 9:06 AM | [7 empty] | มาจาก Sprint 14 | Done |  | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Sub-task | DEVRDECOM-202 | 36755 | Create frontend template for Backoffice Shopify shops | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Medium | Done |  | 22/Dec/25 10:29 AM | 24/Dec/25 9:06 AM | [7 empty] | มาจาก Sprint 14 | Done |  | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Sub-task | DEVRDECOM-203 | 36753 | Create API template for Shopify shops module | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Medium | Done |  | 22/Dec/25 10:29 AM | 22/Dec/25 10:31 AM | [7 empty] | มาจาก Sprint 14 | Done |  | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Sub-task | RDAPS-367 | 36748 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 22/Dec/25 10:13 AM | 07/Jan/26 12:42 PM | [7 empty] | มาจาก Sprint 14 | To Do |  | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Sub-task | RDAPS-366 | 36746 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 22/Dec/25 10:13 AM | 05/Jan/26 10:08 AM | [7 empty] | มาจาก Sprint 14 | To Do |  | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Sub-task | RDAPS-365 | 36744 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 22/Dec/25 10:12 AM | 06/Jan/26 10:06 AM | [7 empty] | มาจาก Sprint 14 | To Do |  | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Sub-task | RDAPS-364 | 36742 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 22/Dec/25 10:12 AM | 05/Jan/26 10:08 AM | [7 empty] | มาจาก Sprint 14 | To Do |  | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Sub-task | RDAPS-362 | 36738 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 22/Dec/25 10:12 AM | 06/Jan/26 10:16 AM | [7 empty] | มาจาก Sprint 14 | To Do |  | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Sub-task | RDAPS-358 | 36729 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 22/Dec/25 10:10 AM | 05/Jan/26 10:07 AM | [7 empty] | มาจาก Sprint 14 | In Progress |  | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Story | RDAPS-349 | 36428 | [Dev][RD][PL] Add 8x8 SMS Logging for RequestOtp Function | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 18/Dec/25 9:54 AM | 30/Dec/25 10:04 AM | 19/Dec/25 12:00 AM | 2 |  |  |  |  | 0 | มาจาก Sprint 14 | Ready To Test | 115200 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Story | DEVRDECOM-201 | 36281 | [DEV][RD][Ecom][Ecommerce-Shopify] Enhance Shopify Webhook Processing: Add Delay for Refund Update Flow | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 17/Dec/25 9:16 AM | 30/Dec/25 10:05 AM |  | 3 |  |  |  |  | 0 | มาจาก Sprint 14 | Ready To Test | 43200 | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Story | DEVRDSUP-318 | 36245 | [SUP-381][Widget] Request to remove many expired rewards from associated widgets to improve RR app performance on RR store page. | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Ready to Staging |  | 16/Dec/25 5:45 PM | 08/Jan/26 9:48 AM |  | 2 | BURequest | widget |  |  | 28800 |  |  |  | [Dev][All Project] Sprint 15
Story | RDAPS-347 | 36157 | [Dev][RD][Enhancement][REM] Add x-request-id header for outbound API calls to DA | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 16/Dec/25 11:06 AM | 07/Jan/26 9:15 AM |  | 3 |  |  |  |  | 0 | มาจาก Sprint 14 | Ready To Test | 28800 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Story | RDAPS-346 | 36156 | [Dev][RD][Enhancement][ORD] Add x-request-id header for outbound API calls to DA | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 16/Dec/25 11:06 AM | 30/Dec/25 10:04 AM |  | 3 |  |  |  |  | 0 | มาจาก Sprint 14 | Ready To Test | 28800 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Story | DEVRDECOM-200 | 35957 | [DEV][RD][Ecom][RR-Backoffice] Implement Backoffice for Shopify Login Logs | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready to Staging |  | 15/Dec/25 10:44 AM | 08/Jan/26 3:20 PM | 07/Jan/26 12:00 AM | 5 |  |  |  |  | 50400 |  |  |  | [Dev][RD][Ecom] Sprint 15
Story | DEVRDECOM-199 | 35956 | [DEV][RD][Ecom][RR-Backoffice] Implement Backoffice for Shopify Refunds | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready to Staging |  | 15/Dec/25 10:38 AM | 07/Jan/26 11:08 AM |  | 5 | [8 empty] | [Dev][RD][Ecom] Sprint 15
Story | DEVRDECOM-198 | 35955 | [DEV][RD][Ecom][RR-Backoffice] Implement Backoffice for Shopify Transactions | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 15/Dec/25 10:35 AM | 07/Jan/26 11:08 AM |  | 3 |  |  |  |  | 0 | มาจาก Sprint 14 | Ready To Test | 28800 | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Story | DEVRDADJ-73 | 35954 | [DEV][RD][LNF][Deeplink] Re-generate deeplink when item internal name was changed | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 15/Dec/25 10:33 AM | 29/Dec/25 10:21 AM | 18/Dec/25 12:00 AM | 5 |  |  |  |  | 0 | มาจาก Sprint 14 | Ready To Test | 57600 | [Dev][RDAdjust] Sprint 14 | [Dev][RDAdjust] Sprint 15
Story | DEVRDECOM-197 | 35948 | [DEV][RD][Ecom][RR-Backoffice] Implement Backoffice for Shopify Webhooks | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 15/Dec/25 10:26 AM | 07/Jan/26 11:08 AM | 25/Dec/25 12:00 AM | 3 |  |  |  |  | 0 | มาจาก Sprint 14 | Ready To Test | 57600 | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Story | DEVRDECOM-196 | 35946 | [DEV][RD][Ecom][RR-Backoffice] Implement Backoffice for Warehouse Order Status | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 15/Dec/25 10:18 AM | 08/Jan/26 3:54 PM |  | 3 |  |  |  |  | 0 | มาจาก Sprint 14 | Ready To Test | 28800 | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Story | DEVRDECOM-195 | 35944 | [DEV][RD][Ecom][RR-Backoffice] Implement Backoffice for Shopify Orders | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Progress |  | 15/Dec/25 10:11 AM | 08/Jan/26 3:50 PM | 24/Dec/25 12:00 AM | 3 |  |  |  |  | 0 | มาจาก Sprint 14 | Ready To Test | 28800 | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Story | DEVRDECOM-194 | 35943 | [DEV][RD][Ecom][RR-Backoffice] Implement Backoffice for Shopify Members | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 15/Dec/25 9:48 AM | 07/Jan/26 11:08 AM |  | 5 |  |  |  |  | 0 | มาจาก Sprint 14 | Ready To Test | 57600 | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Story | DEVRDECOM-193 | 35941 | [DEV][RD][Ecom][RR-Backoffice] Implement Backoffice for Shopify Credentials | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 15/Dec/25 9:24 AM | 07/Jan/26 11:08 AM |  | 5 |  |  |  |  | 0 | มาจาก Sprint 14 | Ready To Test | 57600 | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Story | DEVRDECOM-192 | 35940 | [DEV][RD][Ecom][RR-Backoffice] Implement Backoffice for Shopify Shops | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 15/Dec/25 9:14 AM | 07/Jan/26 11:08 AM | 22/Dec/25 12:00 AM | 5 |  |  |  |  | 0 | มาจาก Sprint 14 | Ready To Test | 57600 | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Story | RDAPS-337 | 35903 | [DEV][RD][APH] Add survey request log | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 14/Dec/25 2:39 PM | 30/Dec/25 10:04 AM | 17/Dec/25 12:00 AM | 3 |  |  |  |  | 0 | มาจาก Sprint 14 | Ready To Test | 28800 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Story | RDAPS-336 | 35902 | [DEV][RD][APH] Change bug log to discord noti | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 14/Dec/25 2:36 PM | 30/Dec/25 10:04 AM | 19/Dec/25 12:00 AM | 3 |  |  |  |  | 0 | มาจาก Sprint 14 | Ready To Test | 28800 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Story | RDAPS-335 | 35901 | [DEV][RD][APH] Integrate bug notification to discord | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 14/Dec/25 2:36 PM | 30/Dec/25 10:04 AM |  | 3 |  |  |  |  | 0 | มาจาก Sprint 14 | Ready To Test | 28800 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Story | RDAPS-333 | 35795 | [Dev][RD][REM] Adjust the coupon expiry date logic when restate a coupon to Redeemed | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 12/Dec/25 2:35 PM | 06/Jan/26 9:55 AM | 17/Dec/25 12:00 AM | 5 | redemption-api |  |  |  | 0 | มาจาก Sprint 14 | Ready To Test | 43200 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Story | RDAPS-329 | 35717 | [Dev][RD][BOF] Optimize query performance for Coupons Transaction Report | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 11/Dec/25 4:46 PM | 08/Jan/26 4:44 PM |  | 13 |  |  |  |  | 0 | มาจาก Sprint 14 | Ready To Test | 115200 | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Story | RDAPS-328 | 35715 | [Dev][RD][BOF] Switch "Subscription V2/ TXN Report" to use new endpoint | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 11/Dec/25 3:57 PM | 08/Jan/26 4:44 PM | 16/Dec/25 12:00 AM | 2 | rr-backoffice |  |  |  | 0 | มาจาก Sprint 14 | Ready To Test | 14400 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Test Plan | DEVRDCT-342 | 35712 | [TP] Sprint #13 |  |  | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 11/Dec/25 3:26 PM | 08/Jan/26 4:39 PM | [7 empty] | มาจาก Sprint 14 | To Do |  | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15
Story | RDAPS-326 | 35705 | [DEV][RD][HRS] Enhance employee import flow support schedule | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 11/Dec/25 11:47 AM | 07/Jan/26 12:42 PM |  | 3 |  |  |  |  | 0 | มาจาก Sprint 14 | Ready To Test | 28800 | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Sub-task | RDAPS-325 | 35704 | Check BU still active |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 11/Dec/25 11:39 AM | 11/Dec/25 11:39 AM | [7 empty] | มาจาก Sprint 14 | To Do |  | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Story | RDAPS-324 | 35702 | [DEV][RD][HRS] Add action to retry button in schedule datatable | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 11/Dec/25 11:13 AM | 06/Jan/26 10:08 AM | 12/Dec/25 12:00 AM | 3 |  |  |  |  | 0 | มาจาก Sprint 14 | Ready To Test | 28800 | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Bug | DEVRDSUP-299 | 35664 | [SUP-362][SUB] Package TXNs is "Expired" and payment was completed but SUB TXN report shows payment fail and last TXN update was change on Nov while TXN was expired since Aug. | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Low | Resolved |  | 10/Dec/25 5:36 PM | 06/Jan/26 9:50 AM | 08/Jan/26 12:00 AM |  | data | mid-sprint | prod-issue | sub |  | มาจาก Sprint 14 | Resolved |  | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Story | RDAPS-322 | 35656 | [DEV][RD][MSG] Change support email | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 10/Dec/25 1:27 PM | 08/Jan/26 10:15 AM |  | 2 | [8 empty] | [Dev][All Project] Sprint 15
Bug | RDTHANA-424 | 35591 | [S3][ฺBanner][Deeplink] Unable to save Banner with Full Deeplink (Link from Deeplink Page) | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Resolved |  | 09/Dec/25 10:09 AM | 29/Dec/25 10:20 AM | [7 empty] | มาจาก Sprint 14 | Resolved |  | [Dev][RD][Thana] Sprint 13 | [Dev][RD][Thana] Sprint 14 | [Dev][RD][Thana] Sprint 15
Bug | RDAPS-316 | 35558 | [Dev][RD][RRS] Fix datetime filter logic to support millisecond precision for redemption ETL | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Pass : Waiting for deployment |  | 08/Dec/25 5:57 PM | 06/Jan/26 8:16 AM |  | 2 | [5 empty] | มาจาก Sprint 14 | Fixing |  | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Bug | DEVRDCT-341 | 35533 | [S3][DEV][RD][RLP] Cannot command initial sync LIME Pay member to Line OA Account | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Lucas - Saksorn Srisak | 712020:289e7d91-50e6-438c-9b32-23b14017a585 | Medium | Closed |  | 08/Dec/25 10:13 AM | 08/Jan/26 5:08 PM | [7 empty] | มาจาก Sprint 14 | Resolved |  | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15
Sub-task | RDAPS-315 | 35441 | [QA] Create Test case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 04/Dec/25 10:13 AM | 05/Jan/26 10:08 AM | [7 empty] | มาจาก Sprint 14 | To Do |  | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Sub-task | RDAPS-314 | 35439 | [QA] Create Test case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 04/Dec/25 10:12 AM | 05/Jan/26 10:08 AM | [7 empty] | มาจาก Sprint 14 | To Do |  | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Sub-task | RDAPS-310 | 35431 | [QA] Create Test case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 04/Dec/25 10:11 AM | 15/Dec/25 3:03 PM | [7 empty] | มาจาก Sprint 14 | Done |  | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Story | RDAPS-305 | 35378 | [DEV][RD][SRS] Change support email | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 03/Dec/25 2:08 PM | 08/Jan/26 10:14 AM |  | 2 | [8 empty] | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 15
Story | RDAPS-301 | 35202 | [DEV][RD][SA] Consult/Suggest API call flow to integrate with Paypoint system | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 01/Dec/25 12:42 PM | 05/Jan/26 1:35 PM |  | 8 | [5 empty] | มาจาก Sprint 14 | In Progress |  | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Epic | DEVRDCT-326 | 35192 | CT-POINT-ISSUE |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 01/Dec/25 9:58 AM | 08/Jan/26 4:39 PM | [7 empty] | มาจาก Sprint 14 | To Do |  | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15
Epic | DEVRDCT-325 | 35191 | CTxSHOPIFY |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 01/Dec/25 9:55 AM | 08/Jan/26 4:39 PM | [7 empty] | มาจาก Sprint 14 | To Do |  | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15
Story | RDAPS-299 | 35157 | [DEV][RD][HRS][Queue] Create queue for send upload report | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 30/Nov/25 7:00 PM | 06/Jan/26 10:16 AM | 10/Dec/25 12:00 AM | 3 |  |  |  |  | 0 | มาจาก Sprint 14 | Ready To Test | 28800 | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Story | RDAPS-297 | 35120 | [DEV][RD][HRS][CRONJOB] Create command to import schedule upload | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 28/Nov/25 5:14 PM | 08/Jan/26 9:51 AM | 09/Dec/25 12:00 AM | 3 | hr-solution | No-QA |  |  | 0 | มาจาก Sprint 14 | Ready To Test | 57600 | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Story | RDAPS-293 | 35112 | [DEV][RD][HRS][MEMBER] Enhance registerRabbitMemberV2 function support upload error message | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 28/Nov/25 4:45 PM | 05/Jan/26 2:19 PM | 02/Dec/25 12:00 AM | 5 | hr-solution |  |  |  | 0 | มาจาก Sprint 14 | Ready To Test | 43200 | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Story | DM-102 | 34927 | [DEV][RD][AWSTH] RR CronJob Cleanup Unused Code After Migration | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | In Progress |  | 26/Nov/25 4:56 PM | 08/Jan/26 3:22 PM |  | 3 | [8 empty] | [Dev][RD][AWS] Sprint 15
Story | DM-100 | 34925 | [DEV][RD][AWSTH] Merchant API Cleanup Unused Code After Migration | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | To Do |  | 26/Nov/25 4:56 PM | 02/Jan/26 11:20 AM |  | 3 | No-QA |  |  |  | 28800 |  |  |  | [Dev][RD][AWS] Sprint 15
Epic | DEVRDCT-309 | 34545 | ct-member-tier |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 19/Nov/25 2:49 PM | 08/Jan/26 4:39 PM | [7 empty] | มาจาก Sprint 14 | To Do |  | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15
Epic | DEVRDCT-308 | 34539 | ct-campaign-type |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 19/Nov/25 10:41 AM | 08/Jan/26 4:39 PM |  |  | redemption-api |  |  |  |  | มาจาก Sprint 14 | To Do |  | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14 | [Dev][RD][CleverTap] Sprint 15
Story | RDTHANA-393 | 34499 | [DEV][RD][APH] Enhance record "source" when save participant | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 18/Nov/25 9:20 AM | 29/Dec/25 10:20 AM | 19/Nov/25 12:00 AM | 3 | No-QA |  |  |  | 0 | มาจาก Sprint 14 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13 | [Dev][RD][Thana] Sprint 14 | [Dev][RD][Thana] Sprint 15
Story | DEVRDECOM-173 | 34379 | [DEV][RD][Eco][security/risk] Check list | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Low | In Review |  | 16/Nov/25 5:08 PM | 30/Dec/25 10:05 AM |  | 3 | No-QA |  |  |  | 0 | มาจาก Sprint 14 | In Review | 28800 | [Dev][RD][Ecom] Sprint 12 | [Dev][RD][Ecom] Sprint 13 | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Bug | RDAPS-269 | 34036 | [DEV][RD][Cron-job][Merchant Ranking] Enhance get merchant with active store only | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Pass : Waiting for deployment |  | 11/Nov/25 1:09 PM | 30/Dec/25 10:04 AM |  | 2 | No-QA |  |  |  |  | มาจาก Sprint 14 | Pass : Waiting for deployment |  | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Bug | RDTHANA-377 | 33695 | [S4][Survey][Step 2] Club Status(Active/Inavtive) NOT update after change from HR-solution | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Resolved |  | 06/Nov/25 1:54 PM | 29/Dec/25 10:20 AM | [7 empty] | มาจาก Sprint 14 | Resolved |  | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13 | [Dev][RD][Thana] Sprint 14 | [Dev][RD][Thana] Sprint 15
Story | RDAPS-255 | 33340 | [Dev][RD][CID] Add log to Binding API to investigate double binding cases | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Nov/25 4:28 PM | 30/Dec/25 10:04 AM | 06/Nov/25 12:00 AM | 3 | rr-cloudid-api |  |  |  | 0 | มาจาก Sprint 14 | Ready To Test | 21600 | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Story | RDTHANA-353 | 33197 | [Dev][RD][Survey Web] Remove Survey web from SEO | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 28/Oct/25 1:53 PM | 29/Dec/25 10:20 AM |  | 2 | rr-aphrodite |  |  |  |  | มาจาก Sprint 14 | Ready To Test |  | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13 | [Dev][RD][Thana] Sprint 14 | [Dev][RD][Thana] Sprint 15
Story | RDAPS-233 | 32777 | [Dev][RD][RRS] Enhance Redemption ETL to add fields 'USING_AT' and 'COUNTDOWN_EXPIRED_AT' | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Blocked |  | 19/Oct/25 3:24 PM | 30/Dec/25 10:04 AM | 21/Oct/25 12:00 AM | 2 | rr-scheduler |  |  |  | 0 | มาจาก Sprint 14 | Blocked | 14400 | [Dev][All Project] Sprint 10 | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Story | RDTHANA-289 | 31700 | [DEV][RD][BOF][CR] Enhance survey ranking question | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 26/Sep/25 2:02 PM | 29/Dec/25 10:20 AM | 30/Sep/25 12:00 AM | 3 |  |  |  |  | 0 | มาจาก Sprint 14 | Ready To Test | 21600 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13 | [Dev][RD][Thana] Sprint 14 | [Dev][RD][Thana] Sprint 15
Epic | DEVRDECOM-107 | 31506 | Shopify Webhook |  |  | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | To Do |  | 23/Sep/25 9:52 AM | 30/Dec/25 10:05 AM | [7 empty] | มาจาก Sprint 14 | To Do |  | [Dev][RD][Ecom] Sprint 8 | [Dev][RD][Ecom] Sprint 9 | [Dev][RD][Ecom] Sprint 10 | [Dev][RD][Ecom] Sprint 11 | [Dev][RD][Ecom] Sprint 12 | [Dev][RD][Ecom] Sprint 13 | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Story | RDTHANA-244 | 31447 | [DEV][RD][APH] Enhance sorry page support dynamic error message and CTA button | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 22/Sep/25 11:36 AM | 29/Dec/25 10:20 AM | 29/Sep/25 12:00 AM | 1 | [5 empty] | มาจาก Sprint 14 | Ready To Test |  | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13 | [Dev][RD][Thana] Sprint 14 | [Dev][RD][Thana] Sprint 15
Story | RDTHANA-241 | 31432 | [DEV][RD][APH] Enhance survey html render support survey appearance "Thank you" tab | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 21/Sep/25 9:13 PM | 29/Dec/25 10:20 AM | 29/Sep/25 12:00 AM | 3 |  |  |  |  | 0 | มาจาก Sprint 14 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13 | [Dev][RD][Thana] Sprint 14 | [Dev][RD][Thana] Sprint 15
Story | RDTHANA-238 | 31429 | [DEV][RD][APH] Create survey theme | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Highest | Ready To Test |  | 21/Sep/25 8:49 PM | 29/Dec/25 10:20 AM | 23/Sep/25 12:00 AM | 3 | rr-aphrodite |  |  |  | 0 | มาจาก Sprint 14 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13 | [Dev][RD][Thana] Sprint 14 | [Dev][RD][Thana] Sprint 15
Story | RDAPS-187 | 31237 | [Dev][RD][RRS][Technical] Optimize performance for coupons report | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Highest | Ready To Test |  | 16/Sep/25 4:03 PM | 09/Jan/26 10:22 AM |  | 13 | rr-scheduler |  |  |  |  | มาจาก Sprint 14 | In Progress |  | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Story | RDAPS-160 | 29972 | [DEV][RD][SSO-Backoffice] Disable SEO tracking | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 20/Aug/25 11:21 AM | 30/Dec/25 10:04 AM | 04/Sep/25 12:00 AM | 1 |  |  |  |  | 0 | มาจาก Sprint 14 | Ready To Test | 7200 | [Dev][All project]Sprint 6 | [Dev][All project]Sprint 7 | [Dev][All Project] Sprint 9 | [Dev][All Project] Sprint 10 | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Story | RDTHANA-20 | 29950 | [Dev][RD][APH] Enhance check token | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 19/Aug/25 7:46 PM | 29/Dec/25 10:20 AM |  | 3 |  |  |  |  | 0 | มาจาก Sprint 14 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13 | [Dev][RD][Thana] Sprint 14 | [Dev][RD][Thana] Sprint 15

## Summarize Sprint 14
Column 1 | Total Stories Point | Total Manhour | Point Done | Manhour Done | Note
1 Dec - 12 Dec
Dev Resource Available | 17 | 471.25
Meeting Planned |  |  |  |  | Ref
Additional Meeting |  |  |  |  | Ref
Deployment |  | 4.5 |  |  | 3 ครั้ง 1. 3 คน 2. 1 คน 3. 2 คน
Development Sprint Total | 353 | 325.25 | 166 | 95.25
Ad-hoc Mid Sprint | 0 | 0.5 | 1 | 12 | 0 tasks
Requirement changes after refinement? | 0 |  | 0 | 0 | 0 tasks
Aek | 10 | 10.75 | 5 | 6.75
A | 33 | 50 | 27 | 50
Aom | 79 | 4.5 | 29 | 4.5
Zan | 18 | 0 | 8 | 0
Mai | 41 | 46 | 18 | 6
Mac | 47 | 36 | 31 | 16
Mos | 32 | 40 | 3 | 0
Jack | 14 | 0 | 14 | 0
Art | 0 | 0 | 0 | 0
Kae | 3 | 0 | 3 | 0
Nim | 37 | 48 | 10 | 0
Arm | 39 | 90 | 18 | 12
| System Architech |  |  |  | Permanent Dev. |  |  | Outsources
Projects (Stories Points) | Aek | Zan | Aom | Jack | A | Art | Mai | Kae | Mac | Nim | Mos | Arm
Das Haus - Thana City & Das Haus | 0 | 8 | 0 | 3 | 6 | 0 | 9 | 0 | 5 | 5 | 3 | 2
E-commerce 1.1. E-Commerce x Shopify Plus 1.2. Shopify:Snackmaker 1.3. Shopify: Turtle Delivery 1.4. Shopify: Turtle Delivery | 3 | 0 | 0 | 3 | 0 | 0 | 5 | 0 | 3 | 8 | 6 | 9
CleverTap - MKT Automation Tool | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 5 | 27 | 5 | 5 | 4
Adjust Integration | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 1 | 0
Adhoc - Non-Epics - Turtle Display club tier on POS - Data Mart Migration | 3 | 10 | 38 | 0 | 1 | 0 | 18 | 3 | 11 | 0 | 17 | 24
Support Incidents | 4 | 0 | 41 | 0 | 0 | 0 | 4 | 0 | 1 | 2 | 0 | 0
| System Architech |  |  |  | Permanent Dev. |  |  | Outsources
Projects (Manhour) | Aek | Zan | Aom | Jack | A | Art | Mai | Kae | Mac | Nim | Mos | Arm
Das Haus - Thana City & Das Haus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E-commerce 1.1. E-Commerce x Shopify Plus 1.2. Shopify:Snackmaker 1.3. Shopify: Turtle Delivery 1.4. Shopify: Turtle Delivery | 4 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 8 | 24 | 20 | 34
CleverTap - MKT Automation Tool | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0
Adjust Integration | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0
Adhoc - Non-Epics - Turtle Display club tier on POS - Data Mart Migration | 4.5 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 12 | 24 | 20 | 56
Support Incidents | 2.25 | 0 | 4.5 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0

## Sprint 14
Issue Type | Issue key | Issue id | Summary | Assignee | Assignee Id | Reporter | Reporter Id | Priority | Status | Resolution | Created | Updated | Due date | Custom field (Story Points) | Labels | Labels | Labels | Labels | Labels | Original estimate | Sprint Movement | Sprint 13 | Note | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint
Sub-task | RDAPS-380 | 37548 | [QA] Retest coupon expiry date logic when restate a coupon to Redeemed | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | In Progress |  | 30/Dec/25 10:35 AM | 30/Dec/25 10:45 AM | [11 empty] | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Bug | DEVRDCT-361 | 37305 | [S4][Shopify][CT Event][REFUND] Lack of 'TRANSACTION_ID' fields | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Resolved |  | 25/Dec/25 10:30 PM | 29/Dec/25 6:36 PM | [11 empty] | [Dev][RD][CT] Sprint 14
Story | DEVRDSUP-342 | 37304 | [SUP-412][Dev][DevOpt][BU] Point expire 2025 - Donation | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Thanakrit Chanthaworn | 712020:3fc982cb-c268-4f1d-9265-d3dd8fb08304 | Medium | Done |  | 25/Dec/25 5:52 PM | 29/Dec/25 10:02 AM |  |  | mid-sprint |  |  |  |  | 1800 |  |  |  | [Dev][All Project] Sprint 14
Story | DM-155 | 37227 | [DEV][RD][AWS][POC] RR BackOffice Compatibility Check After Database Migration from MariaDB to PostgreSQL | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 25/Dec/25 9:36 AM | 30/Dec/25 10:00 AM | 26/Dec/25 12:00 AM | 3 | No-QA | [8 empty] | [Dev][RD][AWS] Sprint 14
Story | RDAPS-376 | 37226 | [Dev][RD][Adhoc] BSS team request access to SSO back office for Support My Rabbit project | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 25/Dec/25 8:58 AM | 25/Dec/25 9:46 AM |  | 1 | [5 empty] | 1800 |  |  |  | [Dev][All Project] Sprint 14
Story | DM-154 | 37191 | [DEV][RD][AWSTH] Update Partner DB config for RR BackOffice with PostgreSQL | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 24/Dec/25 3:40 PM | 26/Dec/25 9:33 AM | 25/Dec/25 12:00 AM | 1 | No-QA |  |  |  |  | 7200 |  |  |  | [Dev][RD][AWS] Sprint 14
Bug | DEVRDCT-360 | 37090 | [S4][Shopify][CT Event][Charge - PAYMENT_PAID] Lack of some data fields | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Closed |  | 24/Dec/25 11:19 AM | 29/Dec/25 1:56 PM |  | 1 | [9 empty] | [Dev][RD][CT] Sprint 14
Bug | RDAPS-374 | 37022 | [S2][Member][Member Information] Updated success but member information is not updated | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Rejected |  | 23/Dec/25 9:10 PM | 24/Dec/25 11:01 AM | [11 empty] | [Dev][All Project] Sprint 14
Story | DEVRDECOM-208 | 36982 | [DEV][RD][Ecom][Ecommerce-Shopify] Add created_by and updated_by columns to shopify_shops and shopify_credentials table | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 23/Dec/25 2:44 PM | 30/Dec/25 10:05 AM | 24/Dec/25 12:00 AM | 1 | [5 empty] | 7200 |  |  |  | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Story | DEVRDSUP-336 | 36980 | [SUP-403][SSO Backoffice][backoffice] Admin Access on UAT and PROD | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Thanakrit Chanthaworn | 712020:3fc982cb-c268-4f1d-9265-d3dd8fb08304 | Medium | Done |  | 23/Dec/25 2:14 PM | 25/Dec/25 9:01 AM |  | 1 | [5 empty] | 900 |  |  |  | [Dev][All Project] Sprint 14
Story | DEVRDSUP-333 | 36972 | [SUP-400]SUB : Request to fill in the Secret Key for T8 Add-on | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Thanakrit Chanthaworn | 712020:3fc982cb-c268-4f1d-9265-d3dd8fb08304 | Medium | Done |  | 23/Dec/25 11:26 AM | 24/Dec/25 10:41 AM | 24/Dec/25 12:00 AM | 1 | mid-sprint | sub |  |  |  | 1800 |  |  |  | [Dev][All Project] Sprint 14
Story | RDAPS-371 | 36968 | [DEV][RD][HRS] Create cancel button for schedule upload | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 23/Dec/25 11:16 AM | 30/Dec/25 10:04 AM |  | 3 | [5 empty] | 28800 |  |  |  | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Story | DEVRDSUP-331 | 36967 | [SUP-398][Dev][DevOpt][BU] Point expire 2025 - Donation | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Thanakrit Chanthaworn | 712020:3fc982cb-c268-4f1d-9265-d3dd8fb08304 | Medium | Done |  | 23/Dec/25 11:14 AM | 24/Dec/25 1:40 PM | 24/Dec/25 12:00 AM | 1 | mid-sprint |  |  |  |  | 3600 |  |  |  | [Dev][All Project] Sprint 14
Story | DM-153 | 36931 | [DEV][RD][AWS] Prepare document for S3 URL Locations for New S3 Path Migration | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 23/Dec/25 9:55 AM | 25/Dec/25 4:25 PM | 24/Dec/25 12:00 AM | 2 | No-QA |  |  |  |  | 14400 |  |  |  | [Dev][RD][AWS] Sprint 14
Epic | DEVRDCT-359 | 36930 | FIX-Identity-Error |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 23/Dec/25 9:38 AM | 23/Dec/25 9:38 AM | [11 empty] | [Dev][RD][CT] Sprint 14
Bug | DEVRDCT-358 | 36929 | [DEV][RD][HRS] Delay Auto CLUB_BINDING to Prevent Intermittent Identity Error | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Resolved |  | 23/Dec/25 8:59 AM | 23/Dec/25 11:43 AM |  | 2 | [9 empty] | [Dev][RD][CT] Sprint 14
Bug | DEVRDSUP-330 | 36896 | [SUP-391][REM] Reward can be created twice if user click submit button twice quickly. | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Low | Resolved |  | 22/Dec/25 5:57 PM | 29/Dec/25 10:06 AM | 22/Jan/26 12:00 AM | 1 | mid-sprint | prod-issue | rem | rr-backoffice | [5 empty] | [Dev][All Project] Sprint 14
Bug | DEVRDSUP-329 | 36895 | [SUP-389][Card Binding] #20251100021238 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Rejected |  | 22/Dec/25 5:28 PM | 24/Dec/25 10:50 AM | 05/Jan/26 12:00 AM | 1 | challenge | mid-sprint | prod-issue | [6 empty] | [Dev][All Project] Sprint 14
Story | RDAPS-370 | 36861 | [DEV][RD][HRS] Enhance update import data log when empty employee id | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 22/Dec/25 3:49 PM | 30/Dec/25 10:04 AM |  | 3 | [5 empty] | 28800 |  |  |  | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Story | DEVRDSUP-327 | 36860 | [SUP-395][Dev][BU] Point expire 2025 - Donation | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Thanakrit Chanthaworn | 712020:3fc982cb-c268-4f1d-9265-d3dd8fb08304 | Medium | Done |  | 22/Dec/25 3:34 PM | 23/Dec/25 10:37 AM |  | 1 | BURequest | mid-sprint |  |  |  | 1800 |  |  |  | [Dev][All Project] Sprint 14
Story | DM-152 | 36825 | [DEV][RD][AWSTH] Prepare docker file to support RDS Aurora | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 22/Dec/25 11:46 AM | 25/Dec/25 4:25 PM | 24/Dec/25 12:00 AM | 3 | No-QA |  |  |  |  | 28800 |  |  |  | [Dev][RD][AWS] Sprint 14
Test Plan | RDAPS-368 | 36821 | [TP] MEMBER-ENHANCEMENT |  |  | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | To Do |  | 22/Dec/25 10:48 AM | 30/Dec/25 10:04 AM | [11 empty] | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Sub-task | DEVRDECOM-207 | 36760 | Integrate frontend with Shopify shops API endpoints | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Medium | Done |  | 22/Dec/25 10:30 AM | 24/Dec/25 9:06 AM | [11 empty] | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Sub-task | DEVRDECOM-206 | 36758 | Develop frontend create/edit form with validation for Shopify shops | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Medium | Done |  | 22/Dec/25 10:30 AM | 24/Dec/25 9:06 AM | [11 empty] | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Sub-task | DEVRDECOM-205 | 36757 | Implement API endpoint for Shopify shops datatable | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Medium | Done |  | 22/Dec/25 10:29 AM | 22/Dec/25 10:31 AM | [11 empty] | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Sub-task | DEVRDECOM-204 | 36756 | Implement API endpoints for Create, Read, and Update Shopify shops | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Medium | Done |  | 22/Dec/25 10:29 AM | 24/Dec/25 9:06 AM | [11 empty] | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Sub-task | DEVRDECOM-202 | 36755 | Create frontend template for Backoffice Shopify shops | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Medium | Done |  | 22/Dec/25 10:29 AM | 24/Dec/25 9:06 AM | [11 empty] | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Sub-task | DEVRDECOM-203 | 36753 | Create API template for Shopify shops module | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Medium | Done |  | 22/Dec/25 10:29 AM | 22/Dec/25 10:31 AM | [11 empty] | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Sub-task | RDAPS-367 | 36748 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | To Do |  | 22/Dec/25 10:13 AM | 22/Dec/25 10:13 AM | [11 empty] | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Sub-task | RDAPS-366 | 36746 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | To Do |  | 22/Dec/25 10:13 AM | 22/Dec/25 10:13 AM | [11 empty] | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Sub-task | RDAPS-365 | 36744 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | To Do |  | 22/Dec/25 10:12 AM | 22/Dec/25 10:12 AM | [11 empty] | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Sub-task | RDAPS-364 | 36742 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | To Do |  | 22/Dec/25 10:12 AM | 22/Dec/25 10:12 AM | [11 empty] | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Sub-task | RDAPS-363 | 36740 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 22/Dec/25 10:12 AM | 24/Dec/25 10:29 AM | [11 empty] | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14
Sub-task | RDAPS-362 | 36738 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | To Do |  | 22/Dec/25 10:12 AM | 22/Dec/25 10:12 AM | [11 empty] | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Sub-task | RDAPS-361 | 36736 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 22/Dec/25 10:10 AM | 22/Dec/25 10:10 AM | [11 empty] | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14
Sub-task | RDAPS-360 | 36734 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 22/Dec/25 10:10 AM | 25/Dec/25 10:04 AM | [11 empty] | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14
Sub-task | RDAPS-359 | 36731 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 22/Dec/25 10:10 AM | 25/Dec/25 12:11 PM | [11 empty] | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14
Sub-task | RDAPS-358 | 36729 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | In Progress |  | 22/Dec/25 10:10 AM | 25/Dec/25 3:54 PM | [11 empty] | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Sub-task | RDAPS-357 | 36727 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 22/Dec/25 10:09 AM | 25/Dec/25 3:50 PM | [11 empty] | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14
Sub-task | RDAPS-356 | 36725 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 22/Dec/25 10:09 AM | 22/Dec/25 10:09 AM | [11 empty] | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14
Sub-task | RDAPS-355 | 36723 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 22/Dec/25 10:09 AM | 22/Dec/25 10:09 AM | [11 empty] | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14
Sub-task | RDAPS-354 | 36721 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 22/Dec/25 10:08 AM | 22/Dec/25 10:08 AM | [11 empty] | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14
Story | RDAPS-353 | 36513 | [Dev][RD][Adhoc] Prepare OAuth2 Client Credentials for New Development Environment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 18/Dec/25 5:43 PM | 25/Dec/25 6:21 PM | 23/Dec/25 12:00 AM | 1 | No-QA | [8 empty] | [Dev][All Project] Sprint 14
Story | RDAPS-352 | 36512 | [DEV][RD][Bifros] Enhance ETL command for BSS_SSO_ADD_LINKOPENED, BSS_SSO_ADD_POPUP, and BSS_SSO_ADD_SMSREACHED to support date range | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 18/Dec/25 5:31 PM | 23/Dec/25 5:04 PM | [11 empty] | [Dev][All Project] Sprint 14
Story | RDAPS-351 | 36507 | [Dev][RD][RM] Redesign Thank You Page for the Point Donation Landing Page | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Done |  | 18/Dec/25 4:02 PM | 29/Dec/25 10:10 AM | 18/Dec/25 12:00 AM | 2 | mid-sprint |  |  |  |  | 14400 |  |  |  | [Dev][All Project] Sprint 14
Bug | DEVRDSUP-322 | 36500 | [SUP-387][SUB][SSO] Found a user with incorrect LP binding couldn't purchase an offline package. | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Rejected |  | 18/Dec/25 3:00 PM | 25/Dec/25 3:39 PM | 19/Dec/25 12:00 AM | 1 | mid-sprint | offline | prod-issue | sub | [5 empty] | [Dev][All Project] Sprint 14
Story | DEVRDSUP-320 | 36497 | [SUP-386]Requesting to export request body for 3 failed redeem with point purchase TXNs | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 18/Dec/25 2:01 PM | 22/Dec/25 5:05 PM |  | 1 | mid-sprint | sub |  |  |  | 3600 |  |  |  | [Dev][All Project] Sprint 14
Story | RDAPS-349 | 36428 | [Dev][RD][PL] Add 8x8 SMS Logging for RequestOtp Function | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 18/Dec/25 9:54 AM | 30/Dec/25 10:04 AM | 19/Dec/25 12:00 AM | 2 | [5 empty] | 115200 |  |  |  | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Story | DEVRDECOM-201 | 36281 | [DEV][RD][Ecom][Ecommerce-Shopify] Enhance Shopify Webhook Processing: Add Delay for Refund Update Flow | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 17/Dec/25 9:16 AM | 30/Dec/25 10:05 AM |  | 3 | [5 empty] | 43200 |  |  |  | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Story | DM-151 | 36238 | [DEV][RD][AWSTH] Prepare a new migration files for HR Solution | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Low | Done |  | 16/Dec/25 4:18 PM | 25/Dec/25 4:25 PM | 18/Dec/25 12:00 AM | 3 | mid-sprint | No-QA | [7 empty] | [Dev][RD][AWS] Sprint 14
Story | DEVRDSUP-315 | 36237 | [SUP-376][SUB] CS-20251200022394 รบกวน Mark Used คูปองเที่ยวเดินทาง 13773038 เนื่องจาก Back to Redeem ผิดค่ะ | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 16/Dec/25 4:03 PM | 18/Dec/25 11:04 AM |  | 1 | mid-sprint | sub |  |  |  | 1800 |  |  |  | [Dev][All Project] Sprint 14
Story | DEVRDSUP-314 | 36226 | [SUP-375][SUB] Missing Receipt and not found in RR Backoffice (16 Dec) | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Thanakrit Chanthaworn | 712020:3fc982cb-c268-4f1d-9265-d3dd8fb08304 | Medium | Done |  | 16/Dec/25 2:12 PM | 16/Dec/25 3:49 PM | 16/Dec/25 12:00 AM | 1 | mid-sprint |  |  |  |  | 7200 |  |  |  | [Dev][All Project] Sprint 14
Story | RDAPS-347 | 36157 | [Dev][RD][Enhancement][REM] Add x-request-id header for outbound API calls to DA | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 16/Dec/25 11:06 AM | 30/Dec/25 10:04 AM |  | 3 | [5 empty] | 28800 |  |  |  | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Story | RDAPS-346 | 36156 | [Dev][RD][Enhancement][ORD] Add x-request-id header for outbound API calls to DA | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 16/Dec/25 11:06 AM | 30/Dec/25 10:04 AM |  | 3 | [5 empty] | 28800 |  |  |  | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Story | DEVRDSUP-312 | 36123 | [SUP-373][SUB] Receipt is not generated after SUB transaction is made (15 Dec) | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Thanakrit Chanthaworn | 712020:3fc982cb-c268-4f1d-9265-d3dd8fb08304 | Highest | Done |  | 16/Dec/25 10:49 AM | 16/Dec/25 11:00 AM | 16/Dec/25 12:00 AM | 1 | mid-sprint |  |  |  |  | 1800 |  |  |  | [Dev][All Project] Sprint 14
Story | DEVRDSUP-311 | 36088 | [SUP-372]CLONE - SUB : Incorrect E-Receipt Naming via BCC Automail (9-11 Dec) | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Thanakrit Chanthaworn | 712020:3fc982cb-c268-4f1d-9265-d3dd8fb08304 | Medium | Done |  | 16/Dec/25 10:30 AM | 17/Dec/25 9:28 AM | 17/Dec/25 12:00 AM | 1 | mid-sprint |  |  |  |  | 7200 |  |  |  | [Dev][All Project] Sprint 14
Story | RDAPS-345 | 36021 | [Dev][RD][RLP] Run command manually for clevertap initial rlp linemember | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 16/Dec/25 9:27 AM | 25/Dec/25 9:01 AM |  | 2 | [5 empty] | 14400 |  |  |  | [Dev][All Project] Sprint 14
Sub-task | RDAPS-344 | 35988 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 15/Dec/25 5:33 PM | 16/Dec/25 6:39 PM | [11 empty] | [Dev][All Project] Sprint 14
Sub-task | RDAPS-343 | 35986 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 15/Dec/25 5:33 PM | 16/Dec/25 2:47 PM | [11 empty] | [Dev][All Project] Sprint 14
Story | RDAPS-342 | 35969 | [DEV][RD][RR-Scheduler] Cleanup Unused SFTP Configuration for Legacy ETL Data Delivery (DA) | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 15/Dec/25 4:16 PM | 30/Dec/25 9:49 AM | 19/Dec/25 12:00 AM | 1 | [5 empty] | 7200 |  |  |  | [Dev][All Project] Sprint 14
Story | RDAPS-341 | 35968 | [DEV][RD][Bifros] Cleanup Unused SFTP Configuration for Legacy ETL Data Delivery (DA) | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 15/Dec/25 4:09 PM | 30/Dec/25 9:37 AM | 19/Dec/25 12:00 AM | 1 | [5 empty] | 7200 |  |  |  | [Dev][All Project] Sprint 14
Bug | DEVRDSUP-307 | 35967 | [SUP-371][HRSolution] Member's rabbit card validation is not correct. User have 4RC+1LP but HR solution doesn't allow to add 1 more RC for binding. | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Resolved |  | 15/Dec/25 3:53 PM | 22/Dec/25 10:46 AM | 30/Dec/25 12:00 AM | 2 | hop | hr-solution | mid-sprint | prod-issue | [5 empty] | [Dev][All Project] Sprint 14
Story | DEVRDECOM-198 | 35955 | [DEV][RD][Ecom][RR-Backoffice] Implement Backoffice for Shopify Transactions | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 15/Dec/25 10:35 AM | 30/Dec/25 10:05 AM |  | 3 | [5 empty] | 28800 |  |  |  | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Story | DEVRDADJ-73 | 35954 | [DEV][RD][LNF][Deeplink] Re-generate deeplink when item internal name was changed | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 15/Dec/25 10:33 AM | 29/Dec/25 10:21 AM | 18/Dec/25 12:00 AM | 5 | [5 empty] | 57600 |  |  |  | [Dev][RDAdjust] Sprint 14 | [Dev][RDAdjust] Sprint 15
Story | DEVRDECOM-197 | 35948 | [DEV][RD][Ecom][RR-Backoffice] Implement Backoffice for Shopify Webhooks | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 15/Dec/25 10:26 AM | 30/Dec/25 10:05 AM | 25/Dec/25 12:00 AM | 3 | [5 empty] | 57600 |  |  |  | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Story | DEVRDECOM-196 | 35946 | [DEV][RD][Ecom][RR-Backoffice] Implement Backoffice for Warehouse Order Status | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 15/Dec/25 10:18 AM | 30/Dec/25 10:05 AM |  | 3 | [5 empty] | 28800 |  |  |  | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Story | DM-150 | 35945 | [DEV][RD][AWSTH] Verify database after migration to Landing Zone | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | High | Done |  | 15/Dec/25 10:13 AM | 24/Dec/25 5:04 PM | 17/Dec/25 12:00 AM | 5 | No-QA |  |  |  |  | 86400 |  |  |  | [Dev][RD][AWS] Sprint 14
Story | DEVRDECOM-195 | 35944 | [DEV][RD][Ecom][RR-Backoffice] Implement Backoffice for Shopify Orders | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 15/Dec/25 10:11 AM | 30/Dec/25 10:05 AM | 24/Dec/25 12:00 AM | 3 | [5 empty] | 28800 |  |  |  | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Story | DEVRDECOM-194 | 35943 | [DEV][RD][Ecom][RR-Backoffice] Implement Backoffice for Shopify Members | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 15/Dec/25 9:48 AM | 30/Dec/25 10:05 AM |  | 5 | [5 empty] | 57600 |  |  |  | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Story | DEVRDECOM-193 | 35941 | [DEV][RD][Ecom][RR-Backoffice] Implement Backoffice for Shopify Credentials | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 15/Dec/25 9:24 AM | 30/Dec/25 10:05 AM |  | 5 | [5 empty] | 57600 |  |  |  | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Story | DEVRDECOM-192 | 35940 | [DEV][RD][Ecom][RR-Backoffice] Implement Backoffice for Shopify Shops | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 15/Dec/25 9:14 AM | 30/Dec/25 10:05 AM | 22/Dec/25 12:00 AM | 5 | [5 empty] | 57600 |  |  |  | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Story | DEVRDCT-346 | 35907 | [RD][DEV][CT][POC] API for LINE OA Message Webhook | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 14/Dec/25 5:58 PM | 22/Dec/25 2:58 PM | 22/Dec/25 12:00 AM | 8 | CleverTap | No-QA | POC |  |  | 57600 |  |  |  | [Dev][RD][CT] Sprint 14
Story | RDAPS-337 | 35903 | [DEV][RD][APH] Add survey request log | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 14/Dec/25 2:39 PM | 30/Dec/25 10:04 AM | 17/Dec/25 12:00 AM | 3 | [5 empty] | 28800 |  |  |  | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Story | RDAPS-336 | 35902 | [DEV][RD][APH] Change bug log to discord noti | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 14/Dec/25 2:36 PM | 30/Dec/25 10:04 AM | 19/Dec/25 12:00 AM | 3 | [5 empty] | 28800 |  |  |  | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Story | RDAPS-335 | 35901 | [DEV][RD][APH] Integrate bug notification to discord | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 14/Dec/25 2:36 PM | 30/Dec/25 10:04 AM |  | 3 | [5 empty] | 28800 |  |  |  | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Story | RDTHANA-425 | 35804 | [DEV][API DOC][SA] API to feed real-time data to Datamart - Data from POS/3rd Party | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 12/Dec/25 2:57 PM | 22/Dec/25 9:32 AM |  | 8 | Document | No-QA | [7 empty] | [Dev][RD][Thana] Sprint 14
Story | RDAPS-333 | 35795 | [Dev][RD][REM] Adjust the coupon expiry date logic when restate a coupon to Redeemed | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 12/Dec/25 2:35 PM | 30/Dec/25 10:23 AM | 17/Dec/25 12:00 AM | 5 | redemption-api |  |  |  |  | 43200 |  |  |  | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Story | RDAPS-332 | 35794 | [Dev][RD] Create a new landing page for donating expired Rabbit Rewards points | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Highest | Done |  | 12/Dec/25 1:17 PM | 17/Dec/25 9:54 AM | 16/Dec/25 12:00 AM | 3 | [5 empty] | 28800 |  |  |  | [Dev][All Project] Sprint 14
Story | RDAPS-329 | 35717 | [Dev][RD][BOF] Optimize query performance for Coupons Transaction Report | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 11/Dec/25 4:46 PM | 30/Dec/25 10:04 AM |  | 13 | [5 empty] | 0 | มาจาก Sprint 13 | Ready To Test | 115200 | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Story | RDAPS-328 | 35715 | [Dev][RD][BOF] Switch "Subscription V2/ TXN Report" to use new endpoint | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 11/Dec/25 3:57 PM | 30/Dec/25 10:04 AM | 16/Dec/25 12:00 AM | 2 | rr-backoffice |  |  |  |  | 14400 |  |  |  | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Test Plan | DEVRDCT-342 | 35712 | [TP] Sprint #13 |  |  | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 11/Dec/25 3:26 PM | 15/Dec/25 10:06 AM | [8 empty] | มาจาก Sprint 13 | To Do |  | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Bug | DEVRDADJ-71 | 35707 | [S3][RR-backoffice][Deeplink] Missing Submit button for manual created item | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Low | Closed |  | 11/Dec/25 1:38 PM | 25/Dec/25 4:26 PM |  | 1 | [9 empty] | [Dev][RDAdjust] Sprint 14
Story | RDAPS-326 | 35705 | [DEV][RD][HRS] Enhance employee import flow support schedule | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 11/Dec/25 11:47 AM | 30/Dec/25 10:04 AM |  | 3 | [5 empty] | 0 | มาจาก Sprint 13 | Ready To Test | 28800 | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Sub-task | RDAPS-325 | 35704 | Check BU still active |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 11/Dec/25 11:39 AM | 11/Dec/25 11:39 AM | [8 empty] | มาจาก Sprint 13 | To Do |  | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Story | RDAPS-324 | 35702 | [DEV][RD][HRS] Add action to retry button in schedule datatable | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 11/Dec/25 11:13 AM | 30/Dec/25 10:04 AM | 12/Dec/25 12:00 AM | 3 | [5 empty] | 14400 | มาจาก Sprint 13 | In Progress | 28800 -> 14400 | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Bug | DEVRDSUP-301 | 35668 | [SUP-364][Club][HR Solution] Club tier get removed entirely when user deletes the Tier name (EN), Tier name (TH) text string. | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Low | Resolved |  | 11/Dec/25 12:41 AM | 22/Dec/25 9:31 AM | 08/Jan/26 12:00 AM |  | hr-solution | mid-sprint | [7 empty] | [Dev][All Project] Sprint 14
Bug | DEVRDSUP-300 | 35666 | [SUP-363][Club][HR Solution] Club tier order can't be updated | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Resolved |  | 11/Dec/25 12:23 AM | 22/Dec/25 9:25 AM | 25/Dec/25 12:00 AM |  | hr-solution | mid-sprint | [7 empty] | [Dev][All Project] Sprint 14
Bug | DEVRDSUP-299 | 35664 | [SUP-362][SUB] Package TXNs is "Expired" and payment was completed but SUB TXN report shows payment fail and last TXN update was change on Nov while TXN was expired since Aug. | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Low | Resolved |  | 10/Dec/25 5:36 PM | 23/Dec/25 3:08 PM | 08/Jan/26 12:00 AM |  | data | mid-sprint | prod-issue | sub | [5 empty] | [Dev][All Project] Sprint 14
Bug | DEVRDSUP-298 | 35654 | [SUP-354][REM][Deeplink] If save a reward with internal name A and then change to B then deeplink path doesn't get updated. | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Enhancement |  | 10/Dec/25 11:57 AM | 17/Dec/25 10:23 AM | [11 empty] | [Dev][All Project] Sprint 14
Sub-task | DEVRDSUP-297 | 35652 | [QA] Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 10/Dec/25 9:54 AM | 15/Dec/25 3:45 PM | [8 empty] | มาจาก Sprint 13 | In Progress |  | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14
Story | DM-148 | 35648 | [DEV][RD][AWSTH] Change Partner Loyalty DB from MariaDB to PostgreSQL | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 10/Dec/25 9:47 AM | 25/Dec/25 4:25 PM | 18/Dec/25 12:00 AM | 1 | No-QA |  |  |  |  | 7200 |  |  |  | [Dev][RD][AWS] Sprint 14
Story | DM-147 | 35647 | [DEV][RD][AWSTH] Update container's work directory for HR Solution | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 10/Dec/25 8:40 AM | 23/Dec/25 2:36 PM |  | 1 | No-QA | [8 empty] | [Dev][RD][AWS] Sprint 14
Sub-task | RDAPS-320 | 35606 | [QA] Create Test case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 09/Dec/25 3:22 PM | 09/Dec/25 3:23 PM | [8 empty] | มาจาก Sprint 13 | Done |  | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14
Task | RDAPS-319 | 35603 | [BOF] Add placeholder for deeplink infinite scroll | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Medium | Done |  | 09/Dec/25 1:55 PM | 26/Dec/25 10:12 AM | 11/Dec/25 12:00 AM | 1 | No-QA | rr-backoffice |  |  |  | 0 | มาจาก Sprint 13 | Ready To Test | 7200 | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14
Bug | RDTHANA-424 | 35591 | [S3][ฺBanner][Deeplink] Unable to save Banner with Full Deeplink (Link from Deeplink Page) | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Resolved |  | 09/Dec/25 10:09 AM | 29/Dec/25 10:20 AM | [8 empty] | มาจาก Sprint 13 | Resolved |  | [Dev][RD][Thana] Sprint 13 | [Dev][RD][Thana] Sprint 14 | [Dev][RD][Thana] Sprint 15
Bug | RDAPS-316 | 35558 | [Dev][RD][RRS] Fix datetime filter logic to support millisecond precision for redemption ETL | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Fixing |  | 08/Dec/25 5:57 PM | 30/Dec/25 10:04 AM |  | 2 | [6 empty] | มาจาก Sprint 13 | Fixing |  | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Story | DEVRDSUP-295 | 35557 | [SUP-360][REM] Request to export reward TXN report data due to issue on RR backoffice where data can't be exported. Unicorn+visionary | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Done |  | 08/Dec/25 5:17 PM | 15/Dec/25 3:45 PM | 11/Dec/25 12:00 AM | 5 | mid-sprint | rem |  |  |  |  | มาจาก Sprint 13 | In Review |  | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14
Story | DEVRDSUP-294 | 35556 | [SUP-361][REM] Request to export reward TXN report data due to issue on RR backoffice where data can't be exported. RR Unicorn + RR visionary + 90014725 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Done |  | 08/Dec/25 5:17 PM | 15/Dec/25 3:46 PM | 11/Dec/25 12:00 AM | 5 | mid-sprint | rem |  |  |  | 0 | มาจาก Sprint 13 | In Review | 1800 | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14
Bug | DEVRDCT-341 | 35533 | [S3][DEV][RD][RLP] Cannot command initial sync LIME Pay member to Line OA Account | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Lucas - Saksorn Srisak | 712020:289e7d91-50e6-438c-9b32-23b14017a585 | Medium | Resolved |  | 08/Dec/25 10:13 AM | 15/Dec/25 2:27 PM | [8 empty] | มาจาก Sprint 13 | Resolved |  | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Bug | DEVRDSUP-293 | 35457 | [SUP-347][HOP] Available to import customers under the same Member ID.” | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Enhancement |  | 04/Dec/25 5:35 PM | 22/Dec/25 10:24 AM | 18/Dec/25 12:00 AM |  | hop | hr-solution | mid-sprint | prod-issue | [5 empty] | [Dev][All Project] Sprint 14
Bug | DEVRDSUP-291 | 35452 | [SUP-339][Issue] Subscription Voucher Issue of Nov 25 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Closed |  | 04/Dec/25 1:53 PM | 15/Dec/25 3:47 PM |  |  | data | etl | mid-sprint | prod-issue | sub |  |  |  |  | [Dev][All Project] Sprint 14
Bug | DEVRDSUP-290 | 35449 | [SUP-332][Clevertap] Some user already bound with Turtle Club but in user properties not have club binding details | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Resolved |  | 04/Dec/25 1:35 PM | 24/Dec/25 1:10 PM | 18/Dec/25 12:00 AM |  | CleverTap | mid-sprint | prod-issue | turtle | [5 empty] | [Dev][All Project] Sprint 14
Sub-task | RDAPS-315 | 35441 | [QA] Create Test case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | To Do |  | 04/Dec/25 10:13 AM | 04/Dec/25 10:13 AM | [8 empty] | มาจาก Sprint 13 | To Do |  | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Sub-task | RDAPS-314 | 35439 | [QA] Create Test case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | To Do |  | 04/Dec/25 10:12 AM | 04/Dec/25 10:12 AM | [8 empty] | มาจาก Sprint 13 | To Do |  | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Sub-task | RDAPS-313 | 35437 | [QA] Create Test case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 04/Dec/25 10:11 AM | 16/Dec/25 10:02 AM | [8 empty] | มาจาก Sprint 13 | Done |  | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14
Sub-task | RDAPS-312 | 35435 | [QA] Create Test case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 04/Dec/25 10:11 AM | 15/Dec/25 4:28 PM | [8 empty] | มาจาก Sprint 13 | Done |  | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14
Sub-task | RDAPS-311 | 35433 | [QA] Create Test case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 04/Dec/25 10:11 AM | 15/Dec/25 4:06 PM | [8 empty] | มาจาก Sprint 13 | Done |  | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14
Sub-task | RDAPS-310 | 35431 | [QA] Create Test case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 04/Dec/25 10:11 AM | 15/Dec/25 3:03 PM | [8 empty] | มาจาก Sprint 13 | In Progress |  | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Sub-task | RDAPS-309 | 35429 | [QA] Create Test case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 04/Dec/25 10:10 AM | 09/Dec/25 10:01 AM | [8 empty] | มาจาก Sprint 13 | Done |  | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14
Sub-task | RDAPS-308 | 35427 | [QA] Create Test case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 04/Dec/25 10:10 AM | 15/Dec/25 10:47 AM | [8 empty] | มาจาก Sprint 13 | Done |  | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14
Sub-task | RDAPS-307 | 35425 | [QA] Create Test case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 04/Dec/25 10:10 AM | 04/Dec/25 10:13 AM | [8 empty] | มาจาก Sprint 13 | Done |  | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14
Sub-task | RDAPS-306 | 35423 | [QA] Create Test case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 04/Dec/25 10:10 AM | 04/Dec/25 10:13 AM | [8 empty] | มาจาก Sprint 13 | Done |  | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14
Bug | RDTHANA-419 | 35387 | [S4][HRS][Company setting][Club Tier] Tier management cannot clear input box of Tier name | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Closed |  | 03/Dec/25 6:13 PM | 25/Dec/25 4:26 PM | 16/Dec/25 12:00 AM | 2 | [9 empty] | [Dev][RD][Thana] Sprint 14
Bug | RDTHANA-418 | 35386 | [S4][HRS][Company setting][Club Tier] Tier management cannot re-order tiers | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Closed |  | 03/Dec/25 5:48 PM | 25/Dec/25 4:26 PM |  | 3 | [9 empty] | [Dev][RD][Thana] Sprint 14
Sub-task | DEVRDCT-339 | 35298 | [QA] (On STG) Test execution check "Redeem" Event to have a "Campaign Type" | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 02/Dec/25 11:48 AM | 25/Dec/25 4:17 PM | [8 empty] | มาจาก Sprint 13 | In Progress |  | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Sub-task | DEVRDCT-338 | 35296 | [QA] Add test case "Redeem" Event to have a "Campaign Type" | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 02/Dec/25 11:47 AM | 11/Dec/25 3:46 PM | [8 empty] | มาจาก Sprint 13 | Done |  | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Sub-task | DEVRDCT-337 | 35294 | [QA] Test execution check "WEBHOOK_POINT_ISSUING_TXN" Event | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 02/Dec/25 11:45 AM | 30/Dec/25 10:12 AM | [8 empty] | มาจาก Sprint 13 | To Do |  | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Sub-task | DEVRDCT-336 | 35292 | [QA] Create test case "WEBHOOK_POINT_ISSUING_TXN" Event | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 02/Dec/25 11:45 AM | 29/Dec/25 5:49 PM | [8 empty] | มาจาก Sprint 13 | To Do |  | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Sub-task | DEVRDCT-335 | 35290 | [QA] Test execution check "ORDER_SUCCESS" Event Payload | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 02/Dec/25 11:44 AM | 25/Dec/25 4:20 PM | [8 empty] | มาจาก Sprint 13 | To Do |  | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Sub-task | DEVRDCT-334 | 35288 | [QA] Create test case "ORDER_SUCCESS" Event Payload | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 02/Dec/25 11:43 AM | 17/Dec/25 4:19 PM | [8 empty] | มาจาก Sprint 13 | To Do |  | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Sub-task | DEVRDCT-333 | 35286 | [QA] Test execution check REFUND Event Payload | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 02/Dec/25 11:42 AM | 26/Dec/25 2:15 PM | [8 empty] | มาจาก Sprint 13 | To Do |  | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Sub-task | DEVRDCT-332 | 35284 | [QA] Create test case REFUND Event Payload | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 02/Dec/25 11:42 AM | 17/Dec/25 4:20 PM | [8 empty] | มาจาก Sprint 13 | To Do |  | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Sub-task | DEVRDCT-331 | 35282 | [QA] Test execution check "PAYMENT_PAID" Event Payload | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 02/Dec/25 11:41 AM | 24/Dec/25 4:29 PM | [8 empty] | มาจาก Sprint 13 | In Progress |  | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Sub-task | DEVRDCT-330 | 35280 | [QA] Create test case "PAYMENT_PAID" Event Payload | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 02/Dec/25 11:40 AM | 13/Dec/25 11:24 PM | [8 empty] | มาจาก Sprint 13 | Done |  | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Sub-task | DEVRDCT-329 | 35278 | [QA] Test execution check "Charged" Event Payload | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 02/Dec/25 11:39 AM | 25/Dec/25 4:49 PM | [8 empty] | มาจาก Sprint 13 | In Progress |  | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Sub-task | DEVRDCT-328 | 35276 | [QA] Create test case "Charged" Event Payload | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 02/Dec/25 11:38 AM | 11/Dec/25 3:45 PM | [8 empty] | มาจาก Sprint 13 | Done |  | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Sub-task | DEVRDCT-327 | 35274 | - |  |  | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 02/Dec/25 11:35 AM | 02/Dec/25 11:37 AM | [8 empty] | มาจาก Sprint 13 | To Do |  | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Story | RDAPS-301 | 35202 | [DEV][RD][SA] Consult/Suggest API call flow to integrate with Paypoint system | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Progress |  | 01/Dec/25 12:42 PM | 30/Dec/25 10:04 AM |  | 8 | [6 empty] | มาจาก Sprint 13 | To Do |  | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Story | RDAPS-300 | 35199 | [DEV][RD][HRS][Log file] Enhance member log file page | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 01/Dec/25 11:17 AM | 24/Dec/25 10:10 AM |  | 2 | [5 empty] | 0 | มาจาก Sprint 13 | Ready To Test | 14400 | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14
Epic | DEVRDCT-326 | 35192 | CT-POINT-ISSUE |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 01/Dec/25 9:58 AM | 15/Dec/25 10:06 AM | [8 empty] | มาจาก Sprint 13 | To Do |  | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Epic | DEVRDCT-325 | 35191 | CTxSHOPIFY |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 01/Dec/25 9:55 AM | 15/Dec/25 10:06 AM | [8 empty] | มาจาก Sprint 13 | To Do |  | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Story | RDAPS-299 | 35157 | [DEV][RD][HRS][Queue] Create queue for send upload report | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 30/Nov/25 7:00 PM | 30/Dec/25 10:04 AM | 10/Dec/25 12:00 AM | 3 | [5 empty] | 0 | มาจาก Sprint 13 | Ready to Staging | 28800 | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Story | RDAPS-298 | 35156 | [DEV][RD][Bifrost] Catch-up resend missing BSS_SSO_ADD_CLICKYES in a monthly batch for KYC report from 27 Aug - 24 Nov 2025 | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 30/Nov/25 3:08 PM | 17/Dec/25 9:43 AM |  | 2 | [5 empty] | 0 | มาจาก Sprint 13 | Ready to Staging | 14400 | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14
Story | RDAPS-297 | 35120 | [DEV][RD][HRS][CRONJOB] Create command to import schedule upload | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 28/Nov/25 5:14 PM | 30/Dec/25 10:04 AM | 09/Dec/25 12:00 AM | 3 | [5 empty] | 0 | มาจาก Sprint 13 | Ready To Test | 57600 | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Story | RDAPS-296 | 35119 | [DEV][RD][HRS][MEMBER] Enhance member detail pages | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 28/Nov/25 5:12 PM | 23/Dec/25 8:55 PM | 04/Dec/25 12:00 AM | 2 | hr-solution |  |  |  |  | 0 | มาจาก Sprint 13 | Ready to Staging | 14400 | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14
Story | RDAPS-295 | 35118 | [DEV][RD][HRS][MEMBER] Create export member endpoint | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 28/Nov/25 5:05 PM | 24/Dec/25 11:16 AM |  | 5 | [5 empty] | 0 | มาจาก Sprint 13 | Ready To Test | 57600 | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14
Story | RDAPS-294 | 35115 | [DEV][RD][HRS][MEMBER] Enhance employee import file report | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 28/Nov/25 4:50 PM | 25/Dec/25 12:11 PM |  | 3 | [6 empty] | มาจาก Sprint 13 | Ready To Test |  | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14
Story | RDAPS-293 | 35112 | [DEV][RD][HRS][MEMBER] Enhance registerRabbitMemberV2 function support upload error message | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 28/Nov/25 4:45 PM | 30/Dec/25 10:04 AM | 02/Dec/25 12:00 AM | 5 | hr-solution |  |  |  |  | 0 | มาจาก Sprint 13 | Ready To Test | 43200 | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Story | RDAPS-292 | 35104 | [DEV][RD][HRS][MEMBER] Add schedule upload datatable | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 28/Nov/25 4:12 PM | 25/Dec/25 3:50 PM | 09/Dec/25 12:00 AM | 5 | hr-solution |  |  |  |  | 0 | มาจาก Sprint 13 | Ready to Staging | 57600 | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14
Story | RDAPS-290 | 35076 | [DEV][RD][HRS][MEMBER] Create import member with scheduled type | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 28/Nov/25 2:05 PM | 25/Dec/25 12:26 PM |  | 5 | hr-solution |  |  |  |  | 0 | มาจาก Sprint 13 | Ready To Test | 57600 | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14
Story | RDAPS-289 | 35075 | [DEV][RD][HRS][MEMBER] Enhance import member page - instant | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 28/Nov/25 1:33 PM | 23/Dec/25 9:29 PM | 03/Dec/25 12:00 AM | 5 | hr-solution |  |  |  |  | 0 | มาจาก Sprint 13 | Ready To Test | 57600 | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14
Story | RDAPS-287 | 35069 | [Dev][RD][HRS][MEMBER] Enhance Member Index | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 28/Nov/25 11:22 AM | 22/Dec/25 2:13 PM | 04/Dec/25 12:00 AM | 2 | hr-solution |  |  |  |  | 0 | มาจาก Sprint 13 | Ready to Staging | 14400 | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14
Story | DEVRDCT-324 | 35000 | [DEV][RD][IPF] Implement Event API Point issued | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 27/Nov/25 4:09 PM | 29/Dec/25 5:52 PM | 11/Dec/25 12:00 AM | 8 | rr-issue-point-function |  |  |  |  | 0 | มาจาก Sprint 13 | Ready To Test | 86400 | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Sub-task | DEVRDSUP-270 | 34994 | [Dev] Re-send missing file in monthly batches. |  |  | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 27/Nov/25 3:34 PM | 30/Dec/25 10:04 AM | [8 empty] | มาจาก Sprint 13 | To Do |  | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14
Story | DEVRDSUP-269 | 34992 | [DEVRDSUP-236] Catch-up resend missing BSS_SSO_ADD_CLICKYES in a monthly batch for KYC report from 27 Aug - 24 Nov 2025 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 27/Nov/25 3:22 PM | 25/Dec/25 5:58 PM |  | 1 | etl |  |  |  |  | 7200 | มาจาก Sprint 13 | To Do |  | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14
Story | DEVRDCT-323 | 34991 | [DEV][RD][ECS] Collect and Structure Data for Event ORDER_SUCCESS Payload | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 27/Nov/25 3:14 PM | 25/Dec/25 4:20 PM | 08/Dec/25 12:00 AM | 8 | ecommerce-shopify-api |  |  |  |  | 0 | มาจาก Sprint 13 | Ready To Test | 86400 | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Story | DEVRDCT-322 | 34990 | [DEV][RD][ECS] Collect and Structure Data for Event REFUND Payload | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 27/Nov/25 3:13 PM | 26/Dec/25 2:15 PM | 08/Dec/25 12:00 AM | 3 | ecommerce-shopify-api |  |  |  |  | 0 | มาจาก Sprint 13 | Ready To Test | 28800 | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Story | DEVRDCT-321 | 34989 | [DEV][RD][ECS] Collect and Structure Data for PAYMENT_PAID Event Payload | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 27/Nov/25 3:12 PM | 25/Dec/25 4:06 PM | 08/Dec/25 12:00 AM | 3 | ecommerce-shopify-api |  |  |  |  | 0 | มาจาก Sprint 13 | Ready To Test | 28800 | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Story | DEVRDCT-320 | 34988 | [DEV][RD][ECS] Collect and Structure Data for "Charged" Event Payload | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 27/Nov/25 3:11 PM | 25/Dec/25 5:12 PM | 04/Dec/25 12:00 AM | 5 | ecommerce-shopify-api |  |  |  |  | 0 | มาจาก Sprint 13 | Ready To Test | 57600 | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Story | DEVRDCT-319 | 34987 | [DEV][RD][ECS] Create Centralized Function for Publishes to RabbitMQ | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 27/Nov/25 3:04 PM | 25/Dec/25 7:25 PM | 03/Dec/25 12:00 AM | 3 | ecommerce-shopify-api | No-QA |  |  |  | 0 | มาจาก Sprint 13 | Ready To Test | 28800 | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Story | DEVRDCT-318 | 34986 | [DEV][RD][ECS] Add internal_name Field to shopify_shops Table and Set Default Values | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 27/Nov/25 3:02 PM | 25/Dec/25 7:25 PM | 01/Dec/25 12:00 AM | 1 | ecommerce-shopify-api | No-QA |  |  |  | 0 | มาจาก Sprint 13 | Ready To Test |  | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Bug | RDTHANA-414 | 34982 | [S3][PROD][HRS][Welcome message][Pop up setting] Website tab setting cannot save setting changes | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | High | Closed |  | 27/Nov/25 1:54 PM | 25/Dec/25 4:26 PM | [8 empty] | มาจาก Sprint 13 | Resolved |  | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13 | [Dev][RD][Thana] Sprint 14
Story | DM-98 | 34923 | [DEV][RD][AWSTH] Notification API Cleanup Unused Code After Migration | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 26/Nov/25 4:54 PM | 30/Dec/25 9:31 AM | 29/Dec/25 12:00 AM | 3 | No-QA | [8 empty] | [Dev][RD][AWS] Sprint 14
Story | DM-97 | 34922 | [DEV][RD][AWSTH] Deeplink API Cleanup Unused Code After Migration | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 26/Nov/25 4:54 PM | 30/Dec/25 9:31 AM | 29/Dec/25 12:00 AM | 3 | No-QA |  |  |  |  | 28800 |  |  |  | [Dev][RD][AWS] Sprint 14
Bug | DEVRDECOM-181 | 34638 | [S3][eCommerce Shopify] Order is not created on Shopify DB | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 21/Nov/25 10:54 AM | 15/Dec/25 4:36 PM | [8 empty] | มาจาก Sprint 13 | Fixing |  | [Dev][RD][Ecom] Sprint 12 | [Dev][RD][Ecom] Sprint 13 | [Dev][RD][Ecom] Sprint 14
Epic | DEVRDCT-309 | 34545 | ct-member-tier |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 19/Nov/25 2:49 PM | 15/Dec/25 10:06 AM | [8 empty] | มาจาก Sprint 13 | To Do |  | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Epic | DEVRDCT-308 | 34539 | ct-campaign-type |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 19/Nov/25 10:41 AM | 15/Dec/25 10:06 AM |  |  | redemption-api | [5 empty] | มาจาก Sprint 13 | To Do |  | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Story | DEVRDSUP-252 | 34528 | [SUP-312][SUB] Skipped Receipt GR Offline (Ticket 6 Nov) | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | To Do |  | 18/Nov/25 3:37 PM | 15/Dec/25 3:46 PM | 26/Dec/25 12:00 AM | 8 | [6 empty] | มาจาก Sprint 13 | To Do |  | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14
Story | RDTHANA-393 | 34499 | [DEV][RD][APH] Enhance record "source" when save participant | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 18/Nov/25 9:20 AM | 29/Dec/25 10:20 AM | 19/Nov/25 12:00 AM | 3 | No-QA |  |  |  |  | 0 | มาจาก Sprint 13 | Ready to Staging | 28800 | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13 | [Dev][RD][Thana] Sprint 14 | [Dev][RD][Thana] Sprint 15
Story | DEVRDECOM-173 | 34379 | [DEV][RD][Eco][security/risk] Check list | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Low | In Review |  | 16/Nov/25 5:08 PM | 30/Dec/25 10:05 AM |  | 3 | No-QA |  |  |  |  | 14400 | มาจาก Sprint 13 | In Progress | 28800 -> 14400 | [Dev][RD][Ecom] Sprint 12 | [Dev][RD][Ecom] Sprint 13 | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Story | DEVRDECOM-172 | 34378 | [DEV][RD][Eco][ETL] Import missing txn to datamart | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 16/Nov/25 5:03 PM | 22/Dec/25 4:44 PM |  | 3 | [6 empty] | มาจาก Sprint 13 | In Progress |  | [Dev][RD][Ecom] Sprint 12 | [Dev][RD][Ecom] Sprint 13 | [Dev][RD][Ecom] Sprint 14
Improvement | DEVRDSUP-242 | 34266 | [DEVRDSUP-93][REM] POC - solution finding on how to sync reward stock count to algolia tp prevent stock missmatch | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | In Review |  | 14/Nov/25 2:01 PM | 18/Dec/25 1:32 PM | 12/Dec/25 12:00 AM |  | rem | [5 empty] | มาจาก Sprint 13 | In Progress |  | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14
Story | DEVRDCT-305 | 34254 | [DEV][RD][RDS][ENH] Enhance "Redeem" Event to have a "Campaign Type" | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 14/Nov/25 8:09 AM | 25/Dec/25 4:18 PM | 19/Nov/25 12:00 AM | 2 | redemption-api |  |  |  |  | 0 | มาจาก Sprint 13 | Ready To Test | 14400 | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Bug | RDAPS-269 | 34036 | [DEV][RD][Cron-job][Merchant Ranking] Enhance get merchant with active store only | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Pass : Waiting for deployment |  | 11/Nov/25 1:09 PM | 30/Dec/25 10:04 AM |  | 2 | No-QA | [5 empty] | มาจาก Sprint 13 | Pass : Waiting for deployment |  | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Story | RDAPS-266 | 33791 | [Dev][RD][Order] Improve process to sync transaction to DA | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 07/Nov/25 3:13 PM | 25/Dec/25 10:58 AM | 20/Nov/25 12:00 AM | 3 | order-consumer |  |  |  |  | 0 | มาจาก Sprint 13 | Ready To Test | 28800 | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14
Bug | RDTHANA-377 | 33695 | [S4][Survey][Step 2] Club Status(Active/Inavtive) NOT update after change from HR-solution | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Resolved |  | 06/Nov/25 1:54 PM | 29/Dec/25 10:20 AM | [8 empty] | มาจาก Sprint 13 | Resolved |  | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13 | [Dev][RD][Thana] Sprint 14 | [Dev][RD][Thana] Sprint 15
Bug | DEVRDSUP-221 | 33625 | [SUP-281][RR-Backoffice] Reward Coupon Transaction Report found error after search | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | RETESTING |  | 05/Nov/25 1:30 PM | 29/Dec/25 1:56 PM | 01/Dec/25 12:00 AM | 8 | mid-sprint | prod-issue | rem |  |  |  | มาจาก Sprint 13 | Fixing |  | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14
Story | RDAPS-261 | 33609 | [Dev][RD][RRS] Add additional data to msg payload for Package Confirmation Email | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 05/Nov/25 11:19 AM | 25/Dec/25 10:58 AM |  |  | rr-scheduler | [5 empty] | มาจาก Sprint 13 | Ready To Test |  | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14
Story | DEVRDSUP-213 | 33377 | [SUB] Request to mark used many BTS vouchers due to cloud ID incident on 16/10/2025 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Done |  | 03/Nov/25 6:49 PM | 18/Dec/25 3:35 PM | 01/Dec/25 12:00 AM | 8 | bts | prod-issue | sub | [6 empty] | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 14
Story | RDAPS-256 | 33341 | [Dev][RD][CID] Implement CLI to remove double binding account records | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Blocked |  | 02/Nov/25 4:37 PM | 30/Dec/25 10:04 AM |  | 5 | rr-cloudid-api |  |  |  |  | 0 | มาจาก Sprint 13 | Blocked | 115200 | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Story | RDAPS-255 | 33340 | [Dev][RD][CID] Add log to Binding API to investigate double binding cases | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Nov/25 4:28 PM | 30/Dec/25 10:04 AM | 06/Nov/25 12:00 AM | 3 | rr-cloudid-api |  |  |  |  | 0 | มาจาก Sprint 13 | Ready To Test | 21600 | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Story | RDTHANA-353 | 33197 | [Dev][RD][Survey Web] Remove Survey web from SEO | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 28/Oct/25 1:53 PM | 29/Dec/25 10:20 AM |  | 2 | rr-aphrodite | [5 empty] | มาจาก Sprint 13 | Ready To Test |  | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13 | [Dev][RD][Thana] Sprint 14 | [Dev][RD][Thana] Sprint 15
Bug | DEVRDSUP-196 | 32935 | [SUP-252][REM] Reward's stock amount shows incorrect value on RR app and stock count on RR app doesn't match actual stock on RR back office. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Closed |  | 21/Oct/25 4:45 PM | 16/Dec/25 10:48 AM | 05/Nov/25 12:00 AM | 1 | prod-issue | rem | [7 empty] | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 14
Story | RDAPS-238 | 32907 | [Dev][RD] Create script to mark vouchers as used for Cloud ID cases (issued on 16 Oct) | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 21/Oct/25 2:10 PM | 22/Dec/25 10:29 AM |  | 5 | rr-scheduler |  |  |  |  | 0 | มาจาก Sprint 13 | Blocked | 72000 | [Dev][All Project] Sprint 10 | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14
Story | RDAPS-233 | 32777 | [Dev][RD][RRS] Enhance Redemption ETL to add fields 'USING_AT' and 'COUNTDOWN_EXPIRED_AT' | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Blocked |  | 19/Oct/25 3:24 PM | 30/Dec/25 10:04 AM | 21/Oct/25 12:00 AM | 2 | rr-scheduler |  |  |  |  | 0 | มาจาก Sprint 13 | Blocked | 14400 | [Dev][All Project] Sprint 10 | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Bug | DEVRDCT-241 | 31866 | [S3][CT][Webhook][Club Binding Event] Opt-in type club binding status event not show correctly on CT through Webhook API | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Closed |  | 30/Sep/25 3:31 PM | 22/Dec/25 10:37 AM | [8 empty] | มาจาก Sprint 13 | Open |  | [Dev][CT] Sprint 9 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Story | RDTHANA-289 | 31700 | [DEV][RD][BOF][CR] Enhance survey ranking question | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 26/Sep/25 2:02 PM | 29/Dec/25 10:20 AM | 30/Sep/25 12:00 AM | 3 | [5 empty] | 0 | มาจาก Sprint 13 | Ready To Test | 21600 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13 | [Dev][RD][Thana] Sprint 14 | [Dev][RD][Thana] Sprint 15
Epic | DEVRDECOM-107 | 31506 | Shopify Webhook |  |  | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | To Do |  | 23/Sep/25 9:52 AM | 30/Dec/25 10:05 AM | [8 empty] | มาจาก Sprint 13 | To Do |  | [Dev][RD][Ecom] Sprint 8 | [Dev][RD][Ecom] Sprint 9 | [Dev][RD][Ecom] Sprint 10 | [Dev][RD][Ecom] Sprint 11 | [Dev][RD][Ecom] Sprint 12 | [Dev][RD][Ecom] Sprint 13 | [Dev][RD][Ecom] Sprint 14 | [Dev][RD][Ecom] Sprint 15
Story | RDTHANA-244 | 31447 | [DEV][RD][APH] Enhance sorry page support dynamic error message and CTA button | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 22/Sep/25 11:36 AM | 29/Dec/25 10:20 AM | 29/Sep/25 12:00 AM | 1 | [6 empty] | มาจาก Sprint 13 | Ready To Test |  | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13 | [Dev][RD][Thana] Sprint 14 | [Dev][RD][Thana] Sprint 15
Story | RDTHANA-241 | 31432 | [DEV][RD][APH] Enhance survey html render support survey appearance "Thank you" tab | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 21/Sep/25 9:13 PM | 29/Dec/25 10:20 AM | 29/Sep/25 12:00 AM | 3 | [5 empty] | 0 | มาจาก Sprint 13 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13 | [Dev][RD][Thana] Sprint 14 | [Dev][RD][Thana] Sprint 15
Story | RDTHANA-238 | 31429 | [DEV][RD][APH] Create survey theme | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Highest | Ready To Test |  | 21/Sep/25 8:49 PM | 29/Dec/25 10:20 AM | 23/Sep/25 12:00 AM | 3 | rr-aphrodite |  |  |  |  | 0 | มาจาก Sprint 13 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13 | [Dev][RD][Thana] Sprint 14 | [Dev][RD][Thana] Sprint 15
Story | RDTHANA-231 | 31359 | [DEV][RD][APH] Enhance survey html render support survey appearance "General" tab | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Done |  | 19/Sep/25 10:43 AM | 26/Dec/25 1:16 PM | 26/Sep/25 12:00 AM | 5 | [5 empty] | 0 | มาจาก Sprint 13 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13 | [Dev][RD][Thana] Sprint 14
Story | RDTHANA-230 | 31358 | [DEV][RD][APH] Enhance getMemberToken support sources session | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Done |  | 19/Sep/25 10:42 AM | 26/Dec/25 1:15 PM | 26/Sep/25 12:00 AM | 2 | No-QA |  |  |  |  | 0 | มาจาก Sprint 13 | Ready To Test | 7200 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13 | [Dev][RD][Thana] Sprint 14
Story | RDAPS-187 | 31237 | [Dev][RD][RRS][Technical] Optimize performance for coupons report | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Highest | In Progress |  | 16/Sep/25 4:03 PM | 30/Dec/25 10:04 AM |  | 13 | rr-scheduler | [8 empty] | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Sub-task | RDTHANA-118 | 30812 | [QA] Create Test Case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 09/Sep/25 11:23 AM | 23/Dec/25 10:13 AM | [8 empty] | มาจาก Sprint 13 | To Do |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13 | [Dev][RD][Thana] Sprint 14
Story | RDTHANA-106 | 30689 | [Dev][RD][Service][CMS API] Create service filter api | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 04/Sep/25 4:08 PM | 16/Dec/25 10:11 AM | 11/Sep/25 12:00 AM | 3 | cms-api | No-QA |  |  |  | 0 | มาจาก Sprint 13 | Ready To Test | 18000 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13 | [Dev][RD][Thana] Sprint 14
Story | RDTHANA-90 | 30622 | [Dev][RD][Section][BOF][QA] Enhance Section Feature: Add new widget types | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 02/Sep/25 9:16 PM | 23/Dec/25 10:13 AM |  | 0 | [6 empty] | มาจาก Sprint 13 | Ready To Test |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13 | [Dev][RD][Thana] Sprint 14
Story | RDAPS-160 | 29972 | [DEV][RD][SSO-Backoffice] Disable SEO tracking | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 20/Aug/25 11:21 AM | 30/Dec/25 10:04 AM | 04/Sep/25 12:00 AM | 1 | [5 empty] | 0 | มาจาก Sprint 13 | Ready To Test | 7200 | [Dev][All project]Sprint 6 | [Dev][All project]Sprint 7 | [Dev][All Project] Sprint 9 | [Dev][All Project] Sprint 10 | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 13 | [Dev][All Project] Sprint 14 | [Dev][All Project] Sprint 15
Story | RDTHANA-20 | 29950 | [Dev][RD][APH] Enhance check token | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 19/Aug/25 7:46 PM | 29/Dec/25 10:20 AM |  | 3 | [5 empty] | 0 | มาจาก Sprint 13 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13 | [Dev][RD][Thana] Sprint 14 | [Dev][RD][Thana] Sprint 15
Bug | DEVRDSUP-95 | 29929 | [SUP-54][Noti] Whole NBO page gets frozen when user uses "internal link" and tries to search for internal content. | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Lowest | Closed |  | 19/Aug/25 4:47 PM | 26/Dec/25 4:22 PM | 19/Sep/25 12:00 AM | 3 | [9 empty] | [Dev][All Project] Sprint 10 | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 14

## Summarize Sprint 13
Column 1 | Total Stories Point | Total Manhour | Point Done | Manhour Done | Note
1 Dec - 12 Dec
Dev Resource Available | 14 | 438.75
Meeting Planned |  |  |  |  | Ref
Additional Meeting |  |  |  |  | Ref
Deployment |  | 9 |  |  | 2 ครั้ง 1. 4 คน 2. 5 คน
Development Sprint Total | 325 | 360.5 | 139 | 118.5
Ad-hoc Mid Sprint | 0 | 0 | 0 | 0.5 | 0 tasks
Requirement changes after refinement? | 0 |  | 0 | 0 | 0 tasks
Aek | 26 | 22 | 23 | 18
A | 46 | 76 | 40 | 76
Aom | 54 | 32.5 | 8 | 0.5
Zan | 10 | 2 | 0 | 2
Mai | 38 | 30 | 16 | 4
Mac | 32 | 51 | 3 | 3
Mos | 19 | 44 | 5 | 8
Jack | 16 | 27 | 2 | 3
Art | 20 | 0 | 20 | 0
Kae | 10 | 0 | 2 | 0
Nim | 26 | 32 | 8 | 0
Arm | 28 | 44 | 12 | 4
| System Architech |  |  |  | Permanent Dev. |  |  | Outsources
Projects (Stories Points) | Aek | Zan | Aom | Jack | A | Art | Mai | Kae | Mac | Nim | Mos | Arm
Das Haus - Thana City & Das Haus | 0 | 0 | 0 | 3 | 6 | 3 | 22 | 0 | 5 | 5 | 0 | 2
E-commerce 1.1. E-Commerce x Shopify Plus 1.2. Shopify:Snackmaker 1.3. Shopify: Turtle Delivery 1.4. Shopify: Turtle Delivery | 18 | 0 | 0 | 3 | 0 | 1 | 2 | 2 | 0 | 0 | 2 | 2
CleverTap - MKT Automation Tool | 8 | 0 | 0 | 10 | 0 | 13 | 0 | 6 | 18 | 6 | 6 | 4
Adjust Integration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Adhoc - Non-Epics - Turtle Display club tier on POS - Data Mart Migration | 0 | 10 | 28 | 0 | 0 | 3 | 14 | 8 | 9 | 0 | 11 | 20
Support Incidents | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| System Architech |  |  |  | Permanent Dev. |  |  | Outsources
Projects (Manhour) | Aek | Zan | Aom | Jack | A | Art | Mai | Kae | Mac | Nim | Mos | Arm
Das Haus - Thana City & Das Haus | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
E-commerce 1.1. E-Commerce x Shopify Plus 1.2. Shopify:Snackmaker 1.3. Shopify: Turtle Delivery 1.4. Shopify: Turtle Delivery | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 4
CleverTap - MKT Automation Tool | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 48 | 0 | 8 | 8
Adjust Integration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Adhoc - Non-Epics - Turtle Display club tier on POS - Data Mart Migration | 0 | 2 | 32 | 0 | 0 | 0 | 28 | 0 | 3 | 32 | 28 | 32
Support Incidents | 0 | 0 | 0.5 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 13
Issue Type | Issue key | Issue id | Summary | Assignee | Assignee Id | Reporter | Reporter Id | Priority | Status | Resolution | Created | Updated | Due date | Custom field (Story Points) | Labels | Labels | Labels | Labels | Original estimate | Sprint Movement | Sprint 12 | Note | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint
Story | DEVRDSUP-306 | 35824 | [SUP-365][RDxDA][ETL] Daily Redemption Report has failed - Missing REDEMPTIONMASTER Files (20251209, 20251210) | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 12/Dec/25 4:34 PM | 12/Dec/25 5:09 PM |  |  | data | mid-sprint | [6 empty] | [Dev][All Project] Sprint 13
Sub-task | DEVRDSUP-304 | 35720 | [Dev] Export all receipts from 9-11 Dec 2025 |  |  | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | To Do |  | 11/Dec/25 5:21 PM | 11/Dec/25 5:21 PM | [10 empty] | [Dev][All Project] Sprint 13
Story | DEVRDSUP-303 | 35718 | [SUP-367]SUB : Incorrect E-Receipt Naming via BCC Automail (9-11 Dec) | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 11/Dec/25 5:17 PM | 15/Dec/25 12:20 PM |  |  | mid-sprint | sub |  |  | 1800 |  |  |  | [Dev][All Project] Sprint 13
Story | RDAPS-329 | 35717 | [Dev][RD][BOF] Optimize query performance for Coupons Transaction Report | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 11/Dec/25 4:46 PM | 12/Dec/25 2:43 PM |  | 13 |  |  |  |  | 115200 |  |  |  | [Dev][All Project] Sprint 13
Test Plan | DEVRDCT-342 | 35712 | [TP] Sprint #13 |  |  | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 11/Dec/25 3:26 PM | 15/Dec/25 10:06 AM | [10 empty] | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Story | DM-149 | 35706 | [DEV][RD][AWSTH] Update container's work directory for Rabbit Sky Web | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 11/Dec/25 1:13 PM | 11/Dec/25 1:43 PM | 12/Dec/25 12:00 AM | 1 | No-QA |  |  |  | 7200 |  |  |  | [Dev][RD][AWS] Sprint 13
Story | RDAPS-326 | 35705 | [DEV][RD][HRS] Enhance employee import flow support schedule | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 11/Dec/25 11:47 AM | 12/Dec/25 10:35 AM |  | 3 |  |  |  |  | 28800 |  |  |  | [Dev][All Project] Sprint 13
Sub-task | RDAPS-325 | 35704 | Check BU still active |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 11/Dec/25 11:39 AM | 11/Dec/25 11:39 AM | [10 empty] | [Dev][All Project] Sprint 13
Story | RDAPS-324 | 35702 | [DEV][RD][HRS] Add action to retry button in schedule datatable | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Progress |  | 11/Dec/25 11:13 AM | 12/Dec/25 10:35 AM | 12/Dec/25 12:00 AM | 3 |  |  |  |  | 28800 |  |  |  | [Dev][All Project] Sprint 13
Bug | RDAPS-323 | 35657 | [HOTFIX][DEV][RD][LNF] Missing new parameter in create temp deeplink flow | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Closed |  | 10/Dec/25 2:06 PM | 10/Dec/25 11:44 PM |  |  | No-QA | [7 empty] | [Dev][All Project] Sprint 13
Sub-task | DEVRDSUP-297 | 35652 | [QA] Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 10/Dec/25 9:54 AM | 10/Dec/25 9:54 AM | [10 empty] | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 13
Sub-task | RDAPS-321 | 35650 | [QA] \Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 10/Dec/25 9:53 AM | 11/Dec/25 1:00 PM | [10 empty] | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 13
Story | DM-146 | 35646 | [DEV][RD][AWSTH] Update container's work directory for Partner Loyalty | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 10/Dec/25 8:37 AM | 11/Dec/25 1:42 PM | 11/Dec/25 12:00 AM | 2 | No-QA |  |  |  | 7200 |  |  |  | [Dev][RD][AWS] Sprint 13
Sub-task | RDAPS-320 | 35606 | [QA] Create Test case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 09/Dec/25 3:22 PM | 09/Dec/25 3:23 PM | [10 empty] | [Dev][All Project] Sprint 13
Task | RDAPS-319 | 35603 | [BOF] Add placeholder for deeplink infinite scroll | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Medium | Ready To Test |  | 09/Dec/25 1:55 PM | 12/Dec/25 1:27 PM | 11/Dec/25 12:00 AM | 1 | No-QA | rr-backoffice |  |  | 7200 |  |  |  | [Dev][All Project] Sprint 13
Story | RDAPS-317 | 35597 | [DEV][RD][BOF] Create migration to change data type | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 09/Dec/25 12:48 PM | 12/Dec/25 3:00 PM |  | 1 | No-QA | rabbit-cms-api |  |  | 3600 |  |  |  | [Dev][All Project] Sprint 13
Story | DM-145 | 35596 | [DEV][RD][AWSTH] Update Docker and config to support new pipeline for Point Engine Proxy | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 09/Dec/25 11:40 AM | 09/Dec/25 1:24 PM | 10/Dec/25 12:00 AM | 1 | infra | No-QA |  |  | 7200 |  |  |  | [Dev][RD][AWS] Sprint 13
Bug | RDTHANA-424 | 35591 | [S3][ฺBanner][Deeplink] Unable to save Banner with Full Deeplink (Link from Deeplink Page) | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Resolved |  | 09/Dec/25 10:09 AM | 12/Dec/25 3:00 PM | [10 empty] | [Dev][RD][Thana] Sprint 13
Bug | RDAPS-316 | 35558 | [Dev][RD][RRS] Fix datetime filter logic to support millisecond precision for redemption ETL | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Fixing |  | 08/Dec/25 5:57 PM | 12/Dec/25 2:45 PM |  | 2 | [8 empty] | [Dev][All Project] Sprint 13
Story | DEVRDSUP-295 | 35557 | [SUP-360][REM] Request to export reward TXN report data due to issue on RR backoffice where data can't be exported. Unicorn+visionary | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | In Review |  | 08/Dec/25 5:17 PM | 11/Dec/25 5:46 PM | 11/Dec/25 12:00 AM | 5 | mid-sprint | rem | [6 empty] | [Dev][All Project] Sprint 13
Story | DEVRDSUP-294 | 35556 | [SUP-361][REM] Request to export reward TXN report data due to issue on RR backoffice where data can't be exported. RR Unicorn + RR visionary + 90014725 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | In Review |  | 08/Dec/25 5:17 PM | 12/Dec/25 11:59 AM | 11/Dec/25 12:00 AM | 5 | mid-sprint | rem | [6 empty] | [Dev][All Project] Sprint 13
Story | DM-144 | 35553 | [DEV][RD][AWSTH] Update Docker and config to support new pipeline for Redemption Consumer | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 08/Dec/25 4:48 PM | 09/Dec/25 11:37 AM | 10/Dec/25 12:00 AM | 1 | infra | No-QA |  |  | 7200 |  |  |  | [Dev][RD][AWS] Sprint 13
Story | DM-143 | 35552 | [DEV][RD][AWSTH] Update Docker and config to support new pipeline for Redemption API | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 08/Dec/25 4:46 PM | 09/Dec/25 11:33 AM | 10/Dec/25 12:00 AM | 1 | infra | No-QA |  |  | 7200 |  |  |  | [Dev][RD][AWS] Sprint 13
Story | DM-142 | 35551 | [DEV][RD][AWSTH] Update Docker and config to support new pipeline for Rewards Consumer | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 08/Dec/25 4:46 PM | 09/Dec/25 11:26 AM | 10/Dec/25 12:00 AM | 1 | infra | No-QA |  |  | 7200 |  |  |  | [Dev][RD][AWS] Sprint 13
Story | DM-141 | 35550 | [DEV][RD][AWSTH] Update Docker and config to support new pipeline for Rewards API | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 08/Dec/25 4:45 PM | 09/Dec/25 11:14 AM | 10/Dec/25 12:00 AM | 1 | infra | No-QA |  |  | 7200 |  |  |  | [Dev][RD][AWS] Sprint 13
Story | DM-140 | 35549 | [DEV][RD][AWSTH] Update Docker and config to support new pipeline for RR CronJob | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 08/Dec/25 4:43 PM | 09/Dec/25 9:53 AM | 10/Dec/25 12:00 AM | 1 | infra | No-QA |  |  | 7200 |  |  |  | [Dev][RD][AWS] Sprint 13
Story | DM-139 | 35548 | [DEV][RD][AWSTH] Update Docker and config to support new pipeline for CMS API | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 08/Dec/25 4:42 PM | 09/Dec/25 9:38 AM | 10/Dec/25 12:00 AM | 1 | infra | No-QA |  |  | 7200 |  |  |  | [Dev][RD][AWS] Sprint 13
Story | DM-138 | 35547 | [DEV][RD][AWSTH] Update Docker and config to support new pipeline for Notification API | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 08/Dec/25 4:41 PM | 09/Dec/25 9:37 AM | 10/Dec/25 12:00 AM | 1 | infra | No-QA |  |  | 7200 |  |  |  | [Dev][RD][AWS] Sprint 13
Story | DM-137 | 35546 | [DEV][RD][AWSTH] Update Docker and config to support new pipeline for Merchant API | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 08/Dec/25 4:40 PM | 09/Dec/25 9:37 AM | 10/Dec/25 12:00 AM | 1 | infra | No-QA |  |  | 7200 |  |  |  | [Dev][RD][AWS] Sprint 13
Story | DM-136 | 35545 | [DEV][RD][AWSTH] Update Docker and config to support new pipeline for Exclusive Store API | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 08/Dec/25 4:39 PM | 09/Dec/25 9:36 AM | 10/Dec/25 12:00 AM | 1 | infra | No-QA |  |  | 7200 |  |  |  | [Dev][RD][AWS] Sprint 13
Story | DM-135 | 35544 | [DEV][RD][AWSTH] Update Docker and config to support new pipeline for Deeplink API | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 08/Dec/25 4:38 PM | 08/Dec/25 5:11 PM | 10/Dec/25 12:00 AM | 1 | [8 empty] | [Dev][RD][AWS] Sprint 13
Story | DM-134 | 35539 | [DEV][RD][AWSTH] Update Docker and config to support new pipeline for Rabbit App BFF | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 08/Dec/25 1:12 PM | 08/Dec/25 2:41 PM | 09/Dec/25 12:00 AM | 1 | No-QA |  |  |  | 7200 |  |  |  | [Dev][RD][AWS] Sprint 13
Bug | DEVRDCT-341 | 35533 | [S3][DEV][RD][RLP] Cannot command initial sync LIME Pay member to Line OA Account | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Lucas - Saksorn Srisak | 712020:289e7d91-50e6-438c-9b32-23b14017a585 | Medium | Resolved |  | 08/Dec/25 10:13 AM | 15/Dec/25 10:06 AM | [10 empty] | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Sub-task | RDTHANA-423 | 35531 | [QA] Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 08/Dec/25 10:08 AM | 10/Dec/25 9:53 AM | [10 empty] | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13
Sub-task | RDTHANA-422 | 35529 | [QA] Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 08/Dec/25 10:08 AM | 08/Dec/25 10:08 AM | [10 empty] | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13
Sub-task | RDTHANA-421 | 35527 | [QA] Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 08/Dec/25 10:08 AM | 10/Dec/25 9:53 AM | [10 empty] | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13
Sub-task | RDTHANA-420 | 35525 | [QA] Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 08/Dec/25 10:08 AM | 08/Dec/25 4:50 PM | [10 empty] | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13
Story | DM-133 | 35523 | [DEV][RD][AWSTH] Update Docker and config to support new pipeline for RR E-commerce shopify | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 08/Dec/25 9:36 AM | 08/Dec/25 1:11 PM | 09/Dec/25 12:00 AM | 1 | No-QA |  |  |  | 7200 |  |  |  | [Dev][RD][AWS] Sprint 13
Story | DEVRDCT-340 | 35490 | [DEV][RD][CL] Improve Message Filtering Logic in allow event for Shopify | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 07/Dec/25 8:20 AM | 12/Dec/25 10:18 AM | 08/Dec/25 12:00 AM | 2 | CleverTap | No-QA |  |  | 10800 |  |  |  | [Dev][RD][CT] Sprint 13
Story | DM-132 | 35456 | [DEV][RD][AWSTH] Update Docker and config to support new pipeline for Offline Subscription BFF | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 04/Dec/25 5:11 PM | 08/Dec/25 3:48 PM | 09/Dec/25 12:00 AM | 1 | No-QA |  |  |  | 7200 |  |  |  | [Dev][RD][AWS] Sprint 13
Story | DM-131 | 35454 | [DEV][RD][AWSTH] Update Docker and config to support new pipeline for RR CloudID API | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 04/Dec/25 4:00 PM | 08/Dec/25 3:47 PM | 08/Dec/25 12:00 AM | 1 | No-QA |  |  |  | 7200 |  |  |  | [Dev][RD][AWS] Sprint 13
Story | DM-130 | 35446 | [DEV][RD][AWSTH] Update Docker and config to support new pipeline for RR Order API | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 04/Dec/25 11:17 AM | 08/Dec/25 9:08 AM | 08/Dec/25 12:00 AM | 1 | No-QA |  |  |  | 7200 |  |  |  | [Dev][RD][AWS] Sprint 13
Sub-task | DEVRDECOM-191 | 35445 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 04/Dec/25 10:13 AM | 11/Dec/25 12:54 AM | [10 empty] | [Dev][RD][Ecom] Sprint 13
Sub-task | DEVRDECOM-190 | 35443 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 04/Dec/25 10:13 AM | 04/Dec/25 10:13 AM | [10 empty] | [Dev][RD][Ecom] Sprint 13
Sub-task | RDAPS-315 | 35441 | [QA] Create Test case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | To Do |  | 04/Dec/25 10:13 AM | 04/Dec/25 10:13 AM | [10 empty] | [Dev][All Project] Sprint 13
Sub-task | RDAPS-314 | 35439 | [QA] Create Test case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | To Do |  | 04/Dec/25 10:12 AM | 04/Dec/25 10:12 AM | [10 empty] | [Dev][All Project] Sprint 13
Sub-task | RDAPS-313 | 35437 | [QA] Create Test case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 04/Dec/25 10:11 AM | 12/Dec/25 10:03 AM | [10 empty] | [Dev][All Project] Sprint 13
Sub-task | RDAPS-312 | 35435 | [QA] Create Test case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 04/Dec/25 10:11 AM | 12/Dec/25 10:03 AM | [10 empty] | [Dev][All Project] Sprint 13
Sub-task | RDAPS-311 | 35433 | [QA] Create Test case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 04/Dec/25 10:11 AM | 09/Dec/25 10:01 AM | [10 empty] | [Dev][All Project] Sprint 13
Sub-task | RDAPS-310 | 35431 | [QA] Create Test case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | In Progress |  | 04/Dec/25 10:11 AM | 15/Dec/25 10:47 AM | [10 empty] | [Dev][All Project] Sprint 13
Sub-task | RDAPS-309 | 35429 | [QA] Create Test case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 04/Dec/25 10:10 AM | 09/Dec/25 10:01 AM | [10 empty] | [Dev][All Project] Sprint 13
Sub-task | RDAPS-308 | 35427 | [QA] Create Test case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 04/Dec/25 10:10 AM | 15/Dec/25 10:47 AM | [10 empty] | [Dev][All Project] Sprint 13
Sub-task | RDAPS-307 | 35425 | [QA] Create Test case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 04/Dec/25 10:10 AM | 04/Dec/25 10:13 AM | [10 empty] | [Dev][All Project] Sprint 13
Sub-task | RDAPS-306 | 35423 | [QA] Create Test case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 04/Dec/25 10:10 AM | 04/Dec/25 10:13 AM | [10 empty] | [Dev][All Project] Sprint 13
Story | DM-129 | 35382 | [DEV][RD][AWSTH] Update Docker and config to support new pipeline for RR DataHub GQL | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 03/Dec/25 4:06 PM | 08/Dec/25 3:47 PM | 08/Dec/25 12:00 AM | 1 | No-QA |  |  |  | 7200 |  |  |  | [Dev][RD][AWS] Sprint 13
Story | DM-128 | 35381 | [DEV][RD][AWSTH] Update Docker and config to support new pipeline for RR CleverTap | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 03/Dec/25 3:53 PM | 08/Dec/25 3:47 PM | 08/Dec/25 12:00 AM | 1 | No-QA |  |  |  | 7200 |  |  |  | [Dev][RD][AWS] Sprint 13
Story | DM-127 | 35380 | [DEV][RD][AWSTH] Update Docker and config to support new pipeline for RR Cart API | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 03/Dec/25 3:40 PM | 08/Dec/25 3:47 PM | 08/Dec/25 12:00 AM | 1 | No-QA |  |  |  | 7200 |  |  |  | [Dev][RD][AWS] Sprint 13
Story | RDAPS-305 | 35378 | [DEV][RD][SRS] Change support email |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 03/Dec/25 2:08 PM | 15/Dec/25 10:57 AM | [10 empty] | [Dev][All Project] Sprint 13
Sub-task | DEVRDECOM-189 | 35375 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 03/Dec/25 1:23 PM | 08/Dec/25 11:38 AM | [10 empty] | [Dev][RD][Ecom] Sprint 13
Sub-task | DEVRDECOM-188 | 35373 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 03/Dec/25 1:23 PM | 03/Dec/25 1:23 PM | [10 empty] | [Dev][RD][Ecom] Sprint 13
Story | DEVRDSUP-287 | 35361 | [SUP-352]Request for RR back office access 02/12/2025 | Thanakrit Chanthaworn | 712020:3fc982cb-c268-4f1d-9265-d3dd8fb08304 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 03/Dec/25 11:18 AM | 04/Dec/25 10:33 AM | 03/Dec/25 12:00 AM |  | access | [7 empty] | [Dev][All Project] Sprint 13
Story | RDAPS-304 | 35320 | [DEV][RD][REWARDS API][REWARDS] Change Expiry date logic | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 02/Dec/25 4:28 PM | 11/Dec/25 4:34 PM | [10 empty] | [Dev][All Project] Sprint 13
Story | RDAPS-303 | 35319 | [DEV][RD][BOF][REWARDS] Change Expiry date logic Example display | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 02/Dec/25 4:27 PM | 11/Dec/25 4:34 PM | 03/Dec/25 12:00 AM | 1 |  |  |  |  | 7200 |  |  |  | [Dev][All Project] Sprint 13
Story | DM-126 | 35306 | [DEV][AWS][AWSTH][POC] Migrate RDS from MariaDB to Postgres Aurora for Partner Loyalty | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 02/Dec/25 2:44 PM | 10/Dec/25 9:42 AM | 10/Dec/25 12:00 AM | 2 | No-QA |  |  |  | 14400 |  |  |  | [Dev][RD][AWS] Sprint 13
Sub-task | DEVRDCT-339 | 35298 | [QA] (On STG) Test execution check "Redeem" Event to have a "Campaign Type" | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | In Progress |  | 02/Dec/25 11:48 AM | 11/Dec/25 10:14 AM | [10 empty] | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Sub-task | DEVRDCT-338 | 35296 | [QA] Add test case "Redeem" Event to have a "Campaign Type" | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 02/Dec/25 11:47 AM | 11/Dec/25 3:46 PM | [10 empty] | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Sub-task | DEVRDCT-337 | 35294 | [QA] Test execution check "WEBHOOK_POINT_ISSUING_TXN" Event | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 02/Dec/25 11:45 AM | 02/Dec/25 11:45 AM | [10 empty] | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Sub-task | DEVRDCT-336 | 35292 | [QA] Create test case "WEBHOOK_POINT_ISSUING_TXN" Event | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 02/Dec/25 11:45 AM | 02/Dec/25 11:45 AM | [10 empty] | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Sub-task | DEVRDCT-335 | 35290 | [QA] Test execution check "ORDER_SUCCESS" Event Payload | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 02/Dec/25 11:44 AM | 02/Dec/25 11:44 AM | [10 empty] | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Sub-task | DEVRDCT-334 | 35288 | [QA] Create test case "ORDER_SUCCESS" Event Payload | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 02/Dec/25 11:43 AM | 02/Dec/25 11:43 AM | [10 empty] | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Sub-task | DEVRDCT-333 | 35286 | [QA] Test execution check REFUND Event Payload | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 02/Dec/25 11:42 AM | 02/Dec/25 11:42 AM | [10 empty] | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Sub-task | DEVRDCT-332 | 35284 | [QA] Create test case REFUND Event Payload | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 02/Dec/25 11:42 AM | 02/Dec/25 11:42 AM | [10 empty] | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Sub-task | DEVRDCT-331 | 35282 | [QA] Test execution check "PAYMENT_PAID" Event Payload | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | In Progress |  | 02/Dec/25 11:41 AM | 12/Dec/25 10:08 AM | [10 empty] | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Sub-task | DEVRDCT-330 | 35280 | [QA] Create test case "PAYMENT_PAID" Event Payload | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 02/Dec/25 11:40 AM | 13/Dec/25 11:24 PM | [10 empty] | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Sub-task | DEVRDCT-329 | 35278 | [QA] Test execution check "Charged" Event Payload | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | In Progress |  | 02/Dec/25 11:39 AM | 11/Dec/25 3:14 PM | [10 empty] | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Sub-task | DEVRDCT-328 | 35276 | [QA] Create test case "Charged" Event Payload | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 02/Dec/25 11:38 AM | 11/Dec/25 3:45 PM | [10 empty] | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Sub-task | DEVRDCT-327 | 35274 | - |  |  | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 02/Dec/25 11:35 AM | 02/Dec/25 11:37 AM | [10 empty] | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Bug | DEVRDSUP-282 | 35272 | [SUP-348]#20251100021733 Unable to top up trips in Line Pay account, and the card number displays incorrectly. | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Closed |  | 02/Dec/25 11:29 AM | 09/Dec/25 5:25 PM |  |  | mid-sprint | [7 empty] | [Dev][All Project] Sprint 13
Bug | RDAPS-302 | 35271 | [S2][Dev][RD][REM] rule for coupon_valid_until_at was miscalculation | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Lucas - Saksorn Srisak | 712020:289e7d91-50e6-438c-9b32-23b14017a585 | Medium | Rejected |  | 02/Dec/25 11:11 AM | 02/Dec/25 5:13 PM | [10 empty] | [Dev][All Project] Sprint 13
Story | DM-125 | 35236 | [DEV][RD][AWSTH] Update Docker and config to support new pipeline for RR BTS Officer Web | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 01/Dec/25 7:37 PM | 04/Dec/25 3:21 PM | 04/Dec/25 12:00 AM | 1 | No-QA |  |  |  | 7200 |  |  |  | [Dev][RD][AWS] Sprint 13
Story | DM-124 | 35235 | [DEV][RD][AWSTH] Update Docker and config to support new pipeline for RRScheduler | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 01/Dec/25 7:37 PM | 04/Dec/25 5:10 PM | 08/Dec/25 12:00 AM | 1 | No-QA |  |  |  | 7200 |  |  |  | [Dev][RD][AWS] Sprint 13
Story | DM-123 | 35234 | [DEV][RD][AWSTH] Update Docker and config to support new pipeline for RR Member Acquisition | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 01/Dec/25 7:36 PM | 08/Dec/25 9:12 AM | 08/Dec/25 12:00 AM | 1 | No-QA |  |  |  | 7200 |  |  |  | [Dev][RD][AWS] Sprint 13
Story | DM-122 | 35233 | [DEV][RD][AWSTH] Update Docker and config to support new pipeline for RR Member Web | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 01/Dec/25 7:36 PM | 04/Dec/25 2:21 PM | 04/Dec/25 12:00 AM | 1 | No-QA |  |  |  | 7200 |  |  |  | [Dev][RD][AWS] Sprint 13
Story | DM-121 | 35232 | [DEV][RD][AWSTH] Update Docker and config to support new pipeline for RR Link Notify | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 01/Dec/25 7:36 PM | 04/Dec/25 4:29 PM | 08/Dec/25 12:00 AM | 1 | No-QA |  |  |  | 7200 |  |  |  | [Dev][RD][AWS] Sprint 13
Story | DM-120 | 35231 | [DEV][RD][AWSTH] Update Docker and config to support new pipeline for RR BackOffice Web | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 01/Dec/25 7:35 PM | 09/Dec/25 9:26 AM | 09/Dec/25 12:00 AM | 1 | No-QA |  |  |  | 7200 |  |  |  | [Dev][RD][AWS] Sprint 13
Story | DM-119 | 35230 | [DEV][RD][AWSTH] Update Docker and config to support new pipeline for RR Athena API | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 01/Dec/25 7:35 PM | 08/Dec/25 4:44 PM | 04/Dec/25 12:00 AM | 1 | No-QA |  |  |  | 7200 |  |  |  | [Dev][RD][AWS] Sprint 13
Bug | DEVRDSUP-280 | 35227 | [SUP-345][HRSolution][Club][Turtle] After updating "Member Benefit", RR app doesn't show updated content on RR app. | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Closed |  | 01/Dec/25 5:43 PM | 04/Dec/25 12:21 AM | 04/Dec/25 12:00 AM |  | club | mid-sprint | prod-issue | turtle |  |  |  |  | [Dev][All Project] Sprint 13
Bug | DEVRDSUP-279 | 35225 | [SUP-346][HRSolution][Club][Turtle] User can't see any section content on Member's page but appears again if switch to non-member's page tab and switched back . | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Low | Closed |  | 01/Dec/25 5:17 PM | 03/Dec/25 11:34 PM | 05/Jan/26 12:00 AM |  | club | hr-solution | mid-sprint | prod-issue |  |  |  |  | [Dev][All Project] Sprint 13
Sub-task | DEVRDSUP-278 | 35220 | [Dev] Investigate failure in user creation from HR Solution to SSO | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | In Progress |  | 01/Dec/25 4:39 PM | 11/Dec/25 10:13 AM | [10 empty] | [Dev][All Project] Sprint 13
Story | DEVRDSUP-277 | 35218 | [SUP-338][SUB] : Request to export receipt due to Incomplete Emails Received by BTSC (November2025) | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Done |  | 01/Dec/25 4:06 PM | 04/Dec/25 1:49 PM | 03/Dec/25 12:00 AM | 2 | sub |  |  |  | 14400 |  |  |  | [Dev][All Project] Sprint 13
Story | DM-118 | 35217 | [DEV][RD][AWSTH] Update Docker and config to support new pipeline for RR Aphrodite Web | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 01/Dec/25 3:50 PM | 08/Dec/25 2:50 PM | 04/Dec/25 12:00 AM | 1 | No-QA |  |  |  | 7200 |  |  |  | [Dev][RD][AWS] Sprint 13
Story | DM-117 | 35215 | [DEV][RD][AWSTH] Update Docker and config to support new pipeline for Rabbit Sky Web | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 01/Dec/25 3:49 PM | 04/Dec/25 11:21 AM | 04/Dec/25 12:00 AM | 1 | No-QA |  |  |  | 7200 |  |  |  | [Dev][RD][AWS] Sprint 13
Story | DM-116 | 35214 | [DEV][RD][AWSTH] Update Docker and config to support new pipeline for Rabbit Sky API | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 01/Dec/25 3:49 PM | 08/Dec/25 4:19 PM | 04/Dec/25 12:00 AM | 1 | No-QA |  |  |  | 7200 |  |  |  | [Dev][RD][AWS] Sprint 13
Story | DM-115 | 35213 | [DEV][RD][AWSTH] Update Docker and config to support new pipeline for HR Solution | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 01/Dec/25 3:49 PM | 04/Dec/25 3:35 PM | 04/Dec/25 12:00 AM | 1 | No-QA |  |  |  | 7200 |  |  |  | [Dev][RD][AWS] Sprint 13
Bug | DEVRDSUP-276 | 35212 | [SUP-343][HRSolution] Member can be imported successfully, but user is not created on SSO and not bind with provided BU. | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Closed |  | 01/Dec/25 3:38 PM | 03/Dec/25 1:51 PM | 15/Dec/25 12:00 AM |  | club | hop | hr-solution | [5 empty] | [Dev][All Project] Sprint 13
Story | DM-114 | 35210 | [DEV][RD][AWSTH] Update Docker and config to support new pipeline for Partner Loyalty API | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 01/Dec/25 2:37 PM | 03/Dec/25 10:05 AM | 03/Dec/25 12:00 AM | 1 | No-QA |  |  |  | 7200 |  |  |  | [Dev][RD][AWS] Sprint 13
Story | DM-113 | 35203 | [DEV][AWS][AWSTH][POC] Migrate RDS from MariaDB to MySQL Aurora for HR Solution | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 01/Dec/25 1:09 PM | 12/Dec/25 10:05 AM | 03/Dec/25 12:00 AM | 2 | No-QA |  |  |  | 14400 |  |  |  | [Dev][RD][AWS] Sprint 13
Story | RDAPS-301 | 35202 | [DEV][RD][SA] Consult/Suggest API call flow to integrate with Paypoint system | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 01/Dec/25 12:42 PM | 15/Dec/25 10:08 AM |  | 8 | [8 empty] | [Dev][All Project] Sprint 13
Story | RDAPS-300 | 35199 | [DEV][RD][HRS][Log file] Enhance member log file page | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 01/Dec/25 11:17 AM | 12/Dec/25 10:18 AM |  | 2 |  |  |  |  | 14400 |  |  |  | [Dev][All Project] Sprint 13
Epic | DEVRDCT-326 | 35192 | CT-POINT-ISSUE |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 01/Dec/25 9:58 AM | 15/Dec/25 10:06 AM | [10 empty] | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Epic | DEVRDCT-325 | 35191 | CTxSHOPIFY |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 01/Dec/25 9:55 AM | 15/Dec/25 10:06 AM | [10 empty] | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Story | DEVRDECOM-187 | 35190 | [DEV][RD][Eco][Ecommerce-Shopify] Adjust logic check club require and lead user to Show T&C | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 01/Dec/25 8:48 AM | 04/Dec/25 1:48 PM |  | 2 | [8 empty] | [Dev][RD][Ecom] Sprint 13
Story | RDAPS-299 | 35157 | [DEV][RD][HRS][Queue] Create queue for send upload report | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 30/Nov/25 7:00 PM | 11/Dec/25 1:01 PM | 10/Dec/25 12:00 AM | 3 |  |  |  |  | 28800 |  |  |  | [Dev][All Project] Sprint 13
Story | RDAPS-298 | 35156 | [DEV][RD][Bifrost] Catch-up resend missing BSS_SSO_ADD_CLICKYES in a monthly batch for KYC report from 27 Aug - 24 Nov 2025 | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready to Staging |  | 30/Nov/25 3:08 PM | 15/Dec/25 9:33 AM |  | 2 |  |  |  |  | 14400 |  |  |  | [Dev][All Project] Sprint 13
Story | DEVRDECOM-186 | 35155 | [DEV][RD][Eco][Ecommerce-Shopify] Send Customer Phone Number to Shopify in Two Formats | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 30/Nov/25 3:02 PM | 11/Dec/25 9:19 AM |  | 2 |  |  |  |  | 28800 |  |  |  | [Dev][RD][Ecom] Sprint 13
Story | DEVRDECOM-185 | 35154 | [DEV][RD][Eco][Rewards-Member] Contact us ¦ Business Policy ¦ Privacy Policy link in verify email should open at web browser | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 30/Nov/25 3:01 PM | 10/Dec/25 11:42 AM | 03/Dec/25 12:00 AM | 2 |  |  |  |  | 14400 |  |  |  | [Dev][RD][Ecom] Sprint 13
Story | RDAPS-297 | 35120 | [DEV][RD][HRS][CRONJOB] Create command to import schedule upload | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 28/Nov/25 5:14 PM | 11/Dec/25 10:44 AM | 09/Dec/25 12:00 AM | 3 | [8 empty] | [Dev][All Project] Sprint 13
Story | RDAPS-296 | 35119 | [DEV][RD][HRS][MEMBER] Enhance member detail pages | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 28/Nov/25 5:12 PM | 10/Dec/25 11:47 AM | 04/Dec/25 12:00 AM | 2 | hr-solution |  |  |  | 14400 |  |  |  | [Dev][All Project] Sprint 13
Story | RDAPS-295 | 35118 | [DEV][RD][HRS][MEMBER] Create export member endpoint | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 28/Nov/25 5:05 PM | 12/Dec/25 10:18 AM |  | 5 |  |  |  |  | 57600 |  |  |  | [Dev][All Project] Sprint 13
Story | RDAPS-294 | 35115 | [DEV][RD][HRS][MEMBER] Enhance employee import file report | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 28/Nov/25 4:50 PM | 12/Dec/25 9:21 AM |  | 3 | [8 empty] | [Dev][All Project] Sprint 13
Story | RDAPS-293 | 35112 | [DEV][RD][HRS][MEMBER] Enhance registerRabbitMemberV2 function support upload error message | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 28/Nov/25 4:45 PM | 11/Dec/25 9:18 AM | 02/Dec/25 12:00 AM | 5 | hr-solution |  |  |  | 43200 |  |  |  | [Dev][All Project] Sprint 13
Story | RDAPS-292 | 35104 | [DEV][RD][HRS][MEMBER] Add schedule upload datatable | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 28/Nov/25 4:12 PM | 11/Dec/25 4:53 PM | 09/Dec/25 12:00 AM | 5 | hr-solution |  |  |  | 57600 |  |  |  | [Dev][All Project] Sprint 13
Story | RDAPS-290 | 35076 | [DEV][RD][HRS][MEMBER] Create import member with scheduled type | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 28/Nov/25 2:05 PM | 10/Dec/25 10:14 AM |  | 5 | hr-solution |  |  |  | 57600 |  |  |  | [Dev][All Project] Sprint 13
Story | RDAPS-289 | 35075 | [DEV][RD][HRS][MEMBER] Enhance import member page - instant | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 28/Nov/25 1:33 PM | 10/Dec/25 10:14 AM | 03/Dec/25 12:00 AM | 5 | hr-solution |  |  |  | 57600 |  |  |  | [Dev][All Project] Sprint 13
Story | RDAPS-288 | 35074 | [DEV][RD][HRS] Create migration | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 28/Nov/25 1:31 PM | 11/Dec/25 4:23 PM | 02/Dec/25 12:00 AM | 1 | hr-solution | No-QA |  |  | 7200 |  |  |  | [Dev][All Project] Sprint 13
Story | RDAPS-287 | 35069 | [Dev][RD][HRS][MEMBER] Enhance Member Index | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 28/Nov/25 11:22 AM | 10/Dec/25 11:46 AM | 04/Dec/25 12:00 AM | 2 | hr-solution |  |  |  | 14400 |  |  |  | [Dev][All Project] Sprint 13
Bug | RDAPS-285 | 35009 | [S4][HRS][Company setting][Club Tier] Tier setting not show after set up club tiers | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Closed |  | 27/Nov/25 5:26 PM | 04/Dec/25 12:05 AM | [7 empty] | มาจาก Sprint 12 | Fixing |  | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 13
Story | DEVRDCT-324 | 35000 | [DEV][RD][IPF] Implement Event API Point issued | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready To Test |  | 27/Nov/25 4:09 PM | 15/Dec/25 10:06 AM | 11/Dec/25 12:00 AM | 8 | rr-issue-point-function |  |  |  | 86400 |  |  |  | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Sub-task | DEVRDSUP-270 | 34994 | [Dev] Re-send missing file in monthly batches. |  |  | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | To Do |  | 27/Nov/25 3:34 PM | 03/Dec/25 8:22 AM | [10 empty] | [Dev][All Project] Sprint 13
Story | DEVRDSUP-269 | 34992 | [DEVRDSUP-236] Catch-up resend missing BSS_SSO_ADD_CLICKYES in a monthly batch for KYC report from 27 Aug - 24 Nov 2025 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | To Do |  | 27/Nov/25 3:22 PM | 03/Dec/25 8:40 AM |  |  | etl | [7 empty] | [Dev][All Project] Sprint 13
Story | DEVRDCT-323 | 34991 | [DEV][RD][ECS] Collect and Structure Data for Event ORDER_SUCCESS Payload | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready To Test |  | 27/Nov/25 3:14 PM | 15/Dec/25 10:06 AM | 08/Dec/25 12:00 AM | 8 | ecommerce-shopify-api |  |  |  | 86400 |  |  |  | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Story | DEVRDCT-322 | 34990 | [DEV][RD][ECS] Collect and Structure Data for Event REFUND Payload | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready To Test |  | 27/Nov/25 3:13 PM | 15/Dec/25 10:06 AM | 08/Dec/25 12:00 AM | 3 | ecommerce-shopify-api |  |  |  | 28800 |  |  |  | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Story | DEVRDCT-321 | 34989 | [DEV][RD][ECS] Collect and Structure Data for PAYMENT_PAID Event Payload | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready To Test |  | 27/Nov/25 3:12 PM | 15/Dec/25 10:06 AM | 08/Dec/25 12:00 AM | 3 | ecommerce-shopify-api |  |  |  | 28800 |  |  |  | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Story | DEVRDCT-320 | 34988 | [DEV][RD][ECS] Collect and Structure Data for "Charged" Event Payload | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready To Test |  | 27/Nov/25 3:11 PM | 15/Dec/25 10:06 AM | 04/Dec/25 12:00 AM | 5 | ecommerce-shopify-api |  |  |  | 57600 |  |  |  | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Story | DEVRDCT-319 | 34987 | [DEV][RD][ECS] Create Centralized Function for Publishes to RabbitMQ | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready To Test |  | 27/Nov/25 3:04 PM | 15/Dec/25 10:06 AM | 03/Dec/25 12:00 AM | 3 | ecommerce-shopify-api | No-QA |  |  | 28800 |  |  |  | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Story | DEVRDCT-318 | 34986 | [DEV][RD][ECS] Add internal_name Field to shopify_shops Table and Set Default Values | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready To Test |  | 27/Nov/25 3:02 PM | 15/Dec/25 10:06 AM | 01/Dec/25 12:00 AM | 1 | ecommerce-shopify-api | No-QA |  |  | 0 |  |  |  | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Bug | RDTHANA-414 | 34982 | [S3][PROD][HRS][Welcome message][Pop up setting] Website tab setting cannot save setting changes | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | High | Resolved |  | 27/Nov/25 1:54 PM | 03/Dec/25 9:58 AM | [7 empty] | มาจาก Sprint 12 | Fixing |  | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13
Story | RDTHANA-412 | 34795 | [DEV][RD][APH] Enhance sorry page remove callback condition | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 24/Nov/25 10:39 AM | 03/Dec/25 5:37 PM | 08/Oct/25 12:00 AM | 3 | rr-aphrodite |  |  |  | 7200 |  |  |  | [Dev][RD][Thana] Sprint 13
Sub-task | DEVRDCT-314 | 34763 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 24/Nov/25 10:09 AM | 02/Dec/25 3:15 PM | [7 empty] | มาจาก Sprint 12 | To Do |  | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13
Sub-task | DEVRDCT-313 | 34761 | [QA] Create test case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 24/Nov/25 10:09 AM | 02/Dec/25 3:15 PM | [7 empty] | มาจาก Sprint 12 | In Progress |  | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13
Sub-task | DEVRDCT-312 | 34759 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 24/Nov/25 10:08 AM | 02/Dec/25 3:48 PM | [7 empty] | มาจาก Sprint 12 | To Do |  | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13
Sub-task | DEVRDCT-311 | 34757 | [QA] Create test case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 24/Nov/25 10:08 AM | 02/Dec/25 3:48 PM | [7 empty] | มาจาก Sprint 12 | In Progress |  | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13
Bug | DEVRDECOM-181 | 34638 | [S3][eCommerce Shopify] Order is not created on Shopify DB | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Fixing |  | 21/Nov/25 10:54 AM | 01/Dec/25 9:37 AM | [7 empty] | มาจาก Sprint 12 | Fixing |  | [Dev][RD][Ecom] Sprint 12 | [Dev][RD][Ecom] Sprint 13
Sub-task | DEVRDECOM-180 | 34589 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 20/Nov/25 10:11 AM | 28/Nov/25 11:33 AM | [7 empty] | มาจาก Sprint 12 | Done |  | [Dev][RD][Ecom] Sprint 12 | [Dev][RD][Ecom] Sprint 13
Sub-task | DEVRDECOM-179 | 34587 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 20/Nov/25 10:11 AM | 21/Nov/25 4:28 PM | [7 empty] | มาจาก Sprint 12 | Done |  | [Dev][RD][Ecom] Sprint 12 | [Dev][RD][Ecom] Sprint 13
Story | DEVRDCT-310 | 34585 | [DEV][RD][HRS] Add bound_at and unboard_at Fields for CLUB_BINDING event | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 20/Nov/25 9:15 AM | 02/Dec/25 3:15 PM |  | 3 | hr-solution |  |  |  | 0 | มาจาก Sprint 12 | Ready To Test | 57600 | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13
Story | DEVRDECOM-178 | 34584 | [DEV][RD][Eco][Setup] Setup new store : Pando Production | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | High | Done |  | 20/Nov/25 8:40 AM | 04/Dec/25 5:19 PM |  | 2 |  |  |  |  | 7200 | มาจาก Sprint 12 | In Progress | 14400 -> 7,200 | [Dev][RD][Ecom] Sprint 12 | [Dev][RD][Ecom] Sprint 13
Epic | DEVRDCT-309 | 34545 | ct-member-tier |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 19/Nov/25 2:49 PM | 15/Dec/25 10:06 AM | [7 empty] | มาจาก Sprint 12 | To Do |  | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Epic | DEVRDCT-308 | 34539 | ct-campaign-type |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 19/Nov/25 10:41 AM | 15/Dec/25 10:06 AM |  |  | redemption-api |  |  |  |  | มาจาก Sprint 12 | To Do |  | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Story | DEVRDSUP-252 | 34528 | [SUP-312][SUB] Skipped Receipt GR Offline (Ticket 6 Nov) | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | To Do |  | 18/Nov/25 3:37 PM | 11/Dec/25 10:12 AM | 26/Dec/25 12:00 AM | 8 | [8 empty] | [Dev][All Project] Sprint 13
Story | RDTHANA-393 | 34499 | [DEV][RD][APH] Enhance record "source" when save participant | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready to Staging |  | 18/Nov/25 9:20 AM | 03/Dec/25 9:58 AM | 19/Nov/25 12:00 AM | 3 |  |  |  |  | 0 | มาจาก Sprint 12 | Ready to Staging | 28800 | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13
Story | RDAPS-281 | 34452 | [Dev][RD][BOF] Optimize query performance for Subscription Transaction Report | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Highest | Done |  | 17/Nov/25 4:10 PM | 11/Dec/25 4:49 PM |  | 8 | rr-backoffice |  |  |  | 0 | มาจาก Sprint 12 | Ready To Test | 108000 | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 13
Story | DEVRDECOM-176 | 34440 | [DEV][RD][Eco][Shopify-Extension] Hide logout button at checkout page | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 17/Nov/25 2:00 PM | 04/Dec/25 5:19 PM |  | 5 |  |  |  |  | 43200 |  |  |  | [Dev][RD][Ecom] Sprint 13
Story | DEVRDECOM-173 | 34379 | [DEV][RD][Eco][security/risk] Check list | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Progress |  | 16/Nov/25 5:08 PM | 08/Dec/25 11:29 AM |  | 3 | No-QA |  |  |  | 14400 | มาจาก Sprint 12 | In Progress | 28800 -> 14400 | [Dev][RD][Ecom] Sprint 12 | [Dev][RD][Ecom] Sprint 13
Story | DEVRDECOM-172 | 34378 | [DEV][RD][Eco][ETL] Import missing txn to datamart | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Progress |  | 16/Nov/25 5:03 PM | 02/Dec/25 10:43 AM |  | 3 | [5 empty] | มาจาก Sprint 12 | In Progress |  | [Dev][RD][Ecom] Sprint 12 | [Dev][RD][Ecom] Sprint 13
Story | DEVRDECOM-171 | 34377 | [DEV][RD][Eco][POC][BU][Eco][POC] Turtle delivery : Send auto email by inventory | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 16/Nov/25 5:03 PM | 12/Dec/25 9:37 AM |  | 3 | No-QA |  |  |  | 14400 | มาจาก Sprint 12 | In Progress | 28800 -> 14400 | [Dev][RD][Ecom] Sprint 12 | [Dev][RD][Ecom] Sprint 13
Story | RDTHANA-388 | 34375 | [DEV][RD][BOF][Deeplink] Enhance deeplink datatable support survey | Art: Narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 16/Nov/25 1:59 PM | 11/Dec/25 4:34 PM |  | 3 | [5 empty] | มาจาก Sprint 12 | Ready To Test |  | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13
Story | RDTHANA-387 | 34374 | [DEV][RD][BOF] Survey Observer for create deeplink | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 16/Nov/25 1:48 PM | 11/Dec/25 4:34 PM |  | 2 |  |  |  |  | 0 | มาจาก Sprint 12 | Ready To Test | 14400 | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13
Story | RDTHANA-386 | 34373 | [DEV][RD][LNF] Clarify flow and add database connection | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 16/Nov/25 1:44 PM | 11/Dec/25 4:34 PM | 24/Nov/25 12:00 AM | 5 | link-notify | No-QA |  |  | 0 | มาจาก Sprint 12 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13
Story | RDAPS-279 | 34372 | [DEV][RD][SA] Compare duplicate SSO ID in RLP and RR Line Account | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 16/Nov/25 1:23 PM | 08/Dec/25 10:33 AM | [6 empty] | 3600 | มาจาก Sprint 12 | In Progress | 7200 -> 3600 | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 13
Story | RDAPS-278 | 34371 | [DEV][RD][SA] Clear duplicate BU Allocation | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 16/Nov/25 1:22 PM | 08/Dec/25 10:33 AM | [6 empty] | 3600 | มาจาก Sprint 12 | In Progress | 7200 -> 3600 | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 13
Improvement | DEVRDSUP-242 | 34266 | [DEVRDSUP-93][REM] POC - solution finding on how to sync reward stock count to algolia tp prevent stock missmatch | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | In Progress |  | 14/Nov/25 2:01 PM | 09/Dec/25 10:08 AM | 12/Dec/25 12:00 AM |  | rem | [7 empty] | [Dev][All Project] Sprint 13
Story | DEVRDCT-306 | 34255 | [DEV][RD][HRS] User Property Update after Downgrade Turtle Plus Member Tier | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | High | Done |  | 14/Nov/25 9:26 AM | 03/Dec/25 10:24 AM |  | 8 | hr-solution |  |  |  | 0 | มาจาก Sprint 12 | Ready To Test | 144000 | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13
Story | DEVRDCT-305 | 34254 | [DEV][RD][RDS][ENH] Enhance "Redeem" Event to have a "Campaign Type" | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready To Test |  | 14/Nov/25 8:09 AM | 15/Dec/25 10:06 AM | 19/Nov/25 12:00 AM | 2 | redemption-api |  |  |  | 0 | มาจาก Sprint 12 | Ready to Staging | 14400 | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Story | RDTHANA-383 | 34199 | [DEV][RD][LNF] Add new path to deeplink auto generate flow for survey | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 13/Nov/25 1:11 PM | 11/Dec/25 4:34 PM | 26/Nov/25 12:00 AM | 5 |  |  |  |  | 0 | มาจาก Sprint 12 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13
Story | RDAPS-275 | 34192 | [Dev][RD][DB] Create SQL script to stamp default expiry_type field for existing data | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 13/Nov/25 11:36 AM | 08/Dec/25 1:55 PM | 19/Nov/25 12:00 AM | 1 | rewards-db |  |  |  | 0 | มาจาก Sprint 12 | Ready to Staging | 7200 | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 13
Story | DEVRDECOM-170 | 34188 | [Dev][RD][BOF] Enhance widget setting for service-type items | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 13/Nov/25 10:54 AM | 03/Dec/25 4:57 PM | 21/Nov/25 12:00 AM | 2 | rr-backoffice |  |  |  | 0 | มาจาก Sprint 12 | Ready to Staging | 14400 | [Dev][RD][Ecom] Sprint 12 | [Dev][RD][Ecom] Sprint 13
Story | RDAPS-271 | 34185 | [DEV][RD][HRS] Enhance import member validation | Art: Narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 13/Nov/25 9:55 AM | 03/Dec/25 10:36 AM |  | 3 | hr-solution |  |  |  |  | มาจาก Sprint 12 | Ready to Staging |  | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 13
Bug | RDAPS-269 | 34036 | [DEV][RD][Cron-job][Merchant Ranking] Enhance get merchant with active store only | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Pass : Waiting for deployment |  | 11/Nov/25 1:09 PM | 02/Dec/25 10:03 AM |  | 2 | No-QA |  |  |  |  | มาจาก Sprint 12 | Pass : Waiting for deployment |  | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 13
Story | RDAPS-266 | 33791 | [Dev][RD][Order] Improve process to sync transaction to DA | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 07/Nov/25 3:13 PM | 10/Dec/25 5:26 PM | 20/Nov/25 12:00 AM | 3 | order-consumer |  |  |  | 0 | มาจาก Sprint 12 | Ready To Test | 28800 | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 13
Sub-task | DEVRDCT-298 | 33724 | [QA] (Staging) Test execution Line Pay Unbound Event | Lucas - Saksorn Srisak | 712020:289e7d91-50e6-438c-9b32-23b14017a585 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 06/Nov/25 5:54 PM | 08/Dec/25 10:08 AM | [7 empty] | มาจาก Sprint 12 | To Do |  | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13
Sub-task | DEVRDCT-297 | 33722 | [QA] Create test case Line Pay Unbound Event | Lucas - Saksorn Srisak | 712020:289e7d91-50e6-438c-9b32-23b14017a585 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 06/Nov/25 5:54 PM | 08/Dec/25 10:08 AM | [7 empty] | มาจาก Sprint 12 | To Do |  | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13
Bug | RDTHANA-377 | 33695 | [S4][Survey][Step 2] Club Status(Active/Inavtive) NOT update after change from HR-solution | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Resolved |  | 06/Nov/25 1:54 PM | 03/Dec/25 9:58 AM | [7 empty] | มาจาก Sprint 12 | Resolved |  | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13
Bug | DEVRDSUP-221 | 33625 | [SUP-281][RR-Backoffice] Reward Coupon Transaction Report found error after search | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Fixing |  | 05/Nov/25 1:30 PM | 12/Dec/25 11:59 AM | 01/Dec/25 12:00 AM | 8 | mid-sprint | prod-issue | rem |  |  | มาจาก Sprint 12 | UNDER VALIDATION |  | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 13
Story | RDAPS-261 | 33609 | [Dev][RD][RRS] Add additional data to msg payload for Package Confirmation Email | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Nov/25 11:19 AM | 02/Dec/25 11:38 AM |  |  | rr-scheduler |  |  |  |  | มาจาก Sprint 12 | Ready To Test |  | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 13
Sub-task | DEVRDCT-289 | 33481 | [QA](Staging) Test execution LINE_PAY_BINDING Event push to CT (WEB) | Lucas - Saksorn Srisak | 712020:289e7d91-50e6-438c-9b32-23b14017a585 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 04/Nov/25 6:01 PM | 08/Dec/25 10:07 AM | [7 empty] | มาจาก Sprint 12 | To Do |  | [Dev][CT] Sprint 9 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13
Sub-task | DEVRDCT-288 | 33479 | [QA] Create test case LINE_PAY_BINDING Event push to CT (WEB) | Lucas - Saksorn Srisak | 712020:289e7d91-50e6-438c-9b32-23b14017a585 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 04/Nov/25 6:00 PM | 08/Dec/25 10:07 AM | [7 empty] | มาจาก Sprint 12 | To Do |  | [Dev][CT] Sprint 9 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13
Sub-task | DEVRDCT-287 | 33477 | [QA](Staging) Test execution LINE_PAY_BINDING Event push to CT (API) | Lucas - Saksorn Srisak | 712020:289e7d91-50e6-438c-9b32-23b14017a585 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 04/Nov/25 5:59 PM | 08/Dec/25 10:07 AM | [7 empty] | มาจาก Sprint 12 | To Do |  | [Dev][CT] Sprint 9 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13
Sub-task | DEVRDCT-286 | 33475 | [QA] Create test case LINE_PAY_BINDING Event push to CT (API) | Lucas - Saksorn Srisak | 712020:289e7d91-50e6-438c-9b32-23b14017a585 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 04/Nov/25 5:59 PM | 08/Dec/25 10:07 AM | [7 empty] | มาจาก Sprint 12 | To Do |  | [Dev][CT] Sprint 9 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13
Sub-task | DEVRDCT-285 | 33473 | [QA](Staging) Line OA and Friend event to CleverTap(API) | Lucas - Saksorn Srisak | 712020:289e7d91-50e6-438c-9b32-23b14017a585 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 04/Nov/25 5:49 PM | 02/Dec/25 4:42 PM | [7 empty] | มาจาก Sprint 12 | To Do |  | [Dev][CT] Sprint 9 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13
Sub-task | DEVRDCT-283 | 33465 | [QA](Staging) Line OA and Friend event to CleverTap(WEB) | Lucas - Saksorn Srisak | 712020:289e7d91-50e6-438c-9b32-23b14017a585 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 04/Nov/25 5:46 PM | 08/Dec/25 10:07 AM | [7 empty] | มาจาก Sprint 12 | To Do |  | [Dev][CT] Sprint 9 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13
Story | DEVRDECOM-151 | 33383 | [DEV][RD][Eco] Change image demo in create/edit service page | Art: Narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 04/Nov/25 9:48 AM | 01/Dec/25 9:44 AM | 04/Nov/25 12:00 AM | 1 |  |  |  |  | 0 | มาจาก Sprint 12 | Ready To Test | 3600 | [Dev][RD][Ecom] Sprint 11 | [Dev][RD][Ecom] Sprint 12 | [Dev][RD][Ecom] Sprint 13
Story | RDAPS-256 | 33341 | [Dev][RD][CID] Implement CLI to remove double binding account records | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Blocked |  | 02/Nov/25 4:37 PM | 07/Dec/25 2:34 PM |  | 5 | rr-cloudid-api |  |  |  | 0 | มาจาก Sprint 12 | Ready to Staging | 115200 | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 13
Story | RDAPS-255 | 33340 | [Dev][RD][CID] Add log to Binding API to investigate double binding cases | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Nov/25 4:28 PM | 02/Dec/25 11:38 AM | 06/Nov/25 12:00 AM | 3 | rr-cloudid-api |  |  |  | 0 | มาจาก Sprint 12 | Ready To Test | 21600 | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 13
Story | DEVRDECOM-145 | 33275 | [DEV][RD[Eco][Turtle][POC] Dynamic Section by Customer Location | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Low | Done |  | 31/Oct/25 12:47 PM | 12/Dec/25 9:37 AM |  | 5 | No-QA |  |  |  |  | มาจาก Sprint 12 | In Progress |  | [Dev][RD][Ecom] Sprint 10 | [Dev][RD][Ecom] Sprint 11 | [Dev][RD][Ecom] Sprint 12 | [Dev][RD][Ecom] Sprint 13
Story | RDAPS-247 | 33250 | [Dev][RD][RRS] Optimize import coupons | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Done |  | 30/Oct/25 2:22 PM | 11/Dec/25 4:52 PM |  | 8 | rr-scheduler |  |  |  | 0 | มาจาก Sprint 12 | Ready To Test | 86400 | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 13
Story | RDTHANA-353 | 33197 | [Dev][RD][Survey Web] Remove Survey web from SEO | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 28/Oct/25 1:53 PM | 03/Dec/25 9:58 AM |  | 2 | rr-aphrodite |  |  |  |  | มาจาก Sprint 12 | Ready To Test |  | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13
Story | RDAPS-238 | 32907 | [Dev][RD] Create script to mark vouchers as used for Cloud ID cases (issued on 16 Oct) | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Blocked |  | 21/Oct/25 2:10 PM | 02/Dec/25 10:03 AM |  | 5 | rr-scheduler |  |  |  |  | มาจาก Sprint 12 | Blocked |  | [Dev][All Project] Sprint 10 | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 13
Story | DEVRDCT-269 | 32785 | [DEV][RD][RLP][API] Line Pay Unbound Event | Art: Narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 20/Oct/25 9:30 AM | 11/Dec/25 3:14 PM | 21/Oct/25 12:00 AM | 3 |  |  |  |  | 0 | มาจาก Sprint 12 | Ready To Test | 28800 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13
Story | RDAPS-233 | 32777 | [Dev][RD][RRS] Enhance Redemption ETL to add fields 'USING_AT' and 'COUNTDOWN_EXPIRED_AT' | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Blocked |  | 19/Oct/25 3:24 PM | 02/Dec/25 10:03 AM | 21/Oct/25 12:00 AM | 2 | rr-scheduler |  |  |  | 0 | มาจาก Sprint 12 | Blocked | 14400 | [Dev][All Project] Sprint 10 | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 13
Story | DEVRDCT-258 | 32213 | [DEV][RD][RLP][WEP] LINE_PAY_BINDING Event push to CT | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 13/Oct/25 5:00 PM | 04/Dec/25 11:49 AM |  | 2 | No-QA |  |  |  | 0 | มาจาก Sprint 12 | Ready To Test | 10800 | [Dev][CT] Sprint 9 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13
Story | DEVRDCT-257 | 32071 | [DEV][RD][RLP][API] LINE_PAY_BINDING Event push to CT | Art: Narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 07/Oct/25 3:13 PM | 11/Dec/25 3:14 PM |  | 5 | [5 empty] | มาจาก Sprint 12 | Ready To Test |  | [Dev][CT] Sprint 9 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13
Sub-task | DEVRDCT-253 | 32062 | [QA] Create test case Line OA and Friend event to CleverTap (API) | Lucas - Saksorn Srisak | 712020:289e7d91-50e6-438c-9b32-23b14017a585 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 07/Oct/25 2:09 PM | 02/Dec/25 4:42 PM | [7 empty] | มาจาก Sprint 12 | To Do |  | [Dev][CT] Sprint 9 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13
Sub-task | DEVRDCT-252 | 32060 | [QA] Create test case Line OA and Friend event to CleverTap(WEB) | Lucas - Saksorn Srisak | 712020:289e7d91-50e6-438c-9b32-23b14017a585 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 07/Oct/25 2:04 PM | 08/Dec/25 10:07 AM | [7 empty] | มาจาก Sprint 12 | To Do |  | [Dev][CT] Sprint 9 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13
Sub-task | DEVRDCT-251 | 32058 | [QA](PROD) Test execution sync initial RLP member to RR Line member | Lucas - Saksorn Srisak | 712020:289e7d91-50e6-438c-9b32-23b14017a585 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 07/Oct/25 2:03 PM | 11/Dec/25 4:17 PM | [7 empty] | มาจาก Sprint 12 | Done |  | [Dev][CT] Sprint 9 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13
Story | DEVRDCT-250 | 32004 | [DEV][RD][RLP] Create script to sync initial RLP member to RR Line member | Art: Narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 06/Oct/25 10:03 AM | 11/Dec/25 4:17 PM | 10/Oct/25 12:00 AM | 5 | rlp-middleware |  |  |  | 0 | มาจาก Sprint 12 | Ready To Test | 57600 | [Dev][CT] Sprint 9 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13
Story | DEVRDCT-249 | 31984 | [DEV][RD][RLP][WEB] Sent Line OA and Friend event to CleverTap | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 05/Oct/25 4:45 PM | 04/Dec/25 11:49 AM |  | 3 | No-QA |  |  |  | 0 | มาจาก Sprint 12 | Ready To Test | 10800 | [Dev][CT] Sprint 9 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13
Story | DEVRDCT-248 | 31983 | [DEV][RD][RLP][API] Sent Line OA and Friend event to CleverTap | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 05/Oct/25 4:45 PM | 02/Dec/25 4:41 PM |  | 3 | No-QA | rlp-middleware |  |  | 0 | มาจาก Sprint 12 | Ready To Test | 10800 | [Dev][CT] Sprint 9 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13
Bug | DEVRDCT-241 | 31866 | [S3][CT][Webhook][Club Binding Event] Opt-in type club binding status event not show correctly on CT through Webhook API | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Open |  | 30/Sep/25 3:31 PM | 15/Dec/25 10:06 AM | [7 empty] | มาจาก Sprint 12 | Open |  | [Dev][CT] Sprint 9 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12 | [Dev][RD][CT] Sprint 13 | [Dev][RD][CT] Sprint 14
Story | RDTHANA-289 | 31700 | [DEV][RD][BOF][CR] Enhance survey ranking question | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 26/Sep/25 2:02 PM | 03/Dec/25 9:58 AM | 30/Sep/25 12:00 AM | 3 |  |  |  |  | 0 | มาจาก Sprint 12 | Ready To Test | 21600 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13
Epic | DEVRDECOM-107 | 31506 | Shopify Webhook |  |  | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | To Do |  | 23/Sep/25 9:52 AM | 01/Dec/25 9:37 AM | [7 empty] | มาจาก Sprint 12 | To Do |  | [Dev][RD][Ecom] Sprint 8 | [Dev][RD][Ecom] Sprint 9 | [Dev][RD][Ecom] Sprint 10 | [Dev][RD][Ecom] Sprint 11 | [Dev][RD][Ecom] Sprint 12 | [Dev][RD][Ecom] Sprint 13
Story | RDTHANA-244 | 31447 | [DEV][RD][APH] Enhance sorry page support dynamic error message and CTA button | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 22/Sep/25 11:36 AM | 03/Dec/25 9:58 AM | 29/Sep/25 12:00 AM | 1 | [5 empty] | มาจาก Sprint 12 | Ready To Test |  | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13
Story | RDTHANA-241 | 31432 | [DEV][RD][APH] Enhance survey html render support survey appearance "Thank you" tab | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 21/Sep/25 9:13 PM | 03/Dec/25 9:58 AM | 29/Sep/25 12:00 AM | 3 |  |  |  |  | 0 | มาจาก Sprint 12 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13
Story | RDTHANA-238 | 31429 | [DEV][RD][APH] Create survey theme | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Highest | Ready To Test |  | 21/Sep/25 8:49 PM | 03/Dec/25 9:58 AM | 23/Sep/25 12:00 AM | 3 | rr-aphrodite |  |  |  | 0 | มาจาก Sprint 12 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13
Story | RDTHANA-231 | 31359 | [DEV][RD][APH] Enhance survey html render support survey appearance "General" tab | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 19/Sep/25 10:43 AM | 03/Dec/25 9:58 AM | 26/Sep/25 12:00 AM | 5 |  |  |  |  | 0 | มาจาก Sprint 12 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13
Story | RDTHANA-230 | 31358 | [DEV][RD][APH] Enhance getMemberToken support sources session | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 19/Sep/25 10:42 AM | 03/Dec/25 9:58 AM | 26/Sep/25 12:00 AM | 2 |  |  |  |  | 0 | มาจาก Sprint 12 | Ready To Test | 7200 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13
Sub-task | RDTHANA-118 | 30812 | [QA] Create Test Case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 09/Sep/25 11:23 AM | 09/Sep/25 11:23 AM | [7 empty] | มาจาก Sprint 12 | To Do |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13
Story | RDTHANA-106 | 30689 | [Dev][RD][Service][CMS API] Create service filter api | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 04/Sep/25 4:08 PM | 03/Dec/25 9:58 AM | 11/Sep/25 12:00 AM | 3 | cms-api | No-QA |  |  | 0 | มาจาก Sprint 12 | Ready To Test | 18000 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13
Story | RDTHANA-90 | 30622 | [Dev][RD][Section][BOF][QA] Enhance Section Feature: Add new widget types | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Sep/25 9:16 PM | 03/Dec/25 9:58 AM |  | 0 | [5 empty] | มาจาก Sprint 12 | Ready To Test |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13
Story | RDAPS-160 | 29972 | [DEV][RD][SSO-Backoffice] Disable SEO tracking | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 20/Aug/25 11:21 AM | 02/Dec/25 10:03 AM | 04/Sep/25 12:00 AM | 1 |  |  |  |  | 0 | มาจาก Sprint 12 | Ready To Test | 7200 | [Dev][All project]Sprint 6 | [Dev][All project]Sprint 7 | [Dev][All Project] Sprint 9 | [Dev][All Project] Sprint 10 | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12 | [Dev][All Project] Sprint 13
Story | RDTHANA-20 | 29950 | [Dev][RD][APH] Enhance check token | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 19/Aug/25 7:46 PM | 03/Dec/25 9:58 AM |  | 3 |  |  |  |  | 0 | มาจาก Sprint 12 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12 | [Dev][RD][Thana] Sprint 13

## Summarize Sprint 12
Column 1 | Total Stories Point | Total Manhour | Point Done | Manhour Done | Note
17 Nov - 28 Nov
Dev Resource Available | 19 | 591.5
Meeting Planned |  | 187 |  |  | Ref
Additional Meeting |  | 15.5 |  |  | Ref
Deployment |  | 11 |  |  | 3 ครั้ง 1. 4 คน 2. 3 คน 3. 4 คน
Development Sprint Total | 424 | 380.5 | 239 | 169.5
Ad-hoc Mid Sprint | 6 | 1 | 7 | 0.5 | 2 tasks
Requirement changes after refinement? | 0 | 0 | 0 | 0 | 0 tasks
Aek | 31 | 38.5 | 10 | 18.5
A | 45 | 74 | 39 | 66
Aom | 54 | 21 | 14 | 21
Zan | 10 | 5 | 5 | 0
Mai | 54 | 42 | 22 | 0
Mac | 69 | 32 | 53 | 12
Mos | 42 | 36 | 39 | 20
Jack | 16 | 0 | 10 | 0
Art | 21 | 0 | 1 | 0
Kae | 25 | 56 | 20 | 24
Nim | 33 | 40 | 20 | 0
Arm | 24 | 36 | 6 | 8
| System Architech |  |  |  | Permanent Dev. |  |  | Outsources
Projects (Stories Points) | Aek | Zan | Aom | Jack | A | Art | Mai | Kae | Mac | Nim | Mos | Arm
Das Haus - Thana City & Das Haus | 0 | 5 | 9 | 8 | 15 | 3 | 38 | 8 | 46 | 16 | 29 | 2
E-commerce 1.1. E-Commerce x Shopify Plus 1.2. Shopify:Snackmaker 1.3. Shopify: Turtle Delivery 1.4. Shopify: Turtle Delivery | 21 | 0 | 0 | 8 | 0 | 1 | 2 | 0 | 0 | 0 | 10 | 3
CleverTap - MKT Automation Tool | 8 | 0 | 0 | 0 | 0 | 13 | 0 | 3 | 6 | 3 | 3 | 8
Adjust Integration | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 3 | 0 | 4 | 0 | 3
Adhoc - Non-Epics - Turtle Display club tier on POS - Data Mart Migration | 0 | 2 | 17 | 0 | 5 | 3 | 3 | 11 | 12 | 0 | 0 | 8
Support Incidents | 2 | 3 | 28 | 0 | 0 | 0 | 8 | 0 | 5 | 0 | 0 | 0
| System Architech |  |  |  | Permanent Dev. |  |  | Outsources
Projects (Manhour) | Aek | Zan | Aom | Jack | A | Art | Mai | Kae | Mac | Nim | Mos | Arm
Das Haus - Thana City & Das Haus | 0 | 0 | 20 | 0 | 8 | 0 | 32 | 0 | 0 | 0 | 0 | 4
E-commerce 1.1. E-Commerce x Shopify Plus 1.2. Shopify:Snackmaker 1.3. Shopify: Turtle Delivery 1.4. Shopify: Turtle Delivery | 37 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 20 | 8
CleverTap - MKT Automation Tool | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 40 | 16 | 0
Adjust Integration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Adhoc - Non-Epics - Turtle Display club tier on POS - Data Mart Migration | 0 | 4 | 0.5 | 0 | 8 | 0 | 6 | 56 | 28 | 0 | 0 | 24
Support Incidents | 1.5 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 12
Issue Type | Issue key | Issue id | Summary | Assignee | Assignee Id | Reporter | Reporter Id | Priority | Status | Resolution | Created | Updated | Due date | Custom field (Story Points) | Labels | Labels | Labels | Labels | Labels | Original estimate | Sprint Movement | Sprint 11 | Note | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint
Bug | RDAPS-285 | 35009 | [S4][HRS][Company setting][Club Tier] Tier setting not show after set up club tiers | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Fixing |  | 27/Nov/25 5:26 PM | 28/Nov/25 4:26 PM | [11 empty] | [Dev][All Project] Sprint 12
Bug | RDTHANA-414 | 34982 | [S3][PROD][HRS][Welcome message][Pop up setting] Website tab setting cannot save setting changes | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | High | Fixing |  | 27/Nov/25 1:54 PM | 27/Nov/25 4:52 PM | [11 empty] | [Dev][RD][Thana] Sprint 12
Story | DM-112 | 34977 | [DEV][RD][AWSTH] Extract Redemption Consumer to standalone repo for CodePipeline deployment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 27/Nov/25 9:21 AM | 27/Nov/25 11:19 PM |  | 1 | No-QA |  |  |  |  | 7200 |  |  |  | [Dev][RD][AWS] Sprint 12
Story | DM-111 | 34976 | [DEV][RD][AWSTH] Extract Redemption API to standalone repo for CodePipeline deployment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 27/Nov/25 9:21 AM | 27/Nov/25 11:10 PM |  | 1 | No-QA |  |  |  |  | 7200 |  |  |  | [Dev][RD][AWS] Sprint 12
Story | DM-110 | 34975 | [DEV][RD][AWSTH] Extract Rewards Consumer to standalone repo for CodePipeline deployment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 27/Nov/25 9:21 AM | 27/Nov/25 11:02 PM |  | 1 | No-QA |  |  |  |  | 7200 |  |  |  | [Dev][RD][AWS] Sprint 12
Story | DM-109 | 34974 | [DEV][RD][AWSTH] Extract Rewards API to standalone repo for CodePipeline deployment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 27/Nov/25 9:21 AM | 27/Nov/25 9:57 PM |  | 2 | No-QA |  |  |  |  | 14400 |  |  |  | [Dev][RD][AWS] Sprint 12
Story | DM-108 | 34973 | [DEV][RD][AWSTH] Extract RR Crobjob to standalone repo for CodePipeline deployment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 27/Nov/25 9:20 AM | 27/Nov/25 9:36 PM |  | 2 | No-QA |  |  |  |  | 14400 |  |  |  | [Dev][RD][AWS] Sprint 12
Story | DM-107 | 34972 | [DEV][RD][AWSTH] Extract Rabbit CMS API to standalone repo for CodePipeline deployment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 27/Nov/25 9:18 AM | 27/Nov/25 7:08 PM |  | 2 | No-QA |  |  |  |  | 14400 |  |  |  | [Dev][RD][AWS] Sprint 12
Story | DM-106 | 34971 | [DEV][RD][AWSTH]Extract Notification API to standalone repo for CodePipeline deployment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 27/Nov/25 9:16 AM | 27/Nov/25 6:44 PM |  | 2 | No-QA |  |  |  |  | 14400 |  |  |  | [Dev][RD][AWS] Sprint 12
Story | DM-105 | 34970 | [DEV][RD][AWSTH] Extract Merchant API to standalone repo for CodePipeline deployment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 27/Nov/25 9:15 AM | 27/Nov/25 6:56 PM |  | 2 | No-QA |  |  |  |  | 14400 |  |  |  | [Dev][RD][AWS] Sprint 12
Story | DM-104 | 34969 | [DEV][RD][AWSTH] Extract Exclusive Store API to standalone repo for CodePipeline deployment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 27/Nov/25 9:13 AM | 27/Nov/25 5:38 PM | 28/Nov/25 12:00 AM | 2 | No-QA |  |  |  |  | 14400 |  |  |  | [Dev][RD][AWS] Sprint 12
Story | DM-103 | 34968 | [DEV][RD][AWSTH] Extract Deeplink API to standalone repo for CodePipeline deployment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 27/Nov/25 9:10 AM | 27/Nov/25 4:23 PM | 28/Nov/25 12:00 AM | 2 | No-QA |  |  |  |  | 14400 |  |  |  | [Dev][RD][AWS] Sprint 12
Story | DEVRDSUP-266 | 34919 | [Dev][RD][BOF] Optimize query performance for Coupons TXN Report | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 26/Nov/25 11:05 AM | 26/Nov/25 11:05 AM |  | 13 | [9 empty] | [Dev][All Project] Sprint 12
Bug | RDTHANA-413 | 34832 | [S4][Service][Contact] Phone number validation incorrect for prefixes 02, 06, 08, 09 | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Closed |  | 24/Nov/25 11:56 PM | 26/Nov/25 11:18 AM | [11 empty] | [Dev][RD][Thana] Sprint 12
Bug | DEVRDECOM-184 | 34826 | [S3][eCommerce Shopify] Email is not updated across platform | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 24/Nov/25 5:38 PM | 26/Nov/25 5:06 PM | [11 empty] | [Dev][RD][Ecom] Sprint 12
Bug | DEVRDCT-316 | 34820 | [DEV][RD][PL] Member Binding API incorrectly send SSO status and Partner status to Webhook | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Closed |  | 24/Nov/25 2:51 PM | 26/Nov/25 9:36 AM | [11 empty] | [Dev][RD][CT] Sprint 12
Bug | DEVRDCT-315 | 34819 | [DEV][RD][EXS] Club Binding Flow Prevent Duplicate Webhook Calls with Partner Loyalty API | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Closed |  | 24/Nov/25 2:42 PM | 26/Nov/25 9:36 AM | [11 empty] | [Dev][RD][CT] Sprint 12
Story | DEVRDSUP-264 | 34803 | [SUP-329]SUB : Request to fill in the Secret Key for Eastin | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 24/Nov/25 11:49 AM | 26/Nov/25 10:58 AM | 26/Nov/25 12:00 AM | 1 | mid-sprint | No-QA | sub |  |  | 1800 |  |  |  | [Dev][All Project] Sprint 12
Sub-task | DEVRDECOM-183 | 34797 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 24/Nov/25 11:10 AM | 24/Nov/25 11:24 AM | [11 empty] | [Dev][RD][Ecom] Sprint 12
Test Execution | QA-881 | 34794 | Test Execution API bind/unbind endpoint support line_pay | Lucas - Saksorn Srisak | 712020:289e7d91-50e6-438c-9b32-23b14017a585 | Lucas - Saksorn Srisak | 712020:289e7d91-50e6-438c-9b32-23b14017a585 | Medium | To Do |  | 24/Nov/25 10:37 AM | 24/Nov/25 10:37 AM | [11 empty] | [Dev][All Project] Sprint 12
Test Plan | QA-880 | 34790 | test case API bind/unbind endpoint support line_pay | Lucas - Saksorn Srisak | 712020:289e7d91-50e6-438c-9b32-23b14017a585 | Lucas - Saksorn Srisak | 712020:289e7d91-50e6-438c-9b32-23b14017a585 | Medium | Done | Done | 24/Nov/25 10:33 AM | 27/Nov/25 4:37 PM | [11 empty] | [Dev][All Project] Sprint 12
Sub-task | RDTHANA-411 | 34789 | [QA] Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 24/Nov/25 10:26 AM | 24/Nov/25 10:27 AM | [11 empty] | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Sub-task | RDTHANA-410 | 34787 | [QA] Test Execution Cronjob update survey to expired | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 24/Nov/25 10:24 AM | 24/Nov/25 10:25 AM | [11 empty] | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Sub-task | RDTHANA-409 | 34784 | [QA]Test Execution Change survey status (FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 24/Nov/25 10:20 AM | 24/Nov/25 10:20 AM | [11 empty] | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Sub-task | RDTHANA-408 | 34782 | [QA] Test Execution Update survey Step 5: Survey Appearance (Input E-mail) (FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 24/Nov/25 10:20 AM | 24/Nov/25 10:20 AM | [11 empty] | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Sub-task | RDTHANA-407 | 34780 | [QA] Test Execution Download Individual Survey Report (FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 24/Nov/25 10:18 AM | 24/Nov/25 10:18 AM | [11 empty] | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Sub-task | RDTHANA-406 | 34778 | [QA] Test Execution Update survey step5.1(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 24/Nov/25 10:17 AM | 24/Nov/25 10:18 AM | [11 empty] | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Sub-task | RDTHANA-405 | 34776 | [QA] Test Execution Update survey step4.1(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 24/Nov/25 10:17 AM | 24/Nov/25 10:17 AM | [11 empty] | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Sub-task | RDTHANA-404 | 34774 | [QA] Test Execution Update survey step3(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 24/Nov/25 10:16 AM | 24/Nov/25 10:16 AM | [11 empty] | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Sub-task | RDTHANA-403 | 34771 | [QA] Test Execution Update survey step2(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 24/Nov/25 10:15 AM | 24/Nov/25 10:15 AM | [11 empty] | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Sub-task | RDTHANA-402 | 34769 | [QA] Test Execution View Survey List (FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 24/Nov/25 10:15 AM | 24/Nov/25 10:15 AM | [11 empty] | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Sub-task | RDTHANA-401 | 34767 | [QA] Test Execution Update survey step1(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 24/Nov/25 10:14 AM | 24/Nov/25 10:14 AM | [11 empty] | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Sub-task | RDTHANA-400 | 34765 | [QA] Test Execution Create survey (FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 24/Nov/25 10:13 AM | 24/Nov/25 10:13 AM | [11 empty] | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Sub-task | DEVRDCT-314 | 34763 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | To Do |  | 24/Nov/25 10:09 AM | 24/Nov/25 10:09 AM | [11 empty] | [Dev][RD][CT] Sprint 12
Sub-task | DEVRDCT-313 | 34761 | [QA] Create test case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | In Progress |  | 24/Nov/25 10:09 AM | 25/Nov/25 10:06 AM | [11 empty] | [Dev][RD][CT] Sprint 12
Sub-task | DEVRDCT-312 | 34759 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | To Do |  | 24/Nov/25 10:08 AM | 24/Nov/25 10:08 AM | [11 empty] | [Dev][RD][CT] Sprint 12
Sub-task | DEVRDCT-311 | 34757 | [QA] Create test case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | In Progress |  | 24/Nov/25 10:08 AM | 25/Nov/25 10:06 AM | [11 empty] | [Dev][RD][CT] Sprint 12
Story | RDAPS-283 | 34689 | [Dev][RD][Deployment Preparation][24Nov]Das haus Phase 1 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 23/Nov/25 10:10 AM | 27/Nov/25 5:14 PM |  | 3 | No-QA | [8 empty] | [Dev][RD][Thana] Sprint 12
Story | DEVRDSUP-260 | 34655 | [SUP-326]ลูกค้ามีบัตร Rabbit Wallet ซ้ำกัน 2 บัญชี | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 21/Nov/25 5:56 PM | 24/Nov/25 2:39 PM | 01/Dec/25 12:00 AM | 1 | prod-issue | RabbitWallet |  |  |  | 1800 |  |  |  | [Dev][All Project] Sprint 12
Story | RDAPS-282 | 34646 | [DEV][RD][BFF] Remove check is active in get product detail endpoint | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 21/Nov/25 1:37 PM | 27/Nov/25 10:26 AM | 21/Nov/25 12:00 AM | 1 | [5 empty] | 7200 |  |  |  | [Dev][All Project] Sprint 12
Bug | DEVRDECOM-182 | 34639 | [S3][eCommerce Shopify] Name from address is not updated to account name | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 21/Nov/25 10:55 AM | 27/Nov/25 10:15 AM | [11 empty] | [Dev][RD][Ecom] Sprint 12
Bug | DEVRDECOM-181 | 34638 | [S3][eCommerce Shopify] Order is not created on Shopify DB | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Fixing |  | 21/Nov/25 10:54 AM | 28/Nov/25 11:24 AM | [11 empty] | [Dev][RD][Ecom] Sprint 12
Story | DM-96 | 34628 | [DEV][RD][AWSTH] prepare ENV for dev environment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | High | Done |  | 21/Nov/25 9:55 AM | 26/Nov/25 5:03 PM | 26/Nov/25 12:00 AM | 5 | [5 empty] | 86400 |  |  |  | [Dev][RD][AWS] Sprint 12
Bug | RDTHANA-398 | 34625 | [Dev][RD][BOF][Service] cannot validate phone number format 02-xxxxxxx | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Lucas - Saksorn Srisak | 712020:289e7d91-50e6-438c-9b32-23b14017a585 | Medium | Closed |  | 21/Nov/25 1:06 AM | 24/Nov/25 2:15 PM | [11 empty] | [Dev][RD][Thana] Sprint 12
Bug | RDTHANA-397 | 34623 | [S4][PROD][RR Backoffice][Widget] Index sorting with alphabetical and status order NOT Updated_at | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Closed |  | 21/Nov/25 12:36 AM | 24/Nov/25 2:18 PM | [11 empty] | [Dev][RD][Thana] Sprint 12
Story | DM-95 | 34590 | [DEV][RD][AWSTH][POC] Load env JSON format to environment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | High | Done |  | 20/Nov/25 10:21 AM | 26/Nov/25 5:04 PM |  | 3 | [9 empty] | [Dev][RD][AWS] Sprint 12
Sub-task | DEVRDECOM-180 | 34589 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 20/Nov/25 10:11 AM | 28/Nov/25 11:33 AM | [11 empty] | [Dev][RD][Ecom] Sprint 12
Sub-task | DEVRDECOM-179 | 34587 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 20/Nov/25 10:11 AM | 21/Nov/25 4:28 PM | [11 empty] | [Dev][RD][Ecom] Sprint 12
Story | DEVRDCT-310 | 34585 | [DEV][RD][HRS] Add bound_at and unboard_at Fields for CLUB_BINDING event | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready To Test |  | 20/Nov/25 9:15 AM | 28/Nov/25 9:34 AM |  | 3 | hr-solution |  |  |  |  | 57600 |  |  |  | [Dev][RD][CT] Sprint 12
Story | DEVRDECOM-178 | 34584 | [DEV][RD][Eco][Setup] Setup new store : Pando Production | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | High | In Progress |  | 20/Nov/25 8:40 AM | 29/Nov/25 1:10 PM |  | 2 | [5 empty] | 14400 |  |  |  | [Dev][RD][Ecom] Sprint 12
Story | DEVRDECOM-177 | 34550 | [DEV][RD][Eco][POC] Find solution for send phone from sso to shopify when auto login | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 19/Nov/25 5:32 PM | 29/Nov/25 1:12 PM |  | 2 | No-QA |  |  |  |  | 3600 |  |  |  | [Dev][RD][Ecom] Sprint 12
Epic | DEVRDCT-309 | 34545 | ct-member-tier |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 19/Nov/25 2:49 PM | 19/Nov/25 2:49 PM | [11 empty] | [Dev][RD][CT] Sprint 12
Epic | DEVRDCT-308 | 34539 | ct-campaign-type |  |  | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 19/Nov/25 10:41 AM | 19/Nov/25 10:41 AM |  |  | redemption-api | [8 empty] | [Dev][RD][CT] Sprint 12
Bug | DEVRDCT-307 | 34538 | [DEV][RD][RDS] Incorrect reward "using" time with MEMBER_COUPON event | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Closed |  | 19/Nov/25 10:23 AM | 20/Nov/25 1:25 PM | 19/Nov/25 12:00 AM |  | redemption-api | [8 empty] | [Dev][RD][CT] Sprint 12
Bug | RDTHANA-396 | 34535 | [S3][HR-Solution][Welcome message][Pop up setting] Website tab setting always show alert modal warning to save change before go to another tab | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Closed |  | 18/Nov/25 6:42 PM | 27/Nov/25 2:07 PM | [11 empty] | [Dev][RD][Thana] Sprint 12
Bug | RDTHANA-395 | 34534 | [S3][HR-Solution][Welcome message][Pop up setting] Website tab setting cannot save changes | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Rejected |  | 18/Nov/25 6:36 PM | 19/Nov/25 5:21 PM | [11 empty] | [Dev][RD][Thana] Sprint 12
Bug | RDTHANA-394 | 34533 | [S3][HR-Solution][Welcome message][Pop up setting] Application tab setting Destination URL cannot save full URL | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Closed |  | 18/Nov/25 6:14 PM | 20/Nov/25 11:39 AM | [11 empty] | [Dev][RD][Thana] Sprint 12
Sub-task | DEVRDADJ-70 | 34509 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 18/Nov/25 11:53 AM | 18/Nov/25 2:50 PM | [11 empty] | [Dev][RDAdjust] Sprint 11 | [Dev][RDAdjust] Sprint 12
Sub-task | DEVRDADJ-69 | 34502 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 18/Nov/25 10:09 AM | 18/Nov/25 11:53 AM | [11 empty] | [Dev][RDAdjust] Sprint 11 | [Dev][RDAdjust] Sprint 12
Story | RDTHANA-393 | 34499 | [DEV][RD][APH] Enhance record "source" when save participant | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready to Staging |  | 18/Nov/25 9:20 AM | 19/Nov/25 10:06 AM | 19/Nov/25 12:00 AM | 3 | [5 empty] | 28800 |  |  |  | [Dev][RD][Thana] Sprint 12
Story | RDAPS-281 | 34452 | [Dev][RD][BOF] Optimize query performance for Subscription Transaction Report | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Highest | Ready To Test |  | 17/Nov/25 4:10 PM | 26/Nov/25 4:26 PM |  | 8 | rr-backoffice | [8 empty] | [Dev][All Project] Sprint 12
Bug | RDTHANA-392 | 34445 | [S3][Survey report ] Survey Souce column show nothing on Survey Report | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Closed |  | 17/Nov/25 2:18 PM | 28/Nov/25 1:31 PM | [11 empty] | [Dev][RD][Thana] Sprint 12
Story | RDAPS-280 | 34444 | [Dev][RD][RWS] Enhance api get reward availability | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 17/Nov/25 2:07 PM | 28/Nov/25 3:16 PM |  | 3 | rewards-api |  |  |  |  | 28800 |  |  |  | [Dev][All Project] Sprint 12
Story | DEVRDECOM-175 | 34423 | [DEV][RD][Eco][Setup] Setup new store : Pando UAT | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | High | Done |  | 17/Nov/25 10:51 AM | 29/Nov/25 1:09 PM |  | 3 | [5 empty] | 28800 |  |  |  | [Dev][RD][Ecom] Sprint 12
Story | DEVRDECOM-174 | 34416 | [DEV][RD][Eco][POC] Shopify pay with coin - Checkout UI Extension | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Highest | Done |  | 17/Nov/25 10:33 AM | 29/Nov/25 1:09 PM |  | 3 | No-QA |  |  |  |  | 28800 |  |  |  | [Dev][RD][Ecom] Sprint 12
Story | RDTHANA-390 | 34413 | [Dev][RD][Deployment Preparation][21Nov]Das haus Phase 1 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 17/Nov/25 9:54 AM | 23/Nov/25 10:09 AM |  | 8 | [5 empty] | 72000 |  |  |  | [Dev][RD][Thana] Sprint 12
Story | DEVRDECOM-173 | 34379 | [DEV][RD][Eco][security/risk] Check list | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Progress |  | 16/Nov/25 5:08 PM | 29/Nov/25 1:10 PM |  | 3 | No-QA |  |  |  |  | 28800 |  |  |  | [Dev][RD][Ecom] Sprint 12
Story | DEVRDECOM-172 | 34378 | [DEV][RD][Eco][ETL] Import missing txn to datamart | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Progress |  | 16/Nov/25 5:03 PM | 28/Nov/25 9:48 AM |  | 3 | [9 empty] | [Dev][RD][Ecom] Sprint 12
Story | DEVRDECOM-171 | 34377 | [DEV][RD][Eco][POC][BU][Eco][POC] Turtle delivery : Send auto email by inventory | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Progress |  | 16/Nov/25 5:03 PM | 29/Nov/25 1:11 PM |  | 3 | No-QA |  |  |  |  | 28800 |  |  |  | [Dev][RD][Ecom] Sprint 12
Story | RDTHANA-388 | 34375 | [DEV][RD][BOF][Deeplink] Enhance deeplink datatable support survey | Art: Narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 16/Nov/25 1:59 PM | 27/Nov/25 2:32 PM |  | 3 | [9 empty] | [Dev][RD][Thana] Sprint 12
Story | RDTHANA-387 | 34374 | [DEV][RD][BOF] Survey Observer for create deeplink | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 16/Nov/25 1:48 PM | 27/Nov/25 5:13 PM |  | 2 | [5 empty] | 14400 |  |  |  | [Dev][RD][Thana] Sprint 12
Story | RDTHANA-386 | 34373 | [DEV][RD][LNF] Clarify flow and add database connection | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 16/Nov/25 1:44 PM | 27/Nov/25 2:42 PM | 24/Nov/25 12:00 AM | 5 | [5 empty] | 57600 |  |  |  | [Dev][RD][Thana] Sprint 12
Story | RDAPS-279 | 34372 | [DEV][RD][SA] Compare duplicate SSO ID in RLP and RR Line Account | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Progress |  | 16/Nov/25 1:23 PM | 28/Nov/25 10:23 AM | [7 empty] | 7200 |  |  |  | [Dev][All Project] Sprint 12
Story | RDAPS-278 | 34371 | [DEV][RD][SA] Clear duplicate BU Allocation | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Progress |  | 16/Nov/25 1:22 PM | 28/Nov/25 10:23 AM | [7 empty] | 7200 |  |  |  | [Dev][All Project] Sprint 12
Story | RDTHANA-385 | 34267 | [Dev][RD][CMS] Add return 'icon_shadow_color' and 'has_icon_shadow' to services filter api | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 14/Nov/25 2:05 PM | 26/Nov/25 9:42 AM |  | 1 | [5 empty] | 0 | มาจาก Sprint 11 | Ready To Test | 3600 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | RDTHANA-384 | 34265 | [Dev][RD][BFF] Add return 'icon_shadow_color' and 'has_icon_shadow' to section contents api | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 14/Nov/25 2:00 PM | 28/Nov/25 1:55 PM |  | 1 | [5 empty] | 0 | มาจาก Sprint 11 | Ready To Test | 3600 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | DEVRDCT-306 | 34255 | [DEV][RD][HRS] User Property Update after Downgrade Turtle Plus Member Tier | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | High | Ready To Test |  | 14/Nov/25 9:26 AM | 28/Nov/25 3:14 PM |  | 8 | hr-solution |  |  |  |  | 144000 |  |  |  | [Dev][RD][CT] Sprint 12
Story | DEVRDCT-305 | 34254 | [DEV][RD][RDS][ENH] Enhance "Redeem" Event to have a "Campaign Type" | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready to Staging |  | 14/Nov/25 8:09 AM | 26/Nov/25 9:41 AM | 19/Nov/25 12:00 AM | 2 | redemption-api |  |  |  |  | 14400 |  |  |  | [Dev][RD][CT] Sprint 12
Story | RDTHANA-383 | 34199 | [DEV][RD][LNF] Add new path to deeplink auto generate flow for survey | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 13/Nov/25 1:11 PM | 27/Nov/25 2:42 PM | 26/Nov/25 12:00 AM | 5 | [5 empty] | 57600 |  |  |  | [Dev][RD][Thana] Sprint 12
Story | RDAPS-275 | 34192 | [Dev][RD][DB] Create SQL script to stamp default expiry_type field for existing data | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 13/Nov/25 11:36 AM | 26/Nov/25 10:06 AM | 19/Nov/25 12:00 AM | 1 | rewards-db |  |  |  |  | 7200 |  |  |  | [Dev][All Project] Sprint 12
Story | RDAPS-274 | 34191 | [Dev][RD[DB] Create database migration to add new schema | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 13/Nov/25 11:31 AM | 27/Nov/25 10:11 AM | 19/Nov/25 12:00 AM | 1 | No-QA | rewards-db |  |  |  | 7200 |  |  |  | [Dev][All Project] Sprint 12
Story | RDAPS-273 | 34190 | [Dev][RD][REM] Enhance the rule for calculation for coupon_valid_until_at | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 13/Nov/25 11:17 AM | 28/Nov/25 5:12 PM |  | 3 | redemption-api |  |  |  |  | 57600 |  |  |  | [Dev][All Project] Sprint 12
Story | RDAPS-272 | 34189 | [Dev][RD][BOF] Enhance coupon expiry settings for rewards | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 13/Nov/25 11:14 AM | 28/Nov/25 5:33 PM | 21/Nov/25 12:00 AM | 3 | rr-backoffice |  |  |  |  | 28800 |  |  |  | [Dev][All Project] Sprint 12
Story | DEVRDECOM-170 | 34188 | [Dev][RD][BOF] Enhance widget setting for service-type items | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 13/Nov/25 10:54 AM | 28/Nov/25 1:02 PM | 21/Nov/25 12:00 AM | 2 | rr-backoffice |  |  |  |  | 14400 |  |  |  | [Dev][RD][Ecom] Sprint 12
Story | RDAPS-271 | 34185 | [DEV][RD][HRS] Enhance import member validation | Art: Narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 13/Nov/25 9:55 AM | 27/Nov/25 2:05 PM |  | 3 | hr-solution | [8 empty] | [Dev][All Project] Sprint 12
Sub-task | DEVRDECOM-169 | 34143 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 12/Nov/25 3:44 PM | 26/Nov/25 11:01 AM | [8 empty] | มาจาก Sprint 11 | To Do |  | [Dev][RD][Ecom] Sprint 11 | [Dev][RD][Ecom] Sprint 12
Sub-task | DEVRDECOM-168 | 34141 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 12/Nov/25 3:44 PM | 19/Nov/25 5:22 PM | [8 empty] | มาจาก Sprint 11 | In Progress |  | [Dev][RD][Ecom] Sprint 11 | [Dev][RD][Ecom] Sprint 12
Sub-task | DEVRDECOM-167 | 34139 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 12/Nov/25 3:44 PM | 19/Nov/25 5:22 PM | [8 empty] | มาจาก Sprint 11 | In Review |  | [Dev][RD][Ecom] Sprint 11 | [Dev][RD][Ecom] Sprint 12
Sub-task | DEVRDECOM-166 | 34137 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 12/Nov/25 3:43 PM | 21/Nov/25 4:19 PM | [8 empty] | มาจาก Sprint 11 | To Do |  | [Dev][RD][Ecom] Sprint 11 | [Dev][RD][Ecom] Sprint 12
Sub-task | DEVRDECOM-165 | 34135 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 12/Nov/25 3:43 PM | 17/Nov/25 1:49 PM | [8 empty] | มาจาก Sprint 11 | In Review |  | [Dev][RD][Ecom] Sprint 11 | [Dev][RD][Ecom] Sprint 12
Bug | DEVRDSUP-236 | 34128 | [SUP-298][RDxDA][ETL] Missing BSS_SSO_ADD_CLICKYES file for kyc_report since 26 Aug 2025 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Closed |  | 12/Nov/25 1:45 PM | 27/Nov/25 3:36 PM | 01/Dec/25 12:00 AM |  | etl | prod-issue | [7 empty] | [Dev][All Project] Sprint 12
Bug | RDAPS-269 | 34036 | [DEV][RD][Cron-job][Merchant Ranking] Enhance get merchant with active store only | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Pass : Waiting for deployment |  | 11/Nov/25 1:09 PM | 18/Nov/25 10:02 AM |  | 2 | No-QA | [8 empty] | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12
Sub-task | DEVRDADJ-68 | 34035 | [QA] Test Execution (No-QA) | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 11/Nov/25 11:25 AM | 17/Nov/25 2:46 PM | [8 empty] | มาจาก Sprint 11 | To Do |  | [Dev][RDAdjust] Sprint 11 | [Dev][RDAdjust] Sprint 12
Sub-task | DEVRDADJ-67 | 34033 | [QA] Test Execution (No-QA) | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 11/Nov/25 11:24 AM | 17/Nov/25 2:44 PM | [8 empty] | มาจาก Sprint 11 | To Do |  | [Dev][RDAdjust] Sprint 11 | [Dev][RDAdjust] Sprint 12
Sub-task | DEVRDADJ-66 | 34031 | [QA] Test Execution - Create cronjob to remove unused deeplink | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | In Progress |  | 11/Nov/25 11:13 AM | 18/Nov/25 11:56 AM | [8 empty] | มาจาก Sprint 11 | To Do |  | [Dev][RDAdjust] Sprint 11 | [Dev][RDAdjust] Sprint 12
Sub-task | DEVRDADJ-65 | 34029 | [QA] Test Execution - No-QA | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 11/Nov/25 11:00 AM | 18/Nov/25 11:47 AM | [8 empty] | มาจาก Sprint 11 | To Do |  | [Dev][RDAdjust] Sprint 11 | [Dev][RDAdjust] Sprint 12
Story | DEVRDECOM-160 | 33794 | [DEV][RD][Eco][Ecommerce-Shopify] Enhance to support original & Updated Shopify domain | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 07/Nov/25 4:16 PM | 26/Nov/25 9:41 AM |  | 3 | ecommerce-shopify-api |  |  |  |  | 28800 |  |  |  | [Dev][RD][Ecom] Sprint 12
Story | DEVRDECOM-159 | 33793 | [DEV][RD][Eco][Ecommerce-Shopify] Enhance CronJob to support scalable | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 07/Nov/25 4:14 PM | 26/Nov/25 11:01 AM | 10/Nov/25 12:00 AM | 2 | ecommerce-shopify-api |  |  |  |  | 0 | มาจาก Sprint 11 | Ready To Test | 28800 | [Dev][RD][Ecom] Sprint 11 | [Dev][RD][Ecom] Sprint 12
Story | RDAPS-266 | 33791 | [Dev][RD][Order] Improve process to sync transaction to DA | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 07/Nov/25 3:13 PM | 26/Nov/25 11:40 AM | 20/Nov/25 12:00 AM | 3 | order-consumer |  |  |  |  | 28800 |  |  |  | [Dev][All Project] Sprint 12
Sub-task | DEVRDADJ-64 | 33778 | [QA] Create Test Case - Integrate delete deeplink when product expired | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 07/Nov/25 9:53 AM | 11/Nov/25 11:41 AM | [8 empty] | มาจาก Sprint 11 | Done |  | [Dev][RDAdjust] Sprint 11 | [Dev][RDAdjust] Sprint 12
Sub-task | DEVRDADJ-63 | 33776 | [QA] Create Test Case - Create cronjob to remove unused deeplink | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 07/Nov/25 9:50 AM | 11/Nov/25 11:13 AM | [8 empty] | มาจาก Sprint 11 | Done |  | [Dev][RDAdjust] Sprint 11 | [Dev][RDAdjust] Sprint 12
Sub-task | DEVRDADJ-62 | 33774 | [QA] Create Test Case - Integrate error notification with Discord | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 07/Nov/25 9:50 AM | 11/Nov/25 11:24 AM | [8 empty] | มาจาก Sprint 11 | Done |  | [Dev][RDAdjust] Sprint 11 | [Dev][RDAdjust] Sprint 12
Sub-task | DEVRDADJ-61 | 33772 | [QA] Create Test Case - Create new endpoint to delete deeplink | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 07/Nov/25 9:49 AM | 11/Nov/25 10:59 AM | [8 empty] | มาจาก Sprint 11 | Done |  | [Dev][RDAdjust] Sprint 11 | [Dev][RDAdjust] Sprint 12
Sub-task | DEVRDCT-303 | 33734 | [QA] Test execution - No QA | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 06/Nov/25 6:10 PM | 24/Nov/25 10:10 AM | [8 empty] | มาจาก Sprint 11 | To Do |  | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12
Sub-task | DEVRDCT-302 | 33732 | [QA] Create test case collect Reward Catalog data for uploading to CleverTap | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 06/Nov/25 6:09 PM | 14/Nov/25 9:59 AM | [8 empty] | มาจาก Sprint 11 | Done |  | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12
Sub-task | DEVRDCT-301 | 33730 | [QA] (Staging) Test execution API to upload the Catalog to CleverTap | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | In Progress |  | 06/Nov/25 6:07 PM | 25/Nov/25 2:43 PM | [8 empty] | มาจาก Sprint 11 | In Progress |  | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12
Sub-task | DEVRDCT-300 | 33728 | [QA] Create test case API to upload the Catalog to CleverTap | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 06/Nov/25 6:06 PM | 14/Nov/25 9:59 AM | [8 empty] | มาจาก Sprint 11 | Done |  | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12
Sub-task | DEVRDCT-298 | 33724 | [QA] (Staging) Test execution Line Pay Unbound Event | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 06/Nov/25 5:54 PM | 25/Nov/25 2:43 PM | [8 empty] | มาจาก Sprint 11 | To Do |  | [Dev][CT] Sprint 11 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12
Sub-task | DEVRDCT-297 | 33722 | [QA] Create test case Line Pay Unbound Event | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 06/Nov/25 5:54 PM | 25/Nov/25 2:43 PM | [8 empty] | มาจาก Sprint 11 | To Do |  | [Dev][CT] Sprint 11 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12
Sub-task | DEVRDCT-296 | 33720 | [QA] (Staging) Test execution API for widget type = clevertab_native_display | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 06/Nov/25 5:50 PM | 26/Nov/25 10:11 AM | [8 empty] | มาจาก Sprint 11 | To Do |  | [Dev][CT] Sprint 11 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12
Sub-task | DEVRDCT-295 | 33718 | [QA] Create test case Sections/Widgets APIs to support widget type = clevertab_native_display | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 06/Nov/25 5:49 PM | 25/Nov/25 2:43 PM | [8 empty] | มาจาก Sprint 11 | To Do |  | [Dev][CT] Sprint 11 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12
Sub-task | DEVRDCT-294 | 33716 | [QA] (Staging) Test execution add Widget type = "CleverTap : Native display" | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 06/Nov/25 5:41 PM | 26/Nov/25 10:11 AM | [8 empty] | มาจาก Sprint 11 | To Do |  | [Dev][CT] Sprint 11 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12
Sub-task | DEVRDCT-293 | 33714 | [QA] Create test case add Widget type = "CleverTap : Native display" | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 06/Nov/25 5:40 PM | 26/Nov/25 10:11 AM | [8 empty] | มาจาก Sprint 11 | To Do |  | [Dev][CT] Sprint 11 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12
Bug | RDTHANA-391 | 33709 | [S3][Survey][Thank you][Incentive Point] when set survey Have Incentive Point, Step 4 not show format Thank you with intentive | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Closed |  | 06/Nov/25 4:55 PM | 19/Nov/25 2:13 PM | [11 empty] | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Bug | RDTHANA-378 | 33707 | [S3][Survey][Survey list] Status NOT update after survey is expire | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Closed |  | 06/Nov/25 4:15 PM | 19/Nov/25 2:12 PM | [8 empty] | มาจาก Sprint 11 | Resolved |  | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | DEVRDSUP-225 | 33702 | [SUP-288][SUB] CS-20251100020461 บัตร 0880061308331 ไม่สามารถเติมเที่ยวเดินทางได้ | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 06/Nov/25 3:24 PM | 29/Nov/25 1:08 PM |  | 1 | bts | mid-sprint | prod-issue | RabbitWallet | sub | 3600 |  |  |  | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12
Bug | RDTHANA-377 | 33695 | [S4][Survey][Step 2] Club Status(Active/Inavtive) NOT update after change from HR-solution | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Resolved |  | 06/Nov/25 1:54 PM | 18/Nov/25 10:40 AM | [8 empty] | มาจาก Sprint 11 | Resolved |  | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | DEVRDADJ-60 | 33631 | [DEV][RD][BOF] Add more parameter in adjust generate deeplink api | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 05/Nov/25 2:49 PM | 18/Nov/25 10:09 AM |  | 1 | rr-backoffice |  |  |  |  | 0 | มาจาก Sprint 11 | Ready To Test | 7200 | [Dev][RDAdjust] Sprint 11 | [Dev][RDAdjust] Sprint 12
Story | DEVRDADJ-59 | 33630 | [DEV][RD][LNF] Add more parameter in adjust generate deeplink API | Art: Narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 05/Nov/25 2:49 PM | 18/Nov/25 2:50 PM |  | 1 | link-notify | [5 empty] | มาจาก Sprint 11 | Ready to Staging |  | [Dev][RDAdjust] Sprint 11 | [Dev][RDAdjust] Sprint 12
Bug | DEVRDSUP-221 | 33625 | [SUP-281][RR-Backoffice] Reward Coupon Transaction Report found error after search | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | UNDER VALIDATION |  | 05/Nov/25 1:30 PM | 26/Nov/25 11:05 AM | 01/Dec/25 12:00 AM |  | mid-sprint | prod-issue | rem | [6 empty] | [Dev][All Project] Sprint 12
Story | RDAPS-261 | 33609 | [Dev][RD][RRS] Add additional data to msg payload for Package Confirmation Email | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 05/Nov/25 11:19 AM | 18/Nov/25 10:02 AM |  |  | rr-scheduler | [8 empty] | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12
Sub-task | DEVRDCT-289 | 33481 | [QA](Staging) Test execution LINE_PAY_BINDING Event push to CT (WEB) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 04/Nov/25 6:01 PM | 25/Nov/25 2:43 PM | [8 empty] | มาจาก Sprint 11 | To Do |  | [Dev][CT] Sprint 9 | [Dev][CT] Sprint 11 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12
Sub-task | DEVRDCT-288 | 33479 | [QA] Create test case LINE_PAY_BINDING Event push to CT (WEB) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 04/Nov/25 6:00 PM | 25/Nov/25 2:43 PM | [8 empty] | มาจาก Sprint 11 | To Do |  | [Dev][CT] Sprint 9 | [Dev][CT] Sprint 11 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12
Sub-task | DEVRDCT-287 | 33477 | [QA](Staging) Test execution LINE_PAY_BINDING Event push to CT (API) | Lucas - Saksorn Srisak | 712020:289e7d91-50e6-438c-9b32-23b14017a585 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 04/Nov/25 5:59 PM | 25/Nov/25 2:43 PM | [8 empty] | มาจาก Sprint 11 | To Do |  | [Dev][CT] Sprint 9 | [Dev][CT] Sprint 11 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12
Sub-task | DEVRDCT-286 | 33475 | [QA] Create test case LINE_PAY_BINDING Event push to CT (API) | Lucas - Saksorn Srisak | 712020:289e7d91-50e6-438c-9b32-23b14017a585 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 04/Nov/25 5:59 PM | 25/Nov/25 2:43 PM | [8 empty] | มาจาก Sprint 11 | To Do |  | [Dev][CT] Sprint 9 | [Dev][CT] Sprint 11 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12
Sub-task | DEVRDCT-285 | 33473 | [QA](Staging) Line OA and Friend event to CleverTap(API) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 04/Nov/25 5:49 PM | 25/Nov/25 2:43 PM | [8 empty] | มาจาก Sprint 11 | To Do |  | [Dev][CT] Sprint 9 | [Dev][CT] Sprint 11 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12
Sub-task | DEVRDCT-284 | 33467 | - |  |  | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 04/Nov/25 5:47 PM | 25/Nov/25 2:43 PM | [8 empty] | มาจาก Sprint 11 | To Do |  | [Dev][CT] Sprint 9 | [Dev][CT] Sprint 11 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12
Sub-task | DEVRDCT-283 | 33465 | [QA](Staging) Line OA and Friend event to CleverTap(WEB) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 04/Nov/25 5:46 PM | 25/Nov/25 2:43 PM | [8 empty] | มาจาก Sprint 11 | To Do |  | [Dev][CT] Sprint 9 | [Dev][CT] Sprint 11 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12
Sub-task | RDTHANA-366 | 33451 | [QA][Survey](Statging) Test execution change status flow to validate required fields | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 04/Nov/25 3:25 PM | 25/Nov/25 2:33 PM | [8 empty] | มาจาก Sprint 11 | To Do |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Sub-task | RDTHANA-365 | 33449 | [QA][Survey] Create test case change status flow to validate required fields | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 04/Nov/25 3:24 PM | 25/Nov/25 2:32 PM | [8 empty] | มาจาก Sprint 11 | To Do |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Sub-task | RDTHANA-364 | 33445 | [QA](Staging) Test execution Separate Welcome message pop up setting between application and website | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 04/Nov/25 3:18 PM | 21/Nov/25 10:26 AM | [8 empty] | มาจาก Sprint 11 | To Do |  | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Sub-task | RDTHANA-363 | 33443 | [QA] Create test case Separate Welcome message pop up setting between application and website | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 04/Nov/25 3:18 PM | 19/Nov/25 1:21 AM | [8 empty] | มาจาก Sprint 11 | To Do |  | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Sub-task | RDTHANA-362 | 33441 | [QA](STG+UAT) Test execution Survey Event CT | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 04/Nov/25 3:16 PM | 27/Nov/25 5:05 PM | [8 empty] | มาจาก Sprint 11 | To Do |  | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Sub-task | RDTHANA-361 | 33439 | [QA] Create Test case Survey Event CT | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 04/Nov/25 3:16 PM | 13/Nov/25 2:25 PM | [8 empty] | มาจาก Sprint 11 | Done |  | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Sub-task | RDTHANA-360 | 33436 | [QA](Statging) Test execution HR Solution Widget type Services | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 04/Nov/25 3:05 PM | 17/Nov/25 1:34 PM | [8 empty] | มาจาก Sprint 11 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Sub-task | DEVRDSUP-216 | 33434 | [DEVRDSUP-214] Fix the duplication creation flow. | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | To Do |  | 04/Nov/25 2:12 PM | 10/Nov/25 5:05 PM | [11 empty] | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12
Sub-task | DEVRDSUP-215 | 33432 | [DEVRDSUP-214] Clear duplicated BU allocation records. | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | In Progress |  | 04/Nov/25 2:11 PM | 28/Nov/25 10:22 AM | [7 empty] | 3600 |  |  |  | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12
Bug | DEVRDSUP-214 | 33430 | [SUP-277][BUG][HR-Solution][RD] If user had been inactive BU and change the BU active again. The BU Allocation has been auto re-create. | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Low | Closed |  | 04/Nov/25 12:01 PM | 19/Nov/25 10:30 AM | 02/Dec/25 12:00 AM |  | hr-solution | mid-sprint | [7 empty] | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12
Story | DEVRDECOM-151 | 33383 | [DEV][RD][Eco] Change image demo in create/edit service page | Art: Narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 04/Nov/25 9:48 AM | 17/Nov/25 3:55 PM | 04/Nov/25 12:00 AM | 1 | [5 empty] | 0 | มาจาก Sprint 11 | Ready to Staging | 3600 | [Dev][RD][Ecom] Sprint 11 | [Dev][RD][Ecom] Sprint 12
Story | DEVRDSUP-213 | 33377 | [SUB] Request to mark used many BTS vouchers due to cloud ID incident on 16/10/2025 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Blocked |  | 03/Nov/25 6:49 PM | 26/Nov/25 8:12 AM | 01/Dec/25 12:00 AM | 8 | bts | prod-issue | sub | [6 empty] | [Dev][All Project] Sprint 12
Story | DEVRDECOM-150 | 33348 | [DEV][RD][Eco][Ecommerce-Shopify] Change Logout Behavior on Website (Shopify) | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 03/Nov/25 9:21 AM | 21/Nov/25 4:19 PM | 13/Nov/25 12:00 AM | 5 | ecommerce-shopify-api |  |  |  |  | 0 | มาจาก Sprint 11 | Ready To Test | 57600 | [Dev][RD][Ecom] Sprint 11 | [Dev][RD][Ecom] Sprint 12
Story | DEVRDECOM-149 | 33347 | [DEV][RD][Eco][DAS HAUS][Ecommerce-Shopify] New Sequence Login and Join Club Flow | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 03/Nov/25 9:17 AM | 26/Nov/25 1:43 PM | 04/Nov/25 12:00 AM | 3 | rr-ecommerce-shopify | [5 empty] | มาจาก Sprint 11 | Ready To Test |  | [Dev][RD][Ecom] Sprint 11 | [Dev][RD][Ecom] Sprint 12
Story | DEVRDADJ-57 | 33343 | [DEV][RD][RRS] Integrate delete deeplink when product expired | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 02/Nov/25 11:10 PM | 19/Nov/25 10:31 AM |  | 3 | link-notify | No-QA |  |  |  | 0 | มาจาก Sprint 11 | Ready To Test | 28800 | [Dev][RDAdjust] Sprint 11 | [Dev][RDAdjust] Sprint 12
Story | DEVRDADJ-56 | 33342 | [DEV][RD][LNF] Create new endpoint to delete deeplink | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 02/Nov/25 10:54 PM | 19/Nov/25 10:31 AM |  | 3 | link-notify | No-QA |  |  |  | 0 | มาจาก Sprint 11 | Ready To Test | 39600 | [Dev][RDAdjust] Sprint 11 | [Dev][RDAdjust] Sprint 12
Story | RDAPS-256 | 33341 | [Dev][RD][CID] Implement CLI to remove double binding account records | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 02/Nov/25 4:37 PM | 18/Nov/25 10:02 AM |  | 5 | rr-cloudid-api |  |  |  |  | 115200 |  |  |  | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12
Story | RDAPS-255 | 33340 | [Dev][RD][CID] Add log to Binding API to investigate double binding cases | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Nov/25 4:28 PM | 18/Nov/25 10:02 AM | 06/Nov/25 12:00 AM | 3 | rr-cloudid-api |  |  |  |  | 21600 |  |  |  | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12
Story | DEVRDADJ-55 | 33338 | [DEV][RD][LNF] Integrate error notification with Discord | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 02/Nov/25 2:59 PM | 19/Nov/25 10:31 AM |  | 3 | link-notify | No-QA |  |  |  | 0 | มาจาก Sprint 11 | Ready To Test | 28800 | [Dev][RDAdjust] Sprint 11 | [Dev][RDAdjust] Sprint 12
Story | DEVRDADJ-54 | 33337 | [DEV][RD][LNF] Create cronjob to remove unused deeplink | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 02/Nov/25 2:46 PM | 28/Nov/25 1:42 PM | 11/Nov/25 12:00 AM | 3 | link-notify |  |  |  |  | 0 | มาจาก Sprint 11 | Ready to Staging | 28800 | [Dev][RDAdjust] Sprint 11 | [Dev][RDAdjust] Sprint 12
Story | DEVRDCT-277 | 33336 | [DEV][RD][RRS] Implement a function to collect Reward Catalog data for uploading to CleverTap | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 02/Nov/25 8:55 AM | 27/Nov/25 5:02 PM |  | 5 | No-QA | rr-scheduler |  |  |  | 0 | มาจาก Sprint 11 | Ready To Test | 86400 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12
Story | DEVRDCT-276 | 33335 | [DEV][RD][CT] Implement API to upload the Catalog to CleverTap | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready To Test |  | 02/Nov/25 8:50 AM | 25/Nov/25 2:43 PM | 11/Nov/25 12:00 AM | 8 | CleverTap |  |  |  |  | 0 | มาจาก Sprint 11 | Ready To Test | 86400 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12
Story | DEVRDECOM-145 | 33275 | [DEV][RD[Eco][Turtle][POC] Dynamic Section by Customer Location | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Low | In Progress |  | 31/Oct/25 12:47 PM | 20/Nov/25 8:49 AM |  | 5 | No-QA | [5 empty] | มาจาก Sprint 11 | In Progress |  | [Dev][RD][Ecom] Sprint 11 | [Dev][RD][Ecom] Sprint 11 | [Dev][RD][Ecom] Sprint 12
Story | RDAPS-247 | 33250 | [Dev][RD][RRS] Optimize import coupons | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready To Test |  | 30/Oct/25 2:22 PM | 28/Nov/25 10:28 AM |  | 8 | rr-scheduler |  |  |  |  | 86400 |  |  |  | [Dev][All Project] Sprint 12
Story | RDTHANA-353 | 33197 | [Dev][RD][Survey Web] Remove Survey web from SEO | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 28/Oct/25 1:53 PM | 18/Nov/25 10:40 AM |  | 2 | rr-aphrodite | [5 empty] | มาจาก Sprint 11 | Ready To Test |  | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Bug | DEVRDSUP-203 | 33157 | [SUP-260][REM] Rewards Alert List - Going to out-of-stock items is not being sent, last alert mail was received on 24/10/2025. | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Closed |  | 27/Oct/25 2:36 PM | 24/Nov/25 2:07 PM | 10/Nov/25 12:00 AM | 3 | mid-sprint | prod-issue | rem | [6 empty] | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12
Story | RDTHANA-344 | 32939 | [DEV][RD][BFF] Enhance change condition for is_enable_opt_in flag | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 21/Oct/25 5:45 PM | 18/Nov/25 12:28 PM | 22/Oct/25 12:00 AM | 1 | [5 empty] | 0 | มาจาก Sprint 11 | Ready To Test | 3600 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | RDTHANA-343 | 32938 | [DEV][RD][Exclusive Store API] Enhance get club detail with BU setting | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 21/Oct/25 5:28 PM | 18/Nov/25 11:43 AM | 22/Oct/25 12:00 AM | 2 | No-QA |  |  |  |  | 0 | มาจาก Sprint 11 | Ready To Test | 10800 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Bug | DEVRDSUP-196 | 32935 | [SUP-252][REM] Reward's stock amount shows incorrect value on RR app and stock count on RR app doesn't match actual stock on RR back office. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | RETESTING |  | 21/Oct/25 4:45 PM | 18/Nov/25 10:02 AM | 05/Nov/25 12:00 AM | 1 | prod-issue | rem | [7 empty] | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12
Story | RDTHANA-341 | 32920 | [Dev][RD][BFF] Create an API to Get Clubs with filtering options | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Done |  | 21/Oct/25 4:00 PM | 18/Nov/25 11:38 AM | 24/Oct/25 12:00 AM | 3 | BFF | mid-sprint |  |  |  | 0 | มาจาก Sprint 11 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | RDTHANA-340 | 32919 | [Dev][RD][EXS] Create an API to Get Clubs with filtering options | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Done |  | 21/Oct/25 4:00 PM | 18/Nov/25 11:44 AM | 22/Oct/25 12:00 AM | 3 | exclusive-store-api | mid-sprint | No-QA |  |  | 0 | มาจาก Sprint 11 | Ready To Test | 43200 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | RDAPS-238 | 32907 | [Dev][RD] Create script to mark vouchers as used for Cloud ID cases (issued on 16 Oct) | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Blocked |  | 21/Oct/25 2:10 PM | 26/Nov/25 8:12 AM |  | 5 | rr-scheduler | [8 empty] | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12
Sub-task | RDTHANA-339 | 32905 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 21/Oct/25 1:43 PM | 18/Nov/25 11:56 AM | [8 empty] | มาจาก Sprint 11 | In Progress |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | RDTHANA-335 | 32813 | [Dev][RD][BFF] Enhance Club Binding API to support popup display separately for app and web | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 20/Oct/25 2:24 PM | 21/Nov/25 10:05 AM | 29/Oct/25 12:00 AM | 3 | [5 empty] | 0 | มาจาก Sprint 11 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | DEVRDCT-269 | 32785 | [DEV][RD][RLP][API] Line Pay Unbound Event | Art: Narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 20/Oct/25 9:30 AM | 25/Nov/25 2:43 PM | 21/Oct/25 12:00 AM | 3 | [5 empty] | 0 | มาจาก Sprint 11 | Ready To Test | 28800 | [Dev][CT] Sprint 11 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12
Story | RDAPS-233 | 32777 | [Dev][RD][RRS] Enhance Redemption ETL to add fields 'USING_AT' and 'COUNTDOWN_EXPIRED_AT' | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Blocked |  | 19/Oct/25 3:24 PM | 18/Nov/25 10:02 AM | 21/Oct/25 12:00 AM | 2 | rr-scheduler |  |  |  |  | 14400 |  |  |  | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12
Story | RDTHANA-333 | 32661 | [DEV][RD][Exclusive Store API][ENH] Enhance BFF to Support Separated Application & Web Settings in Welcome Message | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 17/Oct/25 2:11 PM | 20/Nov/25 8:52 AM | 24/Oct/25 12:00 AM | 3 | BFF |  |  |  |  | 0 | มาจาก Sprint 11 | Ready To Test | 21600 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | RDTHANA-332 | 32659 | [DEV][RD][HRS][ENH] Enhance to separate Welcome message pop up setting between application and website | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 17/Oct/25 12:04 PM | 21/Nov/25 10:26 AM | 28/Oct/25 12:00 AM | 8 | hr-solution |  |  |  |  | 0 | มาจาก Sprint 11 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | DEVRDCT-265 | 32640 | [Dev][RD][BFF] Enhance Sections/Widgets APIs to support a new widget type | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 16/Oct/25 2:58 PM | 27/Nov/25 4:42 PM | 22/Oct/25 12:00 AM | 3 | BFF |  |  |  |  | 0 | มาจาก Sprint 11 | Ready To Test | 28800 | [Dev][CT] Sprint 11 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12
Story | DEVRDCT-264 | 32638 | [Dev][RD][CMS DB] Create migration schemas to support the new widget type | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 16/Oct/25 2:57 PM | 26/Nov/25 10:20 AM | 20/Oct/25 12:00 AM | 1 | cms-database | No-QA | rabbit-cms-api |  |  | 0 | มาจาก Sprint 11 | Ready To Test | 3600 | [Dev][CT] Sprint 11 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12
Story | DEVRDCT-263 | 32637 | [Dev][RD][BOF] Enhance Widget to support "Native Display" | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 16/Oct/25 2:56 PM | 26/Nov/25 10:20 AM | 21/Oct/25 12:00 AM | 3 | rr-backoffice |  |  |  |  | 0 | มาจาก Sprint 11 | Ready To Test | 21600 | [Dev][CT] Sprint 11 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12
Story | DEVRDSUP-175 | 32272 | [SUP-239][ETL] Catch-up redemption data (item_id, using_at, and countdown_expired_at) | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Blocked |  | 14/Oct/25 4:34 PM | 24/Nov/25 11:50 AM | 30/Oct/25 12:00 AM | 5 | etl | [8 empty] | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12
Story | DEVRDSUP-174 | 32269 | [SUP-238][API] Catch-up subscription purchase report (publishPrice) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Done |  | 14/Oct/25 4:14 PM | 24/Nov/25 3:08 PM | 07/Nov/25 12:00 AM | 5 | etl |  |  |  |  | 0 |  |  |  | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12
Story | DEVRDCT-258 | 32213 | [DEV][RD][RLP][WEP] LINE_PAY_BINDING Event push to CT | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 13/Oct/25 5:00 PM | 25/Nov/25 2:43 PM |  | 2 | No-QA |  |  |  |  | 0 | มาจาก Sprint 11 | Ready To Test | 10800 | [Dev][CT] Sprint 9 | [Dev][CT] Sprint 11 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12
Sub-task | RDTHANA-318 | 32088 | [QA] Create Test Case - Enhance sorry page with get deeplink endpoint | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 08/Oct/25 10:19 AM | 03/Nov/25 2:32 PM | [8 empty] | มาจาก Sprint 11 | Done |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | RDTHANA-317 | 32072 | [Dev][RD][BOF] Improve change status flow to validate required fields | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 07/Oct/25 3:16 PM | 25/Nov/25 2:33 PM | 14/Oct/25 12:00 AM | 5 | rr-backoffice |  |  |  |  | 0 | มาจาก Sprint 11 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | DEVRDCT-257 | 32071 | [DEV][RD][RLP][API] LINE_PAY_BINDING Event push to CT | Art: Narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 07/Oct/25 3:13 PM | 25/Nov/25 2:43 PM |  | 5 | [6 empty] | มาจาก Sprint 11 | Ready To Test |  | [Dev][CT] Sprint 9 | [Dev][CT] Sprint 11 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12
Sub-task | DEVRDCT-253 | 32062 | [QA] Create test case Line OA and Friend event to CleverTap (API) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 07/Oct/25 2:09 PM | 25/Nov/25 2:43 PM | [8 empty] | มาจาก Sprint 11 | To Do |  | [Dev][CT] Sprint 9 | [Dev][CT] Sprint 11 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12
Sub-task | DEVRDCT-252 | 32060 | [QA] Create test case Line OA and Friend event to CleverTap(WEB) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 07/Oct/25 2:04 PM | 25/Nov/25 2:43 PM | [8 empty] | มาจาก Sprint 11 | To Do |  | [Dev][CT] Sprint 9 | [Dev][CT] Sprint 11 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12
Sub-task | DEVRDCT-251 | 32058 | [QA](Staging) Test execution sync initial RLP member to RR Line member | Lucas - Saksorn Srisak | 712020:289e7d91-50e6-438c-9b32-23b14017a585 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 07/Oct/25 2:03 PM | 21/Nov/25 10:57 AM | [8 empty] | มาจาก Sprint 11 | To Do |  | [Dev][CT] Sprint 9 | [Dev][CT] Sprint 11 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12
Story | RDTHANA-313 | 32018 | [DEV][RD][BFF] Get club term and condition endpoint | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 06/Oct/25 2:33 PM | 18/Nov/25 12:33 PM | 10/Oct/25 12:00 AM | 2 | BFF |  |  |  |  | 0 | มาจาก Sprint 11 | Ready To Test | 10800 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | RDTHANA-312 | 32017 | [DEV][RD][Exclusive API] Get club term and condition endpoint | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 06/Oct/25 2:33 PM | 18/Nov/25 11:43 AM | 10/Oct/25 12:00 AM | 3 | exclusive-store-api | No-QA |  |  |  | 0 | มาจาก Sprint 11 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | DEVRDCT-250 | 32004 | [DEV][RD][RLP] Create script to sync initial RLP member to RR Line member | Art: Narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 06/Oct/25 10:03 AM | 27/Nov/25 4:42 PM | 10/Oct/25 12:00 AM | 5 | rlp-middleware |  |  |  |  | 0 | มาจาก Sprint 11 | Ready To Test | 57600 | [Dev][CT] Sprint 9 | [Dev][CT] Sprint 11 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12
Story | DEVRDCT-249 | 31984 | [DEV][RD][RLP][WEB] Sent Line OA and Friend event to CleverTap | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 05/Oct/25 4:45 PM | 25/Nov/25 2:43 PM |  | 3 | No-QA |  |  |  |  | 0 | มาจาก Sprint 11 | Ready To Test | 10800 | [Dev][CT] Sprint 9 | [Dev][CT] Sprint 11 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12
Story | DEVRDCT-248 | 31983 | [DEV][RD][RLP][API] Sent Line OA and Friend event to CleverTap | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 05/Oct/25 4:45 PM | 25/Nov/25 2:43 PM |  | 3 | No-QA | rlp-middleware |  |  |  | 0 | มาจาก Sprint 11 | Ready To Test | 10800 | [Dev][CT] Sprint 9 | [Dev][CT] Sprint 11 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12
Story | RDAPS-213 | 31974 | [Dev][Rabbit connect] Remove Login SMS OTP on UAT for ease of testing and lower the SMS cost. | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 04/Oct/25 4:25 PM | 25/Nov/25 4:24 PM |  | 5 | sso-heimdall |  |  |  |  | 28800 |  |  |  | [Dev][All Project] Sprint 9 | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12
Story | RDTHANA-311 | 31957 | [DEV][RD][APH] Enhance sorry page with get deeplink endpoint | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 03/Oct/25 5:11 PM | 28/Nov/25 1:49 PM | 08/Oct/25 12:00 AM | 3 | rr-aphrodite | [5 empty] | มาจาก Sprint 11 | Ready To Test |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Bug | DEVRDCT-241 | 31866 | [S3][CT][Webhook][Club Binding Event] Opt-in type club binding status event not show correctly on CT through Webhook API | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Open |  | 30/Sep/25 3:31 PM | 25/Nov/25 2:44 PM | [8 empty] | มาจาก Sprint 11 | Open |  | [Dev][CT] Sprint 9 | [Dev][CT] Sprint 11 | [Dev][CT] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][CT] Sprint 12
Task | DEVRDSUP-153 | 31856 | Find and remove double bound 1 wallet card to multiple SSO to resolve DEVRDSUP-146 error for other users. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Blocked |  | 30/Sep/25 1:40 PM | 26/Nov/25 8:11 AM | 01/Dec/25 12:00 AM | 5 | [9 empty] | [Dev][All Project] Sprint 9 | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12
Story | RDTHANA-294 | 31845 | [Dev][RD][BFF] Improve get sections contents api v2 | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Done |  | 30/Sep/25 11:56 AM | 18/Nov/25 12:29 PM | 01/Oct/25 12:00 AM | 2 | [5 empty] | 0 | มาจาก Sprint 11 | Ready To Test | 14400 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | RDTHANA-289 | 31700 | [DEV][RD][BOF][CR] Enhance survey ranking question | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 26/Sep/25 2:02 PM | 18/Nov/25 10:45 AM | 30/Sep/25 12:00 AM | 3 | [5 empty] | 0 | มาจาก Sprint 11 | Ready To Test | 21600 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | RDTHANA-268 | 31545 | [Dev][RD][BOF] Disable mode when survey is expired | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 23/Sep/25 3:28 PM | 24/Nov/25 10:44 AM | 30/Sep/25 12:00 AM | 1 | rr-backoffice |  |  |  |  | 0 | มาจาก Sprint 11 | Ready To Test | 3600 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Epic | DEVRDECOM-107 | 31506 | Shopify Webhook |  |  | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | To Do |  | 23/Sep/25 9:52 AM | 17/Nov/25 10:54 AM | [8 empty] | มาจาก Sprint 11 | To Do |  | [Dev][RD][Ecom] Sprint 8 | [Dev][RD][Ecom] Sprint 9 | [Dev][RD][Ecom] Sprint 11 | [Dev][RD][Ecom] Sprint 11 | [Dev][RD][Ecom] Sprint 12
Sub-task | RDTHANA-249 | 31473 | [QA] Create Test Case View Survey List (FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 22/Sep/25 10:06 PM | 24/Nov/25 10:15 AM | [8 empty] | มาจาก Sprint 11 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | RDTHANA-244 | 31447 | [DEV][RD][APH] Enhance sorry page support dynamic error message and CTA button | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 22/Sep/25 11:36 AM | 18/Nov/25 10:45 AM | 29/Sep/25 12:00 AM | 1 | [6 empty] | มาจาก Sprint 11 | Ready To Test |  | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | RDTHANA-241 | 31432 | [DEV][RD][APH] Enhance survey html render support survey appearance "Thank you" tab | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 21/Sep/25 9:13 PM | 18/Nov/25 10:45 AM | 29/Sep/25 12:00 AM | 3 | [5 empty] | 0 | มาจาก Sprint 11 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | RDTHANA-240 | 31431 | [DEV][RD][APH] Enhance survey html render support survey appearance "Email" tab (Issue point form) | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Done |  | 21/Sep/25 9:13 PM | 24/Nov/25 10:43 AM | 26/Sep/25 12:00 AM | 8 | [5 empty] | 0 | มาจาก Sprint 11 | Ready To Test | 144000 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | RDTHANA-239 | 31430 | [DEV][RD][APH] Enhance survey html render support survey appearance "Survey Q&A" tab | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Done |  | 21/Sep/25 9:13 PM | 24/Nov/25 10:43 AM | 26/Sep/25 12:00 AM | 8 | [5 empty] | 0 | มาจาก Sprint 11 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | RDTHANA-238 | 31429 | [DEV][RD][APH] Create survey theme | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Highest | Ready To Test |  | 21/Sep/25 8:49 PM | 18/Nov/25 10:40 AM | 23/Sep/25 12:00 AM | 3 | rr-aphrodite |  |  |  |  | 0 | มาจาก Sprint 11 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | DEVRDECOM-100 | 31424 | [DEV][RD][Eco][Ecommerce-Shopify] Partial refund multiple time in the same order | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 21/Sep/25 9:51 AM | 28/Nov/25 11:23 AM |  | 5 | ecommerce-shopify-api |  |  |  |  | 72000 |  |  |  | [Dev][RD][Ecom] Sprint 12
Story | RDTHANA-232 | 31360 | [DEV][RD][GATEWAY] Mapping get member club detail with internal API | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Highest | Done |  | 19/Sep/25 10:44 AM | 18/Nov/25 12:22 PM |  | 1 | [5 empty] | 0 | มาจาก Sprint 11 | Ready To Test | 7200 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | RDTHANA-231 | 31359 | [DEV][RD][APH] Enhance survey html render support survey appearance "General" tab | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 19/Sep/25 10:43 AM | 18/Nov/25 10:46 AM | 26/Sep/25 12:00 AM | 5 | [5 empty] | 0 | มาจาก Sprint 11 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | RDTHANA-230 | 31358 | [DEV][RD][APH] Enhance getMemberToken support sources session | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 19/Sep/25 10:42 AM | 18/Nov/25 10:46 AM | 26/Sep/25 12:00 AM | 2 | [5 empty] | 0 | มาจาก Sprint 11 | Ready To Test | 7200 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | RDTHANA-229 | 31332 | [DEV][RD][APH] Enhance survey available middleware | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Done |  | 18/Sep/25 4:23 PM | 24/Nov/25 10:27 AM | 26/Sep/25 12:00 AM | 5 | [5 empty] | 0 | มาจาก Sprint 11 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Sub-task | RDTHANA-134 | 30844 | [QA] Create Test Case Download Individual Survey Report (FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 09/Sep/25 11:30 AM | 24/Nov/25 10:18 AM | [8 empty] | มาจาก Sprint 11 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Sub-task | RDTHANA-133 | 30842 | [QA] Create Test Case View Survey Report (FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:30 AM | 05/Oct/25 2:50 PM | [8 empty] | มาจาก Sprint 11 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Sub-task | RDTHANA-132 | 30840 | [QA] Create Test Case Change survey status (FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 09/Sep/25 11:30 AM | 24/Nov/25 10:20 AM | [8 empty] | มาจาก Sprint 11 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Sub-task | RDTHANA-131 | 30838 | [QA] Test Execution Update survey Step 5: Survey Appearance (Thank You) (FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 09/Sep/25 11:29 AM | 24/Nov/25 10:22 AM | [8 empty] | มาจาก Sprint 11 | To Do |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Sub-task | RDTHANA-130 | 30836 | [QA] Create Test Case Update survey Step 5: Survey Appearance (Thank You) (FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 09/Sep/25 11:29 AM | 24/Nov/25 10:22 AM | [8 empty] | มาจาก Sprint 11 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Sub-task | RDTHANA-129 | 30834 | [QA] Create Test Case Update survey Step 5: Survey Appearance (Input E-mail) (FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 09/Sep/25 11:29 AM | 24/Nov/25 10:20 AM | [8 empty] | มาจาก Sprint 11 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Sub-task | RDTHANA-128 | 30832 | [QA] Create Test Case [Dev][RD][BOF] Update survey step5.2(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 09/Sep/25 11:29 AM | 25/Nov/25 10:17 AM | [8 empty] | มาจาก Sprint 11 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Sub-task | RDTHANA-127 | 30830 | [QA] Create Test Case Update survey step5.1(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 09/Sep/25 11:28 AM | 24/Nov/25 10:17 AM | [8 empty] | มาจาก Sprint 11 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Sub-task | RDTHANA-125 | 30826 | [QA] Create Test Case Update survey step4.2(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 09/Sep/25 11:28 AM | 25/Nov/25 10:17 AM | [8 empty] | มาจาก Sprint 11 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Sub-task | RDTHANA-124 | 30824 | [QA] Create Test Case Update survey step4.1(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 09/Sep/25 11:27 AM | 24/Nov/25 10:17 AM | [8 empty] | มาจาก Sprint 11 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Sub-task | RDTHANA-123 | 30822 | [QA] Create Test Case Update survey step3(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 09/Sep/25 11:27 AM | 24/Nov/25 10:16 AM | [8 empty] | มาจาก Sprint 11 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Sub-task | RDTHANA-122 | 30820 | [QA] Create Test Case Update survey step2(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 09/Sep/25 11:26 AM | 24/Nov/25 10:15 AM | [8 empty] | มาจาก Sprint 11 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Sub-task | RDTHANA-121 | 30818 | [QA] Create Test Case Update survey step1(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 09/Sep/25 11:26 AM | 24/Nov/25 10:14 AM | [8 empty] | มาจาก Sprint 11 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Sub-task | RDTHANA-120 | 30816 | [QA] Create Test Case Create survey (FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 09/Sep/25 11:25 AM | 24/Nov/25 10:13 AM | [8 empty] | มาจาก Sprint 11 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Sub-task | RDTHANA-119 | 30814 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 09/Sep/25 11:24 AM | 18/Nov/25 11:46 AM | [8 empty] | มาจาก Sprint 11 | To Do |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Sub-task | RDTHANA-118 | 30812 | [QA] Create Test Case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 09/Sep/25 11:23 AM | 09/Sep/25 11:23 AM | [8 empty] | มาจาก Sprint 11 | To Do |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Sub-task | RDTHANA-115 | 30806 | [QA] Create Test Case Widget Feature: Add 'Service' Type (RR backoffice) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 09/Sep/25 11:22 AM | 10/Nov/25 5:00 PM | [8 empty] | มาจาก Sprint 11 | Done |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | RDTHANA-107 | 30691 | [Dev][RD][APH] Cronjob update survey to expired | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 04/Sep/25 4:56 PM | 24/Nov/25 10:25 AM | 26/Sep/25 12:00 AM | 3 | rr-aphrodite |  |  |  |  | 0 | มาจาก Sprint 11 | Ready To Test | 21600 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | RDTHANA-106 | 30689 | [Dev][RD][Service][CMS API] Create service filter api | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 04/Sep/25 4:08 PM | 18/Nov/25 10:40 AM | 11/Sep/25 12:00 AM | 3 | cms-api | No-QA |  |  |  | 0 | มาจาก Sprint 11 | Ready To Test | 18000 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | RDTHANA-105 | 30687 | [Dev][RD][APH][CT] CleverTap Survey Event | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Done |  | 04/Sep/25 3:56 PM | 28/Nov/25 10:24 AM |  | 5 | [5 empty] | 0 | มาจาก Sprint 11 | Ready To Test | 86400 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | RDTHANA-90 | 30622 | [Dev][RD][Section][BOF][QA] Enhance Section Feature: Add new widget types | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Sep/25 9:16 PM | 18/Nov/25 10:40 AM |  | 0 | [6 empty] | มาจาก Sprint 11 | Ready To Test |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | RDTHANA-88 | 30620 | [Dev][RD][Widget][BOF] Enhance Widget Feature: Add 'Service' Type | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 02/Sep/25 8:56 PM | 21/Nov/25 12:32 AM | 11/Sep/25 12:00 AM | 5 | rr-backoffice |  |  |  |  | 0 | มาจาก Sprint 11 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | RDTHANA-86 | 30618 | [Dev][RD][BOF] Update survey Step 5: Survey Appearance (Thank You) (FE&BE) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 02/Sep/25 8:44 PM | 24/Nov/25 10:22 AM | 15/Sep/25 12:00 AM | 2 | rr-backoffice |  |  |  |  | 0 | มาจาก Sprint 11 | Ready To Test | 10800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | RDTHANA-81 | 30606 | [Dev][RD][BOF] Change survey status (FE&BE) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 02/Sep/25 3:26 PM | 24/Nov/25 10:12 AM | 16/Sep/25 12:00 AM | 3 | rr-backoffice |  |  |  |  | 0 | มาจาก Sprint 11 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | RDTHANA-80 | 30604 | [Dev][RD][BOF] Update survey Step 5: Survey Appearance (Input E-mail) (FE&BE) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 02/Sep/25 3:25 PM | 24/Nov/25 10:20 AM | 15/Sep/25 12:00 AM | 2 | rr-backoffice |  |  |  |  | 0 | มาจาก Sprint 11 | Ready To Test | 10800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | RDTHANA-79 | 30602 | [Dev][RD][BOF] Update survey step5.2(FE&BE) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 02/Sep/25 3:24 PM | 25/Nov/25 10:17 AM | 12/Sep/25 12:00 AM | 2 | rr-backoffice |  |  |  |  | 0 | มาจาก Sprint 11 | Ready To Test | 10800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | RDTHANA-74 | 30366 | [Dev][RD][BOF] Update survey step4.2(FE&BE) | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 26/Aug/25 7:15 PM | 25/Nov/25 10:17 AM |  | 2 | rr-backoffice |  |  |  |  | 0 | มาจาก Sprint 11 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | RDTHANA-73 | 30364 | [Dev][RD][BOF] Download Individual Survey Report (FE&BE) | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 26/Aug/25 7:15 PM | 24/Nov/25 10:18 AM | 18/Sep/25 12:00 AM | 5 | rr-backoffice |  |  |  |  | 0 | มาจาก Sprint 11 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | RDTHANA-72 | 30362 | [Dev][RD][BOF] Update survey step5.1(FE&BE) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 26/Aug/25 7:15 PM | 24/Nov/25 10:18 AM | 12/Sep/25 12:00 AM | 3 | rr-backoffice |  |  |  |  | 0 | มาจาก Sprint 11 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | RDTHANA-71 | 30360 | [Dev][RD][BOF] Update survey step4.1(FE&BE) | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 26/Aug/25 7:15 PM | 24/Nov/25 10:17 AM |  | 8 | rr-backoffice |  |  |  |  | 0 | มาจาก Sprint 11 | Ready To Test | 86400 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | RDTHANA-70 | 30358 | [Dev][RD][BOF] Update survey step3(FE&BE) | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 26/Aug/25 7:14 PM | 24/Nov/25 10:16 AM |  | 5 | rr-backoffice |  |  |  |  | 0 | มาจาก Sprint 11 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | RDTHANA-69 | 30356 | [Dev][RD][BOF] Update survey step2(FE&BE) | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 26/Aug/25 7:09 PM | 24/Nov/25 10:12 AM | 16/Sep/25 12:00 AM | 3 | rr-backoffice |  |  |  |  | 0 | มาจาก Sprint 11 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | RDTHANA-68 | 30354 | [Dev][RD][BOF] View Survey Report (FE&BE) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 26/Aug/25 7:09 PM | 24/Nov/25 10:10 AM | 17/Sep/25 12:00 AM | 3 | rr-backoffice |  |  |  |  | 0 | มาจาก Sprint 11 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | RDTHANA-67 | 30352 | [Dev][RD][BOF] View Survey List (FE&BE) | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 26/Aug/25 7:09 PM | 24/Nov/25 10:15 AM |  | 5 | rr-backoffice |  |  |  |  | 0 | มาจาก Sprint 11 | Ready To Test | 86400 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | RDTHANA-66 | 30350 | [Dev][RD][BOF] Update survey step1(FE&BE) | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 26/Aug/25 7:09 PM | 24/Nov/25 10:14 AM | 15/Sep/25 12:00 AM | 3 | rr-backoffice |  |  |  |  | 0 | มาจาก Sprint 11 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | RDTHANA-65 | 30348 | [Dev][RD][BOF] Create survey (FE&BE) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 26/Aug/25 7:08 PM | 24/Nov/25 10:13 AM | 11/Sep/25 12:00 AM | 5 | rr-backoffice |  |  |  |  | 0 | มาจาก Sprint 11 | Ready To Test | 43200 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | RDTHANA-43 | 30086 | [DEV][RD][DasHaus][BFF] Verify the API to validate matching account | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 22/Aug/25 6:12 AM | 18/Nov/25 11:47 AM |  | 1 | BFF | [5 empty] | มาจาก Sprint 11 | Ready To Test |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Story | RDAPS-160 | 29972 | [DEV][RD][SSO-Backoffice] Disable SEO tracking | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 20/Aug/25 11:21 AM | 18/Nov/25 10:02 AM | 04/Sep/25 12:00 AM | 1 | [5 empty] | 7200 |  |  |  | [Dev][All project]Sprint 6 | [Dev][All project]Sprint 7 | [Dev][All Project] Sprint 9 | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12
Story | RDTHANA-20 | 29950 | [Dev][RD][APH] Enhance check token | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 19/Aug/25 7:46 PM | 18/Nov/25 10:40 AM |  | 3 | [5 empty] | 0 | มาจาก Sprint 11 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 11 | [Dev][RD][Thana] Sprint 12
Bug | DEVRDSUP-95 | 29929 | [SUP-54][Noti] Whole NBO page gets frozen when user uses "internal link" and tries to search for internal content. | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Lowest | Resolved |  | 19/Aug/25 4:47 PM | 18/Nov/25 10:02 AM | 19/Sep/25 12:00 AM | 3 | [9 empty] | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 11 | [Dev][All Project] Sprint 12
Task | RDAPS-138 | 29216 | [Dev][RD][PROD] Data migration for existing rewards | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 04/Aug/25 4:00 PM | 24/Nov/25 11:12 PM | 01/Oct/25 12:00 AM | 1 | No-QA | rewards-db |  |  |  | 1800 |  |  |  | [Dev][All Project] Sprint 12
Story | DEVRDCT-143 | 28765 | [Dev][RD] Load Test Performance for Webhook Push Coupons API | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | To Do |  | 24/Jul/25 8:39 PM | 25/Nov/25 2:44 PM | [11 empty] | [Dev][RD][CT] Sprint 12

## Summarize Sprint 11
Column 1 | Total Stories Point | Total Manhour | Point Done | Manhour Done | Note
3 Nov - 14 Nov
Dev Resource Available | 19 | 565.5
Meeting Planned |  | 198 |  |  | Ref
Additional Meeting |  | 37.5 |  |  | Ref
Deployment |  | 9 |  |  | 3 ครั้ง 1. 4 คน 2. 2 คน 3. 3 คน
Development Sprint Total | 284 | 132 | 44 | 22
Ad-hoc Mid Sprint | 6 | 0 | 0 | 0 | 2 tasks
Requirement changes after refinement? | 0 | 0 | 0 | 0 | 0 tasks
Aek | 16 | 0 | 3 | 0
A | 14 | 4 | 2 | 4
Aom | 1 | 0 | 0 | 0
Zan | 5 | 0 | 0 | 0
Mai | 41 | 8 | 10 | 0
Mac | 51 | 0 | 3 | 0
Mos | 43 | 8 | 9 | 0
Jack | 13 | 16 | 0 | 0
Art | 0 | 0 | 0 | 0
Kae | 17 | 11 | 3 | 0
Nim | 39 | 34 | 3 | 0
Arm | 17 | 50 | 6 | 18
| System Architech |  |  |  | Permanent Dev. |  |  | Outsources
Projects (Stories Points) | Aek | Zan | Aom | Jack | A | Art | Mai | Kae | Mac | Nim | Mos | Arm
Das Haus - Thana City & Das Haus | 0 | 5 | 1 | 8 | 12 | 0 | 35 | 8 | 44 | 16 | 38 | 0
E-commerce 1.1. E-Commerce x Shopify Plus 1.2. Shopify:Snackmaker 1.3. Shopify: Turtle Delivery 1.4. Shopify: Turtle Delivery | 8 | 0 | 0 | 5 | 2 | 0 | 3 | 3 | 3 | 2 | 5 | 6
CleverTap - MKT Automation Tool | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 8
Adjust Integration | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 4 | 0 | 3
Adhoc - Non-Epics - Turtle Display club tier on POS - Data Mart Migration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Support Incidents | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| System Architech |  |  |  | Permanent Dev. |  |  | Outsources
Projects (Manhour) | Aek | Zan | Aom | Jack | A | Art | Mai | Kae | Mac | Nim | Mos | Arm
Das Haus - Thana City & Das Haus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E-commerce 1.1. E-Commerce x Shopify Plus 1.2. Shopify:Snackmaker 1.3. Shopify: Turtle Delivery 1.4. Shopify: Turtle Delivery | 0 | 0 | 0 | 16 | 4 | 0 | 0 | 0 | 0 | 0 | 8 | 18
CleverTap - MKT Automation Tool | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 24
Adjust Integration | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 11 | 0 | 0 | 0 | 8
Adhoc - Non-Epics - Turtle Display club tier on POS - Data Mart Migration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Support Incidents | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 11
Issue Type | Issue key | Issue id | Summary | Assignee | Assignee Id | Reporter | Reporter Id | Priority | Status | Resolution | Created | Updated | Due date | Custom field (Story Points) | Labels | Labels | Labels | Original estimate | Sprint Movement | Sprint 10 | Note | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint
Story | RDTHANA-385 | 34267 | [Dev][RD][CMS] Add return 'icon_shadow_color' and 'has_icon_shadow' to services filter api | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 14/Nov/25 2:05 PM | 14/Nov/25 4:01 PM | [9 empty] | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-384 | 34265 | [Dev][RD][BFF] Add return 'icon_shadow_color' and 'has_icon_shadow' to section contents api | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 14/Nov/25 2:00 PM | 14/Nov/25 4:01 PM | [9 empty] | [Dev][RD][Thana] Sprint 11
Sub-task | DEVRDECOM-169 | 34143 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 12/Nov/25 3:44 PM | 12/Nov/25 3:44 PM | [9 empty] | [Dev][RD][Ecom] Sprint 11
Sub-task | DEVRDECOM-168 | 34141 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Progress |  | 12/Nov/25 3:44 PM | 12/Nov/25 3:44 PM | [9 empty] | [Dev][RD][Ecom] Sprint 11
Sub-task | DEVRDECOM-167 | 34139 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Review |  | 12/Nov/25 3:44 PM | 12/Nov/25 3:44 PM | [9 empty] | [Dev][RD][Ecom] Sprint 11
Sub-task | DEVRDECOM-166 | 34137 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 12/Nov/25 3:43 PM | 12/Nov/25 3:43 PM | [9 empty] | [Dev][RD][Ecom] Sprint 11
Sub-task | DEVRDECOM-165 | 34135 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Review |  | 12/Nov/25 3:43 PM | 12/Nov/25 3:44 PM | [9 empty] | [Dev][RD][Ecom] Sprint 11
Sub-task | DEVRDADJ-68 | 34035 | [QA] Test Execution - Integrate delete deeplink when product expired | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | To Do |  | 11/Nov/25 11:25 AM | 11/Nov/25 11:25 AM | [9 empty] | [Dev][RDAdjust] Sprint 11
Sub-task | DEVRDADJ-67 | 34033 | [QA] Test Execution - Integrate error notification with Discord | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | To Do |  | 11/Nov/25 11:24 AM | 11/Nov/25 11:25 AM | [9 empty] | [Dev][RDAdjust] Sprint 11
Sub-task | DEVRDADJ-66 | 34031 | [QA] Test Execution - Create cronjob to remove unused deeplink | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | To Do |  | 11/Nov/25 11:13 AM | 11/Nov/25 11:25 AM | [9 empty] | [Dev][RDAdjust] Sprint 11
Sub-task | DEVRDADJ-65 | 34029 | [QA] Test Execution - Create new endpoint to delete deeplink | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | To Do |  | 11/Nov/25 11:00 AM | 11/Nov/25 11:25 AM | [9 empty] | [Dev][RDAdjust] Sprint 11
Sub-task | DEVRDECOM-164 | 33845 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 10/Nov/25 9:50 AM | 10/Nov/25 9:50 AM | [9 empty] | [Dev][RD][Ecom] Sprint 11
Sub-task | DEVRDECOM-163 | 33843 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 10/Nov/25 9:50 AM | 10/Nov/25 9:50 AM | [9 empty] | [Dev][RD][Ecom] Sprint 11
Sub-task | DEVRDECOM-162 | 33841 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 10/Nov/25 9:49 AM | 10/Nov/25 9:50 AM | [9 empty] | [Dev][RD][Ecom] Sprint 11
Sub-task | DEVRDECOM-161 | 33839 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 10/Nov/25 9:49 AM | 10/Nov/25 9:49 AM | [9 empty] | [Dev][RD][Ecom] Sprint 11
Bug | RDTHANA-381 | 33795 | [S4][Widget][Type Service][Step2] Add services list shows other status, not only active | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Closed |  | 07/Nov/25 4:42 PM | 12/Nov/25 12:10 PM | [9 empty] | [Dev][RD][Thana] Sprint 11
Story | DEVRDECOM-159 | 33793 | [DEV][RD][Eco][Ecommerce-Shopify] Enhance CronJob to support scalable | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 07/Nov/25 4:14 PM | 12/Nov/25 1:43 PM | 10/Nov/25 12:00 AM | 2 |  |  |  | 28800 |  |  |  | [Dev][RD][Ecom] Sprint 11
Sub-task | DEVRDCT-304 | 33790 | [QA] Create test case API unbind endpoint support line_pay | Lucas - Saksorn Srisak | 712020:289e7d91-50e6-438c-9b32-23b14017a585 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 07/Nov/25 1:24 PM | 07/Nov/25 1:24 PM | [9 empty] | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11
Sub-task | RDTHANA-380 | 33783 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | To Do |  | 07/Nov/25 10:15 AM | 11/Nov/25 1:50 PM | [9 empty] | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Sub-task | RDTHANA-379 | 33781 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | To Do |  | 07/Nov/25 10:15 AM | 11/Nov/25 1:41 PM | [9 empty] | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Sub-task | DEVRDADJ-64 | 33778 | [QA] Create Test Case - Integrate delete deeplink when product expired | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 07/Nov/25 9:53 AM | 11/Nov/25 11:41 AM | [9 empty] | [Dev][RDAdjust] Sprint 11
Sub-task | DEVRDADJ-63 | 33776 | [QA] Create Test Case - Create cronjob to remove unused deeplink | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 07/Nov/25 9:50 AM | 11/Nov/25 11:13 AM | [9 empty] | [Dev][RDAdjust] Sprint 11
Sub-task | DEVRDADJ-62 | 33774 | [QA] Create Test Case - Integrate error notification with Discord | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 07/Nov/25 9:50 AM | 11/Nov/25 11:24 AM | [9 empty] | [Dev][RDAdjust] Sprint 11
Sub-task | DEVRDADJ-61 | 33772 | [QA] Create Test Case - Create new endpoint to delete deeplink | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 07/Nov/25 9:49 AM | 11/Nov/25 10:59 AM | [9 empty] | [Dev][RDAdjust] Sprint 11
Sub-task | DEVRDCT-303 | 33734 | [QA] (Staging) Test execution collect Reward Catalog data for uploading to CleverTap | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 06/Nov/25 6:10 PM | 06/Nov/25 6:10 PM | [9 empty] | [Dev][CT] Sprint 11
Sub-task | DEVRDCT-302 | 33732 | [QA] Create test case collect Reward Catalog data for uploading to CleverTap | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 06/Nov/25 6:09 PM | 14/Nov/25 9:59 AM | [9 empty] | [Dev][CT] Sprint 11
Sub-task | DEVRDCT-301 | 33730 | [QA] (Staging) Test execution API to upload the Catalog to CleverTap | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | In Progress |  | 06/Nov/25 6:07 PM | 14/Nov/25 9:59 AM | [9 empty] | [Dev][CT] Sprint 11
Sub-task | DEVRDCT-300 | 33728 | [QA] Create test case API to upload the Catalog to CleverTap | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 06/Nov/25 6:06 PM | 14/Nov/25 9:59 AM | [9 empty] | [Dev][CT] Sprint 11
Sub-task | DEVRDCT-299 | 33726 | [QA] (Staging) Test execution API unbind endpoint support line_pay | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 06/Nov/25 6:01 PM | 07/Nov/25 1:24 PM | [9 empty] | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11
Sub-task | DEVRDCT-298 | 33724 | [QA] (Staging) Test execution Line Pay Unbound Event | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 06/Nov/25 5:54 PM | 06/Nov/25 5:57 PM | [9 empty] | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11
Sub-task | DEVRDCT-297 | 33722 | [QA] Create test case Line Pay Unbound Event | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 06/Nov/25 5:54 PM | 06/Nov/25 5:54 PM | [9 empty] | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11
Sub-task | DEVRDCT-296 | 33720 | [QA] (Staging) Test execution API for widget type = clevertab_native_display | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 06/Nov/25 5:50 PM | 06/Nov/25 5:50 PM | [9 empty] | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11
Sub-task | DEVRDCT-295 | 33718 | [QA] Create test case Sections/Widgets APIs to support widget type = clevertab_native_display | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 06/Nov/25 5:49 PM | 06/Nov/25 5:50 PM | [9 empty] | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11
Sub-task | DEVRDCT-294 | 33716 | [QA] (Staging) Test execution add Widget type = "CleverTap : Native display" | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 06/Nov/25 5:41 PM | 06/Nov/25 5:41 PM | [9 empty] | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11
Sub-task | DEVRDCT-293 | 33714 | [QA] Create test case add Widget type = "CleverTap : Native display" | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 06/Nov/25 5:40 PM | 06/Nov/25 5:40 PM | [9 empty] | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11
Sub-task | DEVRDCT-292 | 33712 | [QA](Staging) Test execution SSO-User binding line pay | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 06/Nov/25 5:38 PM | 11/Nov/25 10:50 AM | [9 empty] | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11
Bug | DEVRDCT-291 | 33709 | [S3][Survey][Thank you][Incentive Point] when set survey Have Incentive Point, Step 4 not show format Thank you with intentive | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Resolved |  | 06/Nov/25 4:55 PM | 07/Nov/25 10:43 AM | [9 empty] | [Dev][RD][Thana] Sprint 11
Bug | RDTHANA-378 | 33707 | [S3][Survey][Survey list] Status NOT update after survey is expire | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Resolved |  | 06/Nov/25 4:15 PM | 07/Nov/25 4:43 PM | [9 empty] | [Dev][RD][Thana] Sprint 11
Bug | RDTHANA-377 | 33695 | [S4][Survey][Step 2] Club Status(Active/Inavtive) NOT update after change from HR-solution | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Resolved |  | 06/Nov/25 1:54 PM | 10/Nov/25 4:12 PM | [9 empty] | [Dev][RD][Thana] Sprint 11
Bug | RDTHANA-376 | 33689 | [S4][BOF][Section][Widget setting] Add widget warning case wording mismatchs from Figma | Art: Narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Closed |  | 06/Nov/25 10:49 AM | 12/Nov/25 10:44 AM |  | 1 | [7 empty] | [Dev][RD][Thana] Sprint 11
Story | DEVRDECOM-158 | 33687 | [DEV][RD][Eco][Shopify-Theme] Custom theme – Show First & Last Name on Account page | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 06/Nov/25 10:02 AM | 11/Nov/25 1:44 PM |  | 1 | [7 empty] | [Dev][RD][Ecom] Sprint 11
Story | DEVRDECOM-157 | 33679 | [DEV][RD][Eco][Ecommerce-Shopify] Update Firstname / Lastname (Set as default in shopify) to database | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 06/Nov/25 9:19 AM | 14/Nov/25 9:25 AM |  | 1 |  |  |  | 7200 |  |  |  | [Dev][RD][Ecom] Sprint 11
Bug | RDTHANA-375 | 33646 | [S4][BOF][Section][Screen location setting] "Submit" button of add widget modal is not dimmed when incomplete form | Art: Narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Closed |  | 06/Nov/25 1:08 AM | 12/Nov/25 10:51 AM | 07/Nov/25 12:00 AM | 2 | [7 empty] | [Dev][RD][Thana] Sprint 11
Bug | RDTHANA-374 | 33644 | [S4][BOF][Section][Screen location setting] Add screen successful toast wording not matchs the Figma | Art: Narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Closed |  | 06/Nov/25 12:26 AM | 12/Nov/25 11:00 AM | 06/Nov/25 12:00 AM | 1 | [7 empty] | [Dev][RD][Thana] Sprint 11
Bug | RDTHANA-373 | 33643 | [S4][BOF][Section][Screen location setting] Dropdown list does not sorted by status or alphabet | Art: Narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Closed |  | 05/Nov/25 11:54 PM | 12/Nov/25 11:24 AM | 06/Nov/25 12:00 AM | 2 | [7 empty] | [Dev][RD][Thana] Sprint 11
Bug | RDTHANA-372 | 33640 | [S4][BOF][Section][Screen location setting] Create/Edit section step2 does not has {Internal name} on section header | Art: Narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Closed |  | 05/Nov/25 9:56 PM | 12/Nov/25 12:10 PM | 06/Nov/25 12:00 AM | 1 | [7 empty] | [Dev][RD][Thana] Sprint 11
Bug | RDTHANA-371 | 33639 | [S4][RR Backoffice][Surveys] Default color code as not show same Figma | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | THUNDER(QA): PAWICH | 712020:83ff944e-9677-453f-b053-40e92520d905 | Medium | Rejected |  | 05/Nov/25 5:55 PM | 07/Nov/25 1:12 PM | [9 empty] | [Dev][RD][Thana] Sprint 11
Bug | RDTHANA-370 | 33638 | [S4][Backoffice][Widget][UI] Submit button not dimmed and club not show status | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Low | Closed |  | 05/Nov/25 5:20 PM | 11/Nov/25 10:38 AM | [9 empty] | [Dev][RD][Thana] Sprint 11
Story | DEVRDADJ-60 | 33631 | [DEV][RD][BOF] Add more parameter in adjust generate deeplink api | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 05/Nov/25 2:49 PM | 14/Nov/25 2:13 PM |  | 1 |  |  |  | 7200 |  |  |  | [Dev][RDAdjust] Sprint 11
Story | DEVRDADJ-59 | 33630 | [DEV][RD][LNF] Add more parameter in adjust generate deeplink API | Art: Narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 05/Nov/25 2:49 PM | 14/Nov/25 2:13 PM |  | 1 | [7 empty] | [Dev][RDAdjust] Sprint 11
Sub-task | DEVRDECOM-156 | 33619 | [QA] Test execution | GIFT : Netnapa Sarawan | 712020:de8942b7-86cb-492b-95e7-5475add8a3f1 | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 05/Nov/25 1:18 PM | 10/Nov/25 9:45 AM | [9 empty] | [Dev][RD][Ecom] Sprint 11
Sub-task | DEVRDECOM-155 | 33617 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 05/Nov/25 1:18 PM | 05/Nov/25 3:24 PM | [9 empty] | [Dev][RD][Ecom] Sprint 11
Sub-task | DEVRDECOM-154 | 33615 | [QA] Test execution | GIFT : Netnapa Sarawan | 712020:de8942b7-86cb-492b-95e7-5475add8a3f1 | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 05/Nov/25 1:17 PM | 10/Nov/25 9:44 AM | [9 empty] | [Dev][RD][Ecom] Sprint 11
Sub-task | DEVRDECOM-153 | 33613 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 05/Nov/25 1:17 PM | 05/Nov/25 3:24 PM | [9 empty] | [Dev][RD][Ecom] Sprint 11
Story | DEVRDECOM-152 | 33514 | [DEV][RD][Eco][Webhook] Setup webhook and mapping API Gateway | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 05/Nov/25 8:54 AM | 05/Nov/25 11:44 AM |  | 2 | No-QA | [6 empty] | [Dev][RD][Ecom] Sprint 11
Sub-task | DEVRDCT-289 | 33481 | [QA](Staging) Test execution LINE_PAY_BINDING Event push to CT (WEB) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 04/Nov/25 6:01 PM | 04/Nov/25 6:01 PM | [9 empty] | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11
Sub-task | DEVRDCT-288 | 33479 | [QA] Create test case LINE_PAY_BINDING Event push to CT (WEB) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 04/Nov/25 6:00 PM | 04/Nov/25 6:00 PM | [9 empty] | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11
Sub-task | DEVRDCT-287 | 33477 | [QA](Staging) Test execution LINE_PAY_BINDING Event push to CT (API) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 04/Nov/25 5:59 PM | 04/Nov/25 6:01 PM | [9 empty] | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11
Sub-task | DEVRDCT-286 | 33475 | [QA] Create test case LINE_PAY_BINDING Event push to CT (API) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 04/Nov/25 5:59 PM | 04/Nov/25 6:00 PM | [9 empty] | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11
Sub-task | DEVRDCT-285 | 33473 | [QA](Staging) Line OA and Friend event to CleverTap(API) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 04/Nov/25 5:49 PM | 04/Nov/25 5:49 PM | [9 empty] | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11
Sub-task | DEVRDCT-284 | 33467 | - |  |  | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 04/Nov/25 5:47 PM | 04/Nov/25 5:47 PM | [9 empty] | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11
Sub-task | DEVRDCT-283 | 33465 | [QA](Staging) Line OA and Friend event to CleverTap(WEB) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 04/Nov/25 5:46 PM | 04/Nov/25 5:46 PM | [9 empty] | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11
Sub-task | DEVRDCT-282 | 33463 | [QA](Staging) Test execution API binding endpoint support line_pay | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 04/Nov/25 5:27 PM | 07/Nov/25 1:25 PM | [9 empty] | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11
Sub-task | RDTHANA-366 | 33451 | [QA][Survey](Statging) Test execution change status flow to validate required fields | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 04/Nov/25 3:25 PM | 04/Nov/25 3:25 PM | [9 empty] | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Sub-task | RDTHANA-365 | 33449 | [QA][Survey] Create test case change status flow to validate required fields | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 04/Nov/25 3:24 PM | 04/Nov/25 3:25 PM | [9 empty] | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Sub-task | RDTHANA-364 | 33445 | [QA](Staging) Test execution Separate Welcome message pop up setting between application and website | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 04/Nov/25 3:18 PM | 04/Nov/25 3:21 PM | [9 empty] | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Sub-task | RDTHANA-363 | 33443 | [QA] Create test case Separate Welcome message pop up setting between application and website | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 04/Nov/25 3:18 PM | 04/Nov/25 3:18 PM | [9 empty] | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Sub-task | RDTHANA-362 | 33441 | [QA](STG+UAT) Test execution Survey Event CT | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 04/Nov/25 3:16 PM | 04/Nov/25 3:36 PM | [9 empty] | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Sub-task | RDTHANA-361 | 33439 | [QA] Create Test case Survey Event CT | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 04/Nov/25 3:16 PM | 13/Nov/25 2:25 PM | [9 empty] | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Sub-task | RDTHANA-360 | 33436 | [QA](Statging) Test execution HR Solution Widget type Services | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | In Progress |  | 04/Nov/25 3:05 PM | 07/Nov/25 4:46 PM | [9 empty] | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | DEVRDECOM-151 | 33383 | [DEV][RD][Eco] Change image demo in create/edit service page | Art: Narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 04/Nov/25 9:48 AM | 06/Nov/25 9:44 AM | 04/Nov/25 12:00 AM | 1 |  |  |  | 3600 |  |  |  | [Dev][RD][Ecom] Sprint 11
Story | DEVRDECOM-150 | 33348 | [DEV][RD][Eco][Ecommerce-Shopify] Change Logout Behavior on Website (Shopify) | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 03/Nov/25 9:21 AM | 11/Nov/25 3:52 PM | 13/Nov/25 12:00 AM | 5 | ecommerce-shopify-api |  |  | 57600 |  |  |  | [Dev][RD][Ecom] Sprint 11
Story | DEVRDECOM-149 | 33347 | [DEV][RD][Eco][DAS HAUS][Ecommerce-Shopify] New Sequence Login and Join Club Flow | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 03/Nov/25 9:17 AM | 12/Nov/25 10:03 AM | 04/Nov/25 12:00 AM | 3 | rr-ecommerce-shopify | [6 empty] | [Dev][RD][Ecom] Sprint 11
Story | DEVRDECOM-148 | 33346 | [DEV][RD][Eco][Ecommerce-Shopify] Auto login - not replace updated name in Shopify | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 03/Nov/25 9:15 AM | 14/Nov/25 9:25 AM | 05/Nov/25 12:00 AM | 5 | rr-ecommerce-shopify |  |  | 57600 |  |  |  | [Dev][RD][Ecom] Sprint 11
Story | DEVRDECOM-147 | 33345 | [DEV][RD][Eco][Ecommerce-Shopify] Auto login - Do not send address to shopify | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 03/Nov/25 9:06 AM | 06/Nov/25 10:17 AM | 04/Nov/25 12:00 AM | 1 | rr-ecommerce-shopify |  |  | 7200 |  |  |  | [Dev][RD][Ecom] Sprint 11
Story | DEVRDECOM-146 | 33344 | [DEV][RD]Eco][Ecommerce-Shopify] Auto login - If SSO user don't have name send to Shopify as blank | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 03/Nov/25 9:04 AM | 06/Nov/25 10:17 AM | 04/Nov/25 12:00 AM | 1 | rr-ecommerce-shopify |  |  | 7200 |  |  |  | [Dev][RD][Ecom] Sprint 11
Story | DEVRDADJ-57 | 33343 | [DEV][RD][RRS] Integrate delete deeplink when product expired | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 02/Nov/25 11:10 PM | 14/Nov/25 2:13 PM |  | 3 | link-notify |  |  | 28800 |  |  |  | [Dev][RDAdjust] Sprint 11
Story | DEVRDADJ-56 | 33342 | [DEV][RD][LNF] Create new endpoint to delete deeplink | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 02/Nov/25 10:54 PM | 14/Nov/25 2:13 PM |  | 3 | link-notify |  |  | 39600 |  |  |  | [Dev][RDAdjust] Sprint 11
Story | DEVRDADJ-55 | 33338 | [DEV][RD][LNF] Integrate error notification with Discord | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 02/Nov/25 2:59 PM | 14/Nov/25 4:03 PM |  | 3 | link-notify | No-QA |  | 28800 |  |  |  | [Dev][RDAdjust] Sprint 11
Story | DEVRDADJ-54 | 33337 | [DEV][RD][LNF] Create cronjob to remove unused deeplink | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 02/Nov/25 2:46 PM | 14/Nov/25 2:13 PM | 11/Nov/25 12:00 AM | 3 | link-notify |  |  | 28800 |  |  |  | [Dev][RDAdjust] Sprint 11
Story | DEVRDCT-277 | 33336 | [DEV][RD][RRS] Implement a function to collect Reward Catalog data for uploading to CleverTap | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready To Test |  | 02/Nov/25 8:55 AM | 14/Nov/25 2:13 PM |  | 5 | rr-scheduler |  |  | 86400 |  |  |  | [Dev][CT] Sprint 11
Story | DEVRDCT-276 | 33335 | [DEV][RD][CT] Implement API to upload the Catalog to CleverTap | Arm:Worawat Chotipongchoawalit | 712020:2195d849-5cdb-4ec8-866f-e82a3528bff7 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready To Test |  | 02/Nov/25 8:50 AM | 14/Nov/25 2:13 PM | 11/Nov/25 12:00 AM | 8 | CleverTap |  |  | 86400 |  |  |  | [Dev][CT] Sprint 11
Story | DEVRDECOM-145 | 33275 | [DEV][RD[Eco][Turtle][POC] Dynamic Section by Customer Location | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Progress |  | 31/Oct/25 12:47 PM | 10/Nov/25 2:56 PM |  | 5 |  |  |  |  | มาจาก Sprint 10 | In Progress |  | [Dev][RD][Ecom] Sprint 10 | [Dev][RD][Ecom] Sprint 11
Story | RDTHANA-353 | 33197 | [Dev][RD][Survey Web] Remove Survey web from SEO | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 28/Oct/25 1:53 PM | 05/Nov/25 1:59 PM |  | 2 | rr-aphrodite |  |  |  | มาจาก Sprint 10 | Ready to Staging |  | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-344 | 32939 | [DEV][RD][BFF] Enhance change condition for is_enable_opt_in flag | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 21/Oct/25 5:45 PM | 05/Nov/25 1:59 PM | 22/Oct/25 12:00 AM | 1 |  |  |  | 0 | มาจาก Sprint 10 | Ready To Test | 3600 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-343 | 32938 | [DEV][RD][Exclusive Store API] Enhance get club detail with BU setting | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 21/Oct/25 5:28 PM | 05/Nov/25 1:59 PM | 22/Oct/25 12:00 AM | 2 |  |  |  | 0 | มาจาก Sprint 10 | Ready To Test | 10800 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-341 | 32920 | [Dev][RD][BFF] Create an API to Get Clubs with filtering options | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready To Test |  | 21/Oct/25 4:00 PM | 05/Nov/25 1:59 PM | 24/Oct/25 12:00 AM | 3 | BFF | mid-sprint |  | 0 | มาจาก Sprint 10 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-340 | 32919 | [Dev][RD][EXS] Create an API to Get Clubs with filtering options | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready To Test |  | 21/Oct/25 4:00 PM | 05/Nov/25 1:59 PM | 22/Oct/25 12:00 AM | 3 | exclusive-store-api | mid-sprint |  | 0 | มาจาก Sprint 10 | Ready To Test | 43200 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Sub-task | RDTHANA-339 | 32905 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | In Progress |  | 21/Oct/25 1:43 PM | 03/Nov/25 2:32 PM | [6 empty] | มาจาก Sprint 10 | In Progress |  | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-335 | 32813 | [Dev][RD][BFF] Enhance Club Binding API to support popup display separately for app and web | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 20/Oct/25 2:24 PM | 14/Nov/25 2:13 PM | 29/Oct/25 12:00 AM | 3 |  |  |  | 0 | มาจาก Sprint 10 | Ready to Staging | 28800 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | DEVRDCT-270 | 32786 | [DEV][RD][SSO-User] Enhance platform unbind endpoint support line_pay | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 20/Oct/25 9:52 AM | 14/Nov/25 2:13 PM | 21/Oct/25 12:00 AM | 3 |  |  |  |  | มาจาก Sprint 10 | Ready To Test |  | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11
Story | DEVRDCT-269 | 32785 | [DEV][RD][RLP][API] Line Pay Unbound Event | Art: Narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 20/Oct/25 9:30 AM | 14/Nov/25 2:13 PM | 21/Oct/25 12:00 AM | 3 |  |  |  | 0 | มาจาก Sprint 10 | Ready to Staging | 28800 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11
Story | RDTHANA-333 | 32661 | [DEV][RD][Exclusive Store API][ENH] Enhance BFF to Support Separated Application & Web Settings in Welcome Message | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready To Test |  | 17/Oct/25 2:11 PM | 14/Nov/25 2:13 PM | 24/Oct/25 12:00 AM | 3 | BFF |  |  | 0 | มาจาก Sprint 10 | Ready to Staging | 21600 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-332 | 32659 | [DEV][RD][HRS][ENH] Enhance to separate Welcome message pop up setting between application and website | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready To Test |  | 17/Oct/25 12:04 PM | 14/Nov/25 2:13 PM | 28/Oct/25 12:00 AM | 8 | hr-solution |  |  | 0 | มาจาก Sprint 10 | Ready to Staging | 57600 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | DEVRDCT-265 | 32640 | [Dev][RD][BFF] Enhance Sections/Widgets APIs to support a new widget type | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 16/Oct/25 2:58 PM | 14/Nov/25 1:45 PM | 22/Oct/25 12:00 AM | 3 | BFF |  |  | 0 | มาจาก Sprint 10 | Ready to Staging | 28800 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11
Story | DEVRDCT-264 | 32638 | [Dev][RD][CMS DB] Create migration schemas to support the new widget type | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 16/Oct/25 2:57 PM | 14/Nov/25 1:45 PM | 20/Oct/25 12:00 AM | 1 | cms-database | No-QA | rabbit-cms-api | 0 | มาจาก Sprint 10 | Ready to Staging | 3600 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11
Story | DEVRDCT-263 | 32637 | [Dev][RD][BOF] Enhance Widget to support "Native Display" | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 16/Oct/25 2:56 PM | 14/Nov/25 2:13 PM | 21/Oct/25 12:00 AM | 3 | rr-backoffice |  |  | 0 | มาจาก Sprint 10 | Ready to Staging | 21600 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11
Story | DEVRDCT-262 | 32567 | [DEV][RD][USR] Enhance check duplicate line id for binding line pay | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 16/Oct/25 8:30 AM | 14/Nov/25 2:13 PM |  | 1 | sso-user |  |  |  | มาจาก Sprint 10 | Ready To Test |  | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11
Sub-task | RDTHANA-329 | 32558 | [QA](Staging) Test execution widget type: Club - Benefits & Information | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 15/Oct/25 3:44 PM | 07/Nov/25 9:52 AM | [6 empty] | มาจาก Sprint 10 | To Do |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Sub-task | RDTHANA-328 | 32555 | [QA] (Staging) Test execution Section Feature: Add 'Club - Benefits & Info' Location | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 15/Oct/25 3:32 PM | 06/Nov/25 5:10 PM | [6 empty] | มาจาก Sprint 10 | To Do |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | DEVRDCT-258 | 32213 | [DEV][RD][RLP][WEP] LINE_PAY_BINDING Event push to CT | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 13/Oct/25 5:00 PM | 10/Nov/25 6:18 PM |  | 2 | No-QA |  |  | 0 | มาจาก Sprint 10 | Ready to Staging | 10800 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11
Sub-task | DEVRDECOM-134 | 32148 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Progress |  | 09/Oct/25 11:37 AM | 03/Nov/25 1:35 PM | [6 empty] | มาจาก Sprint 10 | In Progress |  | [Dev][RD][Ecom] Sprint 10 | [Dev][RD][Ecom] Sprint 10 | [Dev][RD][Ecom] Sprint 11
Sub-task | DEVRDECOM-133 | 32146 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 09/Oct/25 11:37 AM | 17/Oct/25 6:00 PM | [6 empty] | มาจาก Sprint 10 | Done |  | [Dev][RD][Ecom] Sprint 10 | [Dev][RD][Ecom] Sprint 10 | [Dev][RD][Ecom] Sprint 11
Sub-task | DEVRDECOM-132 | 32144 | [QA] Test execution | THUNDER(QA): PAWICH | 712020:83ff944e-9677-453f-b053-40e92520d905 | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Progress |  | 09/Oct/25 11:36 AM | 04/Nov/25 2:17 PM | [6 empty] | มาจาก Sprint 10 | To Do |  | [Dev][RD][Ecom] Sprint 10 | [Dev][RD][Ecom] Sprint 10 | [Dev][RD][Ecom] Sprint 11
Sub-task | DEVRDECOM-131 | 32142 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 09/Oct/25 11:36 AM | 17/Oct/25 6:01 PM | [6 empty] | มาจาก Sprint 10 | Done |  | [Dev][RD][Ecom] Sprint 10 | [Dev][RD][Ecom] Sprint 10 | [Dev][RD][Ecom] Sprint 11
Sub-task | DEVRDECOM-130 | 32140 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 09/Oct/25 11:36 AM | 13/Nov/25 12:56 PM | [6 empty] | มาจาก Sprint 10 | To Do |  | [Dev][RD][Ecom] Sprint 10 | [Dev][RD][Ecom] Sprint 10 | [Dev][RD][Ecom] Sprint 11
Sub-task | DEVRDECOM-129 | 32138 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 09/Oct/25 11:36 AM | 21/Oct/25 2:13 PM | [6 empty] | มาจาก Sprint 10 | Done |  | [Dev][RD][Ecom] Sprint 10 | [Dev][RD][Ecom] Sprint 10 | [Dev][RD][Ecom] Sprint 11
Sub-task | DEVRDECOM-128 | 32136 | [QA] Test execution | GIFT : Netnapa Sarawan | 712020:de8942b7-86cb-492b-95e7-5475add8a3f1 | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 09/Oct/25 11:36 AM | 03/Nov/25 8:58 PM | [6 empty] | มาจาก Sprint 10 | To Do |  | [Dev][RD][Ecom] Sprint 10 | [Dev][RD][Ecom] Sprint 10 | [Dev][RD][Ecom] Sprint 11
Sub-task | DEVRDECOM-127 | 32134 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 09/Oct/25 11:36 AM | 21/Oct/25 2:13 PM | [6 empty] | มาจาก Sprint 10 | Done |  | [Dev][RD][Ecom] Sprint 10 | [Dev][RD][Ecom] Sprint 10 | [Dev][RD][Ecom] Sprint 11
Sub-task | RDTHANA-318 | 32088 | [QA] Create Test Case - Enhance sorry page with get deeplink endpoint | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 08/Oct/25 10:19 AM | 03/Nov/25 2:32 PM | [6 empty] | มาจาก Sprint 10 | Done |  | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-317 | 32072 | [Dev][RD][BOF] Improve change status flow to validate required fields | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 07/Oct/25 3:16 PM | 05/Nov/25 1:59 PM | 14/Oct/25 12:00 AM | 5 | rr-backoffice |  |  | 0 | มาจาก Sprint 10 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | DEVRDCT-257 | 32071 | [DEV][RD][RLP][API] LINE_PAY_BINDING Event push to CT | Art: Narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 07/Oct/25 3:13 PM | 14/Nov/25 2:13 PM |  | 5 |  |  |  |  | มาจาก Sprint 10 | Ready to Staging |  | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11
Sub-task | DEVRDCT-256 | 32069 | [QA] Create test case API binding endpoint support line_pay | Lucas - Saksorn Srisak | 712020:289e7d91-50e6-438c-9b32-23b14017a585 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 07/Oct/25 2:26 PM | 07/Nov/25 1:25 PM | [6 empty] | มาจาก Sprint 10 | To Do |  | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11
Sub-task | DEVRDCT-253 | 32062 | [QA] Create test case Line OA and Friend event to CleverTap (API) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 07/Oct/25 2:09 PM | 04/Nov/25 5:49 PM | [6 empty] | มาจาก Sprint 10 | To Do |  | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11
Sub-task | DEVRDCT-252 | 32060 | [QA] Create test case Line OA and Friend event to CleverTap(WEB) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 07/Oct/25 2:04 PM | 04/Nov/25 5:45 PM | [6 empty] | มาจาก Sprint 10 | To Do |  | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11
Sub-task | DEVRDCT-251 | 32058 | [QA](Staging) Test execution sync initial RLP member to RR Line member | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 07/Oct/25 2:03 PM | 04/Nov/25 5:52 PM | [6 empty] | มาจาก Sprint 10 | To Do |  | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11
Story | RDTHANA-313 | 32018 | [DEV][RD][BFF] Get club term and condition endpoint | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 06/Oct/25 2:33 PM | 05/Nov/25 1:59 PM | 10/Oct/25 12:00 AM | 2 | BFF |  |  | 0 | มาจาก Sprint 10 | Ready To Test | 10800 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-312 | 32017 | [DEV][RD][Exclusive API] Get club term and condition endpoint | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 06/Oct/25 2:33 PM | 05/Nov/25 1:59 PM | 10/Oct/25 12:00 AM | 3 | exclusive-store-api |  |  | 0 | มาจาก Sprint 10 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | DEVRDCT-250 | 32004 | [DEV][RD][RLP] Create script to sync initial RLP member to RR Line member | Art: Narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 06/Oct/25 10:03 AM | 10/Nov/25 4:22 PM | 10/Oct/25 12:00 AM | 5 | rlp-middleware |  |  | 0 | มาจาก Sprint 10 | Ready to Staging | 57600 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11
Story | DEVRDECOM-122 | 31988 | [DEV][RD][BOF][Widget] Enhance widget asset for service widget | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 05/Oct/25 10:46 PM | 14/Nov/25 2:13 PM | 09/Oct/25 12:00 AM | 3 | rr-backoffice |  |  |  | มาจาก Sprint 10 | Ready To Test |  | [Dev][RD][Ecom] Sprint 10 | [Dev][RD][Ecom] Sprint 10 | [Dev][RD][Ecom] Sprint 11
Story | DEVRDECOM-121 | 31987 | [DEV][RD][BOF][Service] Enhance create/edit service general form support upload JPG file and setup shadow color | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 05/Oct/25 10:44 PM | 14/Nov/25 2:13 PM | 08/Oct/25 12:00 AM | 2 | rr-backoffice |  |  | 0 | มาจาก Sprint 10 | Ready To Test | 14400 | [Dev][RD][Ecom] Sprint 10 | [Dev][RD][Ecom] Sprint 10 | [Dev][RD][Ecom] Sprint 11
Story | DEVRDECOM-120 | 31986 | [DEV][RD][CMS-API] Migration for support shoping page | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 05/Oct/25 10:43 PM | 14/Nov/25 4:16 PM | 06/Oct/25 12:00 AM | 1 | cms-database |  |  | 0 | มาจาก Sprint 10 | Ready To Test | 3600 | [Dev][RD][Ecom] Sprint 10 | [Dev][RD][Ecom] Sprint 10 | [Dev][RD][Ecom] Sprint 11
Story | DEVRDCT-249 | 31984 | [DEV][RD][RLP][WEB] Sent Line OA and Friend event to CleverTap | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 05/Oct/25 4:45 PM | 10/Nov/25 6:18 PM |  | 3 | No-QA |  |  | 0 | มาจาก Sprint 10 | Ready to Staging | 10800 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11
Story | DEVRDCT-248 | 31983 | [DEV][RD][RLP][API] Sent Line OA and Friend event to CleverTap | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 05/Oct/25 4:45 PM | 10/Nov/25 2:10 PM |  | 3 | No-QA | rlp-middleware |  | 0 | มาจาก Sprint 10 | Ready to Staging | 10800 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11
Story | RDTHANA-311 | 31957 | [DEV][RD][APH] Enhance sorry page with get deeplink endpoint | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 03/Oct/25 5:11 PM | 05/Nov/25 1:59 PM | 08/Oct/25 12:00 AM | 3 | rr-aphrodite |  |  |  | มาจาก Sprint 10 | Ready To Test |  | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | DEVRDECOM-117 | 31949 | [Dev][RD][BOF] Enhance Section Menu (FE&BE) | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 03/Oct/25 3:49 PM | 14/Nov/25 2:13 PM | 08/Oct/25 12:00 AM | 3 | rr-backoffice |  |  | 0 | มาจาก Sprint 10 | Ready To Test | 28800 | [Dev][RD][Ecom] Sprint 10 | [Dev][RD][Ecom] Sprint 10 | [Dev][RD][Ecom] Sprint 11
Story | DEVRDECOM-113 | 31942 | [Dev][RD][BFF] Enhance get sections to support new location | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 03/Oct/25 1:56 PM | 13/Nov/25 3:56 PM | 09/Oct/25 12:00 AM | 2 | BFF |  |  | 0 | มาจาก Sprint 10 | Ready To Test | 10800 | [Dev][RD][Ecom] Sprint 10 | [Dev][RD][Ecom] Sprint 10 | [Dev][RD][Ecom] Sprint 11
Story | DEVRDCT-242 | 31922 | [DEV][RD][SSO-User] Enhance platform binding endpoint support line_pay | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 02/Oct/25 5:17 PM | 14/Nov/25 2:13 PM | 09/Oct/25 12:00 AM | 8 | sso-user |  |  | 0 | มาจาก Sprint 10 | Ready To Test | 86400 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11
Bug | DEVRDCT-241 | 31866 | [S3][CT][Webhook][Club Binding Event] Opt-in type club binding status event not show correctly on CT through Webhook API | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Open |  | 30/Sep/25 3:31 PM | 05/Nov/25 12:46 PM | [6 empty] | มาจาก Sprint 10 | Open |  | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 10 | [Dev][CT] Sprint 11
Story | RDTHANA-294 | 31845 | [Dev][RD][BFF] Improve get sections contents api v2 | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready To Test |  | 30/Sep/25 11:56 AM | 05/Nov/25 1:59 PM | 01/Oct/25 12:00 AM | 2 |  |  |  | 0 | มาจาก Sprint 10 | Ready To Test | 14400 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-289 | 31700 | [DEV][RD][BOF][CR] Enhance survey ranking question | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 26/Sep/25 2:02 PM | 05/Nov/25 1:59 PM | 30/Sep/25 12:00 AM | 3 |  |  |  | 0 | มาจาก Sprint 10 | Ready To Test | 21600 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-268 | 31545 | [Dev][RD][BOF] Disable mode when survey is expired | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 23/Sep/25 3:28 PM | 05/Nov/25 1:59 PM | 30/Sep/25 12:00 AM | 1 | rr-backoffice |  |  | 0 | มาจาก Sprint 10 | Ready To Test | 3600 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Epic | DEVRDECOM-107 | 31506 | Shopify Webhook |  |  | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | To Do |  | 23/Sep/25 9:52 AM | 03/Nov/25 3:54 PM | [6 empty] | มาจาก Sprint 10 | To Do |  | [Dev][RD][Ecom] Sprint 10 | [Dev][RD][Ecom] Sprint 10 | [Dev][RD][Ecom] Sprint 10 | [Dev][RD][Ecom] Sprint 11
Sub-task | RDTHANA-249 | 31473 | [QA] Create Test Case View Survey List (FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 22/Sep/25 10:06 PM | 04/Oct/25 12:35 PM | [6 empty] | มาจาก Sprint 10 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-244 | 31447 | [DEV][RD][APH] Enhance sorry page support dynamic error message and CTA button | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 22/Sep/25 11:36 AM | 05/Nov/25 1:59 PM | 29/Sep/25 12:00 AM | 1 |  |  |  |  | มาจาก Sprint 10 | Ready To Test |  | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-241 | 31432 | [DEV][RD][APH] Enhance survey html render support survey appearance "Thank you" tab | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 21/Sep/25 9:13 PM | 05/Nov/25 1:59 PM | 29/Sep/25 12:00 AM | 3 |  |  |  | 0 | มาจาก Sprint 10 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-240 | 31431 | [DEV][RD][APH] Enhance survey html render support survey appearance "Email" tab (Issue point form) | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 21/Sep/25 9:13 PM | 12/Nov/25 9:32 AM | 26/Sep/25 12:00 AM | 8 |  |  |  | 0 | มาจาก Sprint 10 | In Progress | 144000 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-239 | 31430 | [DEV][RD][APH] Enhance survey html render support survey appearance "Survey Q&A" tab | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 21/Sep/25 9:13 PM | 05/Nov/25 1:59 PM | 26/Sep/25 12:00 AM | 8 |  |  |  | 0 | มาจาก Sprint 10 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-238 | 31429 | [DEV][RD][APH] Create survey theme | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Highest | Ready To Test |  | 21/Sep/25 8:49 PM | 05/Nov/25 1:59 PM | 23/Sep/25 12:00 AM | 3 | rr-aphrodite |  |  | 0 | มาจาก Sprint 10 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-236 | 31426 | [Dev][RD][BOF] Rename all related feature and field from ‘Exclusive Store’ ‘Exclusive Partner Store’ to ‘Club - Rewards’ | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 21/Sep/25 2:16 PM | 10/Nov/25 1:27 PM | 01/Oct/25 12:00 AM | 2 | rr-backoffice | rr-scheduler |  |  | มาจาก Sprint 10 | Ready To Test |  | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-232 | 31360 | [DEV][RD][GATEWAY] Mapping get member club detail with internal API | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Highest | Ready To Test |  | 19/Sep/25 10:44 AM | 05/Nov/25 1:59 PM |  | 1 |  |  |  | 0 | มาจาก Sprint 10 | Ready To Test | 7200 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-231 | 31359 | [DEV][RD][APH] Enhance survey html render support survey appearance "General" tab | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 19/Sep/25 10:43 AM | 05/Nov/25 1:59 PM | 26/Sep/25 12:00 AM | 5 |  |  |  | 0 | มาจาก Sprint 10 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-230 | 31358 | [DEV][RD][APH] Enhance getMemberToken support sources session | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 19/Sep/25 10:42 AM | 05/Nov/25 1:59 PM | 26/Sep/25 12:00 AM | 2 |  |  |  | 0 | มาจาก Sprint 10 | Ready To Test | 7200 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-229 | 31332 | [DEV][RD][APH] Enhance survey available middleware | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 18/Sep/25 4:23 PM | 05/Nov/25 1:59 PM | 26/Sep/25 12:00 AM | 5 |  |  |  | 0 | มาจาก Sprint 10 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Sub-task | RDTHANA-134 | 30844 | [QA] Create Test Case Download Individual Survey Report (FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:30 AM | 05/Oct/25 3:00 PM | [6 empty] | มาจาก Sprint 10 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Sub-task | RDTHANA-133 | 30842 | [QA] Create Test Case View Survey Report (FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:30 AM | 05/Oct/25 2:50 PM | [6 empty] | มาจาก Sprint 10 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Sub-task | RDTHANA-132 | 30840 | [QA] Create Test Case Change survey status (FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:30 AM | 04/Oct/25 12:24 PM | [6 empty] | มาจาก Sprint 10 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Sub-task | RDTHANA-131 | 30838 | [QA] |  |  | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 09/Sep/25 11:29 AM | 21/Sep/25 3:00 PM | [6 empty] | มาจาก Sprint 10 | To Do |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Sub-task | RDTHANA-130 | 30836 | [QA] Create Test Case Update survey Step 5: Survey Appearance (Thank You) (FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:29 AM | 04/Oct/25 12:32 PM | [6 empty] | มาจาก Sprint 10 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Sub-task | RDTHANA-129 | 30834 | [QA] Create Test Case Update survey Step 5: Survey Appearance (Input E-mail) (FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:29 AM | 21/Sep/25 3:01 PM | [6 empty] | มาจาก Sprint 10 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Sub-task | RDTHANA-128 | 30832 | [QA] Create Test Case [Dev][RD][BOF] Update survey step5.2(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:29 AM | 21/Sep/25 1:58 PM | [6 empty] | มาจาก Sprint 10 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Sub-task | RDTHANA-127 | 30830 | [QA] Create Test Case Update survey step5.1(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:28 AM | 21/Sep/25 1:55 PM | [6 empty] | มาจาก Sprint 10 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Sub-task | RDTHANA-126 | 30828 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:28 AM | 11/Nov/25 1:41 PM | [6 empty] | มาจาก Sprint 10 | Done |  | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Sub-task | RDTHANA-125 | 30826 | [QA] Create Test Case Update survey step4.2(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:28 AM | 21/Sep/25 1:55 PM | [6 empty] | มาจาก Sprint 10 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Sub-task | RDTHANA-124 | 30824 | [QA] Create Test Case Update survey step4.1(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:27 AM | 21/Sep/25 1:55 PM | [6 empty] | มาจาก Sprint 10 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Sub-task | RDTHANA-123 | 30822 | [QA] Create Test Case Update survey step3(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:27 AM | 21/Sep/25 1:55 PM | [6 empty] | มาจาก Sprint 10 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Sub-task | RDTHANA-122 | 30820 | [QA] Create Test Case Update survey step2(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:26 AM | 21/Sep/25 12:27 PM | [6 empty] | มาจาก Sprint 10 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Sub-task | RDTHANA-121 | 30818 | [QA] Create Test Case Update survey step1(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:26 AM | 21/Sep/25 12:27 PM | [6 empty] | มาจาก Sprint 10 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Sub-task | RDTHANA-120 | 30816 | [QA] Create Test Case Create survey (FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:25 AM | 21/Sep/25 12:27 PM | [6 empty] | มาจาก Sprint 10 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Sub-task | RDTHANA-119 | 30814 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 09/Sep/25 11:24 AM | 09/Sep/25 11:24 AM | [6 empty] | มาจาก Sprint 10 | To Do |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Sub-task | RDTHANA-118 | 30812 | [QA] Create Test Case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 09/Sep/25 11:23 AM | 09/Sep/25 11:23 AM | [6 empty] | มาจาก Sprint 10 | To Do |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Sub-task | RDTHANA-116 | 30808 | [QA] Create Test Case 'Club - Benefits & Info' Location | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 09/Sep/25 11:22 AM | 15/Oct/25 3:36 PM | [6 empty] | มาจาก Sprint 10 | Done |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Sub-task | RDTHANA-115 | 30806 | [QA] Create Test Case Widget Feature: Add 'Service' Type (RR backoffice) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 09/Sep/25 11:22 AM | 10/Nov/25 5:00 PM | [6 empty] | มาจาก Sprint 10 | To Do |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Sub-task | RDTHANA-114 | 30804 | [QA] Create Test Case Widget Type 'Club – Benefits & Information' | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 09/Sep/25 11:21 AM | 15/Oct/25 3:45 PM | [6 empty] | มาจาก Sprint 10 | Done |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-107 | 30691 | [Dev][RD][APH] Cronjob update survey to expired | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 04/Sep/25 4:56 PM | 05/Nov/25 1:59 PM | 26/Sep/25 12:00 AM | 3 | rr-aphrodite |  |  | 0 | มาจาก Sprint 10 | Ready To Test | 21600 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-106 | 30689 | [Dev][RD][Service][CMS API] Create service filter api | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 04/Sep/25 4:08 PM | 05/Nov/25 1:59 PM | 11/Sep/25 12:00 AM | 3 | cms-api | No-QA |  | 0 | มาจาก Sprint 10 | Ready To Test | 18000 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-105 | 30687 | [Dev][RD][APH][CT] CleverTap Survey Event | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 04/Sep/25 3:56 PM | 13/Nov/25 2:44 PM |  | 5 |  |  |  | 0 | มาจาก Sprint 10 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Epic | DEVRDADJ-34 | 30635 | MAID registration |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 03/Sep/25 4:08 PM | 04/Nov/25 9:37 AM | [6 empty] | มาจาก Sprint 10 | To Do |  | [Dev][RDAdjust] Sprint 10 | [Dev][RDAdjust] Sprint 10 | [Dev][RDAdjust] Sprint 10 | [Dev][CT] Sprint 11
Story | RDTHANA-90 | 30622 | [Dev][RD][Section][BOF][QA] Enhance Section Feature: Add new widget types | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Sep/25 9:16 PM | 05/Nov/25 1:59 PM |  | 0 |  |  |  |  | มาจาก Sprint 10 | Ready To Test |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-89 | 30621 | [Dev][RD][Section][BOF] Enhance Section Feature: Add 'Club - Benefits & Info' Location | Art: Narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 02/Sep/25 8:56 PM | 14/Nov/25 2:13 PM |  | 5 | rr-backoffice |  |  |  | มาจาก Sprint 10 | Ready To Test |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-88 | 30620 | [Dev][RD][Widget][BOF] Enhance Widget Feature: Add 'Service' Type | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Sep/25 8:56 PM | 10/Nov/25 5:10 PM | 11/Sep/25 12:00 AM | 5 | rr-backoffice |  |  | 0 | มาจาก Sprint 10 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-87 | 30619 | [Dev][RD][Widget][BOF] Enhance Widget Feature: Add 'Club – Benefits & Information' Type | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 02/Sep/25 8:56 PM | 14/Nov/25 2:13 PM | 10/Sep/25 12:00 AM | 5 | rr-backoffice |  |  | 0 | มาจาก Sprint 10 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-86 | 30618 | [Dev][RD][BOF] Update survey Step 5: Survey Appearance (Thank You) (FE&BE) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Sep/25 8:44 PM | 14/Nov/25 2:13 PM | 15/Sep/25 12:00 AM | 2 | rr-backoffice |  |  | 0 | มาจาก Sprint 10 | Ready To Test | 10800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-81 | 30606 | [Dev][RD][BOF] Change survey status (FE&BE) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Sep/25 3:26 PM | 14/Nov/25 2:13 PM | 16/Sep/25 12:00 AM | 3 | rr-backoffice |  |  | 0 | มาจาก Sprint 10 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-80 | 30604 | [Dev][RD][BOF] Update survey Step 5: Survey Appearance (Input E-mail) (FE&BE) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Sep/25 3:25 PM | 14/Nov/25 2:13 PM | 15/Sep/25 12:00 AM | 2 | rr-backoffice |  |  | 0 | มาจาก Sprint 10 | Ready To Test | 10800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-79 | 30602 | [Dev][RD][BOF] Update survey step5.2(FE&BE) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Sep/25 3:24 PM | 14/Nov/25 2:13 PM | 12/Sep/25 12:00 AM | 2 | rr-backoffice |  |  | 0 | มาจาก Sprint 10 | Ready To Test | 10800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-74 | 30366 | [Dev][RD][BOF] Update survey step4.2(FE&BE) | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:15 PM | 14/Nov/25 2:13 PM |  | 2 | rr-backoffice |  |  | 0 | มาจาก Sprint 10 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-73 | 30364 | [Dev][RD][BOF] Download Individual Survey Report (FE&BE) | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:15 PM | 14/Nov/25 2:13 PM | 18/Sep/25 12:00 AM | 5 | rr-backoffice |  |  | 0 | มาจาก Sprint 10 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-72 | 30362 | [Dev][RD][BOF] Update survey step5.1(FE&BE) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:15 PM | 14/Nov/25 2:13 PM | 12/Sep/25 12:00 AM | 3 | rr-backoffice |  |  | 0 | มาจาก Sprint 10 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-71 | 30360 | [Dev][RD][BOF] Update survey step4.1(FE&BE) | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:15 PM | 14/Nov/25 2:13 PM |  | 8 | rr-backoffice |  |  | 0 | มาจาก Sprint 10 | Ready To Test | 86400 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-70 | 30358 | [Dev][RD][BOF] Update survey step3(FE&BE) | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:14 PM | 14/Nov/25 2:13 PM |  | 5 | rr-backoffice |  |  | 0 | มาจาก Sprint 10 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-69 | 30356 | [Dev][RD][BOF] Update survey step2(FE&BE) | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:09 PM | 14/Nov/25 2:13 PM | 16/Sep/25 12:00 AM | 3 | rr-backoffice |  |  | 0 | มาจาก Sprint 10 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-68 | 30354 | [Dev][RD][BOF] View Survey Report (FE&BE) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:09 PM | 14/Nov/25 2:13 PM | 17/Sep/25 12:00 AM | 3 | rr-backoffice |  |  | 0 | มาจาก Sprint 10 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-67 | 30352 | [Dev][RD][BOF] View Survey List (FE&BE) | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:09 PM | 14/Nov/25 2:13 PM |  | 5 | rr-backoffice |  |  | 0 | มาจาก Sprint 10 | Ready To Test | 86400 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-66 | 30350 | [Dev][RD][BOF] Update survey step1(FE&BE) | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:09 PM | 14/Nov/25 2:13 PM | 15/Sep/25 12:00 AM | 3 | rr-backoffice |  |  | 0 | มาจาก Sprint 10 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-65 | 30348 | [Dev][RD][BOF] Create survey (FE&BE) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:08 PM | 14/Nov/25 2:13 PM | 11/Sep/25 12:00 AM | 5 | rr-backoffice |  |  | 0 | มาจาก Sprint 10 | Ready To Test | 43200 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Bug | DEVRDADJ-25 | 30110 | [S2][Adjust] When change internal name URL not update and can't open | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | UNDER VALIDATION |  | 22/Aug/25 11:12 AM | 13/Nov/25 3:55 PM | [6 empty] | มาจาก Sprint 10 | UNDER VALIDATION |  | [Dev][RDAdjust] Sprint 10 | [Dev][RDAdjust] Sprint 10 | [Dev][CT] Sprint 11
Story | RDTHANA-43 | 30086 | [DEV][RD][DasHaus][BFF] Verify the API to validate matching account | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 22/Aug/25 6:12 AM | 05/Nov/25 1:59 PM |  | 1 | BFF |  |  |  | มาจาก Sprint 10 | Ready To Test |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-20 | 29950 | [Dev][RD][APH] Enhance check token | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 19/Aug/25 7:46 PM | 05/Nov/25 1:59 PM |  | 3 |  |  |  | 0 | มาจาก Sprint 10 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-16 | 29942 | [Dev][RD][Section][BFF] Enhance Sections API | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 19/Aug/25 7:44 PM | 11/Nov/25 2:16 PM |  | 5 | BFF |  |  | 0 | มาจาก Sprint 10 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-15 | 29940 | [Dev][RD][Widget][CMS API] Enhance Widget API | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 19/Aug/25 7:41 PM | 11/Nov/25 2:16 PM |  | 2 | cms-api |  |  | 0 | มาจาก Sprint 10 | Ready To Test | 3600 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11
Story | RDTHANA-14 | 29938 | [Dev][RD][Section][CMS API] Enhance Sections API | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 19/Aug/25 7:37 PM | 11/Nov/25 2:16 PM |  | 2 | cms-api |  |  | 0 | มาจาก Sprint 10 | Ready To Test | 14400 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 10 | [Dev][RD][Thana] Sprint 11

## Summarize Sprint 10
Column 1 | Total Stories Point | Total Manhour | Point Done | Manhour Done | Note
20 Oct - 31 Oct
Dev Resource Available | 16 | 474.5
Meeting Planned |  | 198 |  |  | Ref
Additional Meeting |  | 15 |  |  | Ref
Deployment |  | 8 |  |  | 5 ครั้ง 1. 1 คน 2. 2 คน 3. 4 คน 4. 2 คน 5. 1 คน
Development Sprint Total | 470 | 323.5 | 168 | 84.5
Ad-hoc Mid Sprint | 14 | 5.17 | 12 | 5.17 | 0 tasks
Requirement changes after refinement? | 0 | 0 | 0 | 0 | 0 tasks
Aek | 32 | 28.83 | 18 | 19.83
A | 41 | 58 | 22 | 26
Aom | 48 | 17.67 | 29 | 17.67
Zan | 19 | 8 | 14 | 0
Mai | 64 | 44 | 5 | 6
Mac | 59 | 32 | 0 | 0
Mos | 51 | 48 | 11 | 12
Jack | 22 | 1 | 14 | 1
Art | 0 | 0 | 0 | 0
Kae | 37 | 32 | 23 | 0
Nim | 59 | 28 | 21 | 0
| System Architech |  |  |  | Permanent Dev. |  |  | Outsources
Projects (Stories Points) | Aek | Zan | Aom | Jack | A | Art | Mai | Kae | Mac | Nim | Mos
Das Haus - Thana City & Das Haus | 4 | 5 | 1 | 8 | 23 | 0 | 36 | 26 | 45 | 32 | 40
E-commerce 1.1. E-Commerce x Shopify Plus 1.2. Shopify:Snackmaker 1.3. Shopify: Turtle Delivery 1.4. Shopify: Turtle Delivery | 18 | 0 | 0 | 8 | 7 | 0 | 3 | 8 | 3 | 2 | 11
CleverTap - MKT Automation Tool | 9 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 0
Adjust Integration | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 5 | 0
Adhoc - Non-Epics - Turtle Display club tier on POS - Data Mart Migration | 0 | 14 | 25 | 2 | 11 | 0 | 15 | 0 | 0 | 0 | 0
Support Incidents | 1 | 0 | 19 | 0 | 0 | 0 | 8 | 0 | 5 | 0 | 0
| System Architech |  |  |  | Permanent Dev. |  |  | Outsources
Projects (Manhour) | Aek | Zan | Aom | Jack | A | Art | Mai | Kae | Mac | Nim | Mos
Das Haus - Thana City & Das Haus | 0 | 8 | 0 | 0 | 2 | 0 | 2 | 16 | 21 | 0 | 36
E-commerce 1.1. E-Commerce x Shopify Plus 1.2. Shopify:Snackmaker 1.3. Shopify: Turtle Delivery 1.4. Shopify: Turtle Delivery | 19.67 | 0 | 0 | 0 | 22 | 0 | 0 | 8 | 4 | 4 | 12
CleverTap - MKT Automation Tool | 9 | 0 | 2 | 1 | 0 | 0 | 0 | 8 | 7 | 24 | 0
Adjust Integration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Adhoc - Non-Epics - Turtle Display club tier on POS - Data Mart Migration | 0 | 0 | 11 | 0 | 34 | 0 | 42 | 0 | 0 | 0 | 0
Support Incidents | 0.17 | 0 | 4.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 10
Issue Type | Issue key | Issue id | Summary | Assignee | Assignee Id | Reporter | Reporter Id | Priority | Status | Resolution | Created | Updated | Due date | Custom field (Story Points) | Labels | Labels | Labels | Original estimate | Sprint | Sprint Movement | Sprint 9 | Note | Sprint | Sprint | Sprint | Sprint | Sprint
Story | RDAPS-253 | 33277 | [DEV][RD][HOP IMPROVEMENT] Remove "Unicorn Exclusive store" setting from Visionary rewards in 1st November | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 31/Oct/25 1:00 PM | 03/Nov/25 10:06 AM |  | 3 |  |  |  |  | [Dev][All Project] Sprint 10
Story | RDAPS-252 | 33276 | [DEV][RD][HOP IMPROVEMENT] Export all active users to from Unicorn Hop Club and Visionary Hop club | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 31/Oct/25 12:57 PM | 31/Oct/25 1:03 PM |  | 3 |  |  |  |  | [Dev][All Project] Sprint 10
Story | DEVRDECOM-145 | 33275 | [DEV][RD[Eco][Turtle][POC] Dynamic Section by Customer Location | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Progress |  | 31/Oct/25 12:47 PM | 31/Oct/25 12:49 PM |  | 5 |  |  |  |  | [Dev][RD][Ecom] Sprint 10
Sub-task | RDAPS-249 | 33260 | [QA] Test Retesting QR join club (STAGING) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 30/Oct/25 3:45 PM | 30/Oct/25 4:12 PM | [6 empty] | [Dev][All Project] Sprint 10
Story | RDAPS-248 | 33251 | [Dev][RD][SA] Analyze & split dev tasks for Sprint11 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 30/Oct/25 2:33 PM | 30/Oct/25 2:34 PM |  | 3 |  |  |  |  | [Dev][All Project] Sprint 10
Story | RDAPS-244 | 33245 | [DEV][RD][PROD] Enhance QR code use long link instead of deeplink | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 30/Oct/25 1:09 PM | 30/Oct/25 4:12 PM | 30/Oct/25 12:00 AM | 2 | hr-solution |  |  | 14400 | [Dev][All Project] Sprint 10
Sub-task | RDAPS-243 | 33213 | [RDAPS-234][QA] Test Change SMS Sub Account change on redeem at POS iteration 2 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 29/Oct/25 1:33 PM | 29/Oct/25 1:40 PM | [6 empty] | [Dev][All Project] Sprint 10
Story | DEVRDECOM-144 | 33211 | [DEV][RD][Eco][Rewards-Member] Fix hidden issue | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 29/Oct/25 11:58 AM | 31/Oct/25 11:30 AM |  | 3 |  |  |  | 28800 | [Dev][RD][Ecom] Sprint 10
Sub-task | RDAPS-242 | 33209 | [RDAPS-234][QA] Test Change SMS Sub Account change on redeem at POS iteration 1 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 29/Oct/25 11:23 AM | 29/Oct/25 1:34 PM | 29/Oct/25 12:00 AM | [5 empty] | [Dev][All Project] Sprint 10
Story | RDAPS-241 | 33201 | [Dev][RD] EXPORT TURTLE Rewards available coupon code in 31 October night | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | To Do |  | 28/Oct/25 3:51 PM | 30/Oct/25 2:45 PM | 01/Nov/25 12:00 AM | 2 | mid-sprint | No-QA |  |  | [Dev][All Project] Sprint 10
Story | RDTHANA-353 | 33197 | [Dev][RD][Survey Web] Remove Survey web from SEO | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 28/Oct/25 1:53 PM | 29/Oct/25 1:47 PM |  | 2 | rr-aphrodite |  |  |  | [Dev][RD][Thana] Sprint 10
Story | DEVRDECOM-143 | 33196 | [DEV][RD][Eco][Rewards-Member] Add logic logout redirect for Das Haus shopify shop to solve problem wrong language | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 28/Oct/25 1:14 PM | 29/Oct/25 8:36 PM | 29/Oct/25 12:00 AM | 1 |  |  |  | 7200 | [Dev][RD][Ecom] Sprint 10
Story | DEVRDSUP-206 | 33195 | [SUP-262][SUP-261][Turtle][PartnerLoyalty] Request to query email list per user's phone to perform point issue on failed TXN. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Done |  | 28/Oct/25 12:08 PM | 28/Oct/25 12:58 PM | 28/Oct/25 12:00 AM | 1 | mid-sprint | partnerLoyalty | turtle | 1800 | [Dev][All Project] Sprint 10
Story | DEVRDSUP-205 | 33191 | [SUP-261][Turtle][PartnerLoyalty] Request to query sso list per user's phone to perform point issue on failed TXN. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Done |  | 28/Oct/25 11:18 AM | 28/Oct/25 11:55 AM | 28/Oct/25 12:00 AM | 1 | mid-sprint | partnerLoyalty | turtle | 1800 | [Dev][All Project] Sprint 10
Story | DEVRDSUP-204 | 33161 | [SUP-259][SUB][Request Mark Used] #20251000019927 [coupon 11574800 ] บัตร RW 0887515678172 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 27/Oct/25 6:18 PM | 30/Oct/25 1:16 PM |  | 1 | mid-sprint | sub |  | 1800 | [Dev][All Project] Sprint 10
Sub-task | DEVRDCT-274 | 33152 | [DEV][RD][RWS][ENH] Adjust the TS field in both REDEEM and MEMBER_COUPON events to use UTC +0 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 27/Oct/25 12:56 PM | 30/Oct/25 3:54 PM | 27/Oct/25 12:00 AM |  | No-QA | redemption-api |  | 0 | [Dev][CT] Sprint 10
Story | DEVRDSUP-202 | 33105 | [SUP-250][CS-20251000019735] รบกวน Mark Used คูปองเที่ยวเดินทาง เนื่องจากมีการเติมเที่ยวสำเร็จแล้วค่ะ | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 24/Oct/25 2:16 PM | 24/Oct/25 4:39 PM |  | 1 | bts | mid-sprint | sub | 1800 | [Dev][All Project] Sprint 10
Story | DEVRDCT-273 | 33038 | [DEV][RD][CT] Review and verify the TS field in each event sent to CleverTap | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 24/Oct/25 9:08 AM | 30/Oct/25 3:54 PM |  | 3 |  |  |  |  | [Dev][CT] Sprint 10
Bug | RDTHANA-351 | 32993 | [S4][HR Soulution][Welcome message][SMS] Cannot save change setting 'Destination URL' | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Closed |  | 22/Oct/25 6:07 PM | 29/Oct/25 4:12 PM | 24/Oct/68 12:00 AM | 1 |  |  |  |  | [Dev][RD][Thana] Sprint 10
Story | DEVRDSUP-200 | 32982 | [SUP-256]SUB : Request to fill in the Secret Key for Muvmi | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 22/Oct/25 3:50 PM | 29/Oct/25 2:53 PM | 30/Oct/25 12:00 AM | 1 | sub |  |  | 1800 | [Dev][All Project] Sprint 10
Bug | RDTHANA-350 | 32980 | [S4][HR Solution][Member][Import member] Upload member list file to BU get wrong template error | Art: Narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Closed |  | 22/Oct/25 3:11 PM | 29/Oct/25 4:05 PM | 24/Oct/25 12:00 AM | 3 |  |  |  |  | [Dev][RD][Thana] Sprint 10
Story | DEVRDECOM-142 | 32979 | [DEV][RD][Eco][Shopify-Theme] Setup Das Haus Shop for Production | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 22/Oct/25 2:45 PM | 31/Oct/25 11:25 AM |  | 1 |  |  |  | 1800 | [Dev][RD][Ecom] Sprint 10
Story | DEVRDECOM-141 | 32978 | [DEV][RD][Eco][Shopify-Theme] Setup Snackmaker Shop for Production | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 22/Oct/25 2:44 PM | 31/Oct/25 10:11 AM |  | 1 |  |  |  | 1800 | [Dev][RD][Ecom] Sprint 10
Story | DEVRDECOM-140 | 32977 | [DEV][RD][Eco][Shopify-Theme] Setup Turtle Shop for Production | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 22/Oct/25 2:44 PM | 31/Oct/25 10:11 AM |  | 1 |  |  |  | 1800 | [Dev][RD][Ecom] Sprint 10
Story | RDAPS-239 | 32970 | [DEV][RD][HRS] Remove welcome message setting in import employee process | Art: Narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 22/Oct/25 1:46 PM | 29/Oct/25 4:16 PM | 27/Oct/25 12:00 AM | 1 |  |  |  | 7200 | [Dev][All Project] Sprint 10
Story | DEVRDSUP-199 | 32969 | [SUP-255]Access RR back office and SSO back office | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 22/Oct/25 1:42 PM | 30/Oct/25 3:07 PM | 24/Oct/25 12:00 AM | 1 |  |  |  | 600 | [Dev][All Project] Sprint 10
Story | DEVRDCT-272 | 32968 | [DEV][RD][CT][ADHOC] Request to bypass event "BTS_Ride_Transaction" on UAT for test | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 22/Oct/25 1:35 PM | 22/Oct/25 1:52 PM | 22/Oct/25 12:00 AM | 1 | CleverTap | No-QA |  | 3600 | [Dev][CT] Sprint 10
Story | DEVRDSUP-197 | 32961 | [SUP-253]Requesting to mark used 1 BTS coupon with rabbit wallet card without pass top up. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 22/Oct/25 12:45 PM | 24/Oct/25 3:09 PM |  | 1 | bts | mid-sprint | sub | 1800 | [Dev][All Project] Sprint 10
Sub-task | RDTHANA-349 | 32956 | [QA] Test Execution - Service | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 22/Oct/25 9:40 AM | 03/Nov/25 11:03 AM | [6 empty] | [Dev][RD][Thana] Sprint 7 |  |  |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Sub-task | RDTHANA-348 | 32954 | [QA] Test Execution - Service | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 22/Oct/25 9:39 AM | 03/Nov/25 11:03 AM | [6 empty] | [Dev][RD][Thana] Sprint 7 |  |  |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Sub-task | RDTHANA-347 | 32952 | [QA] Test Execution - Service | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 22/Oct/25 9:39 AM | 03/Nov/25 11:04 AM | [6 empty] | [Dev][RD][Thana] Sprint 7 |  |  |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Sub-task | RDTHANA-346 | 32950 | [QA] Test Execution - Service | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 22/Oct/25 9:39 AM | 03/Nov/25 11:04 AM | [6 empty] | [Dev][RD][Thana] Sprint 7 |  |  |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Sub-task | RDTHANA-345 | 32948 | [QA] Test Execution - Service | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 22/Oct/25 9:38 AM | 03/Nov/25 11:04 AM | [6 empty] | [Dev][RD][Thana] Sprint 7 |  |  |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-344 | 32939 | [DEV][RD][BFF] Enhance change condition for is_enable_opt_in flag | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 21/Oct/25 5:45 PM | 22/Oct/25 1:03 PM | 22/Oct/25 12:00 AM | 1 |  |  |  | 3600 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-343 | 32938 | [DEV][RD][Exclusive Store API] Enhance get club detail with BU setting | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 21/Oct/25 5:28 PM | 22/Oct/25 1:03 PM | 22/Oct/25 12:00 AM | 2 |  |  |  | 10800 | [Dev][RD][Thana] Sprint 10
Test Plan | DEVRDADJ-52 | 32930 | [TP][Adjust] DEVRDADJ-44 |  |  | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 21/Oct/25 4:22 PM | 21/Oct/25 4:35 PM | [6 empty] | [Dev][RDAdjust] Sprint 10
Story | RDTHANA-341 | 32920 | [Dev][RD][BFF] Create an API to Get Clubs with filtering options | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready To Test |  | 21/Oct/25 4:00 PM | 29/Oct/25 1:26 PM | 24/Oct/25 12:00 AM | 3 | BFF | mid-sprint |  | 28800 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-340 | 32919 | [Dev][RD][EXS] Create an API to Get Clubs with filtering options | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready To Test |  | 21/Oct/25 4:00 PM | 29/Oct/25 1:29 PM | 22/Oct/25 12:00 AM | 3 | exclusive-store-api | mid-sprint |  | 43200 | [Dev][RD][Thana] Sprint 10
Sub-task | DEVRDSUP-195 | 32917 | [Dev][DEVRDSUP-194] Generate missing receipt for 1 TXN | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 21/Oct/25 3:30 PM | 21/Oct/25 4:23 PM | [6 empty] | [Dev][All Project] Sprint 10
Story | DEVRDSUP-194 | 32915 | [SUP-249]SUB : Completed Transaction but did not generate receipt (Ticket 21 Oct) | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 21/Oct/25 3:26 PM | 21/Oct/25 4:23 PM |  | 1 | mid-sprint | prod-issue | sub | 600 | [Dev][All Project] Sprint 10
Sub-task | DEVRDADJ-51 | 32914 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 21/Oct/25 2:50 PM | 22/Oct/25 9:32 AM | [6 empty] | [Dev][RDAdjust] Sprint 9 |  |  |  | [Dev][RDAdjust] Sprint 9 | [Dev][RDAdjust] Sprint 10
Story | RDAPS-238 | 32907 | [Dev][RD] Create script to mark vouchers as used for Cloud ID cases (issued on 16 Oct) | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | To Do |  | 21/Oct/25 2:10 PM | 30/Oct/25 2:43 PM |  | 5 | rr-scheduler |  |  |  | [Dev][All Project] Sprint 10
Story | RDAPS-237 | 32906 | [Dev][RD][REM] Enhance CRM “Mark Used” API to support optional skip of issuing BTS Pass for Cloud ID use case | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready to Staging |  | 21/Oct/25 1:44 PM | 03/Nov/25 10:24 AM |  | 8 | redemption-api |  |  |  | [Dev][All Project] Sprint 10
Sub-task | RDTHANA-339 | 32905 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | In Progress |  | 21/Oct/25 1:43 PM | 03/Nov/25 2:32 PM | [6 empty] | [Dev][RD][Thana] Sprint 9 |  |  |  | [Dev][RD][Thana] Sprint 10
Sub-task | RDTHANA-338 | 32903 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 21/Oct/25 1:43 PM | 03/Nov/25 2:05 PM | [6 empty] | [Dev][RD][Thana] Sprint 9 |  |  |  | [Dev][RD][Thana] Sprint 10
Test Execution | RDTHANA-337 | 32901 | [TX][Service] - Sprint10 | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 21/Oct/25 1:31 PM | 03/Nov/25 11:02 AM | [6 empty] | [Dev][RD][Thana] Sprint 10
Test Plan | RDTHANA-336 | 32900 | [TP][Service] - Sprint10 |  |  | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 21/Oct/25 1:29 PM | 03/Nov/25 11:03 AM | [6 empty] | [Dev][RD][Thana] Sprint 10
Story | DEVRDECOM-139 | 32895 | [DEV][RD][Eco][Ecommerce-Shopify] Enhance partial refund to use point ratio from point issued | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 21/Oct/25 11:16 AM | 29/Oct/25 1:27 PM | 21/Oct/25 12:00 AM | 2 |  |  |  | 14400 | [Dev][RD][Ecom] Sprint 10
Story | DEVRDECOM-138 | 32840 | [DEV][RD][Eco][Setup] Shops Backend Configuation for Production | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 21/Oct/25 9:41 AM | 31/Oct/25 10:11 AM |  | 2 | No-QA |  |  | 14400 | [Dev][RD][Ecom] Sprint 10
Story | DEVRDSUP-193 | 32838 | [SUP-248][SUB] Request to disable "E-mail alert to user after redeemed" toggle on all reward items. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Done |  | 21/Oct/25 9:21 AM | 21/Oct/25 1:06 PM | 21/Oct/25 12:00 AM | 1 | mid-sprint | rem |  | 1800 | [Dev][All Project] Sprint 10
Story | RDTHANA-335 | 32813 | [Dev][RD][BFF] Enhance Club Binding API to support popup display separately for app and web | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 20/Oct/25 2:24 PM | 03/Nov/25 10:09 AM | 29/Oct/25 12:00 AM | 3 |  |  |  |  | [Dev][RD][Thana] Sprint 10
Sub-task | DEVRDSUP-192 | 32805 | [Dev][DEVRDSUP-189] Mark used vouchers | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | To Do |  | 20/Oct/25 11:59 AM | 31/Oct/25 12:14 PM | [6 empty] | [Dev][All Project] Sprint 10
Sub-task | DEVRDSUP-191 | 32803 | [Dev][DEVRDSUP-189] Hold coupon prior to mark used the voucher. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Done |  | 20/Oct/25 11:58 AM | 21/Oct/25 1:21 PM | [6 empty] | [Dev][All Project] Sprint 10
Sub-task | DEVRDSUP-190 | 32801 | [Dev][DEVRDSUP-189] Check data from BSS if TXN list info is enough to mark used. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Done |  | 20/Oct/25 11:57 AM | 21/Oct/25 1:24 PM | [6 empty] | [Dev][All Project] Sprint 10
Story | DEVRDSUP-189 | 32799 | [SUP-247][SUB] Request to mark used many BTS vouchers due to cloud ID incident on 16/10/2025 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | In Progress |  | 20/Oct/25 11:56 AM | 31/Oct/25 12:06 PM |  | 8 | bts | prod-issue | sub |  | [Dev][All Project] Sprint 10
Story | RDAPS-236 | 32794 | [Dev][RD][SA] Analyze & split dev tasks for Sprint10 Adhoc, CT, ThanaCity | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 20/Oct/25 11:12 AM | 31/Oct/25 10:01 AM |  | 5 |  |  |  |  | [Dev][All Project] Sprint 10
Story | DEVRDECOM-137 | 32788 | [DEV][RD][Eco][Shopify-Theme] Rename "Buy it Now" to "Book Now" for Das Haus | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 20/Oct/25 10:12 AM | 30/Oct/25 3:11 PM |  | 1 | No-QA |  |  | 600 | [Dev][RD][Ecom] Sprint 10
Story | DEVRDCT-270 | 32786 | [DEV][RD][SSO-User] Enhance platform unbind endpoint support line_pay | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 20/Oct/25 9:52 AM | 22/Oct/25 2:27 PM | 21/Oct/25 12:00 AM | 3 |  |  |  |  | [Dev][CT] Sprint 10
Story | DEVRDCT-269 | 32785 | [DEV][RD][RLP][API] Line Pay Unbound Event | Art: Narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 20/Oct/25 9:30 AM | 29/Oct/25 1:22 PM | 21/Oct/25 12:00 AM | 3 |  |  |  | 28800 | [Dev][CT] Sprint 10
Story | RDAPS-235 | 32780 | [DEV][RD][MIM] Create command to remove RR consent for member who registered from My Rabbit APP | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 19/Oct/25 8:54 PM | 02/Nov/25 3:02 PM |  | 5 |  |  |  | 86400 | [Dev][All Project] Sprint 10
Story | RDAPS-234 | 32779 | [DEV][RD][PL][SMS] Change SMS Sub Account | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 19/Oct/25 8:35 PM | 31/Oct/25 10:00 AM |  | 1 |  |  |  | 7200 | [Dev][All Project] Sprint 10
Story | DEVRDCT-268 | 32778 | [Dev][RD][BFF][API Spec] Update api specification | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 19/Oct/25 3:57 PM | 30/Oct/25 2:58 PM |  | 1 |  |  |  |  | [Dev][CT] Sprint 10
Story | RDAPS-233 | 32777 | [Dev][RD][RRS] Enhance Redemption ETL to add fields 'USING_AT' and 'COUNTDOWN_EXPIRED_AT' | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 19/Oct/25 3:24 PM | 22/Oct/25 9:48 AM | 21/Oct/25 12:00 AM | 2 | rr-scheduler |  |  | 14400 | [Dev][All Project] Sprint 10
Story | RDAPS-232 | 32776 | [Dev][RD][BOF] Enhance Subscription Transaction Report | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready to Staging |  | 19/Oct/25 2:59 PM | 31/Oct/25 9:34 AM | 22/Oct/25 12:00 AM | 5 | rr-backoffice |  |  | 57600 | [Dev][All Project] Sprint 10
Story | RDTHANA-333 | 32661 | [DEV][RD][Exclusive Store API][ENH] Enhance BFF to Support Separated Application & Web Settings in Welcome Message | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready to Staging |  | 17/Oct/25 2:11 PM | 27/Oct/25 2:35 PM | 24/Oct/25 12:00 AM | 3 | BFF |  |  | 21600 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-332 | 32659 | [DEV][RD][HRS][ENH] Enhance to separate Welcome message pop up setting between application and website | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready to Staging |  | 17/Oct/25 12:04 PM | 29/Oct/25 1:26 PM | 28/Oct/25 12:00 AM | 8 | hr-solution |  |  | 57600 | [Dev][RD][Thana] Sprint 10
Sub-task | DEVRDSUP-188 | 32652 | QA verify on UAT | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 16/Oct/25 6:28 PM | 16/Oct/25 6:53 PM | [6 empty] | [Dev][All Project] Sprint 9 | มาจาก Sprint 9 | Done |  | [Dev][All Project] Sprint 10
Story | RDAPS-230 | 32647 | [Dev][RD][SA] Analyze & split dev tasks for Sprint10 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 16/Oct/25 3:14 PM | 21/Oct/25 3:23 PM |  | 3 | No-QA |  |  | 14400 | [Dev][All Project] Sprint 9 | มาจาก Sprint 9 | In Progress |  | [Dev][All Project] Sprint 10
Story | DEVRDCT-266 | 32646 | [Dev][RD][SA] Analyze & split dev tasks for Sprint10 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 16/Oct/25 3:12 PM | 30/Oct/25 2:50 PM |  | 2 | No-QA |  |  | 7200 | [Dev][CT] Sprint 9 | มาจาก Sprint 9 | In Progress |  | [Dev][CT] Sprint 10
Story | DEVRDCT-265 | 32640 | [Dev][RD][BFF] Enhance Sections/Widgets APIs to support a new widget type | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 16/Oct/25 2:58 PM | 24/Oct/25 9:32 AM | 22/Oct/25 12:00 AM | 3 | BFF |  |  | 28800 | [Dev][CT] Sprint 10
Story | DEVRDCT-264 | 32638 | [Dev][RD][CMS DB] Create migration schemas to support the new widget type | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 16/Oct/25 2:57 PM | 20/Oct/25 4:54 PM | 20/Oct/25 12:00 AM | 1 | cms-database | No-QA | rabbit-cms-api | 3600 | [Dev][CT] Sprint 10
Story | DEVRDCT-263 | 32637 | [Dev][RD][BOF] Enhance Widget to support "Native Display" | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 16/Oct/25 2:56 PM | 21/Oct/25 4:22 PM | 21/Oct/25 12:00 AM | 3 | rr-backoffice |  |  | 21600 | [Dev][CT] Sprint 10
Story | RDAPS-226 | 32633 | [Dev][RD][RRS] Enhance Subscription Transactions Search with Advanced Filters & Index Optimization | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready to Staging |  | 16/Oct/25 2:47 PM | 31/Oct/25 9:34 AM | 24/Oct/25 12:00 AM | 5 | rr-scheduler |  |  | 57600 | [Dev][All Project] Sprint 10
Bug | DEVRDSUP-184 | 32628 | [SUP-244][REM] Redeem mail alert sends to user even if "E-mail alert to user after redeemed" is turned off. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Low | Closed |  | 16/Oct/25 12:46 PM | 27/Oct/25 3:55 PM | 14/Nov/25 12:00 AM | 1 | prod-issue | rem |  |  | [Dev][All Project] Sprint 9 | มาจาก Sprint 9 | RETESTING |  | [Dev][All Project] Sprint 10
Story | DEVRDCT-262 | 32567 | [DEV][RD][USR] Enhance check duplicate line id for binding line pay | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 16/Oct/25 8:30 AM | 20/Oct/25 10:59 AM |  | 1 | sso-user |  |  |  | [Dev][CT] Sprint 9 | มาจาก Sprint 9 | Ready To Test |  | [Dev][CT] Sprint 10
Sub-task | DEVRDSUP-183 | 32562 | [Dev][DEVRDSUP-182] Update purchase TXN data in DB | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Highest | To Do |  | 15/Oct/25 4:40 PM | 15/Oct/25 4:40 PM | [6 empty] | [Dev][All Project] Sprint 10
Sub-task | RDTHANA-329 | 32558 | [QA] Test execution | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 15/Oct/25 3:44 PM | 15/Oct/25 3:46 PM | [6 empty] | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | To Do |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Sub-task | RDTHANA-328 | 32555 | [QA] Test execution | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 15/Oct/25 3:32 PM | 15/Oct/25 3:36 PM | [6 empty] | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | To Do |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | DEVRDSUP-182 | 32553 | [SUB][DEVRDSUP-167] Update refund date/ time for TXN that was refunded prior to DEVRDSUP-167 fix. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Highest | Done |  | 15/Oct/25 3:22 PM | 23/Oct/25 6:04 PM |  | 2 | sub |  |  | 1800 | [Dev][All Project] Sprint 10
Sub-task | RDTHANA-327 | 32552 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 15/Oct/25 2:38 PM | 27/Oct/25 10:40 AM | [6 empty] | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | In Progress |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Sub-task | RDTHANA-326 | 32551 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 15/Oct/25 2:38 PM | 27/Oct/25 10:40 AM | [6 empty] | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | In Progress |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Sub-task | RDTHANA-324 | 32549 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 15/Oct/25 2:38 PM | 27/Oct/25 10:40 AM | [6 empty] | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | In Progress |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Test Execution | RDTHANA-322 | 32547 | [TX][Thana city] Feature menu - Sprint 9 |  |  | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 15/Oct/25 2:22 PM | 21/Oct/25 1:22 PM | [6 empty] | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | In Progress |  | [Dev][RD][Thana] Sprint 10
Test Plan | RDTHANA-321 | 32546 | [TP][Thana city] Feature menu - Sprint 9 |  |  | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 15/Oct/25 2:11 PM | 21/Oct/25 1:22 PM | [6 empty] | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | To Do |  | [Dev][RD][Thana] Sprint 10
Bug | DEVRDSUP-181 | 32289 | [SUP-220]HR Solution can't import employee if disable welcome msg feature |  |  | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Enhancement |  | 15/Oct/25 10:15 AM | 31/Oct/25 1:09 PM |  | 3 |  |  |  |  | [Dev][All Project] Sprint 10
Bug | DEVRDSUP-176 | 32274 | [SUP-242][REM] Coupon TXN report's reward start and end date are incorrect. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Lowest | Fixing |  | 14/Oct/25 5:39 PM | 28/Oct/25 6:24 PM | 14/Nov/25 12:00 AM |  | prod-issue | rem | rr-scheduler |  | [Dev][All Project] Sprint 10
Story | DEVRDSUP-175 | 32272 | [SUP-239][ETL] Catch-up redemption data (item_id, using_at, and countdown_expired_at) | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | To Do |  | 14/Oct/25 4:34 PM | 28/Oct/25 6:30 PM | 30/Oct/25 12:00 AM | 5 | etl |  |  |  | [Dev][All Project] Sprint 10
Story | DEVRDSUP-174 | 32269 | [SUP-238][API] Catch-up subscription purchase report (publishPrice) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | To Do |  | 14/Oct/25 4:14 PM | 03/Nov/25 3:20 PM | 30/Oct/25 12:00 AM | 5 | etl |  |  | 0 | [Dev][All Project] Sprint 10
Story | RDTHANA-320 | 32261 | [DEV][RD][GATEWAY] Mapping new gateway endpoint | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 14/Oct/25 2:31 PM | 28/Oct/25 10:03 AM |  | 1 |  |  |  | 7200 | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | Ready to Staging |  | [Dev][RD][Thana] Sprint 10
Story | DEVRDCT-258 | 32213 | [DEV][RD][RLP][WEP] LINE_PAY_BINDING Event push to CT | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 13/Oct/25 5:00 PM | 22/Oct/25 4:26 PM |  | 2 |  |  |  | 10800 | [Dev][CT] Sprint 9 | มาจาก Sprint 9 | In Review |  | [Dev][CT] Sprint 10
Story | RDAPS-223 | 32197 | [DEV][RD][Rewards API] Enhance Get products filter api for support filter by is_reward_store | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Done |  | 10/Oct/25 4:59 PM | 30/Oct/25 2:43 PM |  | 2 | mid-sprint | rewards-api |  | 10800 | [Dev][All Project] Sprint 9 | มาจาก Sprint 9 | Ready To Test |  | [Dev][All Project] Sprint 10
Bug | RDAPS-222 | 32182 | [S4][Rewards Alert List] Rewards with end_date displayed as 10:00 are excluded from scheduled email alert | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Closed |  | 09/Oct/25 4:40 PM | 31/Oct/25 10:02 AM | [6 empty] | [Dev][All Project] Sprint 9 | มาจาก Sprint 9 | Resolved |  | [Dev][All Project] Sprint 10
Sub-task | DEVRDECOM-134 | 32148 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Progress |  | 09/Oct/25 11:37 AM | 03/Nov/25 1:35 PM | [6 empty] | [Dev][RD][Ecom] Sprint 9 | มาจาก Sprint 9 | To Do |  | [Dev][RD][Ecom] Sprint 10
Sub-task | DEVRDECOM-133 | 32146 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 09/Oct/25 11:37 AM | 17/Oct/25 6:00 PM | [6 empty] | [Dev][RD][Ecom] Sprint 9 | มาจาก Sprint 9 | Done |  | [Dev][RD][Ecom] Sprint 10
Sub-task | DEVRDECOM-132 | 32144 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 09/Oct/25 11:36 AM | 09/Oct/25 11:37 AM | [6 empty] | [Dev][RD][Ecom] Sprint 9 | มาจาก Sprint 9 | To Do |  | [Dev][RD][Ecom] Sprint 10
Sub-task | DEVRDECOM-131 | 32142 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 09/Oct/25 11:36 AM | 17/Oct/25 6:01 PM | [6 empty] | [Dev][RD][Ecom] Sprint 9 | มาจาก Sprint 9 | Done |  | [Dev][RD][Ecom] Sprint 10
Sub-task | DEVRDECOM-130 | 32140 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 09/Oct/25 11:36 AM | 09/Oct/25 11:36 AM | [6 empty] | [Dev][RD][Ecom] Sprint 9 | มาจาก Sprint 9 | To Do |  | [Dev][RD][Ecom] Sprint 10
Sub-task | DEVRDECOM-129 | 32138 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 09/Oct/25 11:36 AM | 21/Oct/25 2:13 PM | [6 empty] | [Dev][RD][Ecom] Sprint 9 | มาจาก Sprint 9 | In Progress |  | [Dev][RD][Ecom] Sprint 10
Sub-task | DEVRDECOM-128 | 32136 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 09/Oct/25 11:36 AM | 09/Oct/25 11:36 AM | [6 empty] | [Dev][RD][Ecom] Sprint 9 | มาจาก Sprint 9 | To Do |  | [Dev][RD][Ecom] Sprint 10
Sub-task | DEVRDECOM-127 | 32134 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 09/Oct/25 11:36 AM | 21/Oct/25 2:13 PM | [6 empty] | [Dev][RD][Ecom] Sprint 9 | มาจาก Sprint 9 | In Review |  | [Dev][RD][Ecom] Sprint 10
Sub-task | DEVRDECOM-126 | 32097 | [DEV][RD][Eco][Ecommerce_Shopify] Enhance login to store id_token in shopify login logs | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 08/Oct/25 1:46 PM | 28/Oct/25 10:12 AM | 14/Oct/25 12:00 AM |  | No-QA |  |  | 14400 | [Dev][RD][Ecom] Sprint 9 | มาจาก Sprint 9 | Ready to Staging |  | [Dev][RD][Ecom] Sprint 10
Sub-task | RDTHANA-319 | 32090 | [QA] Create Test Case - Create new endpoint get deeplink with path | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 08/Oct/25 10:20 AM | 03/Nov/25 2:04 PM | [6 empty] | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | In Progress |  | [Dev][RD][Thana] Sprint 10
Sub-task | RDTHANA-318 | 32088 | [QA] Create Test Case - Enhance sorry page with get deeplink endpoint | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 08/Oct/25 10:19 AM | 03/Nov/25 2:32 PM | [6 empty] | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | In Progress |  | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-317 | 32072 | [Dev][RD][BOF] Improve change status flow to validate required fields | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 07/Oct/25 3:16 PM | 03/Nov/25 10:16 AM | 14/Oct/25 12:00 AM | 5 | rr-backoffice |  |  | 57600 | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | Ready To Test |  | [Dev][RD][Thana] Sprint 10
Story | DEVRDCT-257 | 32071 | [DEV][RD][RLP][API] LINE_PAY_BINDING Event push to CT | Art: Narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 07/Oct/25 3:13 PM | 21/Oct/25 3:34 PM | [6 empty] | [Dev][CT] Sprint 9 | มาจาก Sprint 9 | In Review |  | [Dev][CT] Sprint 10
Sub-task | DEVRDCT-256 | 32069 | [QA] Create test case LINE_OA_BINDING and LINE_OA_ADD_FRIEND event | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 07/Oct/25 2:26 PM | 07/Oct/25 2:26 PM | [6 empty] | [Dev][CT] Sprint 9 | มาจาก Sprint 9 | To Do |  | [Dev][CT] Sprint 10
Sub-task | DEVRDCT-253 | 32062 | [QA] Create test case Line OA and Friend event to CleverTap | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 07/Oct/25 2:09 PM | 07/Oct/25 2:10 PM | [6 empty] | [Dev][CT] Sprint 9 | มาจาก Sprint 9 | To Do |  | [Dev][CT] Sprint 10
Sub-task | DEVRDCT-252 | 32060 | [QA] Create test case Line OA and Friend event to CleverTap | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 07/Oct/25 2:04 PM | 07/Oct/25 2:10 PM | [6 empty] | [Dev][CT] Sprint 9 | มาจาก Sprint 9 | To Do |  | [Dev][CT] Sprint 10
Sub-task | DEVRDCT-251 | 32058 | [QA] Create test case | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 07/Oct/25 2:03 PM | 07/Oct/25 2:03 PM | [6 empty] | [Dev][CT] Sprint 9 | มาจาก Sprint 9 | To Do |  | [Dev][CT] Sprint 10
Bug | DEVRDSUP-166 | 32020 | [SUP-229][Clevertap][API] API Issue point got error 400 code | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Rejected |  | 06/Oct/25 3:26 PM | 28/Oct/25 10:17 AM | 21/Oct/25 12:00 AM | [5 empty] | [Dev][All Project] Sprint 10
Story | RDTHANA-313 | 32018 | [DEV][RD][BFF] Get club term and condition endpoint | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 06/Oct/25 2:33 PM | 20/Oct/25 10:58 AM | 10/Oct/25 12:00 AM | 2 | BFF |  |  | 10800 | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | Ready To Test |  | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-312 | 32017 | [DEV][RD][Exclusive API] Get club term and condition endpoint | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 06/Oct/25 2:33 PM | 20/Oct/25 10:58 AM | 10/Oct/25 12:00 AM | 3 | exclusive-store-api |  |  | 28800 | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | Ready To Test |  | [Dev][RD][Thana] Sprint 10
Story | DEVRDCT-250 | 32004 | [DEV][RD][RLP] Create script to sync initial RLP member to RR Line member | Art: Narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 06/Oct/25 10:03 AM | 29/Oct/25 1:24 PM | 10/Oct/25 12:00 AM | 5 | rlp-middleware |  |  | 57600 | [Dev][CT] Sprint 9 | มาจาก Sprint 9 | In Review |  | [Dev][CT] Sprint 10
Story | DEVRDECOM-123 | 31991 | [DEV][RD][Eco][Rewards Member] Enhance custom redirect to solve the problem of user who set default browser is not safari | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 06/Oct/25 9:19 AM | 29/Oct/25 8:36 PM |  | 2 |  |  |  | 10800 | [Dev][RD][Ecom] Sprint 9 | มาจาก Sprint 9 | Ready To Test |  | [Dev][RD][Ecom] Sprint 10
Story | DEVRDECOM-122 | 31988 | [DEV][RD][BOF][Widget] Enhance widget asset for service widget | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 05/Oct/25 10:46 PM | 30/Oct/25 4:01 PM | 09/Oct/25 12:00 AM | 3 | rr-backoffice |  |  |  | [Dev][RD][Ecom] Sprint 9 | มาจาก Sprint 9 | Ready To Test |  | [Dev][RD][Ecom] Sprint 10
Story | DEVRDECOM-121 | 31987 | [DEV][RD][BOF][Service] Enhance create/edit service general form support upload JPG file and setup shadow color | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 05/Oct/25 10:44 PM | 30/Oct/25 4:01 PM | 08/Oct/25 12:00 AM | 2 | rr-backoffice |  |  | 14400 | [Dev][RD][Ecom] Sprint 9 | มาจาก Sprint 9 | Ready To Test |  | [Dev][RD][Ecom] Sprint 10
Story | DEVRDECOM-120 | 31986 | [DEV][RD][CMS-API] Migration for support shoping page | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 05/Oct/25 10:43 PM | 20/Oct/25 9:57 AM | 06/Oct/25 12:00 AM | 1 | cms-database |  |  | 3600 | [Dev][RD][Ecom] Sprint 9 | มาจาก Sprint 9 | Ready To Test |  | [Dev][RD][Ecom] Sprint 10
Story | DEVRDCT-249 | 31984 | [DEV][RD][RLP][WEB] Sent Line OA and Friend event to CleverTap | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 05/Oct/25 4:45 PM | 20/Oct/25 10:59 AM |  | 3 |  |  |  | 10800 | [Dev][CT] Sprint 9 | มาจาก Sprint 9 | Ready to Staging |  | [Dev][CT] Sprint 10
Story | DEVRDCT-248 | 31983 | [DEV][RD][RLP][API] Sent Line OA and Friend event to CleverTap | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 05/Oct/25 4:45 PM | 20/Oct/25 10:59 AM |  | 3 | rlp-middleware |  |  | 10800 | [Dev][CT] Sprint 9 | มาจาก Sprint 9 | Ready to Staging |  | [Dev][CT] Sprint 10
Task | RDAPS-216 | 31978 | [Dev][DL][VGI ONE] Clear WPP Credits & Users | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 05/Oct/25 8:58 AM | 30/Oct/25 4:31 PM | 24/Oct/25 12:00 AM | 2 | vgi-one |  |  |  | [Dev][All Project] Sprint 9 | มาจาก Sprint 9 | To Do |  | [Dev][All Project] Sprint 10
Story | DEVRDCT-243 | 31976 | [DEV][RD][CT][POC] Shopify Catalogue Upload | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Progress |  | 04/Oct/25 4:33 PM | 20/Oct/25 10:59 AM |  | 1 |  |  |  |  | [Dev][CT] Sprint 9 | มาจาก Sprint 9 | In Progress |  | [Dev][CT] Sprint 10
Story | RDAPS-213 | 31974 | [Dev][Rabbit connect] Remove Login SMS OTP on UAT for ease of testing and lower the SMS cost. | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 04/Oct/25 4:25 PM | 20/Oct/25 10:58 AM |  | 5 | sso-heimdall |  |  | 28800 | [Dev][All Project] Sprint 9 | มาจาก Sprint 9 | Ready To Test |  | [Dev][All Project] Sprint 10
Story | DEVRDECOM-118 | 31973 | [DEV][RD][Eco][Ecommerce-Shopify] Logout | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 04/Oct/25 4:18 PM | 29/Oct/25 8:36 PM | 15/Oct/25 12:00 AM | 3 |  |  |  | 28800 | [Dev][RD][Ecom] Sprint 9 | มาจาก Sprint 9 | Ready to Staging |  | [Dev][RD][Ecom] Sprint 10
Story | RDTHANA-311 | 31957 | [DEV][RD][APH] Enhance sorry page with get deeplink endpoint | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 03/Oct/25 5:11 PM | 20/Oct/25 10:58 AM | 08/Oct/25 12:00 AM | 3 | rr-aphrodite |  |  |  | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | Ready To Test |  | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-310 | 31956 | [DEV][RD][LNF] Create new endpoint get deeplink with path | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 03/Oct/25 4:52 PM | 03/Nov/25 2:06 PM | 06/Oct/25 12:00 AM | 1 | link-notify |  |  | 7200 | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | Ready To Test |  | [Dev][RD][Thana] Sprint 10
Story | DEVRDECOM-117 | 31949 | [Dev][RD][BOF] Enhance Section Menu (FE&BE) | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 03/Oct/25 3:49 PM | 30/Oct/25 4:01 PM | 08/Oct/25 12:00 AM | 3 | rr-backoffice |  |  | 28800 | [Dev][RD][Ecom] Sprint 9 | มาจาก Sprint 9 | Ready To Test |  | [Dev][RD][Ecom] Sprint 10
Story | DEVRDECOM-113 | 31942 | [Dev][RD][BFF] Enhance get sections to support new location | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 03/Oct/25 1:56 PM | 03/Nov/25 10:21 AM | 09/Oct/25 12:00 AM | 2 | BFF |  |  | 10800 | [Dev][RD][Ecom] Sprint 9 | มาจาก Sprint 9 | Ready To Test |  | [Dev][RD][Ecom] Sprint 10
Bug | DEVRDSUP-158 | 31925 | [SUP-222][HRSolution][Point Redemption Report] The refunded TXN point amount are included in redeemed point. | Game (Krittapas Tanaprasitpattana) | 712020:85e9f474-8ee8-45ba-9249-cde16fa1cd35 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Rejected |  | 02/Oct/25 6:16 PM | 29/Oct/25 2:28 PM | 23/Oct/25 12:00 AM |  | hop | hr-solution |  |  | [Dev][All Project] Sprint 9 | มาจาก Sprint 9 | UNDER VALIDATION |  | [Dev][All Project] Sprint 10
Story | DEVRDCT-242 | 31922 | [DEV][RD][SSO-User] Enhance platform binding endpoint support line_pay | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 02/Oct/25 5:17 PM | 20/Oct/25 10:59 AM | 09/Oct/25 12:00 AM | 8 | sso-user |  |  | 86400 | [Dev][CT] Sprint 9 | มาจาก Sprint 9 | Ready To Test |  | [Dev][CT] Sprint 10
Story | RDAPS-205 | 31905 | [DEV][RD][REM] Enhance Redemption API to support displaying exclusive rewards in rewards store | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Highest | Done |  | 02/Oct/25 8:21 AM | 30/Oct/25 2:42 PM |  | 3 | mid-sprint | redemption-api |  | 0 | [Dev][All Project] Sprint 9 | มาจาก Sprint 9 | Ready To Test | 21600 | [Dev][All Project] Sprint 9 | [Dev][All Project] Sprint 10
Story | RDAPS-204 | 31904 | [DEV][RD][BOF] Enhance Algolia payload to support displaying exclusive rewards in rewards store | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Highest | Done |  | 02/Oct/25 8:19 AM | 30/Oct/25 2:42 PM |  | 2 | mid-sprint | rr-backoffice |  | 0 | [Dev][All Project] Sprint 9 | มาจาก Sprint 9 | Ready To Test | 14400 | [Dev][All Project] Sprint 9 | [Dev][All Project] Sprint 10
Story | RDAPS-203 | 31890 | [DEV][RD][BFF] Enhance Get section/widget api for support display exclusive rewards on rewards store | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Highest | Done |  | 01/Oct/25 5:25 PM | 30/Oct/25 2:42 PM |  | 3 | BFF | mid-sprint |  | 0 | [Dev][All Project] Sprint 9 | มาจาก Sprint 9 | Ready To Test | 14400 | [Dev][All Project] Sprint 9 | [Dev][All Project] Sprint 10
Bug | DEVRDSUP-154 | 31874 | [SUP-215][RR App] Log in Problem - iOS แสดงหน้าจอ "มีบางอย่างผิดพลาด โปรดลองอีกครั้ง" | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Rejected |  | 01/Oct/25 12:06 AM | 31/Oct/25 9:54 AM | 28/Oct/25 12:00 AM |  | prod-issue |  |  |  | [Dev][All Project] Sprint 9 | มาจาก Sprint 9 | UNDER VALIDATION |  | [Dev][All Project] Sprint 10
Bug | DEVRDCT-241 | 31866 | [S3][CT][Webhook][Club Binding Event] Opt-in type club binding status event not show correctly on CT through Webhook API | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Open |  | 30/Sep/25 3:31 PM | 20/Oct/25 10:59 AM | [6 empty] | [Dev][CT] Sprint 9 | มาจาก Sprint 9 | Open |  | [Dev][CT] Sprint 10
Task | DEVRDSUP-153 | 31856 | Find and remove double bound 1 wallet card to multiple SSO to resolve DEVRDSUP-146 error for other users. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | In Progress |  | 30/Sep/25 1:40 PM | 31/Oct/25 9:51 AM |  | 5 |  |  |  |  | [Dev][All Project] Sprint 9 | มาจาก Sprint 9 | To Do |  | [Dev][All Project] Sprint 10
Story | RDTHANA-294 | 31845 | [Dev][RD][BFF] Improve get sections contents api v2 | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready To Test |  | 30/Sep/25 11:56 AM | 20/Oct/25 10:58 AM | 01/Oct/25 12:00 AM | 2 |  |  |  | 0 | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | Ready To Test | 14400 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Bug | RDAPS-201 | 31814 | [DEV][RD][Portal API][Cronjob] Add log to merchant ranking | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Closed |  | 29/Sep/25 3:00 PM | 31/Oct/25 9:57 AM | [6 empty] | [Dev][All Project] Sprint 9 | มาจาก Sprint 9 | Resolved |  | [Dev][All Project] Sprint 9 | [Dev][All Project] Sprint 10
Story | DEVRDSUP-150 | 31804 | [SUP-211][SUB][BTS] Couldn't mark used a BTS coupon used via wallet card, request to mark used the BTS coupon with wallet card. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 29/Sep/25 10:58 AM | 22/Oct/25 10:39 PM |  | 1 |  |  |  | 1800 | [Dev][All Project] Sprint 9 | มาจาก Sprint 9 | In Progress |  | [Dev][All Project] Sprint 10
Story | RDTHANA-289 | 31700 | [DEV][RD][BOF][CR] Enhance survey ranking question | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 26/Sep/25 2:02 PM | 20/Oct/25 10:58 AM | 30/Sep/25 12:00 AM | 3 |  |  |  | 0 | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | Ready To Test | 21600 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Task | RDAPS-198 | 31673 | [DEV][RD][Merchant Ranking] Add sync data log | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 26/Sep/25 9:39 AM | 31/Oct/25 9:57 AM |  | 3 |  |  |  |  | [Dev][All Project] Sprint 9 | มาจาก Sprint 9 | To Do |  | [Dev][All Project] Sprint 9 | [Dev][All Project] Sprint 10
Bug | RDTHANA-270 | 31550 | [S3][Edit Business Unit][Advanced setting] Feature setting not found due to click link out from error popup | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Closed |  | 23/Sep/25 5:19 PM | 31/Oct/25 11:08 AM | [6 empty] | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | UNDER VALIDATION |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-268 | 31545 | [Dev][RD][BOF] Disable mode when survey is expired | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 23/Sep/25 3:28 PM | 20/Oct/25 10:58 AM | 30/Sep/25 12:00 AM | 1 | rr-backoffice |  |  | 0 | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | Ready To Test | 3600 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Test Plan | RDTHANA-266 | 31540 | [TP][Thana city] Sprint 9 |  |  | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 23/Sep/25 2:06 PM | 20/Oct/25 10:58 AM | [6 empty] | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | To Do |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Epic | DEVRDECOM-107 | 31506 | Shopify Webhook |  |  | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | To Do |  | 23/Sep/25 9:52 AM | 20/Oct/25 9:57 AM | [6 empty] | [Dev][RD][Ecom] Sprint 9 | มาจาก Sprint 9 | To Do |  | [Dev][RD][Ecom] Sprint 9 | [Dev][RD][Ecom] Sprint 10
Sub-task | RDTHANA-259 | 31493 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 22/Sep/25 10:11 PM | 08/Oct/25 1:38 PM | [6 empty] | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | Done |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Sub-task | RDTHANA-258 | 31491 | [QA] Create Test Case - Enhance check eligible to set opt-in setting in advance setting | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 22/Sep/25 10:11 PM | 15/Oct/25 1:40 PM | [6 empty] | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | Done |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Sub-task | RDTHANA-256 | 31487 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 22/Sep/25 10:10 PM | 08/Oct/25 11:42 AM | [6 empty] | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | Done |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Sub-task | RDTHANA-254 | 31483 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 22/Sep/25 10:08 PM | 07/Oct/25 1:58 PM | [6 empty] | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | Done |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Sub-task | RDTHANA-253 | 31481 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 22/Sep/25 10:07 PM | 06/Oct/25 3:56 PM | [6 empty] | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | Done |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Sub-task | RDTHANA-252 | 31479 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 22/Sep/25 10:07 PM | 06/Oct/25 2:16 PM | [6 empty] | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | Done |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Sub-task | RDTHANA-251 | 31477 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 22/Sep/25 10:07 PM | 06/Oct/25 1:07 PM | [6 empty] | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | Done |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Sub-task | RDTHANA-250 | 31475 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 22/Sep/25 10:07 PM | 06/Oct/25 10:47 AM | [6 empty] | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | Done |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Sub-task | RDTHANA-249 | 31473 | [QA] Create Test Case View Survey List (FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 22/Sep/25 10:06 PM | 04/Oct/25 12:35 PM | [6 empty] | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | In Progress |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Sub-task | DEVRDADJ-47 | 31465 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 22/Sep/25 10:04 PM | 19/Oct/25 9:11 PM | [6 empty] | [Dev][RDAdjust] Sprint 9 | มาจาก Sprint 9 | Done |  | [Dev][RDAdjust] Sprint 9 | [Dev][RDAdjust] Sprint 10
Sub-task | DEVRDADJ-45 | 31461 | [QA] Create Test Case & Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 22/Sep/25 10:03 PM | 19/Oct/25 9:11 PM | [6 empty] | [Dev][RDAdjust] Sprint 9 | มาจาก Sprint 9 | Done |  | [Dev][RDAdjust] Sprint 9 | [Dev][RDAdjust] Sprint 10
Story | RDTHANA-244 | 31447 | [DEV][RD][APH] Enhance sorry page support dynamic error message and CTA button | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 22/Sep/25 11:36 AM | 20/Oct/25 10:58 AM | 29/Sep/25 12:00 AM | 1 |  |  |  |  | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | Blocked |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-241 | 31432 | [DEV][RD][APH] Enhance survey html render support survey appearance "Thank you" tab | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 21/Sep/25 9:13 PM | 20/Oct/25 10:58 AM | 29/Sep/25 12:00 AM | 3 |  |  |  |  | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-240 | 31431 | [DEV][RD][APH] Enhance survey html render support survey appearance "Email" tab (Issue point form) | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | In Progress |  | 21/Sep/25 9:13 PM | 03/Nov/25 11:32 AM | 26/Sep/25 12:00 AM | 5 |  |  |  |  | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-239 | 31430 | [DEV][RD][APH] Enhance survey html render support survey appearance "Survey Q&A" tab | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 21/Sep/25 9:13 PM | 20/Oct/25 10:58 AM | 26/Sep/25 12:00 AM | 8 |  |  |  |  | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-238 | 31429 | [DEV][RD][APH] Create survey theme | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Highest | Ready To Test |  | 21/Sep/25 8:49 PM | 20/Oct/25 10:58 AM | 23/Sep/25 12:00 AM | 3 | rr-aphrodite |  |  |  | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-236 | 31426 | [Dev][RD][BOF] Rename all related feature and field from ‘Exclusive Store’ ‘Exclusive Partner Store’ to ‘Club - Rewards’ | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 21/Sep/25 2:16 PM | 20/Oct/25 10:58 AM | 01/Oct/25 12:00 AM | 2 | rr-backoffice | rr-scheduler |  |  | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | Ready To Test |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | DEVRDECOM-101 | 31425 | [DEV][RD][Eco][Shopify-Theme] Update theme to support Rabbit Connect logout. | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 21/Sep/25 10:03 AM | 30/Oct/25 3:10 PM |  | 2 | No-QA |  |  | 10800 | [Dev][RD][Ecom] Sprint 10
Story | DEVRDECOM-99 | 31423 | [DEV][RD][Eco][RR-Ecommerce-Shopify] Create Webhook API Endpoint refunds/create | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 21/Sep/25 9:47 AM | 24/Oct/25 3:41 PM | 01/Oct/25 12:00 AM | 3 |  |  |  |  | [Dev][RD][Ecom] Sprint 9 | มาจาก Sprint 9 | Ready To Test |  | [Dev][RD][Ecom] Sprint 9 | [Dev][RD][Ecom] Sprint 10
Story | DEVRDECOM-98 | 31422 | [DEV][RD][Eco][Deployment] Production preparation | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 21/Sep/25 9:42 AM | 30/Oct/25 3:11 PM |  | 3 | No-QA |  |  | 28800 | [Dev][RD][Ecom] Sprint 10
Story | DEVRDECOM-97 | 31421 | [DEV][RD][Eco][RR-Ecommerce-Shopify] Calculate Point | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 21/Sep/25 9:35 AM | 24/Oct/25 3:42 PM |  | 1 |  |  |  |  | [Dev][RD][Ecom] Sprint 9 | มาจาก Sprint 9 | Ready To Test | 7200 | [Dev][RD][Ecom] Sprint 9 | [Dev][RD][Ecom] Sprint 10
Story | RDTHANA-247 | 31385 | [DEV][RD][Eco][RR-Ecommerce-Shopify][Das Haus] Create Endpoint for Club Binding Callback and Redirect to Shopify | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 19/Sep/25 1:53 PM | 29/Oct/25 7:20 PM | 03/Oct/25 12:00 AM | 3 |  |  |  |  | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-232 | 31360 | [DEV][RD][GATEWAY] Mapping get member club detail with internal API | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Highest | Ready To Test |  | 19/Sep/25 10:44 AM | 20/Oct/25 10:58 AM |  | 1 |  |  |  |  | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | Ready To Test | 7200 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-231 | 31359 | [DEV][RD][APH] Enhance survey html render support survey appearance "General" tab | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 19/Sep/25 10:43 AM | 20/Oct/25 10:58 AM | 26/Sep/25 12:00 AM | 5 |  |  |  |  | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-230 | 31358 | [DEV][RD][APH] Enhance getMemberToken support sources session | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 19/Sep/25 10:42 AM | 20/Oct/25 10:58 AM | 26/Sep/25 12:00 AM | 2 |  |  |  |  | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | Ready To Test | 7200 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | DEVRDECOM-90 | 31343 | [DEV][RD][Eco][RR-Ecommerce-Shopify] Create Scheduled Job for update transport status | Art: Narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 18/Sep/25 7:27 PM | 24/Oct/25 3:42 PM |  | 5 | ecommerce-shopify-api |  |  |  | [Dev][RD][Ecom] Sprint 9 | มาจาก Sprint 9 | Ready To Test |  | [Dev][RD][Ecom] Sprint 9 | [Dev][RD][Ecom] Sprint 10
Story | RDTHANA-245 | 31334 | [DEV][RD][Eco][RR-Ecommerce-Shopify][Das Haus] Enhance Auth Callback Endpoint to checks if the customer is a Das Haus club member. | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 18/Sep/25 5:09 PM | 29/Oct/25 7:20 PM |  | 5 | ecommerce-shopify-api |  |  |  | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | RDAPS-191 | 31333 | [Dev][RD][SA] Enhance Subscription Transactions Search with Advanced Filters & Index Optimization | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Done |  | 18/Sep/25 4:48 PM | 23/Oct/25 6:08 PM |  | 2 | rr-backoffice |  |  | 14400 | [Dev][All Project] Sprint 10
Story | RDTHANA-229 | 31332 | [DEV][RD][APH] Enhance survey available middleware | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 18/Sep/25 4:23 PM | 20/Oct/25 10:58 AM | 26/Sep/25 12:00 AM | 5 |  |  |  |  | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-227 | 31330 | [DEV][RD][HRS] Enhance check eligible to set opt-in setting in popup welcome message | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Done |  | 18/Sep/25 4:06 PM | 22/Oct/25 9:47 AM |  | 2 |  |  |  |  | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | Ready To Test |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-226 | 31329 | [DEV][RD][HRS] Enhance check eligible to set opt-in setting in advance setting | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Done |  | 18/Sep/25 4:05 PM | 22/Oct/25 9:47 AM |  | 3 |  |  |  |  | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | Ready To Test |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-224 | 31327 | [DEV][RD][HRS] Enhance feature setting company level with opt-in BU enable | Art: Narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Done |  | 18/Sep/25 3:59 PM | 22/Oct/25 9:47 AM | 29/Sep/25 12:00 AM | 5 |  |  |  |  | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | Ready To Test |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-246 | 31325 | [DEV][RD][Eco][RR-Ecommerce-Shopify][Das Haus] Enhance login with return_url | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 18/Sep/25 3:22 PM | 29/Oct/25 7:20 PM |  | 2 | ecommerce-shopify-api |  |  |  | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | Ready To Test | 10800 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | DEVRDADJ-44 | 31314 | [DEV][RD][BOF] Enhance RR Backoffice to integrate with ADJUST Deeplink Generated api | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 18/Sep/25 1:53 PM | 30/Oct/25 4:01 PM |  | 5 |  |  |  |  | [Dev][RDAdjust] Sprint 9 | มาจาก Sprint 9 | Ready To Test | 57600 | [Dev][RDAdjust] Sprint 9 | [Dev][RDAdjust] Sprint 10
Story | DEVRDADJ-41 | 31311 | [DEV][RD][LNF] Enhance auto generate deeplink, remove redirect url in request | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 18/Sep/25 1:45 PM | 30/Oct/25 4:01 PM | 25/Sep/25 12:00 AM | 2 |  |  |  |  | [Dev][RDAdjust] Sprint 9 | มาจาก Sprint 9 | Ready To Test | 14400 | [Dev][RDAdjust] Sprint 9 | [Dev][RDAdjust] Sprint 10
Sub-task | RDTHANA-134 | 30844 | [QA] Create Test Case Download Individual Survey Report (FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:30 AM | 05/Oct/25 3:00 PM | [6 empty] | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | In Progress |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Sub-task | RDTHANA-133 | 30842 | [QA] Create Test Case View Survey Report (FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:30 AM | 05/Oct/25 2:50 PM | [6 empty] | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | In Progress |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Sub-task | RDTHANA-132 | 30840 | [QA] Create Test Case Change survey status (FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:30 AM | 04/Oct/25 12:24 PM | [6 empty] | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | In Progress |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Sub-task | RDTHANA-131 | 30838 | [QA] |  |  | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 09/Sep/25 11:29 AM | 21/Sep/25 3:00 PM | [6 empty] | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | To Do |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Sub-task | RDTHANA-130 | 30836 | [QA] Create Test Case Update survey Step 5: Survey Appearance (Thank You) (FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:29 AM | 04/Oct/25 12:32 PM | [6 empty] | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | In Progress |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Sub-task | RDTHANA-129 | 30834 | [QA] Create Test Case Update survey Step 5: Survey Appearance (Input E-mail) (FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:29 AM | 21/Sep/25 3:01 PM | [6 empty] | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | In Progress |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Sub-task | RDTHANA-128 | 30832 | [QA] Create Test Case [Dev][RD][BOF] Update survey step5.2(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:29 AM | 21/Sep/25 1:58 PM | [6 empty] | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | In Progress |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Sub-task | RDTHANA-127 | 30830 | [QA] Create Test Case Update survey step5.1(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:28 AM | 21/Sep/25 1:55 PM | [6 empty] | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | In Progress |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Sub-task | RDTHANA-126 | 30828 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 09/Sep/25 11:28 AM | 17/Oct/25 6:00 PM | [6 empty] | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | Done |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Sub-task | RDTHANA-125 | 30826 | [QA] Create Test Case Update survey step4.2(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:28 AM | 21/Sep/25 1:55 PM | [6 empty] | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | In Progress |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Sub-task | RDTHANA-124 | 30824 | [QA] Create Test Case Update survey step4.1(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:27 AM | 21/Sep/25 1:55 PM | [6 empty] | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | In Progress |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Sub-task | RDTHANA-123 | 30822 | [QA] Create Test Case Update survey step3(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:27 AM | 21/Sep/25 1:55 PM | [6 empty] | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | In Progress |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Sub-task | RDTHANA-122 | 30820 | [QA] Create Test Case Update survey step2(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:26 AM | 21/Sep/25 12:27 PM | [6 empty] | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | In Progress |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Sub-task | RDTHANA-121 | 30818 | [QA] Create Test Case Update survey step1(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:26 AM | 21/Sep/25 12:27 PM | [6 empty] | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | In Progress |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Sub-task | RDTHANA-120 | 30816 | [QA] Create Test Case Create survey (FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:25 AM | 21/Sep/25 12:27 PM | [6 empty] | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | In Progress |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Sub-task | RDTHANA-119 | 30814 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 09/Sep/25 11:24 AM | 09/Sep/25 11:24 AM | [6 empty] | [Dev][Thana City] sprint 6 | มาจาก Sprint 9 | To Do |  | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Sub-task | RDTHANA-118 | 30812 | [QA] Create Test Case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 09/Sep/25 11:23 AM | 09/Sep/25 11:23 AM | [6 empty] | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | To Do |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Sub-task | RDTHANA-117 | 30810 | [QA] Create Test Case | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 09/Sep/25 11:23 AM | 09/Sep/25 11:23 AM | [6 empty] | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | To Do |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Sub-task | RDTHANA-116 | 30808 | [QA] Create Test Case 'Club - Benefits & Info' Location | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 09/Sep/25 11:22 AM | 15/Oct/25 3:36 PM | [6 empty] | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | Done |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Sub-task | RDTHANA-115 | 30806 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 09/Sep/25 11:22 AM | 09/Sep/25 11:22 AM | [6 empty] | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | To Do |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Sub-task | RDTHANA-114 | 30804 | [QA] Create Test Case Widget Type 'Club – Benefits & Information' | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 09/Sep/25 11:21 AM | 15/Oct/25 3:45 PM | [6 empty] | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | Done |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-113 | 30734 | [Dev][RD][BOF][Service] Change service status | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 07/Sep/25 3:21 PM | 03/Nov/25 3:14 PM | 19/Sep/25 12:00 AM | 5 |  |  |  |  | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-107 | 30691 | [Dev][RD][APH] Cronjob update survey to expired | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 04/Sep/25 4:56 PM | 20/Oct/25 10:58 AM | 26/Sep/25 12:00 AM | 3 | rr-aphrodite |  |  |  | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | Ready To Test | 21600 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-106 | 30689 | [Dev][RD][Service][CMS API] Create service filter api | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 04/Sep/25 4:08 PM | 20/Oct/25 10:58 AM | 11/Sep/25 12:00 AM | 3 | cms-api | No-QA |  |  | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | Ready To Test | 18000 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-105 | 30687 | [Dev][RD][APH][CT] CleverTap Event | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 04/Sep/25 3:56 PM | 31/Oct/25 2:06 PM |  | 5 |  |  |  | 28800 | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | In Progress | 57600 -> 28800 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | DEVRDECOM-73 | 30661 | [DEV][RD][Eco][RR-Ecommerce-Shopify] Create Webhook API Endpoint orders | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 04/Sep/25 1:17 PM | 24/Oct/25 3:42 PM | 25/Sep/25 12:00 AM | 5 | ecommerce-shopify-api | No-QA |  |  | [Dev][RD][Ecom] Sprint 9 | มาจาก Sprint 9 | Ready To Test |  | [Dev][RD][Ecom] Sprint 9 | [Dev][RD][Ecom] Sprint 10
Bug | DEVRDSUP-119 | 30657 | [SUP-162]Clevertap - "LINE_FRIEND_STATUS" value is not correct | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Rejected |  | 04/Sep/25 11:35 AM | 28/Oct/25 10:30 AM | [6 empty] | [BU][CT] Sprint 7 |  |  |  | [Dev][All Project] Sprint 10
Bug | DEVRDSUP-118 | 30656 | [SUP-165]Clevertap : Charge Event : Type "SPENDING_PARTNER". Some Turtle shop event not get feed to the platform | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Closed ( Change Request) |  | 04/Sep/25 11:31 AM | 31/Oct/25 9:51 AM | [6 empty] | [Dev][All Project] Sprint 9 | มาจาก Sprint 9 | UNDER VALIDATION |  | [Dev][All Project] Sprint 10
Story | RDTHANA-97 | 30645 | [Dev][RD][BOF][Service] Edit page step 2. | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 03/Sep/25 4:58 PM | 03/Nov/25 3:14 PM | 17/Sep/25 12:00 AM | 8 |  |  |  |  | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | Ready To Test | 86400 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-96 | 30642 | [Dev][RD][BOF][Service] Edit page step 1. | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 03/Sep/25 4:54 PM | 03/Nov/25 3:14 PM | 19/Sep/25 12:00 AM | 5 |  |  |  |  | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | Ready To Test |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-95 | 30641 | [Dev][RD][BOF][Service] Create page step 1 | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 03/Sep/25 4:52 PM | 03/Nov/25 3:14 PM | 12/Sep/25 12:00 AM | 8 |  |  |  | 0 | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | Ready To Test |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-94 | 30639 | [Dev][RD][BOF][Service] create service index page | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 03/Sep/25 4:19 PM | 03/Nov/25 3:13 PM | 12/Sep/25 12:00 AM | 8 |  |  |  | 0 | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Epic | DEVRDADJ-34 | 30635 | MAID registration |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 03/Sep/25 4:08 PM | 20/Oct/25 11:02 AM | [6 empty] | [Dev][RDAdjust] Sprint 9 | มาจาก Sprint 9 | To Do |  | [Dev][RDAdjust] Sprint 9 | [Dev][RDAdjust] Sprint 10
Story | RDTHANA-90 | 30622 | [Dev][RD][Section][BOF][QA] Enhance Section Feature: Add new widget types | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Sep/25 9:16 PM | 20/Oct/25 10:58 AM |  | 0 |  |  |  |  | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | Ready To Test |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-89 | 30621 | [Dev][RD][Section][BOF] Enhance Section Feature: Add 'Club - Benefits & Info' Location | Art: Narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Sep/25 8:56 PM | 31/Oct/25 4:22 PM |  | 5 | rr-backoffice |  |  |  | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | Ready To Test |  | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-88 | 30620 | [Dev][RD][Widget][BOF] Enhance Widget Feature: Add 'Service' Type | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Sep/25 8:56 PM | 20/Oct/25 10:58 AM | 11/Sep/25 12:00 AM | 5 | rr-backoffice |  |  |  | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-87 | 30619 | [Dev][RD][Widget][BOF] Enhance Widget Feature: Add 'Club – Benefits & Information' Type | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Sep/25 8:56 PM | 31/Oct/25 4:22 PM | 10/Sep/25 12:00 AM | 5 | rr-backoffice |  |  |  | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-86 | 30618 | [Dev][RD][BOF] Update survey Step 5: Survey Appearance (Thank You) (FE&BE) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Sep/25 8:44 PM | 31/Oct/25 4:22 PM | 15/Sep/25 12:00 AM | 2 | rr-backoffice |  |  |  | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | Ready To Test | 10800 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-81 | 30606 | [Dev][RD][BOF] Change survey status (FE&BE) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Sep/25 3:26 PM | 31/Oct/25 4:22 PM | 16/Sep/25 12:00 AM | 3 | rr-backoffice |  |  |  | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-80 | 30604 | [Dev][RD][BOF] Update survey Step 5: Survey Appearance (Input E-mail) (FE&BE) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Sep/25 3:25 PM | 31/Oct/25 4:22 PM | 15/Sep/25 12:00 AM | 2 | rr-backoffice |  |  |  | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | Ready To Test | 10800 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-79 | 30602 | [Dev][RD][BOF] Update survey step5.2(FE&BE) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Sep/25 3:24 PM | 31/Oct/25 4:22 PM | 12/Sep/25 12:00 AM | 2 | rr-backoffice |  |  |  | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | Ready To Test | 10800 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | DEVRDSUP-115 | 30548 | [SUP-164][SSO] Request to remove all consents for RR member who never opted to consent, system auto consent to new users who registered from other source. | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | In Review |  | 01/Sep/25 5:17 PM | 02/Nov/25 3:02 PM | 09/Oct/25 12:00 AM | [5 empty] | [Dev][All Project] Sprint 10 | มาจาก Sprint 9 | To Do
Story | RDTHANA-74 | 30366 | [Dev][RD][BOF] Update survey step4.2(FE&BE) | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:15 PM | 31/Oct/25 4:22 PM |  | 2 | rr-backoffice |  |  |  | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-73 | 30364 | [Dev][RD][BOF] Download Individual Survey Report (FE&BE) | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:15 PM | 31/Oct/25 4:22 PM | 18/Sep/25 12:00 AM | 5 | rr-backoffice |  |  |  | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-72 | 30362 | [Dev][RD][BOF] Update survey step5.1(FE&BE) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:15 PM | 31/Oct/25 4:22 PM | 12/Sep/25 12:00 AM | 3 | rr-backoffice |  |  |  | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-71 | 30360 | [Dev][RD][BOF] Update survey step4.1(FE&BE) | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:15 PM | 31/Oct/25 4:22 PM |  | 8 | rr-backoffice |  |  |  | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | Ready To Test | 86400 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-70 | 30358 | [Dev][RD][BOF] Update survey step3(FE&BE) | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:14 PM | 31/Oct/25 4:22 PM |  | 5 | rr-backoffice |  |  |  | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-69 | 30356 | [Dev][RD][BOF] Update survey step2(FE&BE) | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:09 PM | 31/Oct/25 4:22 PM | 16/Sep/25 12:00 AM | 3 | rr-backoffice |  |  |  | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-68 | 30354 | [Dev][RD][BOF] View Survey Report (FE&BE) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:09 PM | 31/Oct/25 4:22 PM | 17/Sep/25 12:00 AM | 3 | rr-backoffice |  |  |  | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-67 | 30352 | [Dev][RD][BOF] View Survey List (FE&BE) | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:09 PM | 31/Oct/25 4:22 PM |  | 5 | rr-backoffice |  |  |  | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | Ready To Test | 86400 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-66 | 30350 | [Dev][RD][BOF] Update survey step1(FE&BE) | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:09 PM | 31/Oct/25 4:22 PM | 15/Sep/25 12:00 AM | 3 | rr-backoffice |  |  |  | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-65 | 30348 | [Dev][RD][BOF] Create survey (FE&BE) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:08 PM | 31/Oct/25 4:22 PM | 11/Sep/25 12:00 AM | 5 | rr-backoffice |  |  |  | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | Ready To Test | 43200 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Bug | DEVRDADJ-25 | 30110 | [S2][Adjust] When change internal name URL not update and can't open | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | UNDER VALIDATION |  | 22/Aug/25 11:12 AM | 31/Oct/25 4:16 PM | [6 empty] | [Dev][RDAdjust] Sprint 9 | มาจาก Sprint 9 | UNDER VALIDATION |  | [Dev][RDAdjust] Sprint 10
Story | RDTHANA-43 | 30086 | [DEV][RD][DasHaus][BFF] Verify the API to validate matching account | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 22/Aug/25 6:12 AM | 20/Oct/25 10:58 AM |  | 1 | BFF |  |  |  | [Dev][Thana City] sprint 6 | มาจาก Sprint 9 | Ready To Test |  | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Bug | DEVRDADJ-24 | 30062 | [S2][Adjust] Deeplinks can be opened when the rewards status is other than Active. | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Closed |  | 21/Aug/25 4:22 PM | 24/Oct/25 4:46 PM | 22/Oct/25 12:00 AM | 2 |  |  |  |  | [Dev][RDAdjust] Sprint 9 | มาจาก Sprint 9 | UNDER VALIDATION |  | [Dev][RDAdjust] Sprint 10
Story | RDAPS-160 | 29972 | [DEV][RD][SSO-Backoffice] Disable SEO tracking | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 20/Aug/25 11:21 AM | 20/Oct/25 10:57 AM | 04/Sep/25 12:00 AM | 1 |  |  |  | 7200 | [Dev][All project]Sprint 6 | มาจาก Sprint 9 | Ready To Test |  | [Dev][All project]Sprint 7 | [Dev][All Project] Sprint 9 | [Dev][All Project] Sprint 10
Story | RDTHANA-20 | 29950 | [Dev][RD][APH] Enhance check token | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 19/Aug/25 7:46 PM | 20/Oct/25 10:58 AM |  | 3 |  |  |  |  | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-19 | 29948 | [Dev][RD][Section][BOF] Enhance Section Index Page | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 19/Aug/25 7:45 PM | 31/Oct/25 4:22 PM |  | 2 |  |  |  |  | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | Ready To Test | 7200 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-16 | 29942 | [Dev][RD][Section][BFF] Enhance Sections API | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 19/Aug/25 7:44 PM | 20/Oct/25 10:58 AM |  | 5 | BFF |  |  |  | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-15 | 29940 | [Dev][RD][Widget][CMS API] Enhance Widget API | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 19/Aug/25 7:41 PM | 20/Oct/25 10:58 AM |  | 2 | cms-api |  |  |  | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | Ready To Test | 3600 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Story | RDTHANA-14 | 29938 | [Dev][RD][Section][CMS API] Enhance Sections API | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 19/Aug/25 7:37 PM | 20/Oct/25 10:58 AM |  | 2 | cms-api |  |  |  | [Dev][RD][Thana] Sprint 7 | มาจาก Sprint 9 | Ready To Test | 14400 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10
Bug | DEVRDSUP-95 | 29929 | [SUP-54][Noti] Whole NBO page gets frozen when user uses "internal link" and tries to search for internal content. | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Lowest | Resolved |  | 19/Aug/25 4:47 PM | 31/Oct/25 9:58 AM | 19/Sep/25 12:00 AM | 3 |  |  |  |  | [Dev][All Project] Sprint 10
Bug | DEVRDSUP-93 | 29890 | [SUP-132][APP] Reward search result doesn't show out of stock on search result and category filter. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | RETESTING |  | 19/Aug/25 11:33 AM | 30/Oct/25 2:41 PM | 02/Sep/25 12:00 AM | 2 | rewards-api |  |  |  | [Dev][All Project] Sprint 9 | มาจาก Sprint 9 | UNDER VALIDATION |  | [Dev][All Project] Sprint 9 | [Dev][All Project] Sprint 10
Bug | DEVRDSUP-87 | 29667 | [SUP-124][HR Solution] Enable to scan QR and get point when Inactive Campaign BU Allocation | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Rejected |  | 13/Aug/25 4:22 PM | 31/Oct/25 9:48 AM | 28/Aug/25 12:00 AM |  | hr-solution |  |  |  | [Dev][All Project] Sprint 10
Story | DEVRDECOM-33 | 29547 | [DEV][RD][Eco][Ecommerce-Shopify] Enhance API Endpoint for Order refunded Webhook | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 10/Aug/25 9:11 PM | 24/Oct/25 3:41 PM |  | 3 | ecommerce-shopify-api |  |  | 28800 | [Dev][RD][Ecom] Sprint 9 | มาจาก Sprint 9 | Ready To Test |  | [Dev][RD][Ecom] Sprint 10
Story | DEVRDECOM-25 | 28845 | [DEV][RD][Eco][Ecommerce-Shopify] Enhance API Endpoint for Order Cancelled Webhook | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 29/Jul/25 12:49 PM | 24/Oct/25 3:42 PM | 01/Oct/25 12:00 AM | 5 | ecommerce-shopify-api |  |  |  | [Dev][RD][Ecom] Sprint 9 | มาจาก Sprint 9 | Ready To Test | 72000 | [Dev][RD][Ecom] Sprint 9 | [Dev][RD][Ecom] Sprint 10
Story | DEVRDECOM-24 | 28843 | [DEV][RD][Eco][RR-Ecommerce-Shopify] Create Scheduled Job for Point Issuance | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 29/Jul/25 11:07 AM | 24/Oct/25 3:42 PM | 02/Oct/25 12:00 AM | 5 | ecommerce-shopify-api |  |  |  | [Dev][RD][Ecom] Sprint 9 | มาจาก Sprint 9 | Ready To Test |  | [Dev][RD][Ecom] Sprint 9 | [Dev][RD][Ecom] Sprint 10
Story | RDTHANA-248 | 28841 | [DEV][RD][Eco][RR-Ecommerce-Shopify][Das Haus] Enhance email verify callback with return_url | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 29/Jul/25 9:57 AM | 29/Oct/25 7:20 PM |  | 2 | ecommerce-shopify-api |  |  |  | [Dev][RD][Thana] Sprint 9 | มาจาก Sprint 9 | Ready To Test | 7200 | [Dev][RD][Thana] Sprint 9 | [Dev][RD][Thana] Sprint 10

## Summarize Sprint 9
Column 1 | Total Stories Point | Total Manhour | Point Done | Manhour Done | Note
6 Oct - 17 Oct
Dev Resource Available | 14 | 435.5
Meeting Planned |  | 198.5 |  |  | Ref
Additional Meeting |  | 7.5 |  |  | Ref
Deployment |  | 5 |  |  | 3 ครั้ง 1. 3 คน 2. 1 คน 3. 1 คน
Development Sprint Total | 394 | 260.67 | 74 | 99.67
Ad-hoc Mid Sprint | 10 | 3.5 | 3 | 3.5 | 3 tasks
Requirement changes after refinement? | 0 | 0 | 0 | 0 | 0 tasks
Aek | 32 | 16.67 | 11 | 2.67
A | 43 | 46 | 12 | 24
Aom | 40 | 36 | 12 | 8
Zan | 18 | 33 | 10 | 17
Mai | 45 | 4 | 3 | 0
Mac | 44 | 21 | 3 | 6
Mos | 48 | 42 | 13 | 34
Jack | 24 | 10 | 7 | 8
Art | 0 | 0 | 0 | 0
Kae | 31 | 24 | 0 | 0
Nim | 46 | 28 | 0 | 0
| System Architech |  |  |  | Permanent Dev. |  |  | Outsources
Projects (Stories Points) | Aek | Zan | Aom | Jack | A | Art | Mai | Kae | Mac | Nim | Mos
Das Haus - Thana City & Das Haus | 4 | 5 | 1 | 8 | 23 | 0 | 36 | 23 | 38 | 30 | 26
E-commerce 1.1. E-Commerce x Shopify Plus 1.2. Shopify:Snackmaker 1.3. Shopify: Turtle Delivery 1.4. Shopify: Turtle Delivery | 14 | 1 | 2 | 8 | 10 | 0 | 3 | 8 | 3 | 2 | 14
CleverTap - MKT Automation Tool | 9 | 0 | 2 | 7 | 0 | 0 | 0 | 4 | 0 | 4 | 4
Adjust Integration | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 5 | 0
Adhoc - Non-Epics - Turtle Display club tier on POS - Data Mart Migration | 3 | 11 | 20 | 1 | 10 | 0 | 4 | 0 | 3 | 0 | 4
Support Incidents | 2 | 1 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| System Architech |  |  |  | Permanent Dev. |  |  | Outsources
Projects (Manhour) | Aek | Zan | Aom | Jack | A | Art | Mai | Kae | Mac | Nim | Mos
Das Haus - Thana City & Das Haus | 0 | 16 | 0 | 0 | 2 | 0 | 2 | 16 | 11 | 0 | 0
E-commerce 1.1. E-Commerce x Shopify Plus 1.2. Shopify:Snackmaker 1.3. Shopify: Turtle Delivery 1.4. Shopify: Turtle Delivery | 3.5 | 0 | 1 | 0 | 20 | 0 | 0 | 8 | 4 | 4 | 24
CleverTap - MKT Automation Tool | 9 | 0 | 0 | 10 | 4 | 0 | 0 | 0 | 0 | 24 | 10
Adjust Integration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Adhoc - Non-Epics - Turtle Display club tier on POS - Data Mart Migration | 2 | 16 | 6 | 0 | 20 | 0 | 2 | 0 | 6 | 0 | 8
Support Incidents | 2.17 | 1 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 9
Issue Type | Issue key | Issue id | Summary | Assignee | Assignee Id | Reporter | Reporter Id | Priority | Status | Resolution | Created | Updated | Due date | Custom field (Story Points) | Labels | Labels | Labels | Original estimate | Sprint Movement | Sprint 8 | Note | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint
Sub-task | DEVRDCT-267 | 32656 | [DEV][RD][CT] Run script feed RR_GENDER field to user property | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Done |  | 17/Oct/25 10:44 AM | 17/Oct/25 11:04 AM | 17/Oct/25 12:00 AM |  | sso-mimir |  |  | 14400 |  |  |  | [Dev][CT] Sprint 9
Story | RDAPS-231 | 32654 | [SUP-239][ETL][OnlyAug] Catch-up redemption data (item_id, using_at, and countdown_expired_at) | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 17/Oct/25 9:57 AM | 17/Oct/25 3:00 PM |  | 2 | mid-sprint | No-QA |  | 10800 |  |  |  | [Dev][All Project] Sprint 9
Sub-task | DEVRDSUP-188 | 32652 | QA verify on UAT | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 16/Oct/25 6:28 PM | 16/Oct/25 6:53 PM | [9 empty] | [Dev][All Project] Sprint 9
Story | DEVRDSUP-187 | 32649 | Remove incorrect binding of a wallet card, incorrect binding causes user to not be able to purchase online/ offline package | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Done |  | 16/Oct/25 4:50 PM | 17/Oct/25 9:00 AM | 17/Oct/25 12:00 AM | 1 | sub |  |  | 600 |  |  |  | [Dev][All Project] Sprint 9
Story | RDAPS-230 | 32647 | [Dev][RD][SA] Analyze & split dev tasks for Sprint10 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 16/Oct/25 3:14 PM | 16/Oct/25 3:16 PM |  | 3 | No-QA | [6 empty] | [Dev][All Project] Sprint 9
Story | DEVRDCT-266 | 32646 | [Dev][RD][SA] Analyze & split dev tasks for Sprint10 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 16/Oct/25 3:12 PM | 16/Oct/25 3:18 PM |  | 2 | No-QA | [6 empty] | [Dev][CT] Sprint 9
Bug | RDTHANA-330 | 32632 | [S3][Service][shopify] Shop ID NOT return as UUID | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Closed |  | 16/Oct/25 2:41 PM | 17/Oct/25 11:31 AM | [9 empty] | [Dev][RD][Thana] Sprint 9
Bug | DEVRDSUP-184 | 32628 | [SUP-244][REM] Redeem mail alert sends to user even if "E-mail alert to user after redeemed" is turned off. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Low | RETESTING |  | 16/Oct/25 12:46 PM | 17/Oct/25 5:07 PM | 14/Nov/25 12:00 AM | 1 | prod-issue | rem |  | 7200 |  |  |  | [Dev][All Project] Sprint 9
Story | DEVRDECOM-136 | 32614 | [DEV][RD][Eco][Ecommerce-Shopify] Resolve all remaining issues in the entire workflow | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 16/Oct/25 9:26 AM | 17/Oct/25 9:34 AM |  | 5 | No-QA |  |  | 57600 |  |  |  | [Dev][RD][Ecom] Sprint 9
Story | DEVRDECOM-135 | 32568 | [DEV][RD][Eco][Ecommerce-Shopify] Improvement Cronjob check warehouse status | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 16/Oct/25 9:21 AM | 17/Oct/25 9:35 AM | 17/Oct/25 12:00 AM | 5 | No-QA | rr-ecommerce-shopify |  | 28800 |  |  |  | [Dev][RD][Ecom] Sprint 9
Story | DEVRDCT-262 | 32567 | [DEV][RD][USR] Enhance check duplicate line id for binding line pay | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 16/Oct/25 8:30 AM | 17/Oct/25 4:24 PM |  | 1 | sso-user | [6 empty] | [Dev][CT] Sprint 9
Sub-task | RDTHANA-329 | 32558 | [QA] Test execution | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 15/Oct/25 3:44 PM | 15/Oct/25 3:46 PM | [9 empty] | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Sub-task | RDTHANA-328 | 32555 | [QA] Test execution | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 15/Oct/25 3:32 PM | 15/Oct/25 3:36 PM | [9 empty] | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Task | RDAPS-225 | 32554 | [SUP-243][REM] Group Rewards - Lucky Draw Amazfit | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 15/Oct/25 3:25 PM | 15/Oct/25 3:29 PM |  | 1 | mid-sprint | No-QA |  | 1800 |  |  |  | [Dev][All Project] Sprint 9
Sub-task | RDTHANA-327 | 32552 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | In Progress |  | 15/Oct/25 2:38 PM | 15/Oct/25 2:38 PM | [9 empty] | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Sub-task | RDTHANA-326 | 32551 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | In Progress |  | 15/Oct/25 2:38 PM | 15/Oct/25 2:38 PM | [9 empty] | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Sub-task | RDTHANA-325 | 32550 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 15/Oct/25 2:38 PM | 15/Oct/25 3:21 PM | [9 empty] | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Sub-task | RDTHANA-324 | 32549 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | In Progress |  | 15/Oct/25 2:38 PM | 15/Oct/25 2:38 PM | [9 empty] | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Sub-task | RDTHANA-323 | 32548 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 15/Oct/25 2:37 PM | 15/Oct/25 3:08 PM | [9 empty] | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Test Execution | RDTHANA-322 | 32547 | [TX][Thana city] Feature menu - Sprint 9 |  |  | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | In Progress |  | 15/Oct/25 2:22 PM | 15/Oct/25 3:38 PM | [9 empty] | [Dev][RD][Thana] Sprint 9
Test Plan | RDTHANA-321 | 32546 | [TP][Thana city] Feature menu - Sprint 9 |  |  | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | To Do |  | 15/Oct/25 2:11 PM | 15/Oct/25 3:38 PM | [9 empty] | [Dev][RD][Thana] Sprint 9
Sub-task | DEVRDCT-261 | 32517 | [QA] Test execution Change "Gender" to "RR_GENDER" field to user property | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 15/Oct/25 2:01 PM | 16/Oct/25 10:58 AM | [9 empty] | [Dev][CT] Sprint 9
Sub-task | RDAPS-224 | 32509 | [QA] Create Test Case & Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 15/Oct/25 10:58 AM | 15/Oct/25 10:58 AM | [9 empty] | [Dev][All Project] Sprint 9
Sub-task | DEVRDCT-260 | 32287 | [QA] Test execution | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 14/Oct/25 7:05 PM | 15/Oct/25 5:40 PM | [9 empty] | [Dev][CT] Sprint 7 | [Dev][CT] Sprint 8 | [Dev][CT] Sprint 9
Sub-task | DEVRDCT-259 | 32285 | [QA] Test execution | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 14/Oct/25 7:04 PM | 15/Oct/25 5:38 PM | [9 empty] | [Dev][CT] Sprint 7 | [Dev][CT] Sprint 8 | [Dev][CT] Sprint 9
Sub-task | DEVRDSUP-180 | 32281 | [Dev][SUP-240] Generate receipt for https://rr-backoffice.rabbit.co.th/dashboard/subscription/v2/orders/68e9c4e0088c8e7563e3e1bf | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 14/Oct/25 6:15 PM | 15/Oct/25 9:43 AM | [9 empty] | [Dev][All Project] Sprint 9
Sub-task | DEVRDSUP-179 | 32279 | [Dev][SUP-240] Root cause finding | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 14/Oct/25 6:14 PM | 15/Oct/25 11:44 AM | [9 empty] | [Dev][All Project] Sprint 9
Bug | DEVRDSUP-178 | 32277 | [SUP-240]SUB : Completed Transaction but did not generate receipt (Ticket 14 Oct) | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Closed |  | 14/Oct/25 6:13 PM | 17/Oct/25 9:46 AM | 28/Oct/25 12:00 AM | 1 | prod-issue | sub |  | 7200 |  |  |  | [Dev][All Project] Sprint 9
Story | RDTHANA-320 | 32261 | [DEV][RD][GATEWAY] Mapping new gateway endpoint | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 14/Oct/25 2:31 PM | 17/Oct/25 10:13 AM |  | 1 |  |  |  | 7200 |  |  |  | [Dev][RD][Thana] Sprint 9
Story | DEVRDCT-258 | 32213 | [DEV][RD][RLP][WEP] LINE_PAY_BINDING Event push to CT | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Review |  | 13/Oct/25 5:00 PM | 17/Oct/25 12:43 PM |  | 2 |  |  |  | 10800 |  |  |  | [Dev][CT] Sprint 9
Story | RDAPS-223 | 32197 | [DEV][RD][Rewards API] Enhance Get products filter api for support filter by is_reward_store | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready To Test |  | 10/Oct/25 4:59 PM | 15/Oct/25 10:46 AM |  | 2 | mid-sprint | rewards-api | [5 empty] | [Dev][All Project] Sprint 9
Story | DEVRDSUP-171 | 32187 | [SUP-234][SUB] Request to init package due to problem with RGW 09/10/2025 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 09/Oct/25 7:06 PM | 14/Oct/25 6:14 PM |  | 1 | init-pack | mid-sprint |  | 1800 |  |  |  | [Dev][All Project] Sprint 9
Bug | RDAPS-222 | 32182 | [S4][Rewards Alert List] Rewards with end_date displayed as 10:00 are excluded from scheduled email alert | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Resolved |  | 09/Oct/25 4:40 PM | 16/Oct/25 1:53 PM | [9 empty] | [Dev][All Project] Sprint 9
Story | DEVRDSUP-169 | 32151 | [SUP-232][SUB] Request to init package due to problem with RGW 09/10/2025 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Done |  | 09/Oct/25 1:56 PM | 09/Oct/25 2:49 PM | 09/Oct/25 12:00 AM | 1 | init-pack | mid-sprint | sub | 1800 |  |  |  | [Dev][All Project] Sprint 9
Sub-task | DEVRDECOM-134 | 32148 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 09/Oct/25 11:37 AM | 09/Oct/25 11:37 AM | [9 empty] | [Dev][RD][Ecom] Sprint 9
Sub-task | DEVRDECOM-133 | 32146 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 09/Oct/25 11:37 AM | 17/Oct/25 6:00 PM | [9 empty] | [Dev][RD][Ecom] Sprint 9
Sub-task | DEVRDECOM-132 | 32144 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 09/Oct/25 11:36 AM | 09/Oct/25 11:37 AM | [9 empty] | [Dev][RD][Ecom] Sprint 9
Sub-task | DEVRDECOM-131 | 32142 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 09/Oct/25 11:36 AM | 17/Oct/25 6:01 PM | [9 empty] | [Dev][RD][Ecom] Sprint 9
Sub-task | DEVRDECOM-130 | 32140 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 09/Oct/25 11:36 AM | 09/Oct/25 11:36 AM | [9 empty] | [Dev][RD][Ecom] Sprint 9
Sub-task | DEVRDECOM-129 | 32138 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Progress |  | 09/Oct/25 11:36 AM | 09/Oct/25 5:09 PM | [9 empty] | [Dev][RD][Ecom] Sprint 9
Sub-task | DEVRDECOM-128 | 32136 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 09/Oct/25 11:36 AM | 09/Oct/25 11:36 AM | [9 empty] | [Dev][RD][Ecom] Sprint 9
Sub-task | DEVRDECOM-127 | 32134 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Review |  | 09/Oct/25 11:36 AM | 09/Oct/25 4:49 PM | [9 empty] | [Dev][RD][Ecom] Sprint 9
Bug | RDAPS-221 | 32129 | [S3][Coupon list] Incorrect data for refunded txn | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 08/Oct/25 10:28 PM | 15/Oct/25 10:45 AM | [9 empty] | [Dev][All Project] Sprint 9
Sub-task | RDAPS-220 | 32105 | [QA] Run Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 08/Oct/25 4:29 PM | 08/Oct/25 4:49 PM | [9 empty] | [Dev][All Project] Sprint 9
Sub-task | DEVRDECOM-126 | 32097 | [DEV][RD][Eco][Ecommerce_Shopify] Enhance login to store id_token in shopify login logs | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Medium | Ready to Staging |  | 08/Oct/25 1:46 PM | 14/Oct/25 10:02 AM | 14/Oct/25 12:00 AM |  |  |  |  | 14400 |  |  |  | [Dev][RD][Ecom] Sprint 9
Sub-task | RDAPS-219 | 32094 | [QA] Create Test Case - Create command to email alerts for rewards expiring within 30 days | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 08/Oct/25 10:23 AM | 08/Oct/25 5:57 PM | [9 empty] | [Dev][All Project] Sprint 8 | [Dev][All Project] Sprint 9
Sub-task | RDTHANA-319 | 32090 | [QA] Create Test Case - Create new endpoint get deeplink with path | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | In Progress |  | 08/Oct/25 10:20 AM | 10/Oct/25 10:17 AM | [9 empty] | [Dev][RD][Thana] Sprint 9
Sub-task | RDTHANA-318 | 32088 | [QA] Create Test Case - Enhance sorry page with get deeplink endpoint | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | In Progress |  | 08/Oct/25 10:19 AM | 10/Oct/25 10:17 AM | [9 empty] | [Dev][RD][Thana] Sprint 9
Story | DEVRDECOM-125 | 32082 | [DEV][RD][Eco][Theme][Das Haus] Adjust font color at Account Page | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 07/Oct/25 9:33 PM | 09/Oct/25 2:22 PM |  | 1 |  |  |  | 1800 |  |  |  | [Dev][RD][Ecom] Sprint 9
Story | RDAPS-218 | 32079 | [DEV][RD][CT][ADHOC] Change "SPENDING_PARTNER" Events to bypass event feed filtering and refeed event that got filtered | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 07/Oct/25 4:54 PM | 08/Oct/25 4:49 PM | 08/Oct/25 12:00 AM | 1 | CleverTap | [6 empty] | [Dev][All Project] Sprint 9
Story | RDTHANA-317 | 32072 | [Dev][RD][BOF] Improve change status flow to validate required fields | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 07/Oct/25 3:16 PM | 15/Oct/25 5:12 PM | 14/Oct/25 12:00 AM | 5 | rr-backoffice |  |  | 57600 |  |  |  | [Dev][RD][Thana] Sprint 9
Story | DEVRDCT-257 | 32071 | [DEV][RD][RLP][API] LINE_PAY_BINDING Event push to CT | Art: Narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Review |  | 07/Oct/25 3:13 PM | 17/Oct/25 2:58 PM | [9 empty] | [Dev][CT] Sprint 9
Sub-task | DEVRDCT-256 | 32069 | [QA] Create test case LINE_OA_BINDING and LINE_OA_ADD_FRIEND event | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 07/Oct/25 2:26 PM | 07/Oct/25 2:26 PM | [9 empty] | [Dev][CT] Sprint 9
Sub-task | DEVRDCT-255 | 32067 | [QA] Test execution Change "Gender" to "RR_GENDER" field to user property | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 07/Oct/25 2:14 PM | 16/Oct/25 10:58 AM | [9 empty] | [Dev][CT] Sprint 9
Sub-task | DEVRDCT-254 | 32065 | [QA] Create test case Feed "RR_GENDER" field to user property CleverTap | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 07/Oct/25 2:11 PM | 15/Oct/25 3:23 PM | [9 empty] | [Dev][CT] Sprint 9
Sub-task | DEVRDCT-253 | 32062 | [QA] Create test case Line OA and Friend event to CleverTap | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 07/Oct/25 2:09 PM | 07/Oct/25 2:10 PM | [9 empty] | [Dev][CT] Sprint 9
Sub-task | DEVRDCT-252 | 32060 | [QA] Create test case Line OA and Friend event to CleverTap | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 07/Oct/25 2:04 PM | 07/Oct/25 2:10 PM | [9 empty] | [Dev][CT] Sprint 9
Sub-task | DEVRDCT-251 | 32058 | [QA] Create test case | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 07/Oct/25 2:03 PM | 07/Oct/25 2:03 PM | [9 empty] | [Dev][CT] Sprint 9
Bug | RDTHANA-316 | 32052 | [S2][HRS][Feature][Default BU] Set Welcome Message button malfunction after Default BU was saved once and moved to another Club | Art: Narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | High | Closed |  | 07/Oct/25 11:42 AM | 09/Oct/25 4:17 PM | [9 empty] | [Dev][RD][Thana] Sprint 9
Story | RDTHANA-313 | 32018 | [DEV][RD][BFF] Get club term and condition endpoint | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 06/Oct/25 2:33 PM | 17/Oct/25 2:07 PM | 10/Oct/25 12:00 AM | 2 | BFF |  |  | 10800 |  |  |  | [Dev][RD][Thana] Sprint 9
Story | RDTHANA-312 | 32017 | [DEV][RD][Exclusive API] Get club term and condition endpoint | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 06/Oct/25 2:33 PM | 14/Oct/25 3:13 PM | 10/Oct/25 12:00 AM | 3 | exclusive-store-api |  |  | 28800 |  |  |  | [Dev][RD][Thana] Sprint 9
Task | RDAPS-217 | 32014 | [Dev[RD]][SUP-228][SUB] Request to init package due to problem with RGW. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 06/Oct/25 11:34 AM | 17/Oct/25 4:04 PM |  | 1 | No-QA |  |  | 1800 |  |  |  | [Dev][All Project] Sprint 9
Story | DEVRDCT-250 | 32004 | [DEV][RD][RLP] Create script to sync initial RLP member to RR Line member | Art: Narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Review |  | 06/Oct/25 10:03 AM | 15/Oct/25 6:54 PM | 10/Oct/25 12:00 AM | 5 | rlp-middleware | [6 empty] | [Dev][CT] Sprint 9
Story | DEVRDECOM-123 | 31991 | [DEV][RD][Eco][Rewards Member] Enhance custom redirect to solve the problem of user who set default browser is not safari | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 06/Oct/25 9:19 AM | 17/Oct/25 8:42 AM |  | 2 |  |  |  | 10800 |  |  |  | [Dev][RD][Ecom] Sprint 9
Story | DEVRDECOM-122 | 31988 | [DEV][RD][BOF][Widget] Enhance widget asset for service widget | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 05/Oct/25 10:46 PM | 17/Oct/25 4:48 PM | 09/Oct/25 12:00 AM | 3 | rr-backoffice | [6 empty] | [Dev][RD][Ecom] Sprint 9
Story | DEVRDECOM-121 | 31987 | [DEV][RD][BOF][Service] Enhance create/edit service general form support upload JPG file and setup shadow color | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 05/Oct/25 10:44 PM | 16/Oct/25 4:33 PM | 08/Oct/25 12:00 AM | 2 | rr-backoffice |  |  | 14400 |  |  |  | [Dev][RD][Ecom] Sprint 9
Story | DEVRDECOM-120 | 31986 | [DEV][RD][CMS-API] Migration for support shoping page | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 05/Oct/25 10:43 PM | 17/Oct/25 9:16 AM | 06/Oct/25 12:00 AM | 1 | cms-database |  |  | 3600 |  |  |  | [Dev][RD][Ecom] Sprint 9
Story | DEVRDCT-249 | 31984 | [DEV][RD][RLP][WEB] Sent Line OA and Friend event to CleverTap | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 05/Oct/25 4:45 PM | 17/Oct/25 8:43 AM |  | 3 |  |  |  | 10800 |  |  |  | [Dev][CT] Sprint 9
Story | DEVRDCT-248 | 31983 | [DEV][RD][RLP][API] Sent Line OA and Friend event to CleverTap | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 05/Oct/25 4:45 PM | 17/Oct/25 8:43 AM |  | 3 | rlp-middleware |  |  | 10800 |  |  |  | [Dev][CT] Sprint 9
Story | DEVRDCT-246 | 31981 | [DEV][RD][USR] On going Feed "RR_GENDER" field to user property | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 05/Oct/25 10:35 AM | 16/Oct/25 4:33 PM |  | 1 | sso-user |  |  | 7200 |  |  |  | [Dev][CT] Sprint 9
Story | DEVRDCT-245 | 31980 | [DEV][RD][CT] Initial Feed "RR_GENDER" field to user property | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 05/Oct/25 9:53 AM | 16/Oct/25 4:33 PM |  | 3 | No-QA |  |  | 28800 |  |  |  | [Dev][CT] Sprint 9
Story | DEVRDCT-244 | 31979 | [DEV][RD][CT][POC] Rabbit Rewards Catalogue Upload | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 05/Oct/25 9:34 AM | 16/Oct/25 9:59 AM | 15/Oct/25 12:00 AM | 3 | No-QA |  |  | 28800 |  |  |  | [Dev][CT] Sprint 9
Task | RDAPS-216 | 31978 | [Dev][DL][VGI ONE] Clear WPP Credits | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 05/Oct/25 8:58 AM | 05/Oct/25 9:00 AM | [9 empty] | [Dev][All Project] Sprint 9
Story | RDAPS-215 | 31977 | [DEV][RD][Git Repo] Move RLP from bitbucket to github | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 04/Oct/25 4:59 PM | 17/Oct/25 9:36 AM |  | 2 |  |  |  | 7200 |  |  |  | [Dev][All Project] Sprint 9
Story | DEVRDCT-243 | 31976 | [DEV][RD][CT][POC] Shopify Catalogue Upload | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Progress |  | 04/Oct/25 4:33 PM | 10/Oct/25 10:38 AM |  | 1 | [7 empty] | [Dev][CT] Sprint 9
Story | RDAPS-214 | 31975 | [Dev][Archive Old Data] Support Devops to archive data for RLP and PL | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 04/Oct/25 4:30 PM | 13/Oct/25 3:17 PM |  | 1 | [7 empty] | [Dev][All Project] Sprint 9
Story | RDAPS-213 | 31974 | [Dev][Rabbit connect] Remove Login SMS OTP on UAT for ease of testing and lower the SMS cost. | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 04/Oct/25 4:25 PM | 17/Oct/25 10:14 AM |  | 5 | sso-heimdall |  |  | 28800 |  |  |  | [Dev][All Project] Sprint 9
Story | DEVRDECOM-118 | 31973 | [DEV][RD][Eco][Ecommerce-Shopify] Logout | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready to Staging |  | 04/Oct/25 4:18 PM | 15/Oct/25 3:51 PM | 15/Oct/25 12:00 AM | 3 |  |  |  | 28800 |  |  |  | [Dev][RD][Ecom] Sprint 9
Bug | DEVRDSUP-162 | 31971 | [SUP-224]Coupon list report : Incorrect Using date / time | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Closed |  | 03/Oct/25 5:53 PM | 17/Oct/25 9:44 AM | 16/Oct/25 12:00 AM | 1 | prod-issue | rem |  | 7200 |  |  |  | [Dev][All Project] Sprint 9
Story | RDAPS-212 | 31959 | [DEV][RD][SA] Design API Spec for pay with point service | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 03/Oct/25 5:36 PM | 17/Oct/25 10:43 AM | [9 empty] | [Dev][All Project] Sprint 9
Story | RDAPS-211 | 31958 | [DEV][RD][SA] Design Pay with point service | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 03/Oct/25 5:34 PM | 17/Oct/25 10:43 AM | [9 empty] | [Dev][All Project] Sprint 9
Story | RDTHANA-311 | 31957 | [DEV][RD][APH] Enhance sorry page with get deeplink endpoint | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 03/Oct/25 5:11 PM | 09/Oct/25 11:52 AM | 08/Oct/25 12:00 AM | 3 | rr-aphrodite | [6 empty] | [Dev][RD][Thana] Sprint 9
Story | RDTHANA-310 | 31956 | [DEV][RD][LNF] Create new endpoint get deeplink with path | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 03/Oct/25 4:52 PM | 09/Oct/25 11:51 AM | 06/Oct/25 12:00 AM | 1 | link-notify |  |  | 7200 |  |  |  | [Dev][RD][Thana] Sprint 9
Task | RDAPS-210 | 31955 | [SUP-218][Issue from MIX team] Subscription Voucher Issue of Sep 25 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 03/Oct/25 4:49 PM | 17/Oct/25 3:56 PM |  | 1 | No-QA |  |  | 7200 |  |  |  | [Dev][All Project] Sprint 9
Bug | DEVRDSUP-161 | 31953 | [SUP-225][SUB] After SUB TXN is made and receipt generation is slow/ failed, the thank you for purchase email doesn't get sent to users nor BCC | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Enhancement |  | 03/Oct/25 4:06 PM | 17/Oct/25 9:44 AM | 07/Oct/25 12:00 AM | 1 | prod-issue | sub |  | 7200 |  |  |  | [Dev][All Project] Sprint 9
Story | RDAPS-208 | 31951 | [Dev][RD][RRS] SUB purchase confirmation email can be sent BCC copy even if user's mail is dummy | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Highest | Done |  | 03/Oct/25 3:56 PM | 10/Oct/25 1:43 PM |  | 2 | BFF | [6 empty] | [Dev][All Project] Sprint 9
Story | RDAPS-207 | 31950 | [Dev][RD][REM] Improve coupon usage limit rule | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Highest | Done |  | 03/Oct/25 3:52 PM | 15/Oct/25 11:04 AM | 08/Oct/25 12:00 AM | 3 | redemption-api |  |  | 21600 |  |  |  | [Dev][All Project] Sprint 9
Story | DEVRDECOM-117 | 31949 | [Dev][RD][BOF] Enhance Section Menu (FE&BE) | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 03/Oct/25 3:49 PM | 17/Oct/25 4:48 PM | 08/Oct/25 12:00 AM | 3 | rr-backoffice |  |  | 28800 |  |  |  | [Dev][RD][Ecom] Sprint 9
Story | DEVRDECOM-114 | 31943 | [Dev][RD][BFF][API Spec] Enhance get sections to support new location | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 03/Oct/25 1:58 PM | 17/Oct/25 9:15 AM |  | 2 | No-QA |  |  | 3600 |  |  |  | [Dev][RD][Ecom] Sprint 9
Story | DEVRDECOM-113 | 31942 | [Dev][RD][BFF] Enhance get sections to support new location | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 03/Oct/25 1:56 PM | 17/Oct/25 5:44 PM | 09/Oct/25 12:00 AM | 2 | BFF |  |  | 10800 |  |  |  | [Dev][RD][Ecom] Sprint 9
Bug | RDAPS-206 | 31931 | [Dev][RD][RRS] Card Info data missing from Redemption ETL | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Closed |  | 03/Oct/25 11:17 AM | 10/Oct/25 1:43 PM | [6 empty] | มาจาก Sprint 8 | Fixing |  | [Dev][All Project] Sprint 8 | [Dev][All Project] Sprint 9
Bug | DEVRDSUP-159 | 31927 | [SUP-223][HRSolution] Can't import employee but HR solution doesn't response anything. | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Closed |  | 03/Oct/25 1:42 AM | 15/Oct/25 1:50 PM | 06/Oct/25 12:00 AM |  | hop | hr-solution |  |  | มาจาก Sprint 8 | UNDER VALIDATION |  | [Dev][All Project] Sprint 8 | [Dev][All Project] Sprint 9
Bug | DEVRDSUP-158 | 31925 | [SUP-222][HRSolution][Point Redemption Report] The refunded TXN point amount are included in redeemed point. | Game (Krittapas Tanaprasitpattana) | 712020:85e9f474-8ee8-45ba-9249-cde16fa1cd35 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | UNDER VALIDATION |  | 02/Oct/25 6:16 PM | 15/Oct/25 10:51 AM | 23/Oct/25 12:00 AM |  | hop | hr-solution | [5 empty] | [Dev][All Project] Sprint 9
Story | DEVRDCT-242 | 31922 | [DEV][RD][SSO-User] Enhance platform binding endpoint support line_pay | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 02/Oct/25 5:17 PM | 17/Oct/25 10:13 AM | 09/Oct/25 12:00 AM | 8 | sso-user |  |  | 86400 |  |  |  | [Dev][CT] Sprint 9
Story | DEVRDSUP-156 | 31917 | [SUP-192]Request to mark used BTS coupon LinePay card. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 02/Oct/25 2:43 PM | 15/Oct/25 1:35 PM | 16/Oct/25 12:00 AM | 1 | bts | [6 empty] | [Dev][All Project] Sprint 9
Story | DEVRDECOM-112 | 31912 | [DEV][RD][LNF] Import new static deeplink | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 02/Oct/25 2:11 PM | 17/Oct/25 1:51 PM |  | 1 | [7 empty] | [Dev][RD][Ecom] Sprint 9
Story | RDAPS-205 | 31905 | [DEV][RD][REM] Enhance Redemption API to support displaying exclusive rewards in rewards store | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Highest | Ready To Test |  | 02/Oct/25 8:21 AM | 17/Oct/25 4:09 PM |  | 3 | mid-sprint | redemption-api |  | 0 | มาจาก Sprint 8 | Ready to Staging | 21600 | [Dev][All Project] Sprint 8 | [Dev][All Project] Sprint 9
Story | RDAPS-204 | 31904 | [DEV][RD][BOF] Enhance Algolia payload to support displaying exclusive rewards in rewards store | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Highest | Ready To Test |  | 02/Oct/25 8:19 AM | 17/Oct/25 4:09 PM |  | 2 | mid-sprint | rr-backoffice |  | 0 | มาจาก Sprint 8 | Ready to Staging | 14400 | [Dev][All Project] Sprint 8 | [Dev][All Project] Sprint 9
Bug | RDTHANA-306 | 31903 | [S4][HR Solution][Welcome message][Advanced Setting] Business Unit Submitting Incomplete alert message has changed | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Low | Closed |  | 02/Oct/25 12:45 AM | 09/Oct/25 4:18 PM | [6 empty] | มาจาก Sprint 8 | Resolved |  | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDAPS-203 | 31890 | [DEV][RD][BFF] Enhance Get section/widget api for support display exclusive rewards on rewards store | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Highest | Ready To Test |  | 01/Oct/25 5:25 PM | 17/Oct/25 4:08 PM |  | 3 | BFF | mid-sprint |  | 0 | มาจาก Sprint 8 | Ready to Staging | 14400 | [Dev][All Project] Sprint 8 | [Dev][All Project] Sprint 9
Story | RDAPS-202 | 31889 | [DEV][RD][SA] Request for export Coupon code from rewards in Turtle Club project | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 01/Oct/25 5:24 PM | 17/Oct/25 10:43 AM | [6 empty] | มาจาก Sprint 8 | In Progress |  | [Dev][All Project] Sprint 8 | [Dev][All Project] Sprint 9
Bug | DEVRDSUP-154 | 31874 | [SUP-215][RR App] Log in Problem - iOS แสดงหน้าจอ "มีบางอย่างผิดพลาด โปรดลองอีกครั้ง" | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | UNDER VALIDATION |  | 01/Oct/25 12:06 AM | 15/Oct/25 10:49 AM | 28/Oct/25 12:00 AM |  | prod-issue | [6 empty] | [Dev][All Project] Sprint 9
Bug | DEVRDCT-241 | 31866 | [S3][CT][Webhook][Club Binding Event] Opt-in type club binding status event not show correctly on CT through Webhook API | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Open |  | 30/Sep/25 3:31 PM | 02/Oct/25 11:21 AM | [9 empty] | [Dev][CT] Sprint 9
Task | DEVRDSUP-153 | 31856 | Find and remove double bound 1 wallet card to multiple SSO to resolve DEVRDSUP-146 error for other users. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | To Do |  | 30/Sep/25 1:40 PM | 17/Oct/25 4:08 PM |  | 5 |  |  |  | 57600 |  |  |  | [Dev][All Project] Sprint 9
Bug | DEVRDSUP-152 | 31850 | [SUP-213][SUB][LP] A user can't bind new LP card to the RR profile, RR app shows the card is already bound | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Rejected |  | 30/Sep/25 12:12 PM | 08/Oct/25 8:19 AM | 10/Oct/25 12:00 AM | 1 |  |  |  | 7200 |  |  |  | [Dev][All Project] Sprint 9
Story | RDTHANA-294 | 31845 | [Dev][RD][BFF] Improve get sections contents api v2 | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready To Test |  | 30/Sep/25 11:56 AM | 08/Oct/25 5:53 PM | 01/Oct/25 12:00 AM | 2 |  |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 14400 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Bug | RDAPS-201 | 31814 | [DEV][RD][Portal API][Cronjob] Add log to merchant ranking | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Resolved |  | 29/Sep/25 3:00 PM | 10/Oct/25 10:01 AM | [6 empty] | มาจาก Sprint 8 | ACCEPTED |  | [Dev][All Project] Sprint 8 | [Dev][All Project] Sprint 9
Story | DEVRDSUP-150 | 31804 | [SUP-211][SUB][BTS] Couldn't mark used a BTS coupon used via wallet card, request to mark used the BTS coupon with wallet card. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | In Progress |  | 29/Sep/25 10:58 AM | 17/Oct/25 4:16 PM |  | 1 | [7 empty] | [Dev][All Project] Sprint 9
Story | RDTHANA-289 | 31700 | [DEV][RD][BOF][CR] Enhance survey ranking question | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 26/Sep/25 2:02 PM | 14/Oct/25 10:03 AM | 30/Sep/25 12:00 AM | 3 |  |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 21600 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDAPS-199 | 31674 | [DEV][RD][Merchant Ranking] Add sync process log | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 26/Sep/25 9:42 AM | 17/Oct/25 10:42 AM |  | 3 |  |  |  |  | มาจาก Sprint 8 | To Do |  | [Dev][All Project] Sprint 8 | [Dev][All Project] Sprint 9
Epic | RDAPS-198 | 31673 | [DEV][RD][Merchant Ranking] Add sync data log | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 26/Sep/25 9:39 AM | 08/Oct/25 3:06 PM |  | 3 |  |  |  |  | มาจาก Sprint 8 | To Do |  | [Dev][All Project] Sprint 8 | [Dev][All Project] Sprint 9
Bug | RDTHANA-270 | 31550 | [S3][Edit Business Unit][Advanced setting] Feature setting not found due to click link out from error popup | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | UNDER VALIDATION |  | 23/Sep/25 5:19 PM | 17/Oct/25 2:57 PM | [6 empty] | มาจาก Sprint 8 | Reopened |  | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDTHANA-268 | 31545 | [Dev][RD][BOF] Disable mode when survey is expired | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 23/Sep/25 3:28 PM | 08/Oct/25 5:53 PM | 30/Sep/25 12:00 AM | 1 | rr-backoffice |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 3600 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Test Plan | RDTHANA-266 | 31540 | [TP][Thana city] Sprint 8 |  |  | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 23/Sep/25 2:06 PM | 08/Oct/25 5:53 PM | [6 empty] | มาจาก Sprint 8 | To Do |  | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Epic | DEVRDECOM-107 | 31506 | Shopify Webhook |  |  | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | To Do |  | 23/Sep/25 9:52 AM | 06/Oct/25 10:42 AM | [6 empty] | มาจาก Sprint 8 | To Do |  | [Dev][RD][Ecom] Sprint 8 | [Dev][RD][Ecom] Sprint 9
Sub-task | DEVRDECOM-104 | 31499 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 22/Sep/25 10:13 PM | 10/Oct/25 9:07 AM | [6 empty] | มาจาก Sprint 8 | To Do |  | [Dev][RD][Ecom] Sprint 8 | [Dev][RD][Ecom] Sprint 9
Sub-task | DEVRDECOM-103 | 31497 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 22/Sep/25 10:13 PM | 10/Oct/25 9:07 AM | [6 empty] | มาจาก Sprint 8 | To Do |  | [Dev][RD][Ecom] Sprint 8 | [Dev][RD][Ecom] Sprint 9
Sub-task | DEVRDECOM-102 | 31495 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 22/Sep/25 10:13 PM | 10/Oct/25 9:07 AM | [6 empty] | มาจาก Sprint 8 | To Do |  | [Dev][RD][Ecom] Sprint 8 | [Dev][RD][Ecom] Sprint 9
Sub-task | RDTHANA-259 | 31493 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 22/Sep/25 10:11 PM | 08/Oct/25 1:38 PM | [6 empty] | มาจาก Sprint 8 | In Progress |  | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Sub-task | RDTHANA-258 | 31491 | [QA] Create Test Case - Enhance check eligible to set opt-in setting in advance setting | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 22/Sep/25 10:11 PM | 15/Oct/25 1:40 PM | [6 empty] | มาจาก Sprint 8 | In Progress |  | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Sub-task | RDTHANA-257 | 31489 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 22/Sep/25 10:11 PM | 01/Oct/25 10:05 AM | [6 empty] | มาจาก Sprint 8 | Done |  | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Sub-task | RDTHANA-256 | 31487 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 22/Sep/25 10:10 PM | 08/Oct/25 11:42 AM | [6 empty] | มาจาก Sprint 8 | In Progress |  | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Sub-task | RDTHANA-255 | 31485 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 22/Sep/25 10:10 PM | 29/Sep/25 9:48 AM | [6 empty] | มาจาก Sprint 8 | Done |  | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Sub-task | RDTHANA-254 | 31483 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 22/Sep/25 10:08 PM | 07/Oct/25 1:58 PM | [6 empty] | มาจาก Sprint 8 | To Do |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Sub-task | RDTHANA-253 | 31481 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 22/Sep/25 10:07 PM | 06/Oct/25 3:56 PM | [6 empty] | มาจาก Sprint 8 | Done |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Sub-task | RDTHANA-252 | 31479 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 22/Sep/25 10:07 PM | 06/Oct/25 2:16 PM | [6 empty] | มาจาก Sprint 8 | Done |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Sub-task | RDTHANA-251 | 31477 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 22/Sep/25 10:07 PM | 06/Oct/25 1:07 PM | [6 empty] | มาจาก Sprint 8 | Done |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Sub-task | RDTHANA-250 | 31475 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 22/Sep/25 10:07 PM | 06/Oct/25 10:47 AM | [6 empty] | มาจาก Sprint 8 | Done |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Sub-task | RDTHANA-249 | 31473 | [QA] Create Test Case View Survey List (FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 22/Sep/25 10:06 PM | 04/Oct/25 12:35 PM | [6 empty] | มาจาก Sprint 8 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Sub-task | DEVRDADJ-47 | 31465 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 22/Sep/25 10:04 PM | 19/Oct/25 9:11 PM | [6 empty] | มาจาก Sprint 8 | To Do |  | [Dev][RDAdjust] Sprint 8 | [Dev][RDAdjust] Sprint 9
Sub-task | DEVRDADJ-45 | 31461 | [QA] Create Test Case & Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 22/Sep/25 10:03 PM | 19/Oct/25 9:11 PM | [6 empty] | มาจาก Sprint 8 | Done |  | [Dev][RDAdjust] Sprint 8 | [Dev][RDAdjust] Sprint 9
Story | RDTHANA-244 | 31447 | [DEV][RD][APH] Enhance sorry page support dynamic error message and CTA button | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Blocked |  | 22/Sep/25 11:36 AM | 08/Oct/25 5:53 PM | 29/Sep/25 12:00 AM | 1 |  |  |  |  | มาจาก Sprint 8 | Blocked |  | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDTHANA-241 | 31432 | [DEV][RD][APH] Enhance survey html render support survey appearance "Thank you" tab | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 21/Sep/25 9:13 PM | 08/Oct/25 5:53 PM | 29/Sep/25 12:00 AM | 3 |  |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDTHANA-240 | 31431 | [DEV][RD][APH] Enhance survey html render support survey appearance "Email" tab (Issue point form) | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 21/Sep/25 9:13 PM | 08/Oct/25 5:53 PM | 26/Sep/25 12:00 AM | 5 |  |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDTHANA-239 | 31430 | [DEV][RD][APH] Enhance survey html render support survey appearance "Survey Q&A" tab | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 21/Sep/25 9:13 PM | 08/Oct/25 5:53 PM | 26/Sep/25 12:00 AM | 8 |  |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDTHANA-238 | 31429 | [DEV][RD][APH] Create survey theme | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Highest | Ready To Test |  | 21/Sep/25 8:49 PM | 08/Oct/25 5:53 PM | 23/Sep/25 12:00 AM | 3 | rr-aphrodite |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDAPS-193 | 31428 | [Dev][RD][RRS] Create command to email alerts for rewards expiring within 30 days | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 21/Sep/25 7:56 PM | 16/Oct/25 1:46 PM | 24/Sep/25 12:00 AM | 3 | rr-scheduler |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 28800 | [Dev][All Project] Sprint 8 | [Dev][All Project] Sprint 9
Story | RDTHANA-236 | 31426 | [Dev][RD][BOF] Rename all related feature and field from ‘Exclusive Store’ ‘Exclusive Partner Store’ to ‘Club - Rewards’ | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 21/Sep/25 2:16 PM | 08/Oct/25 5:53 PM | 01/Oct/25 12:00 AM | 2 | rr-backoffice | rr-scheduler |  |  | มาจาก Sprint 8 | Ready To Test |  | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | DEVRDECOM-99 | 31423 | [DEV][RD][Eco][RR-Ecommerce-Shopify] Create Webhook API Endpoint refunds/create | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 21/Sep/25 9:47 AM | 16/Oct/25 9:56 AM | 01/Oct/25 12:00 AM | 3 |  |  |  |  | มาจาก Sprint 8 | In Review |  | [Dev][RD][Ecom] Sprint 8 | [Dev][RD][Ecom] Sprint 9
Story | DEVRDECOM-97 | 31421 | [DEV][RD][Eco][RR-Ecommerce-Shopify] Calculate Point | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 21/Sep/25 9:35 AM | 15/Oct/25 4:16 PM |  | 1 |  |  |  | 0 | มาจาก Sprint 8 | Ready to Staging | 7200 | [Dev][RD][Ecom] Sprint 8 | [Dev][RD][Ecom] Sprint 9
Story | RDTHANA-247 | 31385 | [DEV][RD][Eco][RR-Ecommerce-Shopify][Das Haus] Create Endpoint for Club Binding Callback and Redirect to Shopify | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 19/Sep/25 1:53 PM | 08/Oct/25 5:53 PM | 03/Oct/25 12:00 AM | 3 |  |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDTHANA-232 | 31360 | [DEV][RD][GATEWAY] Mapping get member club detail with internal API | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Highest | Ready To Test |  | 19/Sep/25 10:44 AM | 08/Oct/25 5:53 PM |  | 1 |  |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 7200 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDTHANA-231 | 31359 | [DEV][RD][APH] Enhance survey html render support survey appearance "General" tab | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 19/Sep/25 10:43 AM | 08/Oct/25 5:53 PM | 26/Sep/25 12:00 AM | 5 |  |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDTHANA-230 | 31358 | [DEV][RD][APH] Enhance getMemberToken support sources session | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 19/Sep/25 10:42 AM | 08/Oct/25 5:53 PM | 26/Sep/25 12:00 AM | 2 |  |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 7200 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | DEVRDECOM-92 | 31345 | [DEV][RD][Eco][Rewards-Member] Setup and Running Redis Queue | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 18/Sep/25 8:00 PM | 07/Oct/25 4:36 PM |  | 2 | No-QA | rewards-member |  | 0 | มาจาก Sprint 8 | Ready to Staging | 14400 | [Dev][RD][Ecom] Sprint 8 | [Dev][RD][Ecom] Sprint 9
Story | DEVRDECOM-90 | 31343 | [DEV][RD][Eco][RR-Ecommerce-Shopify] Create Scheduled Job for update transport status | Art: Narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 18/Sep/25 7:27 PM | 15/Oct/25 4:03 PM |  | 5 | ecommerce-shopify-api |  |  |  | มาจาก Sprint 8 | In Progress |  | [Dev][RD][Ecom] Sprint 8 | [Dev][RD][Ecom] Sprint 9
Story | DEVRDECOM-89 | 31341 | [DEV][RD][Eco][POC] Dynamic Section by Customer Location for Turtle shop | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Progress |  | 18/Sep/25 5:56 PM | 07/Oct/25 2:38 PM |  | 5 | rr-ecommerce-shopify |  |  |  | มาจาก Sprint 8 | In Progress |  | [Dev][RD][Ecom] Sprint 8 | [Dev][RD][Ecom] Sprint 9
Story | DEVRDECOM-86 | 31337 | [DEV][RD][Eco][Setup] Auto login & Verify email for Turtle shop | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 18/Sep/25 5:45 PM | 09/Oct/25 10:50 AM |  | 2 | rr-ecommerce-shopify |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 10800 | [Dev][RD][Ecom] Sprint 8 | [Dev][RD][Ecom] Sprint 9
Story | DEVRDECOM-85 | 31336 | [DEV][RD][Eco][Setup] Auto login & Verify email for Das Haus shop | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 18/Sep/25 5:36 PM | 09/Oct/25 10:50 AM |  | 2 | rr-ecommerce-shopify |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 10800 | [Dev][RD][Ecom] Sprint 8 | [Dev][RD][Ecom] Sprint 9
Story | DEVRDECOM-84 | 31335 | [DEV][RD][Eco][Setup] Auto login & Verify email for Snackmaker shop | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 18/Sep/25 5:30 PM | 09/Oct/25 10:50 AM |  | 2 | rr-ecommerce-shopify |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 10800 | [Dev][RD][Ecom] Sprint 8 | [Dev][RD][Ecom] Sprint 9
Story | RDTHANA-245 | 31334 | [DEV][RD][Eco][RR-Ecommerce-Shopify][Das Haus] Enhance Auth Callback Endpoint to checks if the customer is a Das Haus club member. | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 18/Sep/25 5:09 PM | 08/Oct/25 5:53 PM |  | 5 | ecommerce-shopify-api |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDTHANA-229 | 31332 | [DEV][RD][APH] Enhance survey available middleware | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 18/Sep/25 4:23 PM | 08/Oct/25 5:53 PM | 26/Sep/25 12:00 AM | 5 |  |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDTHANA-227 | 31330 | [DEV][RD][HRS] Enhance check eligible to set opt-in setting in popup welcome message | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 18/Sep/25 4:06 PM | 15/Oct/25 2:01 PM |  | 2 |  |  |  |  | มาจาก Sprint 8 | Ready To Test |  | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDTHANA-226 | 31329 | [DEV][RD][HRS] Enhance check eligible to set opt-in setting in advance setting | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 18/Sep/25 4:05 PM | 15/Oct/25 2:01 PM |  | 3 |  |  |  |  | มาจาก Sprint 8 | Ready To Test |  | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDTHANA-225 | 31328 | [DEV][RD][HRS] Enhance import employee bu list with member_method and is_import | Art: Narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Done |  | 18/Sep/25 4:01 PM | 15/Oct/25 3:37 PM | 29/Sep/25 12:00 AM | 1 |  |  |  |  | มาจาก Sprint 8 | Ready To Test |  | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDTHANA-224 | 31327 | [DEV][RD][HRS] Enhance feature setting company level with opt-in BU enable | Art: Narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 18/Sep/25 3:59 PM | 15/Oct/25 2:01 PM | 29/Sep/25 12:00 AM | 5 |  |  |  |  | มาจาก Sprint 8 | Ready To Test |  | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDTHANA-223 | 31326 | [DEV][RD][HRS] Enhance default bu welcome message link | Art: Narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Done |  | 18/Sep/25 3:56 PM | 15/Oct/25 3:36 PM |  | 2 |  |  |  |  | มาจาก Sprint 8 | Ready To Test |  | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDTHANA-246 | 31325 | [DEV][RD][Eco][RR-Ecommerce-Shopify][Das Haus] Enhance login with return_url | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 18/Sep/25 3:22 PM | 08/Oct/25 5:53 PM |  | 2 | ecommerce-shopify-api |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 10800 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | DEVRDADJ-44 | 31314 | [DEV][RD][BOF] Enhance RR Backoffice to integrate with ADJUST Deeplink Generated api | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 18/Sep/25 1:53 PM | 16/Oct/25 4:33 PM |  | 5 |  |  |  | 0 | มาจาก Sprint 8 | Ready to Staging | 57600 | [Dev][RDAdjust] Sprint 8 | [Dev][RDAdjust] Sprint 9
Story | DEVRDADJ-41 | 31311 | [DEV][RD][LNF] Enhance auto generate deeplink, remove redirect url in request | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 18/Sep/25 1:45 PM | 16/Oct/25 4:33 PM | 25/Sep/25 12:00 AM | 2 |  |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 14400 | [Dev][RDAdjust] Sprint 8 | [Dev][RDAdjust] Sprint 9
Sub-task | RDTHANA-134 | 30844 | [QA] Create Test Case Download Individual Survey Report (FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:30 AM | 05/Oct/25 3:00 PM | [6 empty] | มาจาก Sprint 8 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Sub-task | RDTHANA-133 | 30842 | [QA] Create Test Case View Survey Report (FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:30 AM | 05/Oct/25 2:50 PM | [6 empty] | มาจาก Sprint 8 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Sub-task | RDTHANA-132 | 30840 | [QA] Create Test Case Change survey status (FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:30 AM | 04/Oct/25 12:24 PM | [6 empty] | มาจาก Sprint 8 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Sub-task | RDTHANA-131 | 30838 | [QA] |  |  | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 09/Sep/25 11:29 AM | 21/Sep/25 3:00 PM | [6 empty] | มาจาก Sprint 8 | To Do |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Sub-task | RDTHANA-130 | 30836 | [QA] Create Test Case Update survey Step 5: Survey Appearance (Thank You) (FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:29 AM | 04/Oct/25 12:32 PM | [6 empty] | มาจาก Sprint 8 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Sub-task | RDTHANA-129 | 30834 | [QA] Create Test Case Update survey Step 5: Survey Appearance (Input E-mail) (FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:29 AM | 21/Sep/25 3:01 PM | [6 empty] | มาจาก Sprint 8 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Sub-task | RDTHANA-128 | 30832 | [QA] Create Test Case [Dev][RD][BOF] Update survey step5.2(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:29 AM | 21/Sep/25 1:58 PM | [6 empty] | มาจาก Sprint 8 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Sub-task | RDTHANA-127 | 30830 | [QA] Create Test Case Update survey step5.1(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:28 AM | 21/Sep/25 1:55 PM | [6 empty] | มาจาก Sprint 8 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Sub-task | RDTHANA-126 | 30828 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 09/Sep/25 11:28 AM | 17/Oct/25 6:00 PM | [6 empty] | มาจาก Sprint 8 | To Do |  | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Sub-task | RDTHANA-125 | 30826 | [QA] Create Test Case Update survey step4.2(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:28 AM | 21/Sep/25 1:55 PM | [6 empty] | มาจาก Sprint 8 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Sub-task | RDTHANA-124 | 30824 | [QA] Create Test Case Update survey step4.1(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:27 AM | 21/Sep/25 1:55 PM | [6 empty] | มาจาก Sprint 8 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Sub-task | RDTHANA-123 | 30822 | [QA] Create Test Case Update survey step3(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:27 AM | 21/Sep/25 1:55 PM | [6 empty] | มาจาก Sprint 8 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Sub-task | RDTHANA-122 | 30820 | [QA] Create Test Case Update survey step2(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:26 AM | 21/Sep/25 12:27 PM | [6 empty] | มาจาก Sprint 8 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Sub-task | RDTHANA-121 | 30818 | [QA] Create Test Case Update survey step1(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:26 AM | 21/Sep/25 12:27 PM | [6 empty] | มาจาก Sprint 8 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Sub-task | RDTHANA-120 | 30816 | [QA] Create Test Case Create survey (FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:25 AM | 21/Sep/25 12:27 PM | [6 empty] | มาจาก Sprint 8 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Sub-task | RDTHANA-119 | 30814 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 09/Sep/25 11:24 AM | 09/Sep/25 11:24 AM | [6 empty] | มาจาก Sprint 8 | To Do |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Sub-task | RDTHANA-118 | 30812 | [QA] Create Test Case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 09/Sep/25 11:23 AM | 09/Sep/25 11:23 AM | [6 empty] | มาจาก Sprint 8 | To Do |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Sub-task | RDTHANA-117 | 30810 | [QA] Create Test Case | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 09/Sep/25 11:23 AM | 09/Sep/25 11:23 AM | [6 empty] | มาจาก Sprint 8 | To Do |  | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Sub-task | RDTHANA-116 | 30808 | [QA] Create Test Case 'Club - Benefits & Info' Location | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 09/Sep/25 11:22 AM | 15/Oct/25 3:36 PM | [6 empty] | มาจาก Sprint 8 | Done |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Sub-task | RDTHANA-115 | 30806 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 09/Sep/25 11:22 AM | 09/Sep/25 11:22 AM | [6 empty] | มาจาก Sprint 8 | To Do |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Sub-task | RDTHANA-114 | 30804 | [QA] Create Test Case Widget Type 'Club – Benefits & Information' | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 09/Sep/25 11:21 AM | 15/Oct/25 3:45 PM | [6 empty] | มาจาก Sprint 8 | Done |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Sub-task | DEVRDCT-228 | 30800 | [QA] Update Test Case | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 09/Sep/25 11:14 AM | 14/Oct/25 7:04 PM | [6 empty] | มาจาก Sprint 8 | To Do |  | [Dev][CT] Sprint 7 | [Dev][CT] Sprint 8 | [Dev][CT] Sprint 9
Sub-task | DEVRDCT-227 | 30798 | [QA] Update Test Case | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 09/Sep/25 11:14 AM | 14/Oct/25 7:03 PM | [6 empty] | มาจาก Sprint 8 | To Do |  | [Dev][CT] Sprint 7 | [Dev][CT] Sprint 8 | [Dev][CT] Sprint 9
Story | RDTHANA-113 | 30734 | [Dev][RD][BOF][Service] Change service status | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 07/Sep/25 3:21 PM | 08/Oct/25 5:53 PM | 19/Sep/25 12:00 AM | 5 |  |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDTHANA-107 | 30691 | [Dev][RD][APH] Cronjob update survey to expired | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 04/Sep/25 4:56 PM | 08/Oct/25 5:53 PM | 26/Sep/25 12:00 AM | 3 | rr-aphrodite |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 21600 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | DEVRDSUP-123 | 30690 | [SUP-166]Clevertap : Found Check in Transaction in Charge Event | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 04/Sep/25 4:52 PM | 17/Oct/25 10:25 AM |  | 1 |  |  |  | 3600 |  |  |  | [Dev][All Project] Sprint 9
Story | RDTHANA-106 | 30689 | [Dev][RD][Service][CMS API] Create service filter api | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 04/Sep/25 4:08 PM | 08/Oct/25 5:53 PM | 11/Sep/25 12:00 AM | 3 | cms-api | No-QA |  | 0 | มาจาก Sprint 8 | Ready To Test | 18000 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDTHANA-105 | 30687 | [Dev][RD][APH][CT] CleverTap Event | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | In Progress |  | 04/Sep/25 3:56 PM | 08/Oct/25 5:53 PM |  | 5 |  |  |  | 57600 | มาจาก Sprint 8 | In Progress |  | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | DEVRDECOM-73 | 30661 | [DEV][RD][Eco][RR-Ecommerce-Shopify] Create Webhook API Endpoint orders | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 04/Sep/25 1:17 PM | 15/Oct/25 2:33 PM | 25/Sep/25 12:00 AM | 5 | ecommerce-shopify-api | No-QA |  |  | มาจาก Sprint 8 | Ready to Staging |  | [Dev][RD][Ecom] Sprint 8 | [Dev][RD][Ecom] Sprint 9
Bug | DEVRDSUP-118 | 30656 | [SUP-165]Clevertap : Charge Event : Type "SPENDING_PARTNER". Some Turtle shop event not get feed to the platform | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | UNDER VALIDATION |  | 04/Sep/25 11:31 AM | 17/Oct/25 10:39 AM | [9 empty] | [Dev][All Project] Sprint 9
Bug | DEVRDCT-224 | 30653 | [DEV][RD][RDS] FIX REDEEM EVENT - INTERNAL NAME value now use EN Name as value | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Closed |  | 04/Sep/25 8:46 AM | 14/Oct/25 6:52 PM | 10/Sep/25 12:00 AM | 1 | redemption-api |  |  | 7200 | มาจาก Sprint 8 | Resolved |  | [Dev][CT] Sprint 7 | [Dev][CT] Sprint 8 | [Dev][CT] Sprint 9
Story | DEVRDCT-223 | 30652 | [DEV][RD][RDS] ENH Add "Offer ID" to "REDEEM" EVENT | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 04/Sep/25 7:48 AM | 16/Oct/25 4:33 PM | 10/Sep/25 12:00 AM | 1 | redemption-api |  |  | 0 | มาจาก Sprint 8 | Ready to Staging | 3600 | [Dev][CT] Sprint 7 | [Dev][CT] Sprint 8 | [Dev][CT] Sprint 9
Story | DEVRDCT-222 | 30651 | [DEV][RD][RDS] ENH Add "Offer ID" to "MEMBER COUPON" EVENT | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 04/Sep/25 6:58 AM | 16/Oct/25 4:33 PM | 10/Sep/25 12:00 AM | 2 | redemption-api |  |  | 0 | มาจาก Sprint 8 | Ready to Staging | 7200 | [Dev][CT] Sprint 7 | [Dev][CT] Sprint 8 | [Dev][CT] Sprint 9
Story | RDAPS-175 | 30649 | [DEV][RD][SSO Handover] GCP SSO SSL management & Domain | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 03/Sep/25 5:04 PM | 09/Oct/25 4:17 PM | 09/Oct/25 12:00 AM | 1 | No-QA |  |  | 7200 | มาจาก Sprint 8 | To Do |  | [Dev][All project]Sprint 7 | [Dev][All Project] Sprint 8 | [Dev][All Project] Sprint 9
Story | RDAPS-174 | 30648 | [DEV][RD][SSO Handover] GCP GKE Pipeline Deployment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 03/Sep/25 5:03 PM | 09/Oct/25 4:16 PM | 10/Oct/25 12:00 AM | 3 | No-QA |  |  | 28800 | มาจาก Sprint 8 | To Do |  | [Dev][All project]Sprint 7 | [Dev][All Project] Sprint 8 | [Dev][All Project] Sprint 9
Story | RDAPS-173 | 30647 | [DEV][RD][SSO Handover] Overiew GKE All Cluster | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 03/Sep/25 5:00 PM | 09/Oct/25 4:17 PM | 17/Oct/25 12:00 AM | 1 | No-QA |  |  | 7200 | มาจาก Sprint 8 | To Do |  | [Dev][All project]Sprint 7 | [Dev][All Project] Sprint 8 | [Dev][All Project] Sprint 9
Story | RDTHANA-97 | 30645 | [Dev][RD][BOF][Service] Edit page step 2. | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 03/Sep/25 4:58 PM | 08/Oct/25 5:53 PM | 17/Sep/25 12:00 AM | 8 |  |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 86400 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDTHANA-96 | 30642 | [Dev][RD][BOF][Service] Edit page step 1. | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 03/Sep/25 4:54 PM | 10/Oct/25 3:38 PM | 19/Sep/25 12:00 AM | 5 |  |  |  |  | มาจาก Sprint 8 | Ready To Test |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDTHANA-95 | 30641 | [Dev][RD][BOF][Service] Create page step 1 | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 03/Sep/25 4:52 PM | 08/Oct/25 5:53 PM | 12/Sep/25 12:00 AM | 8 |  |  |  | 0 | มาจาก Sprint 8 | Ready To Test |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDTHANA-94 | 30639 | [Dev][RD][BOF][Service] create service index page | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 03/Sep/25 4:19 PM | 08/Oct/25 5:53 PM | 12/Sep/25 12:00 AM | 8 |  |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Epic | DEVRDADJ-34 | 30635 | MAID registration |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 03/Sep/25 4:08 PM | 15/Oct/25 10:10 AM | [6 empty] | มาจาก Sprint 8 | To Do |  | [Dev][RDAdjust] Sprint 8 | [Dev][RDAdjust] Sprint 9
Story | RDTHANA-90 | 30622 | [Dev][RD][Section][BOF][QA] Enhance Section Feature: Add new widget types | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Sep/25 9:16 PM | 08/Oct/25 5:53 PM |  | 0 |  |  |  |  | มาจาก Sprint 8 | Ready To Test |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDTHANA-89 | 30621 | [Dev][RD][Section][BOF] Enhance Section Feature: Add 'Club - Benefits & Info' Location | Art: Narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Sep/25 8:56 PM | 15/Oct/25 3:35 PM |  | 5 | rr-backoffice |  |  |  | มาจาก Sprint 8 | Ready To Test |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDTHANA-88 | 30620 | [Dev][RD][Widget][BOF] Enhance Widget Feature: Add 'Service' Type | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Sep/25 8:56 PM | 15/Oct/25 3:49 PM | 11/Sep/25 12:00 AM | 5 | rr-backoffice |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDTHANA-87 | 30619 | [Dev][RD][Widget][BOF] Enhance Widget Feature: Add 'Club – Benefits & Information' Type | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Sep/25 8:56 PM | 08/Oct/25 5:53 PM | 10/Sep/25 12:00 AM | 5 | rr-backoffice |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDTHANA-86 | 30618 | [Dev][RD][BOF] Update survey Step 5: Survey Appearance (Thank You) (FE&BE) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Sep/25 8:44 PM | 08/Oct/25 5:53 PM | 15/Sep/25 12:00 AM | 2 | rr-backoffice |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 10800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDTHANA-81 | 30606 | [Dev][RD][BOF] Change survey status (FE&BE) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Sep/25 3:26 PM | 08/Oct/25 5:53 PM | 16/Sep/25 12:00 AM | 3 | rr-backoffice |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDTHANA-80 | 30604 | [Dev][RD][BOF] Update survey Step 5: Survey Appearance (Input E-mail) (FE&BE) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Sep/25 3:25 PM | 08/Oct/25 5:53 PM | 15/Sep/25 12:00 AM | 2 | rr-backoffice |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 10800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDTHANA-79 | 30602 | [Dev][RD][BOF] Update survey step5.2(FE&BE) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Sep/25 3:24 PM | 08/Oct/25 5:53 PM | 12/Sep/25 12:00 AM | 2 | rr-backoffice |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 10800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | DEVRDSUP-115 | 30548 | [SUP-164][SSO] Request to remove all consents for RR member who never opted to consent, system auto consent to new users who registered from other source. | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | To Do |  | 01/Sep/25 5:17 PM | 19/Oct/25 9:23 PM | 09/Oct/25 12:00 AM | [8 empty] | [Dev][All Project] Sprint 9
Story | RDTHANA-74 | 30366 | [Dev][RD][BOF] Update survey step4.2(FE&BE) | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:15 PM | 08/Oct/25 5:53 PM |  | 2 | rr-backoffice |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDTHANA-73 | 30364 | [Dev][RD][BOF] Download Individual Survey Report (FE&BE) | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:15 PM | 08/Oct/25 5:53 PM | 18/Sep/25 12:00 AM | 5 | rr-backoffice |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDTHANA-72 | 30362 | [Dev][RD][BOF] Update survey step5.1(FE&BE) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:15 PM | 08/Oct/25 5:53 PM | 12/Sep/25 12:00 AM | 3 | rr-backoffice |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDTHANA-71 | 30360 | [Dev][RD][BOF] Update survey step4.1(FE&BE) | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:15 PM | 08/Oct/25 5:53 PM |  | 8 | rr-backoffice |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 86400 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDTHANA-70 | 30358 | [Dev][RD][BOF] Update survey step3(FE&BE) | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:14 PM | 08/Oct/25 5:53 PM |  | 5 | rr-backoffice |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDTHANA-69 | 30356 | [Dev][RD][BOF] Update survey step2(FE&BE) | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:09 PM | 08/Oct/25 5:53 PM | 16/Sep/25 12:00 AM | 3 | rr-backoffice |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDTHANA-68 | 30354 | [Dev][RD][BOF] View Survey Report (FE&BE) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:09 PM | 08/Oct/25 5:53 PM | 17/Sep/25 12:00 AM | 3 | rr-backoffice |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDTHANA-67 | 30352 | [Dev][RD][BOF] View Survey List (FE&BE) | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:09 PM | 08/Oct/25 5:53 PM |  | 5 | rr-backoffice |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 86400 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDTHANA-66 | 30350 | [Dev][RD][BOF] Update survey step1(FE&BE) | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:09 PM | 08/Oct/25 5:53 PM | 15/Sep/25 12:00 AM | 3 | rr-backoffice |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDTHANA-65 | 30348 | [Dev][RD][BOF] Create survey (FE&BE) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:08 PM | 08/Oct/25 5:53 PM | 11/Sep/25 12:00 AM | 5 | rr-backoffice |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 43200 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Bug | DEVRDADJ-25 | 30110 | [S2][Adjust] When change internal name URL not update and can't open | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | UNDER VALIDATION |  | 22/Aug/25 11:12 AM | 19/Oct/25 9:12 PM | [9 empty] | [Dev][RDAdjust] Sprint 9
Story | RDTHANA-43 | 30086 | [DEV][RD][DasHaus][BFF] Verify the API to validate matching account | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 22/Aug/25 6:12 AM | 09/Oct/25 11:54 AM |  | 1 | BFF |  |  |  | มาจาก Sprint 8 | Done |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Bug | DEVRDADJ-24 | 30062 | [S2][Adjust] Deeplinks can be opened when the rewards status is other than Active. | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | UNDER VALIDATION |  | 21/Aug/25 4:22 PM | 19/Oct/25 9:13 PM | [9 empty] | [Dev][RDAdjust] Sprint 9
Story | RDAPS-160 | 29972 | [DEV][RD][SSO-Backoffice] Disable SEO tracking | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 20/Aug/25 11:21 AM | 17/Oct/25 4:01 PM | 04/Sep/25 12:00 AM | 1 |  |  |  | 7200 |  |  |  | [Dev][All project]Sprint 6 | [Dev][All project]Sprint 7 | [Dev][All Project] Sprint 9
Story | RDTHANA-20 | 29950 | [Dev][RD][APH] Enhance check token | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 19/Aug/25 7:46 PM | 08/Oct/25 5:53 PM |  | 3 |  |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDTHANA-19 | 29948 | [Dev][RD][Section][BOF] Enhance Section Index Page | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 19/Aug/25 7:45 PM | 08/Oct/25 5:53 PM |  | 2 |  |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 7200 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDTHANA-16 | 29942 | [Dev][RD][Section][BFF] Enhance Sections API | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 19/Aug/25 7:44 PM | 17/Oct/25 5:44 PM |  | 5 | BFF |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDTHANA-15 | 29940 | [Dev][RD][Widget][CMS API] Enhance Widget API | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 19/Aug/25 7:41 PM | 08/Oct/25 5:53 PM |  | 2 | cms-api |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 3600 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDTHANA-14 | 29938 | [Dev][RD][Section][CMS API] Enhance Sections API | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 19/Aug/25 7:37 PM | 08/Oct/25 5:53 PM |  | 2 | cms-api |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 14400 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Bug | DEVRDSUP-93 | 29890 | [SUP-132][APP] Reward search result doesn't show out of stock on search result and category filter. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | UNDER VALIDATION |  | 19/Aug/25 11:33 AM | 17/Oct/25 9:47 AM | 02/Sep/25 12:00 AM | 2 | rewards-api |  |  | 14400 | มาจาก Sprint 8 | UNDER VALIDATION |  | [Dev][All Project] Sprint 8 | [Dev][All Project] Sprint 9
Story | DEVRDECOM-33 | 29547 | [DEV][RD][Eco][Ecommerce-Shopify] Enhance API Endpoint for Order refunded Webhook | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 10/Aug/25 9:11 PM | 16/Oct/25 3:56 PM |  | 3 | ecommerce-shopify-api |  |  | 28800 |  |  |  | [Dev][RD][Ecom] Sprint 9
Task | RDAPS-141 | 29339 | [Dev][RD][POC][SMS sub-account to support new sender IDs] | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 05/Aug/25 5:01 PM | 17/Oct/25 10:42 AM |  | 5 |  |  |  | 57600 | มาจาก Sprint 8 | In Progress |  | [Dev][All project]Sprint 4 | [Dev][All project]Sprint 5 | [Dev][All project]Sprint 6 | [Dev][All project]Sprint 7 | [Dev][All Project] Sprint 8 | [Dev][All Project] Sprint 9
Story | RDAPS-129 | 28895 | [Dev][RD][Redemption Consumer] Enhance coupon codes allocation process | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 29/Jul/25 4:53 PM | 17/Oct/25 4:07 PM |  | 2 | No-QA | redemption-consumer |  | 14400 |  |  |  | [Dev][All project]Sprint 6 | [Dev][All project]Sprint 7 | [Dev][All Project] Sprint 9
Story | DEVRDECOM-25 | 28845 | [DEV][RD][Eco][Ecommerce-Shopify] Enhance API Endpoint for Order Cancelled Webhook | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 29/Jul/25 12:49 PM | 15/Oct/25 4:12 PM | 01/Oct/25 12:00 AM | 5 | ecommerce-shopify-api |  |  | 0 | มาจาก Sprint 8 | Ready to Staging | 72000 | [Dev][RD][Ecom] Sprint 8 | [Dev][RD][Ecom] Sprint 9
Story | DEVRDECOM-24 | 28843 | [DEV][RD][Eco][RR-Ecommerce-Shopify] Create Scheduled Job for Point Issuance | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 29/Jul/25 11:07 AM | 15/Oct/25 4:15 PM | 02/Oct/25 12:00 AM | 5 | ecommerce-shopify-api |  |  |  | มาจาก Sprint 8 | Ready to Staging |  | [Dev][RD][Ecom] Sprint 8 | [Dev][RD][Ecom] Sprint 9
Story | RDTHANA-248 | 28841 | [DEV][RD][Eco][RR-Ecommerce-Shopify][Das Haus] Enhance email verify callback with return_url | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 29/Jul/25 9:57 AM | 08/Oct/25 5:53 PM |  | 2 | ecommerce-shopify-api |  |  | 0 | มาจาก Sprint 8 | Ready To Test | 7200 | [Dev][RD][Thana] Sprint 8 | [Dev][RD][Thana] Sprint 9
Story | RDAPS-113 | 28752 | [Dev][RD][Rewards API] Enhance API to get product by ID, Slug to support new fields for e-commerce type | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 24/Jul/25 7:25 PM | 17/Oct/25 4:07 PM |  | 2 | No-QA | rewards-api |  | 14400 |  |  |  | [Dev][All project]Sprint 4 | [Dev][All project]Sprint 5 | [Dev][All project]Sprint 6 | [Dev][All project]Sprint 7 | [Dev][All Project] Sprint 9

## Summarize Sprint 8
Column 1 | Total Stories Point | Total Manhour | Point Done | Manhour Done | Note
22 Sep - 3 Oct
Dev Resource Available | 18 | 546
Meeting Planned |  | 196.5 |  |  | Ref
Additional Meeting |  | 15.75 |  |  | Ref
Deployment |  | 5 |  |  | 3 ครั้ง 1. 1 คน 2. 1 คน 3. 3 คน
Development Sprint Total | 408 | 457.5 | 100 | 68.5
Ad-hoc Mid Sprint | 5 | 12 | 0 | 0 | 3 tasks
Requirement changes after refinement? | 0 | 0 | 0 | 0 | 0 tasks
Aek | 30 | 32.5 | 13 | 16.5
A | 32 | 54 | 3 | 0
Aom | 35 | 27 | 11 | 7
Zan | 25 | 35 | 5 | 3
Mai | 48 | 38 | 11 | 0
Mac | 51 | 43 | 16 | 8
Mos | 52 | 76 | 15 | 16
Jack | 36 | 42 | 16 | 18
Art | 28 | 22 | 10 | 0
Kae | 28 | 44 | 0 | 0
Nim | 35 | 44 | 0 | 0
| System Architech |  |  |  | Permanent Dev. |  |  | Outsources
Projects (Stories Points) | Aek | Zan | Aom | Jack | A | Art | Mai | Kae | Mac | Nim | Mos
Das Haus - Thana City & Das Haus | 6 | 7 | 1 | 18 | 22 | 23 | 43 | 18 | 46 | 30 | 36
E-commerce 1.1. E-Commerce x Shopify Plus 1.2. Shopify:Snackmaker 1.3. Shopify: Turtle Delivery 1.4. Shopify: Turtle Delivery | 24 | 0 | 0 | 14 | 2 | 5 | 0 | 10 | 0 | 0 | 11
CleverTap - MKT Automation Tool | 0 | 3 | 5 | 4 | 0 | 0 | 0 | 5 | 0 | 5 | 5
Adjust Integration | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 5 | 0
Adhoc - Non-Epics - Turtle Display club tier on POS - Data Mart Migration | 0 | 14 | 13 | 0 | 8 | 0 | 3 | 0 | 3 | 0 | 0
Support Incidents | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| System Architech |  |  |  | Permanent Dev. |  |  | Outsources
Projects (Manhour) | Aek | Zan | Aom | Jack | A | Art | Mai | Kae | Mac | Nim | Mos
Das Haus - Thana City & Das Haus | 7 | 19 | 0 | 0 | 50 | 22 | 26 | 12 | 31 | 28 | 18
E-commerce 1.1. E-Commerce x Shopify Plus 1.2. Shopify:Snackmaker 1.3. Shopify: Turtle Delivery 1.4. Shopify: Turtle Delivery | 25.5 | 0 | 0 | 42 | 4 | 0 | 0 | 32 | 0 | 0 | 42
CleverTap - MKT Automation Tool | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16
Adjust Integration | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0
Adhoc - Non-Epics - Turtle Display club tier on POS - Data Mart Migration | 0 | 16 | 25 | 0 | 0 | 0 | 8 | 0 | 8 | 0 | 0
Support Incidents | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 8
Issue Type | Issue key | Issue id | Summary | Assignee | Assignee Id | Reporter | Reporter Id | Priority | Status | Resolution | Created | Updated | Due date | Custom field (Story Points) | Labels | Labels | Original estimate | Sprint Movement | Sprint 7 | Note | Sprint | Sprint | Sprint | Sprint | Sprint
Bug | RDAPS-206 | 31931 | [Dev][RD][RRS] Card Info data missing from Redemption ETL | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Fixing |  | 03/Oct/25 11:17 AM | 03/Oct/25 11:25 AM | [8 empty] | [Dev][All Project] Sprint 8
Bug | DEVRDSUP-159 | 31927 | [SUP-223][HRSolution] Can't import employee but HR solution doesn't response anything. | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | UNDER VALIDATION |  | 03/Oct/25 1:42 AM | 06/Oct/25 2:05 PM | 06/Oct/25 12:00 AM |  | hop | hr-solution |  |  |  |  | [Dev][All Project] Sprint 8
Story | RDAPS-205 | 31905 | [DEV][RD][REM] Enhance Redemption API to support displaying exclusive rewards in rewards store | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Highest | Ready to Staging |  | 02/Oct/25 8:21 AM | 06/Oct/25 2:15 PM |  | 3 | mid-sprint | redemption-api | 28800 |  |  | No original est | [Dev][All Project] Sprint 8
Story | RDAPS-204 | 31904 | [DEV][RD][BOF] Enhance Algolia payload to support displaying exclusive rewards in rewards store | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Highest | Ready to Staging |  | 02/Oct/25 8:19 AM | 06/Oct/25 2:15 PM |  | 2 | mid-sprint | rr-backoffice | 14400 |  |  | No original est | [Dev][All Project] Sprint 8
Bug | RDTHANA-306 | 31903 | [S4][HR Solution][Welcome message][Advanced Setting] Business Unit Submitting Incomplete alert message has changed | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Low | Resolved |  | 02/Oct/25 12:45 AM | 02/Oct/25 3:08 PM | [8 empty] | [Dev][RD][Thana] Sprint 8
Bug | RDTHANA-305 | 31902 | [S4][HR Solution][Welcome message][Pop up setting] Destination button text fields not set as the required field | Art_narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Low | Closed |  | 02/Oct/25 12:22 AM | 03/Oct/25 1:41 PM | 03/Oct/25 12:00 AM | [7 empty] | [Dev][RD][Thana] Sprint 8
Bug | RDTHANA-304 | 31901 | [S4][HR Solution][Welcome message][Pop up setting] Destination body messages don't have character counter | Art_narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Closed |  | 02/Oct/25 12:03 AM | 03/Oct/25 1:33 PM | 03/Oct/25 12:00 AM | [7 empty] | [Dev][RD][Thana] Sprint 8
Story | RDAPS-203 | 31890 | [DEV][RD][BFF] Enhance Get section/widget api for support display exclusive rewards on rewards store | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Highest | Ready to Staging |  | 01/Oct/25 5:25 PM | 06/Oct/25 2:15 PM |  | 3 | BFF | mid-sprint | 28800 |  |  | No original est | [Dev][All Project] Sprint 8
Story | RDAPS-202 | 31889 | [DEV][RD][SA] Request for export Coupon code from rewards in Turtle Club project | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Progress |  | 01/Oct/25 5:24 PM | 01/Oct/25 5:26 PM | [8 empty] | [Dev][All Project] Sprint 8
Bug | RDTHANA-296 | 31878 | [S2][HR-Solution][Feature] Unable to add more club configuration | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 01/Oct/25 1:52 PM | 02/Oct/25 11:03 AM | [8 empty] | [Dev][RD][Thana] Sprint 8
Bug | DEVRDCT-240 | 31854 | [S3][CleverTap][Webhook][Club Binding Event] Club binding status event unbind not feed to CT through Webhook API | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Closed |  | 30/Sep/25 1:17 PM | 01/Oct/25 10:18 AM | [8 empty] | [Dev][CT] Sprint 8
Story | RDTHANA-294 | 31845 | [Dev][RD][BFF] Improve get sections contents api v2 | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready To Test |  | 30/Sep/25 11:56 AM | 03/Oct/25 9:33 AM | 01/Oct/25 12:00 AM | 2 |  |  | 14400 |  |  |  | [Dev][RD][Thana] Sprint 8
Bug | RDAPS-201 | 31814 | [DEV][RD][Portal API][Cronjob] Add log to merchant ranking | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | ACCEPTED |  | 29/Sep/25 3:00 PM | 29/Sep/25 3:03 PM | [8 empty] | [Dev][All Project] Sprint 8
Sub-task | DEVRDCT-239 | 31813 | [QA] Test execution Club Binding Event | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 29/Sep/25 2:21 PM | 30/Sep/25 9:01 PM | [8 empty] | [Dev][CT] Sprint 7 | [Dev][CT] Sprint 8
Bug | RDAPS-200 | 31808 | [DEV][RD][SSO User][BSS] Disable sync member consent detail to RR member's consent | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Closed |  | 29/Sep/25 1:30 PM | 02/Oct/25 1:17 PM |  | 3 |  |  | 28800 |  |  | No original est | [Dev][All Project] Sprint 8
Sub-task | DEVRDECOM-109 | 31716 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 26/Sep/25 3:55 PM | 02/Oct/25 10:57 AM | [8 empty] | [Dev][RD][Ecom] Sprint 8
Sub-task | DEVRDECOM-108 | 31714 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 26/Sep/25 3:55 PM | 26/Sep/25 4:11 PM | [8 empty] | [Dev][RD][Ecom] Sprint 8
Story | RDTHANA-289 | 31700 | [DEV][RD][BOF][CR] Enhance survey ranking question | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 26/Sep/25 2:02 PM | 03/Oct/25 10:22 AM | 30/Sep/25 12:00 AM | 3 |  |  | 21600 |  |  |  | [Dev][RD][Thana] Sprint 8
Story | RDAPS-199 | 31674 | [DEV][RD][Merchant Ranking] Add sync process log | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 26/Sep/25 9:42 AM | 29/Sep/25 3:00 PM |  | 3 | [6 empty] | [Dev][All Project] Sprint 8
Epic | RDAPS-198 | 31673 | [DEV][RD][Merchant Ranking] Add sync data log | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 26/Sep/25 9:39 AM | 26/Sep/25 9:39 AM |  | 3 |  |  | 28800 |  |  | No original est | [Dev][All Project] Sprint 8
Story | DEVRDCT-238 | 31656 | [Dev][RD][CID] Improve CLI for Initial feed Rabbit Wallet Card to CleverTap | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 25/Sep/25 10:44 AM | 03/Oct/25 9:30 AM |  | 2 |  |  | 7200 |  |  |  | [Dev][CT] Sprint 8
Sub-task | RDAPS-197 | 31655 | [QA] Test - Happy case on UAT | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 25/Sep/25 10:30 AM | 30/Sep/25 4:32 PM | [8 empty] | [Dev][All Project] Sprint 8
Test Set | QA-195 | 31630 | [TS][Thana city] HRS - Business Unit - Welcome Message Setting - Pop up tab |  |  | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | In Progress |  | 24/Sep/25 5:13 PM | 02/Oct/25 1:07 AM | [8 empty] | [Dev][CT] Sprint 8
Bug | RDTHANA-272 | 31552 | [S3][Edit Business Unit][Advanced setting] Advanced Setting is not saved as expected | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Closed |  | 23/Sep/25 5:54 PM | 01/Oct/25 3:31 PM | [8 empty] | [Dev][RD][Thana] Sprint 8
Bug | RDTHANA-271 | 31551 | [S4][Edit Business Unit][Advanced setting] Successful toast wording and design is mismatch from Figma | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Closed |  | 23/Sep/25 5:36 PM | 01/Oct/25 5:04 PM | [8 empty] | [Dev][RD][Thana] Sprint 8
Bug | RDTHANA-270 | 31550 | [S3][Edit Business Unit][Advanced setting] Feature setting not found due to click link out from error popup | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Reopened |  | 23/Sep/25 5:19 PM | 03/Oct/25 9:33 AM | [8 empty] | [Dev][RD][Thana] Sprint 8
Bug | RDTHANA-269 | 31549 | [S4][Edit Business Unit][Advanced setting] "Application" default in "Opt-in via" checkbox design does not have a selected sign | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Closed |  | 23/Sep/25 5:05 PM | 01/Oct/25 5:04 PM | [8 empty] | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-268 | 31545 | [Dev][RD][BOF] Disable mode when survey is expired | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 23/Sep/25 3:28 PM | 29/Sep/25 10:25 AM | 30/Sep/25 12:00 AM | 1 | rr-backoffice |  | 3600 |  |  |  | [Dev][RD][Thana] Sprint 8
Test Plan | RDTHANA-266 | 31540 | [TP][Thana city] Sprint 8 |  |  | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 23/Sep/25 2:06 PM | 23/Sep/25 2:06 PM | [8 empty] | [Dev][RD][Thana] Sprint 8
Test Set | QA-77 | 31538 | [TS][Thana city] HRS - Business Unit - Advance setting |  |  | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done | Done | 23/Sep/25 2:01 PM | 02/Oct/25 1:07 AM | [8 empty] | [Dev][RD][Thana] Sprint 8
Story | RDAPS-196 | 31530 | [Dev][RD][BFF] Change cache TTL for get SSO user profile | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 23/Sep/25 1:40 PM | 03/Oct/25 9:33 AM |  | 1 |  |  | 3600 |  |  |  | [Dev][All Project] Sprint 8
Sub-task | DEVRDCT-237 | 31508 | [QA] Create Test Case | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 23/Sep/25 10:42 AM | 02/Oct/25 11:12 AM | [8 empty] | [Dev][Thana City] sprint 6 | [Dev][CT] Sprint 5 | [Dev][CT] Sprint 6 | [Dev][CT] Sprint 7 | [Dev][CT] Sprint 8
Epic | DEVRDECOM-107 | 31506 | Shopify Webhook |  |  | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | To Do |  | 23/Sep/25 9:52 AM | 06/Oct/25 10:42 AM | [8 empty] | [Dev][RD][Ecom] Sprint 8 | [Dev][RD][Ecom] Sprint 9
Sub-task | DEVRDECOM-104 | 31499 | [QA] Create Test Case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 22/Sep/25 10:13 PM | 23/Sep/25 10:39 AM | [8 empty] | [Dev][RD][Ecom] Sprint 8 | [Dev][RD][Ecom] Sprint 9
Sub-task | DEVRDECOM-103 | 31497 | [QA] Create Test Case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 22/Sep/25 10:13 PM | 23/Sep/25 10:39 AM | [8 empty] | [Dev][RD][Ecom] Sprint 8 | [Dev][RD][Ecom] Sprint 9
Sub-task | DEVRDECOM-102 | 31495 | [QA] Create Test Case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 22/Sep/25 10:13 PM | 24/Sep/25 6:03 PM | [8 empty] | [Dev][RD][Ecom] Sprint 8 | [Dev][RD][Ecom] Sprint 9
Sub-task | RDTHANA-259 | 31493 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 22/Sep/25 10:11 PM | 29/Sep/25 9:48 AM | [8 empty] | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-258 | 31491 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 22/Sep/25 10:11 PM | 29/Sep/25 9:48 AM | [8 empty] | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-257 | 31489 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 22/Sep/25 10:11 PM | 01/Oct/25 10:05 AM | [8 empty] | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-256 | 31487 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 22/Sep/25 10:10 PM | 01/Oct/25 2:37 PM | [8 empty] | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-255 | 31485 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 22/Sep/25 10:10 PM | 29/Sep/25 9:48 AM | [8 empty] | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-254 | 31483 | [QA] Create Test Case |  |  | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 22/Sep/25 10:08 PM | 22/Sep/25 10:08 PM | [8 empty] | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-253 | 31481 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 22/Sep/25 10:07 PM | 06/Oct/25 3:56 PM | [8 empty] | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-252 | 31479 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 22/Sep/25 10:07 PM | 06/Oct/25 2:16 PM | [8 empty] | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-251 | 31477 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 22/Sep/25 10:07 PM | 06/Oct/25 1:07 PM | [8 empty] | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-250 | 31475 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 22/Sep/25 10:07 PM | 06/Oct/25 10:47 AM | [8 empty] | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-249 | 31473 | [QA] Create Test Case View Survey List (FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 22/Sep/25 10:06 PM | 04/Oct/25 12:35 PM | [8 empty] | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | DEVRDADJ-50 | 31471 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 22/Sep/25 10:05 PM | 23/Sep/25 10:53 AM | [8 empty] | [Dev][RDAdjust] Sprint 8
Sub-task | DEVRDADJ-49 | 31469 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 22/Sep/25 10:04 PM | 23/Sep/25 10:52 AM | [8 empty] | [Dev][RDAdjust] Sprint 8
Sub-task | DEVRDADJ-48 | 31467 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 22/Sep/25 10:04 PM | 23/Sep/25 10:52 AM | [8 empty] | [Dev][RDAdjust] Sprint 8
Sub-task | DEVRDADJ-47 | 31465 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 22/Sep/25 10:04 PM | 23/Sep/25 10:52 AM | [8 empty] | [Dev][RDAdjust] Sprint 8
Sub-task | DEVRDADJ-46 | 31463 | [QA] Create Test Case & Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 22/Sep/25 10:04 PM | 01/Oct/25 1:24 PM | [8 empty] | [Dev][RDAdjust] Sprint 8
Sub-task | DEVRDADJ-45 | 31461 | [QA] Create Test Case & Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 22/Sep/25 10:03 PM | 01/Oct/25 1:56 PM | [8 empty] | [Dev][RDAdjust] Sprint 8
Story | RDAPS-195 | 31455 | [Dev][RD] Manual run Redemption ETL & Subscription TXN Report to DA | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 22/Sep/25 5:42 PM | 22/Sep/25 5:44 PM |  | 2 |  |  | 7200 |  |  |  | [Dev][All Project] Sprint 8
Story | RDTHANA-244 | 31447 | [DEV][RD][APH] Enhance sorry page support dynamic error message and CTA button | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Blocked |  | 22/Sep/25 11:36 AM | 03/Oct/25 9:32 AM | 29/Sep/25 12:00 AM | 1 | [6 empty] | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-241 | 31432 | [DEV][RD][APH] Enhance survey html render support survey appearance "Thank you" tab | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 21/Sep/25 9:13 PM | 01/Oct/25 9:45 AM | 29/Sep/25 12:00 AM | 3 |  |  | 28800 |  |  |  | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-240 | 31431 | [DEV][RD][APH] Enhance survey html render support survey appearance "Email" tab (Issue point form) | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 21/Sep/25 9:13 PM | 29/Sep/25 1:04 PM | 26/Sep/25 12:00 AM | 5 |  |  | 57600 |  |  | No original est | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-239 | 31430 | [DEV][RD][APH] Enhance survey html render support survey appearance "Survey Q&A" tab | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 21/Sep/25 9:13 PM | 03/Oct/25 10:25 AM | 26/Sep/25 12:00 AM | 8 |  |  | 57600 |  |  |  | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-238 | 31429 | [DEV][RD][APH] Create survey theme | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Highest | Ready To Test |  | 21/Sep/25 8:49 PM | 01/Oct/25 10:50 AM | 23/Sep/25 12:00 AM | 3 | rr-aphrodite |  | 28800 |  |  |  | [Dev][RD][Thana] Sprint 8
Story | RDAPS-193 | 31428 | [Dev][RD][RRS] Create command to email alerts for rewards expiring within 30 days | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 21/Sep/25 7:56 PM | 06/Oct/25 2:22 PM | 24/Sep/25 12:00 AM | 3 | rr-scheduler |  | 28800 |  |  |  | [Dev][All Project] Sprint 8
Story | RDTHANA-237 | 31427 | [DEV][RD][APH] Create migration | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Highest | Done |  | 21/Sep/25 3:40 PM | 03/Oct/25 10:00 AM |  | 1 | No-QA |  | 7200 |  |  |  | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-236 | 31426 | [Dev][RD][BOF] Rename all related feature and field from ‘Exclusive Store’ ‘Exclusive Partner Store’ to ‘Club - Rewards’ | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 21/Sep/25 2:16 PM | 01/Oct/25 11:22 AM | 01/Oct/25 12:00 AM | 2 | rr-backoffice | rr-scheduler | 7200 |  |  | No original est | [Dev][RD][Thana] Sprint 8
Story | DEVRDECOM-99 | 31423 | [DEV][RD][Eco][RR-Ecommerce-Shopify] Create Webhook API Endpoint refunds/create | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Review |  | 21/Sep/25 9:47 AM | 06/Oct/25 10:42 AM | 01/Oct/25 12:00 AM | 3 |  |  | 28800 |  |  | No original est | [Dev][RD][Ecom] Sprint 8 | [Dev][RD][Ecom] Sprint 9
Story | DEVRDECOM-97 | 31421 | [DEV][RD][Eco][RR-Ecommerce-Shopify] Calculate Point | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready to Staging |  | 21/Sep/25 9:35 AM | 06/Oct/25 10:42 AM |  | 1 |  |  | 7200 |  |  |  | [Dev][RD][Ecom] Sprint 8 | [Dev][RD][Ecom] Sprint 9
Story | DEVRDECOM-96 | 31397 | [DEV][RD][Eco][BFF] Enhance auto-login-url with return_url for Banner link | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 20/Sep/25 9:39 PM | 07/Oct/25 8:37 AM |  | 1 |  |  | 7200 |  |  |  | [Dev][RD][Ecom] Sprint 8
Story | DEVRDECOM-95 | 31396 | [DEV][RD][Eco][RR-Ecommerce-Shopify] Create Data Migration | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 19/Sep/25 8:36 PM | 30/Sep/25 10:03 AM | 24/Sep/25 12:00 AM | 1 | ecommerce-shopify-api | No-QA | 7200 |  |  | No original est | [Dev][RD][Ecom] Sprint 8
Bug | RDTHANA-235 | 31389 | [S4][HRS][Member] Field "Added Member Channel" not type drop down and UI does not match the request | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Closed |  | 19/Sep/25 3:08 PM | 26/Sep/25 3:58 PM | [5 empty] | มาจาก Sprint 7 | UNDER VALIDATION |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-247 | 31385 | [DEV][RD][Eco][RR-Ecommerce-Shopify][Das Haus] Create Endpoint for Club Binding Callback and Redirect to Shopify | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 19/Sep/25 1:53 PM | 06/Oct/25 9:47 AM | 03/Oct/25 12:00 AM | 3 |  |  | 57600 |  |  |  | [Dev][RD][Thana] Sprint 8
Story | DEVRDECOM-93 | 31383 | [DEV][RD][Eco][RR-Ecommerce-Shopify] Enhance auto-login-url with return_url for Banner link | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 19/Sep/25 1:19 PM | 07/Oct/25 8:38 AM |  | 1 |  |  | 7200 |  |  |  | [Dev][RD][Ecom] Sprint 8
Story | RDAPS-192 | 31369 | [Dev][RD][Order] Add 'publishPrice' field to sync data to DA | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Highest | Done |  | 19/Sep/25 10:56 AM | 03/Oct/25 9:32 AM |  | 2 | order-consumer |  | 7200 |  |  |  | [Dev][All Project] Sprint 8
Story | RDTHANA-232 | 31360 | [DEV][RD][GATEWAY] Mapping get member club detail with internal API | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Highest | Ready To Test |  | 19/Sep/25 10:44 AM | 06/Oct/25 9:47 AM |  | 1 |  |  | 7200 |  |  | No original est | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-231 | 31359 | [DEV][RD][APH] Enhance survey html render support survey appearance "General" tab | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 19/Sep/25 10:43 AM | 01/Oct/25 10:51 AM | 26/Sep/25 12:00 AM | 5 |  |  | 57600 |  |  |  | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-230 | 31358 | [DEV][RD][APH] Enhance getMemberToken support sources session | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 19/Sep/25 10:42 AM | 29/Sep/25 10:25 AM | 26/Sep/25 12:00 AM | 2 |  |  | 7200 |  |  |  | [Dev][RD][Thana] Sprint 8
Story | DEVRDECOM-92 | 31345 | [DEV][RD][Eco][Rewards-Member] Setup and Running Redis Queue | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready to Staging |  | 18/Sep/25 8:00 PM | 06/Oct/25 10:42 AM |  | 2 | No-QA | rewards-member | 14400 |  |  |  | [Dev][RD][Ecom] Sprint 8 | [Dev][RD][Ecom] Sprint 9
Story | DEVRDECOM-91 | 31344 | [DEV][RD][Eco][Setup] Setup Webhook and Mapping API Gateway | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 18/Sep/25 7:31 PM | 07/Oct/25 8:39 AM |  | 1 | No-QA | rr-ecommerce-shopify | 7200 |  |  |  | [Dev][RD][Ecom] Sprint 8
Story | DEVRDECOM-90 | 31343 | [DEV][RD][Eco][RR-Ecommerce-Shopify] Create Scheduled Job for update transport status | Art_narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Progress |  | 18/Sep/25 7:27 PM | 06/Oct/25 10:42 AM |  | 5 | ecommerce-shopify-api | [5 empty] | [Dev][RD][Ecom] Sprint 8 | [Dev][RD][Ecom] Sprint 9
Story | DEVRDECOM-89 | 31341 | [DEV][RD][Eco][POC] Dynamic Section by Customer Location for Turtle shop | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Progress |  | 18/Sep/25 5:56 PM | 06/Oct/25 10:42 AM |  | 5 | rr-ecommerce-shopify | [5 empty] | [Dev][RD][Ecom] Sprint 8 | [Dev][RD][Ecom] Sprint 9
Story | DEVRDECOM-88 | 31340 | [DEV][RD][Eco][Ecommerce-Shopify] Sync Order Data from Shopify Stores to Data Mart | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 18/Sep/25 5:55 PM | 02/Oct/25 4:23 PM | 29/Sep/25 12:00 AM | 5 |  |  | 57600 |  |  | No original est | [Dev][RD][Ecom] Sprint 8
Story | DEVRDECOM-87 | 31339 | [DEV][RD][Eco][Spec] Banner link to Shopify with return_url | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 18/Sep/25 5:52 PM | 07/Oct/25 8:39 AM |  | 1 | No-QA | rr-ecommerce-shopify | 7200 |  |  |  | [Dev][RD][Ecom] Sprint 8
Story | DEVRDECOM-86 | 31337 | [DEV][RD][Eco][Setup] Auto login & Verify email for Turtle shop | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 18/Sep/25 5:45 PM | 07/Oct/25 8:40 AM |  | 2 | rr-ecommerce-shopify |  | 10800 |  |  |  | [Dev][RD][Ecom] Sprint 8 | [Dev][RD][Ecom] Sprint 9
Story | DEVRDECOM-85 | 31336 | [DEV][RD][Eco][Setup] Auto login & Verify email for Das Haus shop | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 18/Sep/25 5:36 PM | 07/Oct/25 8:40 AM |  | 2 | rr-ecommerce-shopify |  | 10800 |  |  |  | [Dev][RD][Ecom] Sprint 8 | [Dev][RD][Ecom] Sprint 9
Story | DEVRDECOM-84 | 31335 | [DEV][RD][Eco][Setup] Auto login & Verify email for Snackmaker shop | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 18/Sep/25 5:30 PM | 07/Oct/25 8:41 AM |  | 2 | rr-ecommerce-shopify |  | 10800 |  |  |  | [Dev][RD][Ecom] Sprint 8 | [Dev][RD][Ecom] Sprint 9
Story | RDTHANA-245 | 31334 | [DEV][RD][Eco][RR-Ecommerce-Shopify][Das Haus] Enhance Auth Callback Endpoint to checks if the customer is a Das Haus club member. | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 18/Sep/25 5:09 PM | 06/Oct/25 9:47 AM |  | 5 | ecommerce-shopify-api |  | 57600 |  |  | No original est | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-229 | 31332 | [DEV][RD][APH] Enhance survey available middleware | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 18/Sep/25 4:23 PM | 29/Sep/25 10:41 AM | 26/Sep/25 12:00 AM | 5 |  |  | 57600 |  |  |  | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-227 | 31330 | [DEV][RD][HRS] Enhance check eligible to set opt-in setting in popup welcome message | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 18/Sep/25 4:06 PM | 29/Sep/25 9:41 AM |  | 2 |  |  | 14400 |  |  | No original est | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-226 | 31329 | [DEV][RD][HRS] Enhance check eligible to set opt-in setting in advance setting | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 18/Sep/25 4:05 PM | 26/Sep/25 3:07 PM |  | 3 |  |  | 28800 |  |  | No original est | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-225 | 31328 | [DEV][RD][HRS] Enhance import employee bu list with member_method and is_import | Art_narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 18/Sep/25 4:01 PM | 01/Oct/25 10:03 AM | 29/Sep/25 12:00 AM | 1 |  |  | 7200 |  |  | No original est | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-224 | 31327 | [DEV][RD][HRS] Enhance feature setting company level with opt-in BU enable | Art_narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 18/Sep/25 3:59 PM | 01/Oct/25 10:03 AM | 29/Sep/25 12:00 AM | 5 |  |  | 57600 |  |  | No original est | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-223 | 31326 | [DEV][RD][HRS] Enhance default bu welcome message link | Art_narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 18/Sep/25 3:56 PM | 24/Sep/25 4:02 PM |  | 2 |  |  | 14400 |  |  | No original est | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-246 | 31325 | [DEV][RD][Eco][RR-Ecommerce-Shopify][Das Haus] Enhance login with return_url | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 18/Sep/25 3:22 PM | 07/Oct/25 8:43 AM |  | 2 | ecommerce-shopify-api |  | 10800 |  |  |  | [Dev][RD][Thana] Sprint 8
Story | DEVRDECOM-81 | 31324 | [DEV][RD][Eco][Spec] Join club via RR web with token encryption | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 18/Sep/25 3:21 PM | 07/Oct/25 8:41 AM |  | 1 | No-QA | rr-ecommerce-shopify | 1800 |  |  |  | [Dev][RD][Ecom] Sprint 8
Story | RDAPS-190 | 31318 | [Dev][RD][Order API] Enhancement on refund button to cross check payment status before sending refund request | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Highest | Done |  | 18/Sep/25 2:27 PM | 01/Oct/25 10:14 AM | 23/Sep/25 12:00 AM | 3 | order-api |  | 28800 |  |  |  | [Dev][All Project] Sprint 8
Story | DEVRDADJ-44 | 31314 | [DEV][RD][BOF] Enhance RR Backoffice to integrate with ADJUST Deeplink Generated api | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 18/Sep/25 1:53 PM | 03/Oct/25 10:28 AM |  | 5 |  |  | 57600 | มาจาก Sprint 7 | To Do |  | [Dev][RDAdjust] Sprint 8
Story | DEVRDADJ-43 | 31313 | [DEV][RD][LNF] create script to remove "adj_redirect" in existing deeplink | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 18/Sep/25 1:50 PM | 26/Sep/25 10:33 AM | 24/Sep/25 12:00 AM | 2 |  |  | 14400 | มาจาก Sprint 7 | To Do |  | [Dev][RDAdjust] Sprint 8
Story | DEVRDADJ-41 | 31311 | [DEV][RD][LNF] Enhance auto generate deeplink, remove redirect url in request | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 18/Sep/25 1:45 PM | 06/Oct/25 2:22 PM | 25/Sep/25 12:00 AM | 2 |  |  | 14400 | มาจาก Sprint 7 | To Do |  | [Dev][RDAdjust] Sprint 8
Sub-task | RDTHANA-222 | 31299 | [QA] Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 17/Sep/25 4:37 PM | 23/Sep/25 2:50 PM | [5 empty] | มาจาก Sprint 7 | In Progress |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-221 | 31297 | [QA] Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 17/Sep/25 4:37 PM | 23/Sep/25 1:28 PM | [5 empty] | มาจาก Sprint 7 | In Progress |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-220 | 31295 | [QA] Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 17/Sep/25 4:37 PM | 23/Sep/25 1:27 PM | [5 empty] | มาจาก Sprint 7 | In Progress |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-219 | 31293 | [QA] Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 17/Sep/25 4:37 PM | 24/Sep/25 6:04 PM | [5 empty] | มาจาก Sprint 7 | In Progress |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-218 | 31291 | [QA] Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 17/Sep/25 4:36 PM | 23/Sep/25 1:26 PM | [5 empty] | มาจาก Sprint 7 | In Progress |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Bug | RDTHANA-217 | 31277 | [S4][Welcome message] Tab Welcome message display when setting condition Welcome message is inactive | Art_narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Closed |  | 17/Sep/25 3:13 PM | 02/Oct/25 2:09 PM | 29/Sep/25 12:00 AM |  |  |  |  | มาจาก Sprint 7 | Open |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-216 | 31271 | [QA] Test execution Pop up tab in Welcome message | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 17/Sep/25 1:38 PM | 02/Oct/25 1:27 AM | [5 empty] | มาจาก Sprint 7 | In Progress |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-215 | 31269 | [QA] Test execution Advance Setting Tab | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 17/Sep/25 1:38 PM | 02/Oct/25 1:27 AM | [5 empty] | มาจาก Sprint 7 | In Progress |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-178 | 31139 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 15/Sep/25 3:30 PM | 22/Sep/25 10:46 AM | [5 empty] | มาจาก Sprint 7 | In Progress |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-177 | 31137 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 15/Sep/25 3:30 PM | 02/Oct/25 10:14 AM | [5 empty] | มาจาก Sprint 7 | In Progress |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Bug | RDTHANA-176 | 31135 | [S3][HRS][Feature][Set Welcome Message] When change Default Business Unit the button doesn't disappear | Art_narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | High | Closed |  | 15/Sep/25 3:13 PM | 29/Sep/25 9:43 AM | [8 empty] | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-175 | 31131 | Run import on prod |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 15/Sep/25 2:42 PM | 15/Sep/25 2:42 PM | [5 empty] | มาจาก Sprint 7 | To Do |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-174 | 31129 | Enhance import function |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 15/Sep/25 2:41 PM | 17/Sep/25 3:58 PM |  |  | No-QA |  |  | มาจาก Sprint 7 | Done |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Bug | RDTHANA-173 | 31127 | [S3][HRS][Feature][Field] Default Business Unit for Opt-in Member Channel not required field | Art_narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Closed |  | 15/Sep/25 2:22 PM | 29/Sep/25 9:42 AM | [5 empty] | มาจาก Sprint 7 | Fixing |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Bug | RDTHANA-172 | 31126 | [S4][HRS][Feature][Sort] BU list is not sorted alphabetically. | Art_narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Low | Closed |  | 15/Sep/25 2:04 PM | 26/Sep/25 4:01 PM | [5 empty] | มาจาก Sprint 7 | Fixing |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Bug | RDTHANA-171 | 31125 | [S4][HRS][Feature][Default Business Unit] The display format is incorrect. | Art_narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Low | Closed |  | 15/Sep/25 1:57 PM | 26/Sep/25 4:02 PM | [5 empty] | มาจาก Sprint 7 | Fixing |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-158 | 31036 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 12/Sep/25 1:09 PM | 12/Sep/25 1:09 PM | [5 empty] | มาจาก Sprint 7 | Done |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Bug | RDTHANA-157 | 31032 | [S4][HRS][Business Unit][Filter Name] The filter column name and active column symbol is incorrect according to Figma. | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Low | Closed |  | 12/Sep/25 11:19 AM | 26/Sep/25 3:19 PM | [5 empty] | มาจาก Sprint 7 | Resolved |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-153 | 31022 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 11/Sep/25 10:00 PM | 22/Sep/25 10:46 AM | [5 empty] | มาจาก Sprint 7 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Test Execution | RDTHANA-152 | 31020 | [TX][Thana city] Sprint7 | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 11/Sep/25 9:57 PM | 29/Sep/25 9:45 AM | [5 empty] | มาจาก Sprint 7 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Test Plan | RDTHANA-151 | 31019 | [TP][Thana city] Sprint7 | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 11/Sep/25 9:56 PM | 29/Sep/25 9:45 AM | [5 empty] | มาจาก Sprint 7 | To Do |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Test Set | RDTHANA-150 | 31018 | [TS][Thana city] Sprint7 | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 11/Sep/25 9:56 PM | 29/Sep/25 9:45 AM | [5 empty] | มาจาก Sprint 7 | To Do |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-134 | 30844 | [QA] Create Test Case Download Individual Survey Report (FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:30 AM | 05/Oct/25 3:00 PM | [5 empty] | มาจาก Sprint 7 | To Do |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-133 | 30842 | [QA] Create Test Case View Survey Report (FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:30 AM | 05/Oct/25 2:50 PM | [5 empty] | มาจาก Sprint 7 | To Do |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-132 | 30840 | [QA] Create Test Case Change survey status (FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:30 AM | 04/Oct/25 12:24 PM | [5 empty] | มาจาก Sprint 7 | To Do |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-131 | 30838 | [QA] |  |  | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 09/Sep/25 11:29 AM | 21/Sep/25 3:00 PM | [5 empty] | มาจาก Sprint 7 | To Do |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-130 | 30836 | [QA] Create Test Case Update survey Step 5: Survey Appearance (Thank You) (FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:29 AM | 04/Oct/25 12:32 PM | [5 empty] | มาจาก Sprint 7 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-129 | 30834 | [QA] Create Test Case Update survey Step 5: Survey Appearance (Input E-mail) (FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:29 AM | 21/Sep/25 3:01 PM | [5 empty] | มาจาก Sprint 7 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-128 | 30832 | [QA] Create Test Case [Dev][RD][BOF] Update survey step5.2(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:29 AM | 21/Sep/25 1:58 PM | [5 empty] | มาจาก Sprint 7 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-127 | 30830 | [QA] Create Test Case Update survey step5.1(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:28 AM | 21/Sep/25 1:55 PM | [5 empty] | มาจาก Sprint 7 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-126 | 30828 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 09/Sep/25 11:28 AM | 22/Sep/25 11:02 AM | [8 empty] | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-125 | 30826 | [QA] Create Test Case Update survey step4.2(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:28 AM | 21/Sep/25 1:55 PM | [5 empty] | มาจาก Sprint 7 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-124 | 30824 | [QA] Create Test Case Update survey step4.1(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:27 AM | 21/Sep/25 1:55 PM | [5 empty] | มาจาก Sprint 7 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-123 | 30822 | [QA] Create Test Case Update survey step3(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:27 AM | 21/Sep/25 1:55 PM | [5 empty] | มาจาก Sprint 7 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-122 | 30820 | [QA] Create Test Case Update survey step2(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:26 AM | 21/Sep/25 12:27 PM | [5 empty] | มาจาก Sprint 7 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-121 | 30818 | [QA] Create Test Case Update survey step1(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:26 AM | 21/Sep/25 12:27 PM | [5 empty] | มาจาก Sprint 7 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-120 | 30816 | [QA] Create Test Case Create survey (FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:25 AM | 21/Sep/25 12:27 PM | [5 empty] | มาจาก Sprint 7 | In Progress |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-119 | 30814 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 09/Sep/25 11:24 AM | 09/Sep/25 11:24 AM | [5 empty] | มาจาก Sprint 7 | To Do |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-118 | 30812 | [QA] Create Test Case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 09/Sep/25 11:23 AM | 09/Sep/25 11:23 AM | [5 empty] | มาจาก Sprint 7 | To Do |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-117 | 30810 | [QA] Create Test Case | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 09/Sep/25 11:23 AM | 09/Sep/25 11:23 AM | [8 empty] | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-116 | 30808 | [QA] Create Test Case 'Club - Benefits & Info' Location | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 09/Sep/25 11:22 AM | 18/Sep/25 9:19 AM | [5 empty] | มาจาก Sprint 7 | Done |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-115 | 30806 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 09/Sep/25 11:22 AM | 09/Sep/25 11:22 AM | [5 empty] | มาจาก Sprint 7 | To Do |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-114 | 30804 | [QA] Create Test Case Widget Type 'Club – Benefits & Information' | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 09/Sep/25 11:21 AM | 17/Sep/25 10:52 PM | [5 empty] | มาจาก Sprint 7 | Done |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | DEVRDCT-229 | 30802 | [QA] Create Test Case Club Binding Event | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:14 AM | 02/Oct/25 11:12 AM | [5 empty] | มาจาก Sprint 7 | To Do |  | [Dev][CT] Sprint 7 | [Dev][CT] Sprint 8
Sub-task | DEVRDCT-228 | 30800 | [QA] Create Test Case |  |  | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 09/Sep/25 11:14 AM | 09/Sep/25 11:14 AM | [5 empty] | มาจาก Sprint 7 | To Do |  | [Dev][CT] Sprint 7 | [Dev][CT] Sprint 8
Sub-task | DEVRDCT-227 | 30798 | [QA] Create Test Case |  |  | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 09/Sep/25 11:14 AM | 09/Sep/25 11:14 AM | [5 empty] | มาจาก Sprint 7 | To Do |  | [Dev][CT] Sprint 7 | [Dev][CT] Sprint 8
Story | RDTHANA-113 | 30734 | [Dev][RD][BOF][Service] Change service status | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 07/Sep/25 3:21 PM | 02/Oct/25 11:54 PM | 19/Sep/25 12:00 AM | 5 |  |  | 0 | มาจาก Sprint 7 | Ready to Staging | 57600 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Story | DEVRDADJ-35 | 30728 | [DEV][RD][LNF] Create migration for maid | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 06/Sep/25 4:01 PM | 16/Sep/25 10:05 AM |  | 1 |  |  |  | มาจาก Sprint 7 | To Do |  | [Dev][RDAdjust] Sprint 8
Story | RDTHANA-107 | 30691 | [Dev][RD][APH] Cronjob update survey to expired | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 04/Sep/25 4:56 PM | 03/Oct/25 10:24 AM | 26/Sep/25 12:00 AM | 3 | rr-aphrodite |  | 21600 |  |  |  | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-106 | 30689 | [Dev][RD][Service][CMS API] Create service filter api | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 04/Sep/25 4:08 PM | 06/Oct/25 9:46 AM | 11/Sep/25 12:00 AM | 3 | cms-api | No-QA | 0 | มาจาก Sprint 7 | Ready to Staging | 18000 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-105 | 30687 | [Dev][RD][APH][CT] CleverTap Event | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | In Progress |  | 04/Sep/25 3:56 PM | 03/Oct/25 10:00 AM |  | 5 |  |  | 57600 |  |  |  | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-103 | 30679 | [QA] Test Execution Get club by id | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 04/Sep/25 1:48 PM | 06/Oct/25 10:26 AM | [5 empty] | มาจาก Sprint 7 | In Progress |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-102 | 30677 | [QA] Test Execution get club | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 04/Sep/25 1:47 PM | 06/Oct/25 10:26 AM | [5 empty] | มาจาก Sprint 7 | In Progress |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-101 | 30675 | [QA] Test Execution bind user to partner club | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 04/Sep/25 1:46 PM | 12/Sep/25 1:11 PM | [5 empty] | มาจาก Sprint 7 | In Progress |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-100 | 30673 | [QA] Test Execution check user eligiblility for partner club binding | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 04/Sep/25 1:45 PM | 12/Sep/25 1:11 PM | [5 empty] | มาจาก Sprint 7 | In Progress |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Story | DEVRDECOM-74 | 30662 | [DEV][RD][Eco][User Manual] Create user manual for recheck and Update Theme Code After Shopify Theme Update | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 04/Sep/25 1:18 PM | 07/Oct/25 8:42 AM |  | 3 | No-QA |  | 14400 | มาจาก Sprint 7 | In Progress | 28800 -> 14400 | [Dev][RD][Ecom] Sprint 7 | [Dev][RD][Ecom] Sprint 8
Story | DEVRDECOM-73 | 30661 | [DEV][RD][Eco][RR-Ecommerce-Shopify] Create Webhook API Endpoint orders | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready to Staging |  | 04/Sep/25 1:17 PM | 06/Oct/25 10:42 AM | 25/Sep/25 12:00 AM | 5 | ecommerce-shopify-api | No-QA | 57600 |  |  | No original est | [Dev][RD][Ecom] Sprint 8 | [Dev][RD][Ecom] Sprint 9
Story | DEVRDECOM-72 | 30660 | [DEV][RD][Eco][POC] Adjust Shopify Theme Atelier | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 04/Sep/25 1:16 PM | 07/Oct/25 8:42 AM |  | 5 | No-QA |  | 14400 | มาจาก Sprint 7 | In Progress | 28800 -> 14400 | [Dev][RD][Ecom] Sprint 7 | [Dev][RD][Ecom] Sprint 8
Story | DEVRDCT-225 | 30654 | [DEV][RD][HR] Implement Club Binding Event | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 04/Sep/25 9:14 AM | 02/Oct/25 11:12 AM |  | 5 | hr-solution |  | 57600 | มาจาก Sprint 7 | To Do |  | [Dev][CT] Sprint 7 | [Dev][CT] Sprint 8
Bug | DEVRDCT-224 | 30653 | [DEV][RD][RDS] FIX REDEEM EVENT - INTERNAL NAME value now use EN Name as value | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Resolved |  | 04/Sep/25 8:46 AM | 22/Sep/25 3:40 PM | 10/Sep/25 12:00 AM | 1 | redemption-api |  |  | มาจาก Sprint 7 | Resolved |  | [Dev][CT] Sprint 7 | [Dev][CT] Sprint 8
Story | DEVRDCT-223 | 30652 | [DEV][RD][RDS] ENH Add "Offer ID" to "REDEEM" EVENT | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready to Staging |  | 04/Sep/25 7:48 AM | 22/Sep/25 3:40 PM | 10/Sep/25 12:00 AM | 1 | redemption-api |  | 0 | มาจาก Sprint 7 | Ready to Staging | 3600 | [Dev][CT] Sprint 7 | [Dev][CT] Sprint 8
Story | DEVRDCT-222 | 30651 | [DEV][RD][RDS] ENH Add "Offer ID" to "MEMBER COUPON" EVENT | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready to Staging |  | 04/Sep/25 6:58 AM | 22/Sep/25 3:40 PM | 10/Sep/25 12:00 AM | 2 | redemption-api |  | 0 | มาจาก Sprint 7 | Ready to Staging | 7200 | [Dev][CT] Sprint 7 | [Dev][CT] Sprint 8
Story | RDAPS-175 | 30649 | [DEV][RD][SSO Handover] GCP SSO SSL management & Domain | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | To Do |  | 03/Sep/25 5:04 PM | 02/Oct/25 9:45 AM | 18/Sep/25 12:00 AM | 1 | No-QA |  |  | มาจาก Sprint 7 | To Do |  | [Dev][All project]Sprint 7 | [Dev][All Project] Sprint 8
Story | RDAPS-174 | 30648 | [DEV][RD][SSO Handover] GCP GKE Pipeline Deployment | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | To Do |  | 03/Sep/25 5:03 PM | 06/Oct/25 9:45 AM | 10/Oct/25 12:00 AM | 3 | No-QA |  |  | มาจาก Sprint 7 | To Do |  | [Dev][All project]Sprint 7 | [Dev][All Project] Sprint 8
Story | RDAPS-173 | 30647 | [DEV][RD][SSO Handover] Overiew GKE All Cluster | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | To Do |  | 03/Sep/25 5:00 PM | 06/Oct/25 9:40 AM | 17/Oct/25 12:00 AM | 1 | No-QA |  |  | มาจาก Sprint 7 | To Do |  | [Dev][All project]Sprint 7 | [Dev][All Project] Sprint 8
Story | RDAPS-172 | 30646 | [DEV][RD][SSO Handover] GCP Solution Architecture | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 03/Sep/25 4:59 PM | 06/Oct/25 9:40 AM | 17/Oct/25 12:00 AM | 3 | No-QA |  |  | มาจาก Sprint 7 | To Do |  | [Dev][All project]Sprint 7 | [Dev][All Project] Sprint 8
Story | RDTHANA-97 | 30645 | [Dev][RD][BOF][Service] Edit page step 2. | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 03/Sep/25 4:58 PM | 03/Oct/25 10:27 AM | 17/Sep/25 12:00 AM | 8 |  |  | 0 | มาจาก Sprint 7 | Ready to Staging | 86400 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-96 | 30642 | [Dev][RD][BOF][Service] Edit page step 1. | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 03/Sep/25 4:54 PM | 26/Sep/25 9:57 AM | 19/Sep/25 12:00 AM | 5 |  |  |  | มาจาก Sprint 7 | In Review |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-95 | 30641 | [Dev][RD][BOF][Service] Create page step 1 | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 03/Sep/25 4:52 PM | 26/Sep/25 9:56 AM | 12/Sep/25 12:00 AM | 8 |  |  | 0 | มาจาก Sprint 7 | Ready to Staging |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-94 | 30639 | [Dev][RD][BOF][Service] create service index page | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 03/Sep/25 4:19 PM | 03/Oct/25 10:25 AM | 12/Sep/25 12:00 AM | 8 |  |  | 0 | มาจาก Sprint 7 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Epic | DEVRDADJ-34 | 30635 | MAID registration |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 03/Sep/25 4:08 PM | 03/Sep/25 4:09 PM | [5 empty] | มาจาก Sprint 7 | To Do |  | [Dev][RDAdjust] Sprint 8
Story | DEVRDADJ-33 | 30634 | [DEV][RD][Notification API] Create new endpoint to get maid with sso_id/trader_id |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 03/Sep/25 4:05 PM | 09/Sep/25 11:01 AM |  | 3 |  |  |  | มาจาก Sprint 7 | To Do |  | [Dev][RDAdjust] Sprint 8
Story | DEVRDADJ-32 | 30633 | [DEV][RD][Notification API] Enhance API for bypass maid from RR application |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 03/Sep/25 4:02 PM | 09/Sep/25 11:01 AM |  | 5 |  |  |  | มาจาก Sprint 7 | To Do |  | [Dev][RDAdjust] Sprint 8
Story | RDTHANA-90 | 30622 | [Dev][RD][Section][BOF][QA] Enhance Section Feature: Add new widget types | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Sep/25 9:16 PM | 22/Sep/25 5:12 PM |  | 0 |  |  |  | มาจาก Sprint 7 | Ready To Test |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-89 | 30621 | [Dev][RD][Section][BOF] Enhance Section Feature: Add 'Club - Benefits & Info' Location | Art_narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Sep/25 8:56 PM | 22/Sep/25 5:12 PM |  | 5 | rr-backoffice |  |  | มาจาก Sprint 7 | Ready To Test |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-88 | 30620 | [Dev][RD][Widget][BOF] Enhance Widget Feature: Add 'Service' Type | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Sep/25 8:56 PM | 22/Sep/25 5:12 PM | 11/Sep/25 12:00 AM | 5 | rr-backoffice |  | 0 | มาจาก Sprint 7 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-87 | 30619 | [Dev][RD][Widget][BOF] Enhance Widget Feature: Add 'Club – Benefits & Information' Type | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Sep/25 8:56 PM | 22/Sep/25 5:12 PM | 10/Sep/25 12:00 AM | 5 | rr-backoffice |  | 0 | มาจาก Sprint 7 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-86 | 30618 | [Dev][RD][BOF] Update survey Step 5: Survey Appearance (Thank You) (FE&BE) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Sep/25 8:44 PM | 22/Sep/25 5:12 PM | 15/Sep/25 12:00 AM | 2 | rr-backoffice |  | 0 | มาจาก Sprint 7 | Ready To Test | 10800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-81 | 30606 | [Dev][RD][BOF] Change survey status (FE&BE) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Sep/25 3:26 PM | 23/Sep/25 3:26 PM | 16/Sep/25 12:00 AM | 3 | rr-backoffice |  | 0 | มาจาก Sprint 7 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-80 | 30604 | [Dev][RD][BOF] Update survey Step 5: Survey Appearance (Input E-mail) (FE&BE) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Sep/25 3:25 PM | 22/Sep/25 5:12 PM | 15/Sep/25 12:00 AM | 2 | rr-backoffice |  | 0 | มาจาก Sprint 7 | Ready To Test | 10800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-79 | 30602 | [Dev][RD][BOF] Update survey step5.2(FE&BE) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Sep/25 3:24 PM | 22/Sep/25 5:12 PM | 12/Sep/25 12:00 AM | 2 | rr-backoffice |  |  | มาจาก Sprint 7 | Ready To Test | 10800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-78 | 30600 | Create Test Case Get club by id | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 02/Sep/25 3:04 PM | 04/Sep/25 1:44 PM | [5 empty] | มาจาก Sprint 7 | Done |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Bug | DEVRDSUP-109 | 30515 | [SUP-146][ETL] DA have frequently not received the files for Redemption Vouchers IDD around 24/25th each moth - Cause issue that RR send missing information to BTSG MIX Data Team. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Duplicated |  | 29/Aug/25 3:24 PM | 03/Oct/25 9:34 AM | 12/Sep/25 12:00 AM | [7 empty] | [Dev][All Project] Sprint 8
Story | RDTHANA-76 | 30398 | [DEV][RD][BFF] Get club by id | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 27/Aug/25 4:56 PM | 23/Sep/25 2:50 PM |  | 2 |  |  |  | มาจาก Sprint 7 | Ready To Test |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-75 | 30396 | [DEV][RD][EXS] Get club by id | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 27/Aug/25 4:56 PM | 06/Oct/25 10:26 AM |  | 2 | exclusive-store-api | No-QA | 0 | มาจาก Sprint 7 | Ready To Test | 21600 | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-74 | 30366 | [Dev][RD][BOF] Update survey step4.2(FE&BE) | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:15 PM | 22/Sep/25 5:12 PM |  | 2 | rr-backoffice |  | 0 | มาจาก Sprint 7 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-73 | 30364 | [Dev][RD][BOF] Download Individual Survey Report (FE&BE) | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:15 PM | 22/Sep/25 5:12 PM | 18/Sep/25 12:00 AM | 5 | rr-backoffice |  | 0 | มาจาก Sprint 7 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-72 | 30362 | [Dev][RD][BOF] Update survey step5.1(FE&BE) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:15 PM | 22/Sep/25 5:12 PM | 12/Sep/25 12:00 AM | 3 | rr-backoffice |  | 0 | มาจาก Sprint 7 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-71 | 30360 | [Dev][RD][BOF] Update survey step4.1(FE&BE) | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:15 PM | 22/Sep/25 5:12 PM |  | 8 | rr-backoffice |  | 0 | มาจาก Sprint 7 | Ready To Test | 86400 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-70 | 30358 | [Dev][RD][BOF] Update survey step3(FE&BE) | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:14 PM | 22/Sep/25 5:12 PM |  | 5 | rr-backoffice |  | 0 | มาจาก Sprint 7 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-69 | 30356 | [Dev][RD][BOF] Update survey step2(FE&BE) | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:09 PM | 22/Sep/25 5:12 PM | 16/Sep/25 12:00 AM | 3 | rr-backoffice |  | 0 | มาจาก Sprint 7 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-68 | 30354 | [Dev][RD][BOF] View Survey Report (FE&BE) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:09 PM | 22/Sep/25 5:12 PM | 17/Sep/25 12:00 AM | 3 | rr-backoffice |  | 0 | มาจาก Sprint 7 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-67 | 30352 | [Dev][RD][BOF] View Survey List (FE&BE) | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:09 PM | 22/Sep/25 5:12 PM |  | 5 | rr-backoffice |  | 0 | มาจาก Sprint 7 | Ready To Test | 86400 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-66 | 30350 | [Dev][RD][BOF] Update survey step1(FE&BE) | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:09 PM | 22/Sep/25 5:12 PM | 15/Sep/25 12:00 AM | 3 | rr-backoffice |  | 0 | มาจาก Sprint 7 | Ready To Test | 28800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-65 | 30348 | [Dev][RD][BOF] Create survey (FE&BE) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:08 PM | 22/Sep/25 5:12 PM | 11/Sep/25 12:00 AM | 5 | rr-backoffice |  | 0 | มาจาก Sprint 7 | Ready To Test | 43200 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-63 | 30306 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 26/Aug/25 2:15 PM | 02/Oct/25 2:22 PM | [5 empty] | มาจาก Sprint 7 | Done |  | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-59 | 30293 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 26/Aug/25 2:14 PM | 12/Sep/25 1:08 PM | [5 empty] | มาจาก Sprint 7 | Done |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-58 | 30291 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 26/Aug/25 2:14 PM | 12/Sep/25 1:08 PM | [5 empty] | มาจาก Sprint 7 | Done |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-57 | 30289 | [QA] Create Test Case get club list and config api | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 26/Aug/25 2:13 PM | 04/Sep/25 1:41 PM | [5 empty] | มาจาก Sprint 7 | Done |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-56 | 30287 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 26/Aug/25 2:13 PM | 12/Sep/25 1:08 PM | [5 empty] | มาจาก Sprint 7 | Done |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-55 | 30285 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 26/Aug/25 2:13 PM | 12/Sep/25 1:08 PM | [5 empty] | มาจาก Sprint 7 | Done |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-54 | 30283 | [QA] Create Test Case bind user to partner club | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 26/Aug/25 2:12 PM | 03/Sep/25 2:27 PM | [5 empty] | มาจาก Sprint 7 | Done |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-53 | 30281 | [QA] Create Test Case check user eligiblility for partner club binding | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 26/Aug/25 2:12 PM | 03/Sep/25 1:48 PM | [5 empty] | มาจาก Sprint 7 | Done |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-52 | 30275 | [QA] Create Test Case Pop up Tan in Welcom Message Menu | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 26/Aug/25 2:12 PM | 15/Sep/25 10:42 AM | [5 empty] | มาจาก Sprint 7 | Done |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-51 | 30273 | [QA] Create Test Case Advanced Setting Tab | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 26/Aug/25 2:12 PM | 11/Sep/25 9:19 PM | [5 empty] | มาจาก Sprint 7 | Done |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-50 | 30271 | [QA] Create Test Case create temp deep link endpoint | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 26/Aug/25 2:11 PM | 11/Sep/25 10:10 AM | [5 empty] | มาจาก Sprint 7 | Done |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Sub-task | RDTHANA-49 | 30269 | [QA] Create Test Case Add new input "default bu" | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 26/Aug/25 2:10 PM | 11/Sep/25 10:10 AM | [5 empty] | มาจาก Sprint 7 | Done |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Bug | DEVRDSUP-102 | 30261 | [SUP-150][SUB] a SUB coupon doesn't have any detain in coupon TXN detail screen and coupon can't back to redeem. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Closed |  | 25/Aug/25 8:23 PM | 26/Sep/25 3:29 PM | 26/Aug/25 12:00 AM |  | sub | [5 empty] | [Dev][All Project] Sprint 8
Story | RDTHANA-48 | 30203 | [DEV][RD][DasHaus][BFF] Enhance get club config endpoint | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 25/Aug/25 12:57 AM | 23/Sep/25 1:19 PM |  | 2 |  |  |  | มาจาก Sprint 7 | Ready To Test |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-46 | 30133 | [DEV][RD][DasHaus][HRS] Add "Added Member Channel column & search | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | High | Done |  | 22/Aug/25 4:08 PM | 02/Oct/25 2:21 PM |  | 5 | hr-solution |  | 0 | มาจาก Sprint 7 | Ready To Test | 57600 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-43 | 30086 | [DEV][RD][DasHaus][BFF] Verify the API to validate matching account | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | Done |  | 22/Aug/25 6:12 AM | 03/Oct/25 9:28 AM |  | 1 |  |  |  | มาจาก Sprint 7 | To Do |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-42 | 30085 | [DEV][RD][RR Link Notify] Generate static deeplink | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 21/Aug/25 11:47 PM | 03/Oct/25 10:00 AM |  | 1 | No-QA |  | 3600 | มาจาก Sprint 7 | In Progress | 7200 -> 3600 | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-41 | 30084 | [DEV][RD][DasHaus][BFF] Enhance get club list endpoint | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Done |  | 21/Aug/25 11:42 PM | 23/Sep/25 1:22 PM |  | 2 |  |  | 0 | มาจาก Sprint 7 | Ready To Test | 7200 | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-40 | 30083 | [DEV][RD][DasHaus][Exclusive Store API] Enhance get club list and config api | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Done |  | 21/Aug/25 11:41 PM | 06/Oct/25 10:26 AM |  | 2 | exclusive-store-api |  | 0 | มาจาก Sprint 7 | Ready To Test | 10800 | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-39 | 30082 | [DEV][RD][HR-Solution][Club setting] Add new input "default bu" | Art_narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Highest | Done |  | 21/Aug/25 11:26 PM | 02/Oct/25 2:16 PM |  | 5 | hr-solution |  |  | มาจาก Sprint 7 | Ready To Test |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-38 | 30081 | [DEV][RD][RR Link Notify] Enhance create temp deep link endpoint | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Highest | Done |  | 21/Aug/25 11:12 PM | 02/Oct/25 12:00 PM | 29/Aug/25 12:00 AM | 3 | link-notify |  | 0 | มาจาก Sprint 7 | Ready To Test | 28800 | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-37 | 30080 | [DEV][RD][HR-Solution][BU] Enhance BU welcome message support popup | Art_narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Highest | Done |  | 21/Aug/25 11:02 PM | 02/Oct/25 11:49 AM | 12/Sep/25 12:00 AM | 5 |  |  |  | มาจาก Sprint 7 | Ready To Test |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-35 | 30078 | [DEV][RD][HR][BU] Enhance Advance setting tap | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Highest | Done |  | 21/Aug/25 10:59 PM | 02/Oct/25 11:49 AM | 03/Sep/25 12:00 AM | 8 |  |  | 0 | มาจาก Sprint 7 | Ready To Test | 86400 | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-29 | 30011 | [DEV][RD][DasHaus][EXS] Implement the API to bind user to partner club | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Highest | Done |  | 21/Aug/25 1:10 PM | 01/Oct/25 9:55 AM | 03/Sep/25 12:00 AM | 8 |  |  | 0 | มาจาก Sprint 7 | Ready To Test | 86400 | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-26 | 29997 | [DEV][RD][DasHaus][BFF] Implement the API to bind user to partner club | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Done |  | 20/Aug/25 4:36 PM | 24/Sep/25 4:36 PM |  | 2 |  |  | 0 | มาจาก Sprint 7 | Ready To Test | 28800 | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-25 | 29996 | [DEV][RD][DasHaus][BFF] Implement the API to check user eligiblility for partner club binding | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Done |  | 20/Aug/25 4:36 PM | 23/Sep/25 1:26 PM |  | 3 | BFF |  | 0 | มาจาก Sprint 7 | Ready To Test | 36000 | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-24 | 29995 | [DEV][RD][DasHaus][EXS] Implement the API to check user eligiblility for partner club binding | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Highest | Done |  | 20/Aug/25 4:36 PM | 01/Oct/25 9:55 AM | 29/Aug/25 12:00 AM | 5 | exclusive-store-api |  | 0 | มาจาก Sprint 7 | Ready To Test | 57600 | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Story | DEVRDCT-202 | 29973 | [Dev][RD][CID] Initial feed Rabbit Wallet Card to CleverTap | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | High | Done |  | 20/Aug/25 11:22 AM | 03/Oct/25 9:30 AM | 01/Sep/25 12:00 AM | 3 | No-QA | rr-cloudid-api |  | มาจาก Sprint 7 | Ready to Staging | 144000 | [Dev][Thana City] sprint 6 | [Dev][CT] Sprint 6 | [Dev][CT] Sprint 7 | [Dev][CT] Sprint 8
Story | RDTHANA-20 | 29950 | [Dev][RD][APH] Enhance check token | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 19/Aug/25 7:46 PM | 03/Oct/25 10:12 AM |  | 3 |  |  | 0 | มาจาก Sprint 7 | In Review | 28800 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-19 | 29948 | [Dev][RD][Section][BOF] Enhance Section Index Page | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 19/Aug/25 7:45 PM | 26/Sep/25 3:14 PM |  | 2 |  |  | 7200 |  |  |  | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-16 | 29942 | [Dev][RD][Section][BFF] Enhance Sections API | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 19/Aug/25 7:44 PM | 01/Oct/25 9:20 AM |  | 5 | BFF |  | 57600 |  |  |  | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-15 | 29940 | [Dev][RD][Widget][CMS API] Enhance Widget API | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 19/Aug/25 7:41 PM | 06/Oct/25 9:46 AM |  | 2 | cms-api |  | 0 | มาจาก Sprint 7 | Ready to Staging | 3600 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Story | RDTHANA-14 | 29938 | [Dev][RD][Section][CMS API] Enhance Sections API | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 19/Aug/25 7:37 PM | 06/Oct/25 9:46 AM |  | 2 | cms-api |  | 0 | มาจาก Sprint 7 | Ready to Staging | 14400 | [Dev][RD][Thana] Sprint 7 | [Dev][RD][Thana] Sprint 8
Bug | DEVRDSUP-93 | 29890 | [SUP-132][APP] Reward search result doesn't show out of stock on search result and category filter. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | UNDER VALIDATION |  | 19/Aug/25 11:33 AM | 03/Oct/25 4:11 PM | 02/Sep/25 12:00 AM |  | rewards-api | [5 empty] | [Dev][All Project] Sprint 8
Story | DEVRDCT-177 | 29558 | [DEV][RD][HR-Solution] Initial feed user properties Club Binding with tier | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 11/Aug/25 9:53 AM | 02/Oct/25 11:10 AM |  | 3 |  |  | 0 | มาจาก Sprint 7 | Ready To Test | 28800 | [Dev][Thana City] sprint 6 | [Dev][CT] Sprint 5 | [Dev][CT] Sprint 6 | [Dev][CT] Sprint 7 | [Dev][CT] Sprint 8
Task | RDAPS-141 | 29339 | [Dev][RD][POC][SMS sub-account to support new sender IDs] | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Progress |  | 05/Aug/25 5:01 PM | 26/Sep/25 9:38 AM |  | 5 |  |  |  | มาจาก Sprint 7 | In Progress |  | [Dev][All project]Sprint 4 | [Dev][All project]Sprint 5 | [Dev][All project]Sprint 6 | [Dev][All project]Sprint 7 | [Dev][All Project] Sprint 8
Story | DEVRDECOM-25 | 28845 | [DEV][RD][Eco][Ecommerce-Shopify] Enhance API Endpoint for Order Cancelled Webhook | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready to Staging |  | 29/Jul/25 12:49 PM | 06/Oct/25 10:42 AM | 01/Oct/25 12:00 AM | 5 | ecommerce-shopify-api |  | 72000 |  |  |  | [Dev][RD][Ecom] Sprint 8 | [Dev][RD][Ecom] Sprint 9
Story | DEVRDECOM-24 | 28843 | [DEV][RD][Eco][RR-Ecommerce-Shopify] Create Scheduled Job for Point Issuance | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready to Staging |  | 29/Jul/25 11:07 AM | 06/Oct/25 10:42 AM | 02/Oct/25 12:00 AM | 5 | ecommerce-shopify-api |  | 57600 |  |  | No original est | [Dev][RD][Ecom] Sprint 8 | [Dev][RD][Ecom] Sprint 9
Story | RDTHANA-248 | 28841 | [DEV][RD][Eco][RR-Ecommerce-Shopify][Das Haus] Enhance email verify callback with return_url | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 29/Jul/25 9:57 AM | 07/Oct/25 8:43 AM |  | 2 | ecommerce-shopify-api |  | 7200 |  |  |  | [Dev][RD][Thana] Sprint 8
Bug | DEVRDSUP-48 | 28518 | [SUP-77][SUB] Some TXN's receipts number are getting skipped. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Duplicated |  | 18/Jul/25 5:32 PM | 03/Oct/25 4:19 PM | 22/Jul/25 12:00 AM | 8 | [6 empty] | [Dev][All Project] Sprint 8
Story | DEVRDECOM-25 | 28845 | [DEV][RD][Eco][Ecommerce-Shopify] Enhance API Endpoint for Order Cancelled Webhook | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready to Staging |  | 29/Jul/25 12:49 PM | 06/Oct/25 10:42 AM | 01/Oct/25 12:00 AM | 5 | ecommerce-shopify-api |  | 72000 |  |  |  | [Dev][RD][Ecom] Sprint 8 | [Dev][RD][Ecom] Sprint 9
Story | DEVRDECOM-24 | 28843 | [DEV][RD][Eco][RR-Ecommerce-Shopify] Create Scheduled Job for Point Issuance | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready to Staging |  | 29/Jul/25 11:07 AM | 06/Oct/25 10:42 AM | 02/Oct/25 12:00 AM | 5 | ecommerce-shopify-api |  | 57600 |  |  | No original est | [Dev][RD][Ecom] Sprint 8 | [Dev][RD][Ecom] Sprint 9
Story | RDTHANA-248 | 28841 | [DEV][RD][Eco][RR-Ecommerce-Shopify][Das Haus] Enhance email verify callback with return_url | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 29/Jul/25 9:57 AM | 07/Oct/25 8:43 AM |  | 2 | ecommerce-shopify-api |  | 7200 |  |  |  | [Dev][RD][Thana] Sprint 8
Bug | DEVRDSUP-48 | 28518 | [SUP-77][SUB] Some TXN's receipts number are getting skipped. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Duplicated |  | 18/Jul/25 5:32 PM | 03/Oct/25 4:19 PM | 22/Jul/25 12:00 AM | 8 | [6 empty] | [Dev][All Project] Sprint 8

## Summarize Sprint 7
Column 1 | Total Stories Point | Total Manhour | Point Done | Manhour Done | Note
8 Sep - 19 Sep
Dev Resource Available | 19 | 559
Meeting Planned |  | 199.5 |  |  | Ref
Additional Meeting |  | 52 |  |  | Ref
Deployment |  | 6 |  |  | 3 ครั้ง 1. 2 คน 2. 2 คน 3. 2 คน
Development Sprint Total | 367 | 510.33 | 125 | 167.33
Ad-hoc Mid Sprint | 6 | 17.17 | 6 | 17.17 | 2 tasks
Requirement changes after refinement? | 6 | 0 | 6 | 0 | 2 tasks
Aek | 46 | 30.33 | 38 | 30.33
A | 38 | 40 | 20 | 16
Aom | 33 | 85 | 22 | 85
Zan | 28 | 26 | 10 | 26
Mai | 41 | 64 | 8 | 0
Mac | 39 | 45 | 6 | 0
Mos | 41 | 61 | 8 | 0
Jack | 35 | 37 | 8 | 0
Art | 15 | 48 | 0 | 0
Kae | 15 | 18 | 2 | 2
Nim | 19 | 56 | 3 | 8
| System Architech |  |  |  | Permanent Dev. |  |  | Outsources
Projects (Stories Points) | Aek | Zan | Aom | Jack | A | Art | Mai | Kae | Mac | Nim | Mos
Das Haus - Thana City & Das Haus | 0 | 13 | 13 | 18 | 8 | 15 | 32 | 13 | 33 | 19 | 29
E-commerce 1.1. E-Commerce x Shopify Plus 1.2. Shopify:Snackmaker 1.3. Shopify: Turtle Delivery 1.4. Shopify: Turtle Delivery | 36 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 3
CleverTap - MKT Automation Tool | 6 | 3 | 3 | 14 | 1 | 0 | 0 | 2 | 3 | 2 | 2
Adjust Integration | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Adhoc - Non-Epics - Turtle Display club tier on POS - Data Mart Migration | 1 | 5 | 15 | 0 | 18 | 0 | 1 | 2 | 1 | 0 | 7
Support Incidents | 3 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| System Architech |  |  |  | Permanent Dev. |  |  | Outsources
Projects (Manhour) | Aek | Zan | Aom | Jack | A | Art | Mai | Kae | Mac | Nim | Mos
Das Haus - Thana City & Das Haus | 0 | 26 | 24 | 34 | 24 | 48 | 64 | 16 | 45 | 56 | 61
E-commerce 1.1. E-Commerce x Shopify Plus 1.2. Shopify:Snackmaker 1.3. Shopify: Turtle Delivery 1.4. Shopify: Turtle Delivery | 24 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0
CleverTap - MKT Automation Tool | 5 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Adjust Integration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Adhoc - Non-Epics - Turtle Display club tier on POS - Data Mart Migration | 0.17 | 0 | 60 | 0 | 6 | 0 | 0 | 2 | 0 | 0 | 0
Support Incidents | 1.17 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 7
Issue Type | Issue key | Issue id | Summary | Assignee | Assignee Id | Reporter | Reporter Id | Priority | Status | Resolution | Created | Updated | Due date | Custom field (Story Points) | Labels | Labels | Labels | Original estimate | Sprint Movement | Sprint 6 | Note | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint
Bug | RDTHANA-235 | 31389 | [S4][HRS][Member] Field "Added Member Channel" not type drop down and UI does not match the request | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | UNDER VALIDATION |  | 19/Sep/25 3:08 PM | 19/Sep/25 11:32 PM | [9 empty] | [Dev][RD][Thana] Sprint 7
Story | RDTHANA-228 | 31331 | [Dev][RD][SA] Analyze story for sprint 8 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 18/Sep/25 4:22 PM | 18/Sep/25 4:23 PM |  | 5 | [7 empty] | [Dev][RD][Thana] Sprint 7
Story | RDAPS-189 | 31317 | [Dev][RD][POC] Enhancement on refund button to cross check payment status before sending refund request | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 18/Sep/25 2:25 PM | 18/Sep/25 2:29 PM |  | 3 | mid-sprint |  |  | 57600 |  |  |  | [Dev][All project]Sprint 7
Story | DEVRDADJ-44 | 31314 | [DEV][RD][BOF] Enhance RR Backoffice to integrate with ADJUST Deeplink Generated api |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 18/Sep/25 1:53 PM | 18/Sep/25 2:17 PM |  | 5 | [7 empty] | [Dev][RDAdjust] Sprint 8
Story | DEVRDADJ-43 | 31313 | [DEV][RD][LNF] create script to remove "adj_redirect" in existing deeplink |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 18/Sep/25 1:50 PM | 18/Sep/25 1:54 PM |  | 2 | [7 empty] | [Dev][RDAdjust] Sprint 8
Story | DEVRDADJ-41 | 31311 | [DEV][RD][LNF] Enhance auto generate deeplink, remove redirect url in request |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 18/Sep/25 1:45 PM | 18/Sep/25 2:17 PM |  | 2 | [7 empty] | [Dev][RDAdjust] Sprint 8
Sub-task | RDTHANA-222 | 31299 | [QA] Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 17/Sep/25 4:37 PM | 17/Sep/25 4:37 PM | [9 empty] | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-221 | 31297 | [QA] Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 17/Sep/25 4:37 PM | 17/Sep/25 4:37 PM | [9 empty] | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-220 | 31295 | [QA] Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 17/Sep/25 4:37 PM | 19/Sep/25 1:06 PM | [9 empty] | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-219 | 31293 | [QA] Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 17/Sep/25 4:37 PM | 17/Sep/25 4:37 PM | [9 empty] | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-218 | 31291 | [QA] Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 17/Sep/25 4:36 PM | 17/Sep/25 4:36 PM | [9 empty] | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Sub-task | RDAPS-188 | 31288 | [QA] Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 17/Sep/25 3:46 PM | 17/Sep/25 4:00 PM | [9 empty] | [Dev][All project]Sprint 6 | [Dev][All project]Sprint 7
Bug | RDTHANA-217 | 31277 | [S4][Welcome message] Tab Welcome message display when setting condition Welcome message is inactive | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Open |  | 17/Sep/25 3:13 PM | 17/Sep/25 3:14 PM | [9 empty] | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-216 | 31271 | [QA] Test execution Pop up tab in Welcome message | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | In Progress |  | 17/Sep/25 1:38 PM | 17/Sep/25 1:38 PM | [9 empty] | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-215 | 31269 | [QA] Test execution Advance Setting Tab | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | In Progress |  | 17/Sep/25 1:38 PM | 17/Sep/25 1:38 PM | [9 empty] | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Story | DEVRDSUP-135 | 31261 | [SUP-185][REM] Request to export user redeem TXN with error time out from DA. 17/09/2025 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Done |  | 17/Sep/25 12:08 PM | 22/Sep/25 9:18 AM | 17/Sep/25 12:00 AM | 1 | mid-sprint | turtle |  | 1800 |  |  |  | [Dev][All project]Sprint 7
Sub-task | DEVRDCT-236 | 31254 | [QA] Test execution register new user get MSG-email and MSG-sms status's true | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 16/Sep/25 11:41 PM | 16/Sep/25 11:43 PM | [9 empty] | [Dev][Thana City] sprint 6 | [Dev][CT] Sprint 5 | [Dev][CT] Sprint 6 | [Dev][CT] Sprint 7
Sub-task | DEVRDCT-235 | 31252 | [QA] Test execution consent , MSG-email and MSG-sms | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 16/Sep/25 11:00 PM | 17/Sep/25 2:46 PM | [9 empty] | [Dev][Thana City] sprint 6 | [Dev][CT] Sprint 5 | [Dev][CT] Sprint 6 | [Dev][CT] Sprint 7
Sub-task | RDAPS-186 | 31228 | [QA] Test Execution |  |  | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 16/Sep/25 12:58 PM | 17/Sep/25 11:23 AM | [9 empty] | [Dev][All project]Sprint 5 | [Dev][All project]Sprint 6 | [Dev][All project]Sprint 7
Bug | BUEC-163 | 31224 | [S2][Shopify web] Email verification flow is not working properly | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 16/Sep/25 12:02 PM | 17/Sep/25 1:36 PM | [9 empty] | [Dev][RD][Ecom] Sprint 7
Bug | BUEC-162 | 31198 | [S3][Shopify web] Request verify email is not working properly | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 15/Sep/25 5:41 PM | 16/Sep/25 5:22 PM | [9 empty] | [Dev][RD][Ecom] Sprint 7
Bug | BUEC-161 | 31195 | [S3][Shopify web] Email address format validation is not working properly | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 15/Sep/25 5:16 PM | 16/Sep/25 5:00 PM | [9 empty] | [Dev][RD][Ecom] Sprint 7
Bug | BUEC-160 | 31169 | [S3][Shopify web] Input email page detail is incorrect | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 15/Sep/25 4:33 PM | 17/Sep/25 4:53 PM | [9 empty] | [Dev][RD][Ecom] Sprint 7
Sub-task | RDTHANA-178 | 31139 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | In Progress |  | 15/Sep/25 3:30 PM | 15/Sep/25 3:30 PM | [9 empty] | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-177 | 31137 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | In Progress |  | 15/Sep/25 3:30 PM | 15/Sep/25 3:30 PM | [9 empty] | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Story | DEVRDSUP-131 | 31134 | [SUP-183][SUB] Gather SSO list of wallet bound card on BSS but not bound in RR profile for BSS team to send binding request again. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Highest | Done |  | 15/Sep/25 2:56 PM | 15/Sep/25 3:28 PM | 15/Sep/25 12:00 AM | 1 | sub |  |  | 1800 |  |  |  | [Dev][All project]Sprint 7
Sub-task | RDTHANA-175 | 31131 | Run import on prod |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 15/Sep/25 2:42 PM | 15/Sep/25 2:42 PM | [9 empty] | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-174 | 31129 | Enhance import function |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 15/Sep/25 2:41 PM | 17/Sep/25 3:58 PM |  |  | No-QA | [6 empty] | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Bug | RDTHANA-173 | 31127 | [S3][HRS][Feature][Field] Default Business Unit for Opt-in Member Channel not required field | Art_narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Fixing |  | 15/Sep/25 2:22 PM | 17/Sep/25 9:11 AM | [9 empty] | [Dev][RD][Thana] Sprint 7
Bug | RDTHANA-172 | 31126 | [S4][HRS][Feature][Sort] BU list is not sorted alphabetically. | Art_narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Low | Fixing |  | 15/Sep/25 2:04 PM | 17/Sep/25 9:08 AM | [9 empty] | [Dev][RD][Thana] Sprint 7
Bug | RDTHANA-171 | 31125 | [S4][HRS][Feature][Default Business Unit] The display format is incorrect. | Art_narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Low | Fixing |  | 15/Sep/25 1:57 PM | 17/Sep/25 9:07 AM | [9 empty] | [Dev][RD][Thana] Sprint 7
Story | DEVRDSUP-130 | 31105 | [SUP-179][SUB] User paid but didn't receive the package, request dev to mark package status to "waiting for payment" | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Done |  | 15/Sep/25 12:01 PM | 18/Sep/25 2:58 PM | 15/Sep/25 12:00 AM | 1 | mid-sprint |  |  | 1800 |  |  |  | [Dev][All project]Sprint 7
Story | RDTHANA-159 | 31091 | [Dev][RD][SA] Clean test data in HR-Solution UAT | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 15/Sep/25 9:28 AM | 16/Sep/25 10:04 AM |  | 3 |  |  |  | 28800 |  |  | No Original Est | [Dev][RD][Thana] Sprint 7
Story | DEVRDSUP-127 | 31038 | [SUP-176]Request to create account for new team member. | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Low | Done |  | 12/Sep/25 2:06 PM | 22/Sep/25 9:18 AM | 16/Sep/25 12:00 AM | 1 | mid-sprint |  |  | 600 |  |  |  | [Dev][All project]Sprint 7
Sub-task | RDTHANA-158 | 31036 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 12/Sep/25 1:09 PM | 12/Sep/25 1:09 PM | [9 empty] | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Bug | RDTHANA-157 | 31032 | [S4][HRS][Business Unit][Filter Name] The filter column name and active column symbol is incorrect according to Figma. | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Low | Resolved |  | 12/Sep/25 11:19 AM | 16/Sep/25 10:05 AM | [9 empty] | [Dev][RD][Thana] Sprint 7
Epic | RDAPS-185 | 31029 | [DEV][RD][HRS][SA] Remove unused data | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 12/Sep/25 10:13 AM | 12/Sep/25 10:16 AM |  | 5 | [7 empty] | [Dev][All project]Sprint 7
Sub-task | RDTHANA-156 | 31028 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 11/Sep/25 10:02 PM | 15/Sep/25 3:29 PM | [9 empty] | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-155 | 31026 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | In Progress |  | 11/Sep/25 10:00 PM | 15/Sep/25 3:31 PM | [9 empty] | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-154 | 31024 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | Done |  | 11/Sep/25 10:00 PM | 15/Sep/25 3:29 PM | [9 empty] | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-153 | 31022 | [QA] Test Execution | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | In Progress |  | 11/Sep/25 10:00 PM | 19/Sep/25 1:42 PM | [9 empty] | [Dev][RD][Thana] Sprint 7
Test Execution | RDTHANA-152 | 31020 | [TX][Thana city] Sprint7 | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | In Progress |  | 11/Sep/25 9:57 PM | 19/Sep/25 2:43 PM | [9 empty] | [Dev][RD][Thana] Sprint 7
Test Plan | RDTHANA-151 | 31019 | [TP][Thana city] Sprint7 |  |  | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | To Do |  | 11/Sep/25 9:56 PM | 11/Sep/25 9:56 PM | [9 empty] | [Dev][RD][Thana] Sprint 7
Test Set | RDTHANA-150 | 31018 | [TS][Thana city] Sprint7 |  |  | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | To Do |  | 11/Sep/25 9:56 PM | 11/Sep/25 9:56 PM | [9 empty] | [Dev][RD][Thana] Sprint 7
Sub-task | RDAPS-184 | 30995 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 11/Sep/25 1:46 PM | 11/Sep/25 3:29 PM | [9 empty] | [Dev][All project]Sprint 6 | [Dev][All project]Sprint 7
Bug | DEVRDCT-234 | 30957 | [S4][CleverTap][AutoPushCoupon]Failed to auto push event on CleverTap missing "MERCHANT_NAME" value | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Closed |  | 10/Sep/25 4:45 PM | 15/Sep/25 12:32 PM | 11/Sep/25 12:00 AM | [8 empty] | [Dev][CT] Sprint 7
Sub-task | DEVRDCT-233 | 30956 | [QA] Test execution Fail auto-push coupon | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 10/Sep/25 4:21 PM | 10/Sep/25 5:14 PM | [9 empty] | [Dev][Thana City] sprint 6 | [Dev][CT] Sprint 6 | [Dev][CT] Sprint 7
Story | DEVRDCT-232 | 30954 | [Dev][RD][APIs Gateway] Mapping webhook endpoint | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Done |  | 10/Sep/25 4:18 PM | 15/Sep/25 10:04 AM | 15/Sep/25 12:00 AM | 1 |  |  |  | 7200 |  |  |  | [Dev][CT] Sprint 7
Test Execution | DEVRDCT-231 | 30867 | [TX][RR-backoffice] Rewards setting - Auto push Sprint7 - UAT |  |  | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 10/Sep/25 11:27 AM | 12/Sep/25 3:51 PM | [9 empty] | [Dev][CT] Sprint 7
Test Plan | DEVRDCT-230 | 30866 | [TP][RR-backoffice] Rewards setting - Sprint7 |  |  | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 10/Sep/25 11:24 AM | 12/Sep/25 2:01 PM | [9 empty] | [Dev][CT] Sprint 7
Bug | RDAPS-181 | 30857 | [S2][Coupon] [S2][Coupon] Coupon details response is inncorrect | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 09/Sep/25 6:06 PM | 15/Sep/25 1:58 PM | [9 empty] | [Dev][All project]Sprint 7
Bug | DEVRDSUP-125 | 30854 | [SUP-173][HOP] Top merchant learderboard shows 0 txn when ETL failed to send to DA. | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Solution Proposal Pending |  | 09/Sep/25 4:33 PM | 12/Sep/25 2:36 PM | [9 empty] | [Dev][All project]Sprint 7
Epic | RDAPS-180 | 30852 | clever-tap-3 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 09/Sep/25 4:25 PM | 09/Sep/25 4:25 PM | [9 empty] | [Dev][CT] Sprint 7
Sub-task | RDTHANA-134 | 30844 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 09/Sep/25 11:30 AM | 09/Sep/25 11:30 AM | [9 empty] | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-133 | 30842 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 09/Sep/25 11:30 AM | 09/Sep/25 11:30 AM | [9 empty] | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-132 | 30840 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 09/Sep/25 11:30 AM | 09/Sep/25 11:30 AM | [9 empty] | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-131 | 30838 | [QA] |  |  | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 09/Sep/25 11:29 AM | 21/Sep/25 3:00 PM | [9 empty] | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-130 | 30836 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:29 AM | 21/Sep/25 3:00 PM | [9 empty] | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-129 | 30834 | [QA] Create Test Case Update survey Step 5: Survey Appearance (Input E-mail) (FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:29 AM | 21/Sep/25 3:01 PM | [9 empty] | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-128 | 30832 | [QA] Create Test Case [Dev][RD][BOF] Update survey step5.2(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:29 AM | 21/Sep/25 1:58 PM | [9 empty] | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-127 | 30830 | [QA] Create Test Case Update survey step5.1(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:28 AM | 21/Sep/25 1:55 PM | [9 empty] | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-125 | 30826 | [QA] Create Test Case Update survey step4.2(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:28 AM | 21/Sep/25 1:55 PM | [9 empty] | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-124 | 30824 | [QA] Create Test Case Update survey step4.1(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:27 AM | 21/Sep/25 1:55 PM | [9 empty] | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-123 | 30822 | [QA] Create Test Case Update survey step3(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:27 AM | 21/Sep/25 1:55 PM | [9 empty] | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-122 | 30820 | [QA] Create Test Case Update survey step2(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:26 AM | 21/Sep/25 12:27 PM | [9 empty] | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-121 | 30818 | [QA] Create Test Case Update survey step1(FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:26 AM | 21/Sep/25 12:27 PM | [9 empty] | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-120 | 30816 | [QA] Create Test Case Create survey (FE&BE) | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 09/Sep/25 11:25 AM | 21/Sep/25 12:27 PM | [9 empty] | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-119 | 30814 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 09/Sep/25 11:24 AM | 09/Sep/25 11:24 AM | [9 empty] | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-118 | 30812 | [QA] Create Test Case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 09/Sep/25 11:23 AM | 09/Sep/25 11:23 AM | [9 empty] | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-116 | 30808 | [QA] Create Test Case 'Club - Benefits & Info' Location | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 09/Sep/25 11:22 AM | 18/Sep/25 9:19 AM | [9 empty] | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-115 | 30806 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 09/Sep/25 11:22 AM | 09/Sep/25 11:22 AM | [9 empty] | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-114 | 30804 | [QA] Create Test Case Widget Type 'Club – Benefits & Information' | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 09/Sep/25 11:21 AM | 17/Sep/25 10:52 PM | [9 empty] | [Dev][RD][Thana] Sprint 7
Sub-task | DEVRDCT-229 | 30802 | [QA] Create Test Case |  |  | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 09/Sep/25 11:14 AM | 09/Sep/25 11:14 AM | [9 empty] | [Dev][CT] Sprint 7
Sub-task | DEVRDCT-228 | 30800 | [QA] Create Test Case |  |  | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 09/Sep/25 11:14 AM | 09/Sep/25 11:14 AM | [9 empty] | [Dev][CT] Sprint 7
Sub-task | DEVRDCT-227 | 30798 | [QA] Create Test Case |  |  | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 09/Sep/25 11:14 AM | 09/Sep/25 11:14 AM | [9 empty] | [Dev][CT] Sprint 7
Sub-task | DEVRDCT-226 | 30796 | Create Test Case |  |  | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 09/Sep/25 11:13 AM | 09/Sep/25 4:51 PM | [9 empty] | [Dev][CT] Sprint 7
Story | DEVRDSUP-124 | 30784 | [SUP-171]Rabbit Life Point Issue Incomplete of Aug 2025 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 08/Sep/25 5:27 PM | 22/Sep/25 9:17 AM | 18/Sep/25 12:00 AM | 1 | rlife |  |  | 1800 |  |  |  | [Dev][All project]Sprint 7
Story | RDAPS-179 | 30768 | [DEV][RD][RRS] Optimize Performance Import Coupons | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Done |  | 08/Sep/25 10:47 AM | 18/Sep/25 2:03 PM |  | 5 | rr-scheduler |  |  | 86400 |  |  |  | [Dev][All project]Sprint 7
Story | DEVRDECOM-80 | 30765 | [DEV][RD][Eco][RR-Ecommerce-Shopify] Review Test Case | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 08/Sep/25 7:44 AM | 22/Sep/25 9:23 AM |  | 1 | No-QA |  |  | 3600 |  |  |  | [Dev][RD][Ecom] Sprint 7
Story | RDTHANA-113 | 30734 | [Dev][RD][BOF][Service] Change service status | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 07/Sep/25 3:21 PM | 19/Sep/25 10:05 AM | 19/Sep/25 12:00 AM | 5 |  |  |  | 57600 |  |  |  | [Dev][RD][Thana] Sprint 7
Story | DEVRDECOM-79 | 30733 | [DEV][RD][Eco][RR-Ecommerce-Shopify] Enhance generate multipass token | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 06/Sep/25 8:04 PM | 22/Sep/25 9:23 AM |  | 3 | No-QA |  |  | 7200 |  |  |  | [Dev][RD][Ecom] Sprint 7
Story | DEVRDECOM-78 | 30732 | [DEV][RD][Eco][Reward-Memberber] Adjust template for responsive | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 06/Sep/25 8:01 PM | 22/Sep/25 9:22 AM |  | 2 | No-QA |  |  | 7200 |  |  |  | [Dev][RD][Ecom] Sprint 7
Story | DEVRDADJ-35 | 30728 | [DEV][RD][LNF] Create migration for maid | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 06/Sep/25 4:01 PM | 16/Sep/25 10:05 AM |  | 1 | [7 empty] | [Dev][RDAdjust] Sprint 8
Sub-task | RDAPS-178 | 30714 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 05/Sep/25 3:53 PM | 15/Sep/25 1:45 PM | [9 empty] | [Dev][All project]Sprint 6 | [Dev][All project]Sprint 7
Bug | DEVRDECOM-77 | 30711 | [S2] Email address is updated even without confirming the email verification | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 05/Sep/25 3:15 PM | 09/Sep/25 2:35 PM | [9 empty] | [Dev][RD][Ecom] Sprint 7
Story | RDTHANA-106 | 30689 | [Dev][RD][Service][CMS API] Create service filter api | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 04/Sep/25 4:08 PM | 18/Sep/25 2:14 PM | 11/Sep/25 12:00 AM | 3 | cms-api | No-QA |  | 18000 |  |  |  | [Dev][RD][Thana] Sprint 7
Story | RDAPS-176 | 30680 | [DEV][RD][Arichive DB][RLP][PL] Prepare command to lean data | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 04/Sep/25 1:54 PM | 22/Sep/25 9:17 AM |  | 1 |  |  |  | 600 |  |  |  | [Dev][All project]Sprint 7
Sub-task | RDTHANA-103 | 30679 | [QA] Test Execution Get club by id | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 04/Sep/25 1:48 PM | 12/Sep/25 1:12 PM | [6 empty] | มาจาก Sprint 6 | To Do |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-102 | 30677 | [QA] Test Execution get club | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 04/Sep/25 1:47 PM | 12/Sep/25 1:11 PM | [6 empty] | มาจาก Sprint 6 | To Do |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-101 | 30675 | [QA] Test Execution bind user to partner club | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 04/Sep/25 1:46 PM | 12/Sep/25 1:11 PM | [6 empty] | มาจาก Sprint 6 | To Do |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-100 | 30673 | [QA] Test Execution check user eligiblility for partner club binding | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 04/Sep/25 1:45 PM | 12/Sep/25 1:11 PM | [6 empty] | มาจาก Sprint 6 | To Do |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Story | DEVRDECOM-75 | 30663 | [DEV][RD][Eco][RR-Ecommerce-Shopify][Reward-Memberber] Request and Prepare PVT | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 04/Sep/25 1:26 PM | 22/Sep/25 9:22 AM |  | 2 | No-QA |  |  | 10800 |  |  |  | [Dev][RD][Ecom] Sprint 7
Story | DEVRDECOM-74 | 30662 | [DEV][RD][Eco][User Manual] Create user manual for recheck and Update Theme Code After Shopify Theme Update | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Progress |  | 04/Sep/25 1:18 PM | 22/Sep/25 8:45 AM |  | 3 | No-QA | [6 empty] | [Dev][RD][Ecom] Sprint 7 | [Dev][RD][Ecom] Sprint 8
Story | DEVRDECOM-72 | 30660 | [DEV][RD][Eco][POC] Adjust Shopify Theme Atelier | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Progress |  | 04/Sep/25 1:16 PM | 22/Sep/25 8:45 AM |  | 5 | No-QA | [6 empty] | [Dev][RD][Ecom] Sprint 7 | [Dev][RD][Ecom] Sprint 8
Story | DEVRDECOM-71 | 30659 | [DEV][RD][Eco][POC] Adjust Shopify Theme Dawn | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 04/Sep/25 1:16 PM | 22/Sep/25 9:22 AM |  | 3 | No-QA |  |  | 28800 |  |  |  | [Dev][RD][Ecom] Sprint 7
Story | DEVRDECOM-70 | 30658 | [DEV][RD][Eco][RR-Ecommerce-Shopify] Prepare UAT | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 04/Sep/25 1:16 PM | 22/Sep/25 9:21 AM |  | 1 | No-QA |  |  | 28800 |  |  |  | [Dev][RD][Ecom] Sprint 7
Story | DEVRDCT-225 | 30654 | [DEV][RD][HR] Implement Club Binding Event | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 04/Sep/25 9:14 AM | 08/Sep/25 10:13 AM |  | 5 | hr-solution | [6 empty] | [Dev][CT] Sprint 7
Bug | DEVRDCT-224 | 30653 | [DEV][RD][RDS] FIX REDEEM EVENT - INTERNAL NAME value now use EN Name as value | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Resolved |  | 04/Sep/25 8:46 AM | 09/Sep/25 4:41 PM | 10/Sep/25 12:00 AM | 1 | redemption-api | [6 empty] | [Dev][CT] Sprint 7
Story | DEVRDCT-223 | 30652 | [DEV][RD][RDS] ENH Add "Offer ID" to "REDEEM" EVENT | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready to Staging |  | 04/Sep/25 7:48 AM | 09/Sep/25 4:49 PM | 10/Sep/25 12:00 AM | 1 | redemption-api |  |  | 3600 |  |  |  | [Dev][CT] Sprint 7
Story | DEVRDCT-222 | 30651 | [DEV][RD][RDS] ENH Add "Offer ID" to "MEMBER COUPON" EVENT | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready to Staging |  | 04/Sep/25 6:58 AM | 09/Sep/25 4:49 PM | 10/Sep/25 12:00 AM | 2 | redemption-api |  |  | 7200 |  |  |  | [Dev][CT] Sprint 7
Story | RDAPS-175 | 30649 | [DEV][RD][SSO Handover] GCP SSO SSL management & Domain | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | To Do |  | 03/Sep/25 5:04 PM | 03/Sep/25 5:21 PM | 18/Sep/25 12:00 AM | 1 | No-QA | [6 empty] | [Dev][All project]Sprint 7
Story | RDAPS-174 | 30648 | [DEV][RD][SSO Handover] Overiew GKE All Cluster | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | To Do |  | 03/Sep/25 5:03 PM | 18/Sep/25 1:30 PM | 26/Sep/25 12:00 AM | 3 | No-QA | [6 empty] | [Dev][All project]Sprint 7
Story | RDAPS-173 | 30647 | [DEV][RD][SSO Handover] Overiew GKE All Cluster | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | To Do |  | 03/Sep/25 5:00 PM | 18/Sep/25 1:30 PM | 26/Sep/25 12:00 AM | 1 | No-QA | [6 empty] | [Dev][All project]Sprint 7
Story | RDAPS-172 | 30646 | [DEV][RD][SSO Handover] GCP Solution Architecture | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | To Do |  | 03/Sep/25 4:59 PM | 18/Sep/25 1:28 PM | 26/Sep/25 12:00 AM | 3 | No-QA | [6 empty] | [Dev][All project]Sprint 7
Story | RDTHANA-97 | 30645 | [Dev][RD][BOF][Service] Edit page step 2. | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 03/Sep/25 4:58 PM | 19/Sep/25 4:12 PM | 17/Sep/25 12:00 AM | 8 |  |  |  | 86400 |  |  | No Original Est | [Dev][RD][Thana] Sprint 7
Story | RDAPS-171 | 30644 | [DEV][RD][SSO Handover] GCP Service & Resouce & ENV & parameter | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 03/Sep/25 4:57 PM | 18/Sep/25 1:13 PM | 18/Sep/25 12:00 AM | 1 | No-QA |  |  | 14400 |  |  |  | [Dev][All project]Sprint 7
Story | RDAPS-170 | 30643 | [DEV][RD][SSO Handover] Overview GCP SSO | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 03/Sep/25 4:56 PM | 15/Sep/25 1:17 PM | 15/Sep/25 12:00 AM | 1 | No-QA |  |  | 7200 |  |  | No Original Est | [Dev][All project]Sprint 7
Story | RDTHANA-96 | 30642 | [Dev][RD][BOF][Service] Edit page step 1. | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Review |  | 03/Sep/25 4:54 PM | 22/Sep/25 9:08 AM | 19/Sep/25 12:00 AM | 5 |  |  |  | 57600 |  |  | No Original Est | [Dev][RD][Thana] Sprint 7
Story | RDTHANA-95 | 30641 | [Dev][RD][BOF][Service] Create page step 1 | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 03/Sep/25 4:52 PM | 22/Sep/25 9:08 AM | 12/Sep/25 12:00 AM | 8 |  |  |  | 0 |  |  |  | [Dev][RD][Thana] Sprint 7
Story | RDTHANA-94 | 30639 | [Dev][RD][BOF][Service] create service index page | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 03/Sep/25 4:19 PM | 19/Sep/25 1:01 PM | 12/Sep/25 12:00 AM | 8 |  |  |  | 86400 |  |  | No Original Est | [Dev][RD][Thana] Sprint 7
Story | RDTHANA-93 | 30638 | [Dev][RD][BOF][Migration] create migration services table | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 03/Sep/25 4:17 PM | 18/Sep/25 2:12 PM |  | 2 | No-QA |  |  | 7200 |  |  | No Original Est | [Dev][RD][Thana] Sprint 7
Story | RDTHANA-92 | 30637 | [Dev][RD][BOF][Service] Initial Service feature | Nim : muthita munmueang | 712020:e80312b7-b5b0-43e8-b198-3d8fce4532bb | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 03/Sep/25 4:16 PM | 19/Sep/25 10:21 AM |  | 3 | No-QA |  |  | 28800 |  |  | No Original Est | [Dev][RD][Thana] Sprint 7
Story | RDTHANA-91 | 30636 | [Dev][RD][SA][Service] Analyze and Task Description | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 03/Sep/25 4:13 PM | 16/Sep/25 10:04 AM |  | 5 | No-QA |  |  | 57600 |  |  | No Original Est | [Dev][RD][Thana] Sprint 7
Epic | DEVRDADJ-34 | 30635 | MAID registration |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 03/Sep/25 4:08 PM | 03/Sep/25 4:09 PM | [9 empty] | [Dev][RDAdjust] Sprint 8
Story | DEVRDADJ-33 | 30634 | [DEV][RD][Notification API] Create new endpoint to get maid with sso_id/trader_id |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 03/Sep/25 4:05 PM | 09/Sep/25 11:01 AM |  | 3 | [7 empty] | [Dev][RDAdjust] Sprint 8
Story | DEVRDADJ-32 | 30633 | [DEV][RD][Notification API] Enhance API for bypass maid from RR application |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 03/Sep/25 4:02 PM | 09/Sep/25 11:01 AM |  | 5 | [7 empty] | [Dev][RDAdjust] Sprint 8
Story | DEVRDCT-221 | 30632 | [DEV][RD][PL] Create script to initial Turtle club binding to CT | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 03/Sep/25 3:55 PM | 22/Sep/25 9:19 AM |  | 3 |  |  |  | 18000 |  |  |  | [Dev][CT] Sprint 7
Bug | DEVRDCT-220 | 30623 | [S4][RD][CT] CleverTap is unable to access the DataHub service | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Closed |  | 03/Sep/25 9:01 AM | 09/Sep/25 5:09 PM |  | 0 | No-QA |  |  |  | มาจาก Sprint 6 | Resolved |  | [Dev][Thana City] sprint 6 | [Dev][CT] Sprint 6 | [Dev][CT] Sprint 7
Story | RDTHANA-90 | 30622 | [Dev][RD][Section][BOF][QA] Enhance Section Feature: Add new widget types | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Sep/25 9:16 PM | 18/Sep/25 2:12 PM |  | 0 |  |  |  | 0 |  |  | No Original Est | [Dev][RD][Thana] Sprint 7
Story | RDTHANA-89 | 30621 | [Dev][RD][Section][BOF] Enhance Section Feature: Add 'Club - Benefits & Info' Location | Art_narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Sep/25 8:56 PM | 15/Sep/25 10:41 AM |  | 5 | rr-backoffice |  |  | 57600 |  |  | No Original Est | [Dev][RD][Thana] Sprint 7
Story | RDTHANA-88 | 30620 | [Dev][RD][Widget][BOF] Enhance Widget Feature: Add 'Service' Type | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Sep/25 8:56 PM | 21/Sep/25 1:53 PM | 11/Sep/25 12:00 AM | 5 | rr-backoffice |  |  | 57600 |  |  |  | [Dev][RD][Thana] Sprint 7
Story | RDTHANA-87 | 30619 | [Dev][RD][Widget][BOF] Enhance Widget Feature: Add 'Club – Benefits & Information' Type | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Sep/25 8:56 PM | 18/Sep/25 2:21 PM | 10/Sep/25 12:00 AM | 5 | rr-backoffice |  |  | 57600 |  |  |  | [Dev][RD][Thana] Sprint 7
Story | RDTHANA-86 | 30618 | [Dev][RD][BOF] Update survey Step 5: Survey Appearance (Thank You) (FE&BE) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Sep/25 8:44 PM | 15/Sep/25 2:55 PM | 15/Sep/25 12:00 AM | 2 | rr-backoffice |  |  | 10800 |  |  |  | [Dev][RD][Thana] Sprint 7
Story | RDTHANA-81 | 30606 | [Dev][RD][BOF] Change survey status (FE&BE) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Sep/25 3:26 PM | 17/Sep/25 4:10 PM | 16/Sep/25 12:00 AM | 3 | rr-backoffice |  |  | 28800 |  |  |  | [Dev][RD][Thana] Sprint 7
Story | RDTHANA-80 | 30604 | [Dev][RD][BOF] Update survey Step 5: Survey Appearance (Input E-mail) (FE&BE) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Sep/25 3:25 PM | 15/Sep/25 2:55 PM | 15/Sep/25 12:00 AM | 2 | rr-backoffice |  |  | 10800 |  |  |  | [Dev][RD][Thana] Sprint 7
Story | RDTHANA-79 | 30602 | [Dev][RD][BOF] Update survey step5.2(FE&BE) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 02/Sep/25 3:24 PM | 15/Sep/25 2:55 PM | 12/Sep/25 12:00 AM | 2 | rr-backoffice |  |  | 10800 |  |  |  | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-78 | 30600 | Create Test Case Get club by id | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 02/Sep/25 3:04 PM | 04/Sep/25 1:44 PM | [6 empty] | มาจาก Sprint 6 | Done |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Bug | DEVRDCT-218 | 30509 | [S4][Clever Tap][User Properties][Club binding] Status BOUND/UNBOUND of Club binding properties has lowercases when the Club added the first time and had only 1 BU | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Low | Closed |  | 29/Aug/25 11:17 AM | 09/Sep/25 5:08 PM |  | 0 | hr-solution | No-QA |  |  | มาจาก Sprint 6 | ACCEPTED |  | [Dev][Thana City] sprint 6 | [Dev][CT] Sprint 6 | [Dev][CT] Sprint 7
Story | RDAPS-169 | 30405 | [DEV][RD][RRS] Improve Redemption ETL data | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Done |  | 28/Aug/25 11:36 AM | 18/Sep/25 2:06 PM |  | 5 | rr-scheduler |  |  | 72000 |  |  |  | [Dev][All project]Sprint 7
Story | RDTHANA-76 | 30398 | [DEV][RD][BFF] Get club by id | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 27/Aug/25 4:56 PM | 16/Sep/25 8:13 AM |  | 2 |  |  |  | 7200 | มาจาก Sprint 6 | In Progress | No Original Est | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Story | RDTHANA-75 | 30396 | [DEV][RD][EXS] Get club by id | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 27/Aug/25 4:56 PM | 18/Sep/25 2:15 PM |  | 2 | exclusive-store-api | No-QA |  | 0 | มาจาก Sprint 6 | In Review | 21600 | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Story | RDAPS-167 | 30374 | [DEV][RD][SMS][SSO-Messager] Enhance OTP SMS change sub account | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 27/Aug/25 10:49 AM | 09/Sep/25 4:12 PM | 28/Aug/25 12:00 AM | 2 |  |  |  | 0 | มาจาก Sprint 6 | Ready to Staging | 14400 | [Dev][All project]Sprint 6 | [Dev][All project]Sprint 7
Story | RDTHANA-74 | 30366 | [Dev][RD][BOF] Update survey step4.2(FE&BE) | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:15 PM | 19/Sep/25 10:03 AM |  | 2 | rr-backoffice |  |  | 28800 |  |  |  | [Dev][RD][Thana] Sprint 7
Story | RDTHANA-73 | 30364 | [Dev][RD][BOF] Download Individual Survey Report (FE&BE) | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:15 PM | 19/Sep/25 10:14 AM | 18/Sep/25 12:00 AM | 5 | rr-backoffice |  |  | 57600 |  |  |  | [Dev][RD][Thana] Sprint 7
Story | RDTHANA-72 | 30362 | [Dev][RD][BOF] Update survey step5.1(FE&BE) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:15 PM | 15/Sep/25 2:55 PM | 12/Sep/25 12:00 AM | 3 | rr-backoffice |  |  | 28800 |  |  |  | [Dev][RD][Thana] Sprint 7
Story | RDTHANA-71 | 30360 | [Dev][RD][BOF] Update survey step4.1(FE&BE) | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:15 PM | 19/Sep/25 10:02 AM |  | 8 | rr-backoffice |  |  | 86400 |  |  |  | [Dev][RD][Thana] Sprint 7
Story | RDTHANA-70 | 30358 | [Dev][RD][BOF] Update survey step3(FE&BE) | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:14 PM | 19/Sep/25 10:02 AM |  | 5 | rr-backoffice |  |  | 28800 |  |  |  | [Dev][RD][Thana] Sprint 7
Story | RDTHANA-69 | 30356 | [Dev][RD][BOF] Update survey step2(FE&BE) | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:09 PM | 18/Sep/25 2:19 PM | 16/Sep/25 12:00 AM | 3 | rr-backoffice |  |  | 28800 |  |  |  | [Dev][RD][Thana] Sprint 7
Story | RDTHANA-68 | 30354 | [Dev][RD][BOF] View Survey Report (FE&BE) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:09 PM | 17/Sep/25 4:31 PM | 17/Sep/25 12:00 AM | 3 | rr-backoffice |  |  | 28800 |  |  |  | [Dev][RD][Thana] Sprint 7
Story | RDTHANA-67 | 30352 | [Dev][RD][BOF] View Survey List (FE&BE) | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:09 PM | 18/Sep/25 2:21 PM |  | 5 | rr-backoffice |  |  | 86400 |  |  |  | [Dev][RD][Thana] Sprint 7
Story | RDTHANA-66 | 30350 | [Dev][RD][BOF] Update survey step1(FE&BE) | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:09 PM | 18/Sep/25 2:19 PM | 15/Sep/25 12:00 AM | 3 | rr-backoffice |  |  | 28800 |  |  |  | [Dev][RD][Thana] Sprint 7
Story | RDTHANA-65 | 30348 | [Dev][RD][BOF] Create survey (FE&BE) | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Aug/25 7:08 PM | 15/Sep/25 2:55 PM | 11/Sep/25 12:00 AM | 5 | rr-backoffice |  |  | 43200 |  |  |  | [Dev][RD][Thana] Sprint 7
Sub-task | DEVRD20THB-34 | 30328 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 26/Aug/25 2:25 PM | 01/Sep/25 1:55 PM | [6 empty] | มาจาก Sprint 6 | Done |  | [Dev][RD][20THB] Sprint 6 | [Dev][RD][20THB] Sprint 7
Sub-task | DEVRD20THB-33 | 30326 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 26/Aug/25 2:25 PM | 03/Sep/25 1:27 PM | [9 empty] | [Dev][RD][20THB] Sprint 7
Sub-task | DEVRD20THB-32 | 30324 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 26/Aug/25 2:24 PM | 01/Sep/25 1:08 PM | [6 empty] | มาจาก Sprint 6 | Done |  | [Dev][RD][20THB] Sprint 6 | [Dev][RD][20THB] Sprint 7
Sub-task | DEVRD20THB-31 | 30322 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 26/Aug/25 2:24 PM | 01/Sep/25 1:08 PM | [6 empty] | มาจาก Sprint 6 | Done |  | [Dev][RD][20THB] Sprint 6 | [Dev][RD][20THB] Sprint 7
Sub-task | RDTHANA-64 | 30308 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 26/Aug/25 2:15 PM | 09/Sep/25 4:21 PM | [6 empty] | มาจาก Sprint 6 | To Do |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-63 | 30306 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 26/Aug/25 2:15 PM | 09/Sep/25 4:21 PM | [9 empty] | [Dev][RD][Thana] Sprint 7
Sub-task | DEVRDECOM-62 | 30302 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 26/Aug/25 2:15 PM | 09/Sep/25 2:36 PM | [6 empty] | มาจาก Sprint 6 | In Progress |  | [Dev][RD][Ecom] Sprint 6 | [Dev][RD][Ecom] Sprint 7
Sub-task | DEVRDECOM-61 | 30300 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 26/Aug/25 2:15 PM | 27/Aug/25 2:35 PM | [6 empty] | มาจาก Sprint 6 | Done |  | [Dev][RD][Ecom] Sprint 6 | [Dev][RD][Ecom] Sprint 7
Sub-task | RDTHANA-61 | 30298 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 26/Aug/25 2:15 PM | 03/Sep/25 4:00 PM | [6 empty] | มาจาก Sprint 6 | Done |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-60 | 30296 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 26/Aug/25 2:14 PM | 03/Sep/25 4:00 PM | [6 empty] | มาจาก Sprint 6 | Done |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-59 | 30293 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 26/Aug/25 2:14 PM | 12/Sep/25 1:08 PM | [6 empty] | มาจาก Sprint 6 | To Do |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-58 | 30291 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 26/Aug/25 2:14 PM | 12/Sep/25 1:08 PM | [6 empty] | มาจาก Sprint 6 | To Do |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-57 | 30289 | [QA] Create Test Case get club list and config api | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 26/Aug/25 2:13 PM | 04/Sep/25 1:41 PM | [6 empty] | มาจาก Sprint 6 | Done |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-56 | 30287 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 26/Aug/25 2:13 PM | 12/Sep/25 1:08 PM | [6 empty] | มาจาก Sprint 6 | To Do |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-55 | 30285 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 26/Aug/25 2:13 PM | 12/Sep/25 1:08 PM | [6 empty] | มาจาก Sprint 6 | To Do |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-54 | 30283 | [QA] Create Test Case bind user to partner club | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 26/Aug/25 2:12 PM | 03/Sep/25 2:27 PM | [6 empty] | มาจาก Sprint 6 | Done |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-53 | 30281 | [QA] Create Test Case check user eligiblility for partner club binding | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 26/Aug/25 2:12 PM | 03/Sep/25 1:48 PM | [6 empty] | มาจาก Sprint 6 | Done |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-52 | 30275 | [QA] Create Test Case Pop up Tan in Welcom Message Menu | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 26/Aug/25 2:12 PM | 15/Sep/25 10:42 AM | [6 empty] | มาจาก Sprint 6 | To Do |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-51 | 30273 | [QA] Create Test Case Advanced Setting Tab | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 26/Aug/25 2:12 PM | 11/Sep/25 9:19 PM | [6 empty] | มาจาก Sprint 6 | To Do |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-50 | 30271 | [QA] Create Test Case create temp deep link endpoint | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 26/Aug/25 2:11 PM | 11/Sep/25 10:10 AM | [6 empty] | มาจาก Sprint 6 | To Do |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Sub-task | RDTHANA-49 | 30269 | [QA] Create Test Case Add new input "default bu" | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 26/Aug/25 2:10 PM | 11/Sep/25 10:10 AM | [6 empty] | มาจาก Sprint 6 | To Do |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Sub-task | DEVRDCT-211 | 30246 | [QA] Create test case failed auto-push coupon CT Event | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 25/Aug/25 3:49 PM | 10/Sep/25 5:33 PM | [6 empty] | มาจาก Sprint 6 | To Do |  | [Dev][Thana City] sprint 6 | [Dev][CT] Sprint 6 | [Dev][CT] Sprint 7
Story | RDTHANA-48 | 30203 | [DEV][RD][DasHaus][BFF] Enhance get club config endpoint | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 25/Aug/25 12:57 AM | 16/Sep/25 8:09 AM |  | 2 |  |  |  | 7200 | มาจาก Sprint 6 | In Progress | No Original Est | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Story | RDAPS-166 | 30140 | [DEV][RD][SMS] Enhance OTP SMS change sub account | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Highest | Done |  | 22/Aug/25 5:22 PM | 17/Sep/25 4:00 PM | 28/Aug/25 12:00 AM | 5 |  |  |  | 0 | มาจาก Sprint 6 | Ready to Staging | 57600 | [Dev][All project]Sprint 6 | [Dev][All project]Sprint 7
Story | DEVRDCT-210 | 30135 | [Dev][RD][HR][Bind Hook] Enhance send CT club binding event | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Low | Done |  | 22/Aug/25 4:55 PM | 12/Sep/25 4:02 PM |  | 2 | No-QA |  |  | 0 | มาจาก Sprint 6 | Ready to Staging | 14400 | [Dev][Thana City] sprint 6 | [Dev][CT] Sprint 6 | [Dev][CT] Sprint 7
Story | RDTHANA-47 | 30134 | [DEV][RD][DasHaus][HRS] Rename field from "Employee" to "Member" | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Low | Ready To Test |  | 22/Aug/25 4:09 PM | 19/Sep/25 11:13 AM |  |  | hr-solution |  |  |  | มาจาก Sprint 6 | In Review | No Original Est | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Story | RDTHANA-46 | 30133 | [DEV][RD][DasHaus][HRS] Add "Added Member Channel column & search | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | High | Ready To Test |  | 22/Aug/25 4:08 PM | 19/Sep/25 11:13 AM |  | 5 | hr-solution |  |  | 57600 |  |  |  | [Dev][RD][Thana] Sprint 7
Story | RDTHANA-44 | 30131 | [DEV][RD][DasHaus][HRS] Add "SSO ID" & "Trader ID" field | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Low | Ready To Test |  | 22/Aug/25 4:02 PM | 19/Sep/25 11:13 AM |  |  | hr-solution |  |  |  | มาจาก Sprint 6 | In Review | No Original Est | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Test Execution | DEVRDECOM-60 | 30102 | [TX][ECommerce] BFF Shopify Sprint 6 | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 22/Aug/25 9:55 AM | 11/Sep/25 10:05 AM | [6 empty] | มาจาก Sprint 6 | In Progress |  | [Dev][RD][Ecom] Sprint 6 | [Dev][RD][Ecom] Sprint 7
Test Plan | DEVRDECOM-59 | 30101 | [TP][ECommerce] BFF Shopify - Sprint 6 | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 22/Aug/25 9:53 AM | 19/Sep/25 10:46 AM | [6 empty] | มาจาก Sprint 6 | Done |  | [Dev][RD][Ecom] Sprint 6 | [Dev][RD][Ecom] Sprint 7
Story | DEVRD20THB-30 | 30091 | [DEV][RD][20THB]SSO Backoffice] Enhance to allow CRM team to check customer 20 thb member status | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 22/Aug/25 9:13 AM | 19/Sep/25 1:09 PM | 29/Aug/25 12:00 AM | 3 |  |  |  | 0 | มาจาก Sprint 6 | Ready to Staging | 28800 | [Dev][RD][20THB] Sprint 6 | [Dev][RD][20THB] Sprint 7
Story | DEVRD20THB-29 | 30090 | [DEV][RD][20THB][BFFOFF] Offline subscription Integrate 20thb campaign's member | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Highest | Done |  | 22/Aug/25 6:23 AM | 19/Sep/25 1:09 PM |  | 2 |  |  |  | 14400 |  |  |  | [Dev][RD][20THB] Sprint 7
Story | DEVRD20THB-27 | 30088 | [DEV][RD][20THB][BFF] Checkout endpoint Integrate 20thb campaign's member checking | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Highest | Done |  | 22/Aug/25 6:19 AM | 19/Sep/25 1:09 PM | 26/Aug/25 12:00 AM | 2 |  |  |  | 0 | มาจาก Sprint 6 | Ready to Staging | 14400 | [Dev][RD][20THB] Sprint 6 | [Dev][RD][20THB] Sprint 7
Story | DEVRD20THB-26 | 30087 | [DEV][RD][20THB][BFF] Service Integrate Rabbit API and get token campaign with card id | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Highest | Done |  | 22/Aug/25 6:18 AM | 19/Sep/25 1:09 PM | 26/Aug/25 12:00 AM | 2 |  |  |  | 0 | มาจาก Sprint 6 | Ready to Staging | 14400 | [Dev][RD][20THB] Sprint 6 | [Dev][RD][20THB] Sprint 7
Story | RDTHANA-43 | 30086 | [DEV][RD][DasHaus][BFF] Verify the API to validate matching account | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | To Do |  | 22/Aug/25 6:12 AM | 18/Sep/25 2:10 PM |  | 1 |  |  |  |  | มาจาก Sprint 6 | To Do |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Story | RDTHANA-42 | 30085 | [DEV][RD][RR Link Notify] Generate static deeplink | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Progress |  | 21/Aug/25 11:47 PM | 15/Sep/25 2:42 PM |  | 1 | No-QA |  |  |  | มาจาก Sprint 6 | To Do |  | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Story | RDTHANA-41 | 30084 | [DEV][RD][DasHaus][BFF] Enhance get club list endpoint | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 21/Aug/25 11:42 PM | 16/Sep/25 8:08 AM |  | 2 |  |  |  | 3600 | มาจาก Sprint 6 | In Progress | 7200 -> 3600 | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Story | RDTHANA-40 | 30083 | [DEV][RD][DasHaus][Exclusive Store API] Enhance get club list and config api | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready To Test |  | 21/Aug/25 11:41 PM | 16/Sep/25 8:08 AM |  | 2 | exclusive-store-api |  |  | 0 | มาจาก Sprint 6 | Ready to Staging | 10800 | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Story | RDTHANA-39 | 30082 | [DEV][RD][HR-Solution][Club setting] Add new input "default bu" | Art_narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Highest | Ready To Test |  | 21/Aug/25 11:26 PM | 19/Sep/25 11:13 AM |  | 5 | hr-solution |  |  | 57600 | มาจาก Sprint 6 | Ready to Staging | No Original Est | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Story | RDTHANA-38 | 30081 | [DEV][RD][RR Link Notify] Enhance create temp deep link endpoint | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Highest | Ready To Test |  | 21/Aug/25 11:12 PM | 09/Sep/25 11:09 AM | 29/Aug/25 12:00 AM | 3 | link-notify |  |  | 0 | มาจาก Sprint 6 | Ready To Test | 28800 | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Story | RDTHANA-37 | 30080 | [DEV][RD][HR-Solution][BU] Enhance BU welcome message support popup | Art_narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Highest | Ready To Test |  | 21/Aug/25 11:02 PM | 19/Sep/25 11:13 AM | 12/Sep/25 12:00 AM | 5 |  |  |  | 57600 | มาจาก Sprint 6 | In Review | No Original Est | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Story | RDTHANA-36 | 30079 | [DEV][RD][Backoffice][BU] Enhance business unit index page | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 21/Aug/25 11:00 PM | 19/Sep/25 11:13 AM |  | 2 |  |  |  | 0 | มาจาก Sprint 6 | In Review | 57600 | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Story | RDTHANA-35 | 30078 | [DEV][RD][HR][BU] Enhance Advance setting tap | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Highest | Ready To Test |  | 21/Aug/25 10:59 PM | 19/Sep/25 11:13 AM | 03/Sep/25 12:00 AM | 8 |  |  |  | 0 | มาจาก Sprint 6 | Ready To Test | 86400 | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Story | RDTHANA-29 | 30011 | [DEV][RD][DasHaus][EXS] Implement the API to bind user to partner club | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Highest | Ready To Test |  | 21/Aug/25 1:10 PM | 09/Sep/25 11:09 AM | 03/Sep/25 12:00 AM | 8 |  |  |  | 0 | มาจาก Sprint 6 | Ready To Test | 86400 | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Story | DEVRDECOM-49 | 30006 | [DEV][RD][Eco][Rewards-Member] Create Email Verification Page with Token Input | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 21/Aug/25 9:54 AM | 17/Sep/25 2:58 PM |  | 5 | No-QA | rewards-member |  | 0 | มาจาก Sprint 6 | Ready To Test | 57600 | [Dev][RD][Ecom] Sprint 6 | [Dev][RD][Ecom] Sprint 7
Story | RDTHANA-26 | 29997 | [DEV][RD][DasHaus][BFF] Implement the API to bind user to partner club | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready To Test |  | 20/Aug/25 4:36 PM | 09/Sep/25 11:09 AM |  | 2 |  |  |  | 0 | มาจาก Sprint 6 | Ready To Test | 28800 | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Story | RDTHANA-25 | 29996 | [DEV][RD][DasHaus][BFF] Implement the API to check user eligiblility for partner club binding | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready To Test |  | 20/Aug/25 4:36 PM | 09/Sep/25 11:09 AM |  | 3 | BFF |  |  | 0 | มาจาก Sprint 6 | Ready To Test | 36000 | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Story | RDTHANA-24 | 29995 | [DEV][RD][DasHaus][EXS] Implement the API to check user eligiblility for partner club binding | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Highest | Ready To Test |  | 20/Aug/25 4:36 PM | 09/Sep/25 11:09 AM | 29/Aug/25 12:00 AM | 5 | exclusive-store-api |  |  | 0 | มาจาก Sprint 6 | Ready To Test | 57600 | [Dev][Thana City] sprint 6 | [Dev][RD][Thana] Sprint 6 | [Dev][RD][Thana] Sprint 7
Story | DEVRDCT-203 | 29975 | [Dev][RD][RLP] Initial feed Rabbit Line PAY Card to CleverTap | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | High | Done |  | 20/Aug/25 11:24 AM | 17/Sep/25 2:58 PM |  | 3 |  |  |  | 0 | มาจาก Sprint 6 | Ready to Staging | 21600 | [Dev][Thana City] sprint 6 | [Dev][CT] Sprint 6 | [Dev][CT] Sprint 7
Story | RDAPS-161 | 29974 | [DEV][RD][SUB-MVP1] Disable email | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 20/Aug/25 11:23 AM | 17/Sep/25 10:17 AM |  | 1 | No-QA |  |  | 0 | มาจาก Sprint 6 | Ready to Staging | 3600 | [Dev][All project]Sprint 6 | [Dev][All project]Sprint 7
Story | DEVRDCT-202 | 29973 | [Dev][RD][CID] Initial feed Rabbit Wallet Card to CleverTap | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | High | Ready to Staging |  | 20/Aug/25 11:22 AM | 09/Sep/25 4:53 PM | 01/Sep/25 12:00 AM | 3 | rr-cloudid-api |  |  | 0 | มาจาก Sprint 6 | Ready to Staging | 36000 | [Dev][Thana City] sprint 6 | [Dev][CT] Sprint 6 | [Dev][CT] Sprint 7
Story | RDAPS-160 | 29972 | [DEV][RD][SSO-Backoffice] Disable SEO tracking | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 20/Aug/25 11:21 AM | 08/Sep/25 8:18 PM | 04/Sep/25 12:00 AM | 1 |  |  |  | 0 | มาจาก Sprint 6 | Ready to Staging | 7200 | [Dev][All project]Sprint 6 | [Dev][All project]Sprint 7
Story | RDTHANA-20 | 29950 | [Dev][RD][APH] Enhance check token | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 19/Aug/25 7:46 PM | 17/Sep/25 10:37 PM |  | 3 |  |  |  | 28800 |  |  |  | [Dev][RD][Thana] Sprint 7
Story | RDTHANA-18 | 29946 | [Dev][RD][Widget][CMS] Database Migration | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 19/Aug/25 7:44 PM | 18/Sep/25 2:10 PM |  | 1 | cms-database | No-QA |  | 3600 |  |  |  | [Dev][RD][Thana] Sprint 7
Story | RDTHANA-17 | 29944 | [Dev][RD][SA][BFF] APIs Specification | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 19/Aug/25 7:44 PM | 18/Sep/25 2:09 PM |  | 5 | No-QA |  |  | 72000 |  |  |  | [Dev][RD][Thana] Sprint 7
Story | RDTHANA-15 | 29940 | [Dev][RD][Widget][CMS API] Enhance Widget API | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 19/Aug/25 7:41 PM | 19/Sep/25 10:04 AM |  | 2 | cms-api |  |  | 3600 |  |  |  | [Dev][RD][Thana] Sprint 7
Story | RDTHANA-14 | 29938 | [Dev][RD][Section][CMS API] Enhance Sections API | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 19/Aug/25 7:37 PM | 19/Sep/25 10:04 AM |  | 2 | cms-api |  |  | 14400 |  |  |  | [Dev][RD][Thana] Sprint 7
Story | RDTHANA-12 | 29935 | [Dev][RD][Survey][APH] Database Migration | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 19/Aug/25 7:35 PM | 18/Sep/25 2:08 PM |  | 1 | No-QA | rr-aphrodite |  | 10800 |  |  |  | [Dev][RD][Thana] Sprint 7
Bug | DEVRDSUP-96 | 29930 | [SUP-75][HR SOLUTION] When update My information on APP (email etc.) , data not update on HR solution. | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Closed |  | 19/Aug/25 5:09 PM | 09/Sep/25 2:28 PM | 02/Sep/25 12:00 AM | [5 empty] | มาจาก Sprint 6 | RETESTING |  | [Dev][All project]Sprint 6 | [Dev][All project]Sprint 7
Story | DEVRDECOM-45 | 29873 | [DEV][RD][Eco][RR-Ecommerce-Shopify] Enhance Auth Callback Endpoint to Sync Email to Shopify | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 18/Aug/25 8:21 PM | 18/Sep/25 1:52 PM |  | 3 | No-QA | rr-ecommerce-shopify |  | 14400 | มาจาก Sprint 6 | In Progress | 28800 -> 14400 | [Dev][RD][Ecom] Sprint 6 | [Dev][RD][Ecom] Sprint 7
Bug | DEVRDSUP-92 | 29864 | [SUP-133]User cannot export purchase TXN report, reward TXN report and upload coupon code. | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Open |  | 18/Aug/25 3:57 PM | 08/Sep/25 8:18 PM | 21/Aug/25 12:00 AM | [5 empty] | มาจาก Sprint 6 | Open |  | [Dev][All project]Sprint 6 | [Dev][All project]Sprint 7
Story | DEVRDECOM-43 | 29841 | [DEV][RD][Eco][RR-Ecommerce-Shopify] Enhance Auth Callback Endpoint to check Email Verify | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 16/Aug/25 12:19 PM | 18/Sep/25 1:52 PM |  | 3 | No-QA | rr-ecommerce-shopify |  | 0 | มาจาก Sprint 6 | Ready To Test | 28800 | [Dev][RD][Ecom] Sprint 6 | [Dev][RD][Ecom] Sprint 7
Story | DEVRDECOM-42 | 29840 | [DEV][RD][Eco][RR-Ecommerce-Shopify] Create Endpoint for Email Verified Callback and Redirect to Shopify | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 16/Aug/25 12:16 PM | 18/Sep/25 1:52 PM |  | 3 | No-QA | rr-ecommerce-shopify |  | 0 | มาจาก Sprint 6 | Ready To Test | 28800 | [Dev][RD][Ecom] Sprint 6 | [Dev][RD][Ecom] Sprint 7
Story | DEVRDECOM-41 | 29839 | [DEV][RD][Eco][Rewards-Member] Create Endpoint for Email Verify | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 16/Aug/25 12:13 PM | 17/Sep/25 2:58 PM |  | 3 | No-QA | rewards-member |  | 0 | มาจาก Sprint 6 | Ready To Test | 21600 | [Dev][RD][Ecom] Sprint 6 | [Dev][RD][Ecom] Sprint 7
Story | DEVRDECOM-40 | 29838 | [DEV][RD][Eco][BFF] Create API Endpoint for Email Verify Request | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 16/Aug/25 12:12 PM | 09/Sep/25 2:36 PM |  | 3 | BFF |  |  | 0 | มาจาก Sprint 6 | Ready To Test | 28800 | [Dev][RD][Ecom] Sprint 6 | [Dev][RD][Ecom] Sprint 7
Story | DEVRDECOM-39 | 29837 | [DEV][RD][Eco][Rewards-Member] Create API Endpoint for Email Verify Request | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 16/Aug/25 12:11 PM | 17/Sep/25 2:57 PM |  | 8 | No-QA | rewards-member |  | 0 | มาจาก Sprint 6 | Ready To Test | 86400 | [Dev][RD][Ecom] Sprint 6 | [Dev][RD][Ecom] Sprint 7
Sub-task | DEVRDCT-195 | 29811 | [QA] Update Test Case | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Tong Panuwat Sirirak | 70121:08c3e61f-6853-41cf-86ae-506a1b0d4ff9 | Medium | To Do |  | 14/Aug/25 3:37 PM | 09/Sep/25 4:53 PM | [6 empty] | มาจาก Sprint 6 | To Do |  | [Dev][Thana City] sprint 6 | [Dev][CT] Sprint 5 | [Dev][CT] Sprint 6 | [Dev][CT] Sprint 7
Sub-task | DEVRDCT-193 | 29807 | [QA] Update Test Case | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Tong Panuwat Sirirak | 70121:08c3e61f-6853-41cf-86ae-506a1b0d4ff9 | Medium | To Do |  | 14/Aug/25 3:30 PM | 09/Sep/25 4:53 PM | [6 empty] | มาจาก Sprint 6 | To Do |  | [Dev][Thana City] sprint 6 | [Dev][CT] Sprint 5 | [Dev][CT] Sprint 6 | [Dev][CT] Sprint 7
Sub-task | DEVRD20THB-18 | 29763 | [QA] Create Test Case Using/Use Coupon with 20THB Campaign Checking | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Tong Panuwat Sirirak | 70121:08c3e61f-6853-41cf-86ae-506a1b0d4ff9 | Medium | Done |  | 14/Aug/25 2:56 PM | 04/Sep/25 5:42 PM | [6 empty] | มาจาก Sprint 6 | Done |  | [Dev][RD][20THB] Sprint 6 | [Dev][RD][20THB] Sprint 7
Sub-task | DEVRD20THB-16 | 29759 | [QA] Create Test Case Redeem Rewards with 20THB Campaign Checking | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Tong Panuwat Sirirak | 70121:08c3e61f-6853-41cf-86ae-506a1b0d4ff9 | Medium | Done |  | 14/Aug/25 2:53 PM | 02/Sep/25 2:21 AM | [6 empty] | มาจาก Sprint 6 | Done |  | [Dev][RD][20THB] Sprint 6 | [Dev][RD][20THB] Sprint 7
Story | DEVRD20THB-11 | 29606 | [Dev][RD][20THB][BFF] Enhance mark coupon as using and used | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Highest | Done |  | 12/Aug/25 9:31 AM | 19/Sep/25 1:09 PM | 27/Aug/25 12:00 AM | 3 | BFF | change-request |  | 0 | มาจาก Sprint 6 | Ready to Staging | 28800 | [Dev][RD][20THB] Sprint 6 | [Dev][RD][20THB] Sprint 7
Story | DEVRDCT-177 | 29558 | [DEV][RD][HR-Solution] Initial feed user properties Club Binding with tier | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 11/Aug/25 9:53 AM | 09/Sep/25 4:53 PM |  | 3 |  |  |  | 0 | มาจาก Sprint 6 | Ready To Test | 28800 | [Dev][Thana City] sprint 6 | [Dev][CT] Sprint 5 | [Dev][CT] Sprint 6 | [Dev][CT] Sprint 7
Story | DEVRDCT-175 | 29542 | [Dev][RD][SSO User] Update Sign Up Event to include default values for the fields MSG_Email and MSG_SMS | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 09/Aug/25 4:04 PM | 17/Sep/25 10:18 AM |  | 2 | sso-user |  |  | 0 | มาจาก Sprint 6 | Ready to Staging | 7200 | [Dev][Thana City] sprint 6 | [Dev][CT] Sprint 5 | [Dev][CT] Sprint 6 | [Dev][CT] Sprint 7
Story | DEVRDCT-174 | 29541 | [Dev][RD][SSO User] Close function update MSG_Email and MSG_SMS from consent 1 | Mac: Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 09/Aug/25 2:46 PM | 16/Sep/25 11:17 PM |  | 1 | sso-user |  |  | 0 | มาจาก Sprint 6 | Ready to Staging | 7200 | [Dev][Thana City] sprint 6 | [Dev][CT] Sprint 5 | [Dev][CT] Sprint 6 | [Dev][CT] Sprint 7
Story | RDAPS-151 | 29538 | [Dev][RD][SSO-Messenger] Change OTP SMS for thai language | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Low | Done |  | 09/Aug/25 9:00 AM | 16/Sep/25 1:04 PM |  | 1 | sso-heimdall | sso-messenger |  | 0 | มาจาก Sprint 6 | Ready to Staging | 7200 | [Dev][All project]Sprint 5 | [Dev][All project]Sprint 6 | [Dev][All project]Sprint 7
Story | DEVRD20THB-5 | 29493 | [DEV][RD][20THB][BFF] Redeem endpoint Integrate 20thb campaign checking | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Highest | Done |  | 07/Aug/25 3:32 PM | 19/Sep/25 1:09 PM |  | 3 | BFF | change-request | rewards-api | 0 | มาจาก Sprint 6 | Ready to Staging | 28800 | [Dev][RD][20THB] Sprint 6 | [Dev][RD][20THB] Sprint 7
Sub-task | RDAPS-146 | 29359 | BFF |  |  | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 06/Aug/25 11:40 AM | 26/Aug/25 1:39 PM | [6 empty] | มาจาก Sprint 6 | In Review |  | [Dev][All project]Sprint 3 | [Dev][All project]Sprint 4 | [Dev][All project]Sprint 5 | [Dev][All project]Sprint 6 | [Dev][All project]Sprint 7
Sub-task | RDAPS-145 | 29357 | Redemption API | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 06/Aug/25 11:40 AM | 08/Aug/25 9:00 AM | [6 empty] | มาจาก Sprint 6 | Done |  | [Dev][All project]Sprint 3 | [Dev][All project]Sprint 4 | [Dev][All project]Sprint 5 | [Dev][All project]Sprint 6 | [Dev][All project]Sprint 7
Task | RDAPS-141 | 29339 | [Dev][RD][POC][SMS sub-account to support new sender IDs] | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Progress |  | 05/Aug/25 5:01 PM | 08/Sep/25 8:18 PM | [6 empty] | มาจาก Sprint 6 | In Progress |  | [Dev][All project]Sprint 4 | [Dev][All project]Sprint 5 | [Dev][All project]Sprint 6 | [Dev][All project]Sprint 7
Story | DEVRDSUP-75 | 29257 | [SUP-106][SUB] : Export receipt due to BCC auto email incident #LOT2 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | In Review |  | 04/Aug/25 5:40 PM | 08/Sep/25 8:18 PM | 05/Aug/25 12:00 AM | [5 empty] | มาจาก Sprint 6 | In Review | No Original Est | [Dev][All project]Sprint 4 | [Dev][All project]Sprint 5 | [Dev][All project]Sprint 6 | [Dev][All project]Sprint 7
Story | DEVRDCT-167 | 29192 | [Dev][RD][RDS] Send event 'PUSH_REWARD_FAIL' to CT | Jack: Warin Kesorn | 61a98e8e744c4d00693281d1 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Done |  | 04/Aug/25 12:49 PM | 15/Sep/25 12:32 PM |  | 5 | redemption-consumer |  |  | 0 | มาจาก Sprint 6 | Ready to Staging | 72000 | [Dev][Thana City] sprint 6 | [Dev][CT] Sprint 6 | [Dev][CT] Sprint 7
Story | RDAPS-129 | 28895 | [Dev][RD][Redemption Consumer] Enhance coupon codes allocation process | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 29/Jul/25 4:53 PM | 08/Sep/25 8:18 PM |  | 2 | No-QA | redemption-consumer |  | 0 | มาจาก Sprint 6 | Ready To Test | 14400 | [Dev][All project]Sprint 6 | [Dev][All project]Sprint 7
Story | RDAPS-115 | 28754 | [Dev][RD][Redemption API] Enhance the API for redeeming the product | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 24/Jul/25 7:35 PM | 15/Sep/25 1:58 PM |  | 3 | No-QA | redemption-api |  | 0 | มาจาก Sprint 6 | Ready to Staging | 28800 | [Dev][All project]Sprint 4 | [Dev][All project]Sprint 5 | [Dev][All project]Sprint 6 | [Dev][All project]Sprint 7
Story | RDAPS-114 | 28753 | [Dev][RD][BFF API] Enhance API to get coupon by ID new fields for e-commerce type | Kae: Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 24/Jul/25 7:25 PM | 15/Sep/25 1:58 PM |  | 2 | BFF |  |  | 7200 | มาจาก Sprint 6 | Ready to Staging | No Original Est | [Dev][All project]Sprint 6 | [Dev][All project]Sprint 7
Story | RDAPS-113 | 28752 | [Dev][RD][Rewards API] Enhance API to get product by ID, Slug to support new fields for e-commerce type | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 24/Jul/25 7:25 PM | 08/Sep/25 8:18 PM |  | 2 | No-QA | rewards-api |  | 0 | มาจาก Sprint 6 | Ready to Staging | 14400 | [Dev][All project]Sprint 4 | [Dev][All project]Sprint 5 | [Dev][All project]Sprint 6 | [Dev][All project]Sprint 7
Bug | DEVRDSUP-57 | 28728 | [SUP-57][SUB] Found Sub TXN Offline via Cash Generate empty receipt | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | UNDER VALIDATION |  | 24/Jul/25 2:17 PM | 08/Sep/25 8:18 PM | 28/Jul/25 12:00 AM | [5 empty] | มาจาก Sprint 6 | UNDER VALIDATION |  | [Dev][All project]Sprint 4 | [Dev][All project]Sprint 5 | [Dev][All project]Sprint 6 | [Dev][All project]Sprint 7
Story | RDAPS-104 | 28577 | [Dev][RD] Improve Confirmation E-mail When Customer Redeemed Reward | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 21/Jul/25 9:08 PM | 17/Sep/25 9:52 AM | [8 empty] | No Original Est | [Dev][All project]Sprint 7
Bug | DEVRDSUP-50 | 28559 | [SUP-72][SUB] Some SUB TXN showing coupons as refunded but the package is still active. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | UNDER VALIDATION |  | 21/Jul/25 12:10 PM | 08/Sep/25 8:18 PM | 04/Aug/25 12:00 AM | [5 empty] | มาจาก Sprint 6 | UNDER VALIDATION |  | [Dev][All project]Sprint 4 | [Dev][All project]Sprint 5 | [Dev][All project]Sprint 6 | [Dev][All project]Sprint 7
Bug | DEVRDCT-135 | 28482 | [S2][sso backoffice][Clevertap][Privacy consent] Update privacy consent on sso backoffice get error 500 and NOT updated on Clevertap | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | High | Closed |  | 17/Jul/25 10:11 PM | 09/Sep/25 5:10 PM | [9 empty] | [Dev][CT] Sprint 7
Story | RDAPS-99 | 28480 | [Dev][RD][Redemption API] Pass BTS station info when issuing BTS pass for coupons with 'offline' sale channel | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 17/Jul/25 7:32 PM | 08/Sep/25 8:18 PM |  | 2 | redemption-api |  |  | 0 | มาจาก Sprint 6 | Ready To Test | 21600 | [Dev][All project]Sprint 3 | [Dev][All project]Sprint 4 | [Dev][All project]Sprint 5 | [Dev][All project]Sprint 6 | [Dev][All project]Sprint 7
Story | DEVRDSUP-45 | 28458 | [SUP-60][NBO][Rewards Alert List] - Requesting all exclusive partner rewards list with remaining code count. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 16/Jul/25 5:58 PM | 12/Sep/25 9:59 AM | 18/Jul/25 12:00 AM |  | No-QA |  |  |  | มาจาก Sprint 6 | To Do | No Original Est | [Dev][All project]Sprint 4 | [Dev][All project]Sprint 5 | [Dev][All project]Sprint 6 | [Dev][All project]Sprint 7
Bug | DEVRDSUP-42 | 28359 | [SUP-66][HRsolution] Many point issue TXN are stuck at "distributing" causing sum of point issue to be incorrect in Point Issuing Transaction Report | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Closed |  | 15/Jul/25 7:48 PM | 12/Sep/25 5:41 PM |  | 3 |  |  |  |  | มาจาก Sprint 6 | Resolved |  | [Dev][All project]Sprint 3 | [Dev][All project]Sprint 4 | [Dev][All project]Sprint 5 | [Dev][All project]Sprint 6 | [Dev][All project]Sprint 7
Bug | DEVRDCT-133 | 28344 | [S4][CT][User Properties] Enrichment detail of user properties NOT match to sso_backoffice | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Closed |  | 15/Jul/25 4:58 PM | 09/Sep/25 5:47 PM | [6 empty] | มาจาก Sprint 6 | Resolved |  | [Dev][CT] Sprint 2 | [Dev][CT] Sprint 3 | [Dev][Thana City] sprint 6 | [Dev][CT] Sprint 4 | [Dev][CT] Sprint 4 | [Dev][CT] Sprint 5 | [Dev][CT] Sprint 6 | [Dev][CT] Sprint 7
Bug | DEVRDSUP-35 | 27880 | [SUP-56][NBO][Rewards Alert List] - Rewards Alert List email not being sent | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Resolved |  | 09/Jul/25 1:46 PM | 21/Sep/25 11:01 PM | 14/Jul/25 12:00 AM | 3 | No-QA |  |  |  | มาจาก Sprint 6 | Solution Proposal Pending |  | [Dev][All project]Sprint 4 | [Dev][All project]Sprint 6 | [Dev][All project]Sprint 7
Bug | DEVRDSUP-30 | 27748 | [SUP-50][SUB] Some receipts are not generated after SUB TXN is made. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | UNDER VALIDATION |  | 08/Jul/25 1:43 PM | 08/Sep/25 8:18 PM | 11/Jul/25 12:00 AM | [5 empty] | มาจาก Sprint 6 | UNDER VALIDATION |  | [Dev][All project]Sprint 4 | [Dev][All project]Sprint 5 | [Dev][All project]Sprint 6 | [Dev][All project]Sprint 7

## Summarize Sprint 6
Column 1 | Total Stories Point | Total Manhour | Point Done | Manhour Done | Note
25 Aug - 5 Sep
Dev Resource Available | 17-19 | 500.5
Meeting Planned |  | 189 |  |  | Ref
Additional Meeting |  | 47.5 |  |  | Ref
Deployment |  | 19 |  |  | 3 ครั้ง 1. 3 คน 2. 5 คน 3. 4 คน
Development Sprint Total | 228 | 396.5 | 72 | 92
Ad-hoc Mid Sprint | 0 | 0 | 0 | 0
Requirement changes after refinement? | 6 | 16 | 0 | 0 | 2 tasks
Aek | 26 | 55.5 | 5 | 3
A | 20 | 46 | 0 | 0
Aom | 43 | 67 | 23 | 57
Zan | 23 | 52 | 14 | 32
Mai | 22 | 54 | 2 | 0
Mac | 25 | 49 | 6 | 0
Mos | 28 | 34 | 11 | 0
Jack | 21 | 39 | 3 | 0
Art | 18 | 0 | 8 | 0
Kae | 2 | 0 | 0 | 0

## Sprint 6
Issue Type | Issue key | Issue id | Summary | Assignee | Assignee Id | Reporter | Reporter Id | Priority | Status | Resolution | Created | Updated | Due date | Custom field (Story Points) | Labels | Labels | Labels |  | Original estimate | Sprint Movement | Note | Sprint 5 | Sprint | Sprint | Sprint | Sprint | Sprint | Sprint
Story | RDAPS-177 | 30705 | [DEV][ADHOC] Support NEC SIT: API Enh for Turtle member tier | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Progress |  | 05/Sep/25 10:49 AM | 05/Sep/25 10:49 AM |  | 1 |  |  |  |  | 1800 |  |  |  | [Dev][All project]Sprint 6
Sub-task | RDTHANA-103 | 30679 | [QA] Test Execution Get club by id | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 04/Sep/25 1:48 PM | 04/Sep/25 1:48 PM | [10 empty] | [Dev][RD][Thana] Sprint 6
Sub-task | RDTHANA-102 | 30677 | [QA] Test Execution get club | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 04/Sep/25 1:47 PM | 04/Sep/25 1:47 PM | [10 empty] | [Dev][RD][Thana] Sprint 6
Sub-task | RDTHANA-101 | 30675 | [QA] Test Execution bind user to partner club | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 04/Sep/25 1:46 PM | 04/Sep/25 1:46 PM | [10 empty] | [Dev][RD][Thana] Sprint 6
Sub-task | RDTHANA-100 | 30673 | [QA] Test Execution check user eligiblility for partner club binding | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 04/Sep/25 1:45 PM | 04/Sep/25 1:46 PM | [10 empty] | [Dev][RD][Thana] Sprint 6
Bug | DEVRDCT-220 | 30623 | [S4][RD][CT] CleverTap is unable to access the DataHub service | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Resolved |  | 03/Sep/25 9:01 AM | 05/Sep/25 10:05 AM |  | 0 | [8 empty] | [Dev][CT] Sprint 6
Story | RDTHANA-85 | 30617 | [Dev][RD][SA][Section] Analyze and Task Description | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 02/Sep/25 8:27 PM | 04/Sep/25 4:20 PM |  | 3 | [8 empty] | [Dev][RD][Thana] Sprint 6
Story | RDTHANA-84 | 30616 | [Dev][RD][SA][Widget] Analyze and Task Description | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 02/Sep/25 8:27 PM | 04/Sep/25 4:20 PM |  | 3 | [8 empty] | [Dev][RD][Thana] Sprint 6
Story | RDTHANA-83 | 30611 | [Dev][RD][SA][Survey] Analyze and Task Description | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 02/Sep/25 4:02 PM | 04/Sep/25 4:20 PM |  | 8 | [8 empty] | [Dev][RD][Thana] Sprint 6
Sub-task | RDTHANA-78 | 30600 | Create Test Case Get club by id | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 02/Sep/25 3:04 PM | 04/Sep/25 1:44 PM | [10 empty] | [Dev][RD][Thana] Sprint 6
Story | DEVRDSUP-112 | 30520 | [SUP-154]Rabbit Life Point Issue - July 2025 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 29/Aug/25 7:37 PM | 05/Sep/25 10:50 AM | 04/Sep/25 12:00 AM | 1 | rlife |  |  |  | 3600 |  |  |  | [Dev][All project]Sprint 6
Bug | DEVRDCT-218 | 30509 | [S4][Clever Tap][User Properties][Club binding] Status BOUND/UNBOUND of Club binding properties has lowercases when the Club added the first time and had only 1 BU | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Low | ACCEPTED |  | 29/Aug/25 11:17 AM | 05/Sep/25 10:12 AM | [10 empty] | [Dev][CT] Sprint 6
Sub-task | DEVRDCT-217 | 30508 | [QA] Test execution auto-push coupon redemption send email to queue | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 29/Aug/25 11:07 AM | 01/Sep/25 4:17 PM | [10 empty] | [Dev][CT] Sprint 5 | [Dev][CT] Sprint 6
Sub-task | DEVRDCT-216 | 30435 | [QA] Test execution Auto push coupon send email | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 28/Aug/25 11:05 PM | 01/Sep/25 4:17 PM | [10 empty] | [Dev][CT] Sprint 5 | [Dev][CT] Sprint 6
Story | RDAPS-168 | 30402 | [DEV][RD] Create manual for upload coupons | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 28/Aug/25 12:34 AM | 28/Aug/25 12:35 AM |  | 2 |  |  |  |  | 10800 |  |  |  | [Dev][All project]Sprint 6
Bug | DEVRDSUP-106 | 30400 | [SUP-155][RDxDA][ETL] Daily Redemption Report has failed - Missing Mandatory Files (20250821) | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Closed |  | 27/Aug/25 6:51 PM | 29/Aug/25 3:10 PM | 29/Aug/25 12:00 AM | 1 | etl | [7 empty] | [Dev][All project]Sprint 6
Story | RDTHANA-76 | 30398 | [DEV][RD][BFF] Get club by id | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 27/Aug/25 4:56 PM | 05/Sep/25 10:04 AM |  | 2 | [8 empty] | [Dev][RD][Thana] Sprint 6
Story | RDTHANA-75 | 30396 | [DEV][RD][EXS] Get club by id | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 27/Aug/25 4:56 PM | 04/Sep/25 5:33 AM |  | 2 | exclusive-store-api |  |  |  | 21600 |  |  |  | [Dev][RD][Thana] Sprint 6
Sub-task | DEVRDCT-213 | 30388 | [QA] Test execution validation passed allocate auto push coupons | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 27/Aug/25 2:52 PM | 29/Aug/25 10:30 AM | [10 empty] | [Dev][CT] Sprint 5 | [Dev][CT] Sprint 6
Sub-task | DEVRDCT-212 | 30380 | [QA] Test execution API CleverTap webhooks push-coupon | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 27/Aug/25 1:16 PM | 05/Sep/25 9:58 AM | [10 empty] | [Dev][CT] Sprint 5 | [Dev][CT] Sprint 6
Story | RDAPS-167 | 30374 | [DEV][RD][SMS][SSO-Messager] Enhance OTP SMS change sub account | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 27/Aug/25 10:49 AM | 01/Sep/25 3:13 PM | 28/Aug/25 12:00 AM | 2 |  |  |  |  | 14400 |  |  |  | [Dev][All project]Sprint 6
Sub-task | DEVRD20THB-34 | 30328 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 26/Aug/25 2:25 PM | 01/Sep/25 1:55 PM | [10 empty] | [Dev][RD][20THB] Sprint 6
Sub-task | DEVRD20THB-32 | 30324 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 26/Aug/25 2:24 PM | 01/Sep/25 1:08 PM | [10 empty] | [Dev][RD][20THB] Sprint 6
Sub-task | DEVRD20THB-31 | 30322 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 26/Aug/25 2:24 PM | 01/Sep/25 1:08 PM | [10 empty] | [Dev][RD][20THB] Sprint 6
Sub-task | RDTHANA-64 | 30308 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 26/Aug/25 2:15 PM | 03/Sep/25 10:40 AM | [10 empty] | [Dev][RD][Thana] Sprint 6
Sub-task | RDTHANA-62 | 30304 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 26/Aug/25 2:15 PM | 03/Sep/25 10:40 AM | [10 empty] | [Dev][RD][Thana] Sprint 6
Sub-task | DEVRDECOM-62 | 30302 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Progress |  | 26/Aug/25 2:15 PM | 05/Sep/25 10:17 AM | [10 empty] | [Dev][RD][Ecom] Sprint 6
Sub-task | DEVRDECOM-61 | 30300 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 26/Aug/25 2:15 PM | 27/Aug/25 2:35 PM | [10 empty] | [Dev][RD][Ecom] Sprint 6
Sub-task | RDTHANA-61 | 30298 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 26/Aug/25 2:15 PM | 03/Sep/25 4:00 PM | [10 empty] | [Dev][RD][Thana] Sprint 6
Sub-task | RDTHANA-60 | 30296 | [QA] Create Test Case | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 26/Aug/25 2:14 PM | 03/Sep/25 4:00 PM | [10 empty] | [Dev][RD][Thana] Sprint 6
Sub-task | RDTHANA-59 | 30293 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 26/Aug/25 2:14 PM | 26/Aug/25 2:14 PM | [10 empty] | [Dev][RD][Thana] Sprint 6
Sub-task | RDTHANA-58 | 30291 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 26/Aug/25 2:14 PM | 26/Aug/25 2:14 PM | [10 empty] | [Dev][RD][Thana] Sprint 6
Sub-task | RDTHANA-57 | 30289 | [QA] Create Test Case get club list and config api | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 26/Aug/25 2:13 PM | 04/Sep/25 1:41 PM | [10 empty] | [Dev][RD][Thana] Sprint 6
Sub-task | RDTHANA-56 | 30287 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 26/Aug/25 2:13 PM | 26/Aug/25 2:13 PM | [10 empty] | [Dev][RD][Thana] Sprint 6
Sub-task | RDTHANA-55 | 30285 | [QA] Create Test Case |  |  | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 26/Aug/25 2:13 PM | 26/Aug/25 2:13 PM | [10 empty] | [Dev][RD][Thana] Sprint 6
Sub-task | RDTHANA-54 | 30283 | [QA] Create Test Case bind user to partner club | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 26/Aug/25 2:12 PM | 03/Sep/25 2:27 PM | [10 empty] | [Dev][RD][Thana] Sprint 6
Sub-task | RDTHANA-53 | 30281 | [QA] Create Test Case check user eligiblility for partner club binding | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 26/Aug/25 2:12 PM | 03/Sep/25 1:48 PM | [10 empty] | [Dev][RD][Thana] Sprint 6
Sub-task | RDTHANA-52 | 30275 | [QA] Create Test Case | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 26/Aug/25 2:12 PM | 02/Sep/25 11:10 AM | [10 empty] | [Dev][RD][Thana] Sprint 6
Sub-task | RDTHANA-51 | 30273 | [QA] Create Test Case Advance Setting Tap | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 26/Aug/25 2:12 PM | 05/Sep/25 10:51 AM | [10 empty] | [Dev][RD][Thana] Sprint 6
Sub-task | RDTHANA-50 | 30271 | [QA] Create Test Case create temp deep link endpoint | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 26/Aug/25 2:11 PM | 03/Sep/25 2:49 PM | [10 empty] | [Dev][RD][Thana] Sprint 6
Sub-task | RDTHANA-49 | 30269 | [QA] Create Test Case Add new input "default bu" | Peet : Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 26/Aug/25 2:10 PM | 03/Sep/25 2:49 PM | [10 empty] | [Dev][RD][Thana] Sprint 6
Test Execution | DEVRRBOF-199 | 30253 | [TX][RR-Backoffice] Sprint6 - Staging | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 25/Aug/25 4:35 PM | 26/Aug/25 2:35 PM | [10 empty] | [Dev][All project]Sprint 6
Sub-task | DEVRDCT-211 | 30246 | [QA] Create test case failed auto-push coupon CT Event | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 25/Aug/25 3:49 PM | 25/Aug/25 5:12 PM | [10 empty] | [Dev][CT] Sprint 6
Story | RDTHANA-48 | 30203 | [DEV][RD][DasHaus][BFF] Enhance get club config endpoint | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Progress |  | 25/Aug/25 12:57 AM | 01/Sep/25 5:01 PM |  | 2 | [8 empty] | [Dev][RD][Thana] Sprint 6
Story | RDAPS-166 | 30140 | [DEV][RD][SMS] Enhance OTP SMS change sub account | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Highest | Ready to Staging |  | 22/Aug/25 5:22 PM | 01/Sep/25 3:13 PM | 28/Aug/25 12:00 AM | 5 |  |  |  |  | 57600 |  |  |  | [Dev][All project]Sprint 6
Story | DEVRDCT-210 | 30135 | [Dev][RD][HR][Bind Hook] Enhance send CT club binding event | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Low | Ready to Staging |  | 22/Aug/25 4:55 PM | 05/Sep/25 10:28 AM |  | 2 | No-QA |  |  |  | 14400 |  |  |  | [Dev][CT] Sprint 6
Story | RDTHANA-47 | 30134 | [DEV][RD][DasHaus][HRS] Rename field from "Employee" to "Member" | Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Low | In Review |  | 22/Aug/25 4:09 PM | 04/Sep/25 4:03 PM |  |  | hr-solution | [7 empty] | [Dev][RD][Thana] Sprint 6
Story | RDTHANA-45 | 30132 | [DEV][RD][DasHaus][HRS] Rename “Get Member Method” field to “Added Member Channel” with multiple tag search & opt-in functionality | Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Low | Done |  | 22/Aug/25 4:07 PM | 02/Sep/25 5:32 PM |  |  | hr-solution | No-QA | [6 empty] | [Dev][RD][Thana] Sprint 6
Story | RDTHANA-44 | 30131 | [DEV][RD][DasHaus][HRS] Add "SSO ID" & "Trader ID" field | Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Low | In Review |  | 22/Aug/25 4:02 PM | 04/Sep/25 9:40 AM |  |  | hr-solution | [7 empty] | [Dev][RD][Thana] Sprint 6
Sub-task | DEVRDCT-209 | 30115 | [QA] Test execution Club binding User Propreties CT | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 22/Aug/25 11:43 AM | 29/Aug/25 10:09 AM | [7 empty] | มาจาก Sprint 5 |  |  | [Dev][CT] Sprint 4 | [Dev][CT] Sprint 4 | [Dev][CT] Sprint 5 | [Dev][CT] Sprint 6
Test Execution | DEVRDECOM-60 | 30102 | [TX][ECommerce] Shopify Sprint 6 | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Progress |  | 22/Aug/25 9:55 AM | 27/Aug/25 10:36 AM | [10 empty] | [Dev][RD][Ecom] Sprint 6
Test Plan | DEVRDECOM-59 | 30101 | [TP][ECommerce] Shopify Sprint 6 | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 22/Aug/25 9:53 AM | 05/Sep/25 10:04 AM | [10 empty] | [Dev][RD][Ecom] Sprint 6
Test Set | DEVRDECOM-58 | 30100 | [TS][ECommerce] Shopify Sprint 6 | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 22/Aug/25 9:52 AM | 05/Sep/25 10:04 AM | [10 empty] | [Dev][RD][Ecom] Sprint 6
Story | DEVRD20THB-30 | 30091 | [DEV][RD][20THB]SSO Backoffice] Enhance to allow CRM team to check customer 20 thb member status | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 22/Aug/25 9:13 AM | 29/Aug/25 9:35 AM | 29/Aug/25 12:00 AM | 3 |  |  |  |  | 28800 |  |  |  | [Dev][RD][20THB] Sprint 6
Story | DEVRD20THB-27 | 30088 | [DEV][RD][20THB][BFF] Checkout endpoint Integrate 20thb campaign's member checking | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Highest | Ready to Staging |  | 22/Aug/25 6:19 AM | 04/Sep/25 9:31 AM | 26/Aug/25 12:00 AM | 2 |  |  |  |  | 14400 |  |  |  | [Dev][RD][20THB] Sprint 6
Story | DEVRD20THB-26 | 30087 | [DEV][RD][20THB][BFF] Service Integrate Rabbit API and get token campaign with card id | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Highest | Ready to Staging |  | 22/Aug/25 6:18 AM | 04/Sep/25 9:31 AM | 26/Aug/25 12:00 AM | 2 |  |  |  |  | 14400 |  |  |  | [Dev][RD][20THB] Sprint 6
Story | RDTHANA-43 | 30086 | [DEV][RD][DasHaus][BFF] Implement the API to validate matching account | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Low | To Do |  | 22/Aug/25 6:12 AM | 22/Aug/25 5:03 PM |  | 1 | [8 empty] | [Dev][RD][Thana] Sprint 6
Story | RDTHANA-42 | 30085 | [DEV][RD][RR Link Notify] Generate static deeplink | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 21/Aug/25 11:47 PM | 25/Aug/25 2:39 PM |  | 1 | No-QA | [7 empty] | [Dev][RD][Thana] Sprint 6
Story | RDTHANA-41 | 30084 | [DEV][RD][DasHaus][BFF] Enhance get club list endpoint | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | In Progress |  | 21/Aug/25 11:42 PM | 03/Sep/25 4:06 PM |  | 2 |  |  |  |  | 7200 |  |  |  | [Dev][RD][Thana] Sprint 6
Story | RDTHANA-40 | 30083 | [DEV][RD][DasHaus][Exclusive Store API] Enhance get club list and config api | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Ready to Staging |  | 21/Aug/25 11:41 PM | 04/Sep/25 7:11 AM |  | 2 | exclusive-store-api |  |  |  | 10800 |  |  |  | [Dev][RD][Thana] Sprint 6
Story | RDTHANA-39 | 30082 | [DEV][RD][HR-Solution][Club setting] Add new input "default bu" | Art_narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Highest | Ready to Staging |  | 21/Aug/25 11:26 PM | 04/Sep/25 9:36 AM |  | 5 | hr-solution | [7 empty] | [Dev][RD][Thana] Sprint 6
Story | RDTHANA-38 | 30081 | [DEV][RD][RR Link Notify] Enhance create temp deep link endpoint | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Highest | Ready To Test |  | 21/Aug/25 11:12 PM | 04/Sep/25 9:44 AM | 29/Aug/25 12:00 AM | 3 | link-notify |  |  |  | 28800 |  |  |  | [Dev][RD][Thana] Sprint 6
Story | RDTHANA-37 | 30080 | [DEV][RD][HR-Solution][BU] Enhance BU welcome message support popup | Art_narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Highest | In Review |  | 21/Aug/25 11:02 PM | 05/Sep/25 10:05 AM |  | 5 | [8 empty] | [Dev][RD][Thana] Sprint 6
Story | RDTHANA-36 | 30079 | [DEV][RD][Backoffice][BU] Enhance business unit index page | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Review |  | 21/Aug/25 11:00 PM | 05/Sep/25 10:56 AM |  | 2 |  |  |  |  | 57600 |  |  |  | [Dev][RD][Thana] Sprint 6
Story | RDTHANA-35 | 30078 | [DEV][RD][HR][BU] Enhance Advance setting tap | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Highest | Ready To Test |  | 21/Aug/25 10:59 PM | 05/Sep/25 10:27 AM | 03/Sep/25 12:00 AM | 8 |  |  |  |  | 86400 |  |  |  | [Dev][RD][Thana] Sprint 6
Story | RDTHANA-29 | 30011 | [DEV][RD][DasHaus][EXS] Implement the API to bind user to partner club | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Highest | Ready To Test |  | 21/Aug/25 1:10 PM | 05/Sep/25 9:43 AM | 03/Sep/25 12:00 AM | 8 |  |  |  |  | 86400 |  |  |  | [Dev][RD][Thana] Sprint 6
Story | DEVRDECOM-49 | 30006 | [DEV][RD][Eco][Rewards-Member] Create Email Verification Page with Token Input | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 21/Aug/25 9:54 AM | 05/Sep/25 9:42 AM |  | 5 | No-QA | rewards-member |  |  | 57600 |  |  |  | [Dev][RD][Ecom] Sprint 6
Story | RDTHANA-28 | 30005 | [Dev][RD][HR-Solution][SA] Design data structure | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 21/Aug/25 9:38 AM | 05/Sep/25 10:56 AM |  | 8 | hr-solution | No-QA |  |  | 86400 |  |  |  | [Dev][RD][Thana] Sprint 6
Story | RDTHANA-27 | 30004 | [DEV][RD][HR] Migrations | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 21/Aug/25 9:36 AM | 05/Sep/25 10:56 AM |  | 3 | hr-solution | No-QA |  |  | 28800 |  |  |  | [Dev][RD][Thana] Sprint 6
Story | DEVRDECOM-48 | 29999 | [DEV][RD][Eco][API Spec] Create API Spec for Email Verify Request | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 20/Aug/25 6:50 PM | 29/Aug/25 4:58 PM |  | 1 | No-QA |  |  |  | 3600 |  |  |  | [Dev][RD][Ecom] Sprint 6
Story | RDTHANA-26 | 29997 | [DEV][RD][DasHaus][BFF] Implement the API to bind user to partner club | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready To Test |  | 20/Aug/25 4:36 PM | 05/Sep/25 9:43 AM |  | 2 |  |  |  |  | 28800 |  |  |  | [Dev][RD][Thana] Sprint 6
Story | RDTHANA-25 | 29996 | [DEV][RD][DasHaus][BFF] Implement the API to check user eligiblility for partner club binding | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready To Test |  | 20/Aug/25 4:36 PM | 05/Sep/25 9:43 AM |  | 3 | BFF |  |  |  | 36000 |  |  |  | [Dev][RD][Thana] Sprint 6
Story | RDTHANA-24 | 29995 | [DEV][RD][DasHaus][EXS] Implement the API to check user eligiblility for partner club binding | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Highest | Ready To Test |  | 20/Aug/25 4:36 PM | 05/Sep/25 9:43 AM | 29/Aug/25 12:00 AM | 5 | exclusive-store-api |  |  |  | 57600 |  |  |  | [Dev][RD][Thana] Sprint 6
Story | RDTHANA-23 | 29994 | [DEV][RD][DasHaus][API Spec] | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Highest | Done |  | 20/Aug/25 4:36 PM | 04/Sep/25 4:23 PM | 28/Aug/25 12:00 AM | 8 | No-QA |  |  |  | 86400 |  |  |  | [Dev][RD][Thana] Sprint 6
Story | RDTHANA-22 | 29992 | [DEV][RD][DasHaus][SA] Analyze task for Member joining | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 20/Aug/25 4:31 PM | 01/Sep/25 5:02 PM |  | 8 | No-QA |  |  |  | 108000 |  |  |  | [Dev][RD][Thana] Sprint 6
Sub-task | RDAPS-163 | 29980 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 20/Aug/25 12:14 PM | 26/Aug/25 2:35 PM | [7 empty] | มาจาก Sprint 5 |  |  | [Dev][All project]Sprint 5 | [Dev][All project]Sprint 6
Sub-task | RDAPS-162 | 29978 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 20/Aug/25 12:14 PM | 26/Aug/25 1:55 PM | [7 empty] | มาจาก Sprint 5 |  |  | [Dev][All project]Sprint 5 | [Dev][All project]Sprint 6
Story | DEVRDCT-203 | 29975 | [Dev][RD][RLP] Initial feed Rabbit Line PAY Card to CleverTap | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | High | Ready to Staging |  | 20/Aug/25 11:24 AM | 05/Sep/25 10:36 AM |  | 3 |  |  |  |  | 21600 |  |  |  | [Dev][CT] Sprint 6
Story | RDAPS-161 | 29974 | [DEV][RD][SUB-MVP1] Disable email | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 20/Aug/25 11:23 AM | 03/Sep/25 4:05 PM |  | 1 |  |  |  |  | 3600 |  |  |  | [Dev][All project]Sprint 6
Story | DEVRDCT-202 | 29973 | [Dev][RD][CID] Initial feed Rabbit Wallet Card to CleverTap | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | High | Ready to Staging |  | 20/Aug/25 11:22 AM | 05/Sep/25 10:34 AM | 01/Sep/25 12:00 AM | 3 | rr-cloudid-api |  |  |  | 36000 |  |  |  | [Dev][CT] Sprint 6
Story | RDAPS-160 | 29972 | [DEV][RD][SSO-Backoffice] Disable SEO tracking | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 20/Aug/25 11:21 AM | 05/Sep/25 10:46 AM | 04/Sep/25 12:00 AM | 1 |  |  |  |  | 7200 |  |  |  | [Dev][All project]Sprint 6
Bug | DEVRDSUP-96 | 29930 | [SUP-75][HR SOLUTION] When update My information on APP (email etc.) , data not update on HR solution. | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | RETESTING |  | 19/Aug/25 5:09 PM | 03/Sep/25 2:20 PM | 02/Sep/25 12:00 AM | [9 empty] | [Dev][All project]Sprint 6
Sub-task | DEVRDECOM-47 | 29926 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 19/Aug/25 4:17 PM | 27/Aug/25 4:53 PM | [7 empty] | มาจาก Sprint 5 |  |  | [Dev][RD][Ecom]Sprint 5 | [Dev][RD][Ecom] Sprint 6
Bug | DEVRDSUP-94 | 29908 | [SUP-76]HOP Top merchant show 0 txn | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Rejected |  | 19/Aug/25 1:09 PM | 28/Aug/25 11:30 AM | 29/Aug/25 12:00 AM |  | hop | [7 empty] | [Dev][All project]Sprint 6
Bug | DEVRDSUP-93 | 29890 | [SUP-132][APP] Reward search result doesn't show out of stock on search result and category filter. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Open |  | 19/Aug/25 11:33 AM | 28/Aug/25 10:02 AM | 02/Sep/25 12:00 AM |  | rewards-api | [7 empty] | [Dev][All project]Sprint 6
Story | DEVRDECOM-45 | 29873 | [DEV][RD][Eco][RR-Ecommerce-Shopify] Enhance Auth Callback Endpoint to Sync Email to Shopify | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Progress |  | 18/Aug/25 8:21 PM | 05/Sep/25 9:46 AM |  | 3 | No-QA | rr-ecommerce-shopify |  |  | 28800 |  |  |  | [Dev][RD][Ecom] Sprint 6
Bug | DEVRDSUP-92 | 29864 | [SUP-133]User cannot export purchase TXN report, reward TXN report and upload coupon code. | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Open |  | 18/Aug/25 3:57 PM | 28/Aug/25 9:53 AM | 21/Aug/25 12:00 AM | [9 empty] | [Dev][All project]Sprint 6
Story | DEVRDECOM-44 | 29846 | [DEV][RD][Eco][API Gateway] Create API Gateway | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 17/Aug/25 2:02 PM | 29/Aug/25 4:59 PM |  | 1 | No-QA |  |  |  | 3600 |  |  |  | [Dev][RD][Ecom] Sprint 6
Story | DEVRDECOM-43 | 29841 | [DEV][RD][Eco][RR-Ecommerce-Shopify] Enhance Auth Callback Endpoint to check Email Verify | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 16/Aug/25 12:19 PM | 05/Sep/25 9:44 AM |  | 3 | No-QA | rr-ecommerce-shopify |  |  | 28800 |  |  |  | [Dev][RD][Ecom] Sprint 6
Story | DEVRDECOM-42 | 29840 | [DEV][RD][Eco][RR-Ecommerce-Shopify] Create Endpoint for Email Verified Callback and Redirect to Shopify | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 16/Aug/25 12:16 PM | 05/Sep/25 9:43 AM |  | 3 | No-QA | rr-ecommerce-shopify |  |  | 28800 |  |  |  | [Dev][RD][Ecom] Sprint 6
Story | DEVRDECOM-41 | 29839 | [DEV][RD][Eco][Rewards-Member] Create Endpoint for Email Verify | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 16/Aug/25 12:13 PM | 05/Sep/25 9:41 AM |  | 3 | No-QA | rewards-member |  |  | 21600 |  |  |  | [Dev][RD][Ecom] Sprint 6
Story | DEVRDECOM-40 | 29838 | [DEV][RD][Eco][BFF] Create API Endpoint for Email Verify Request | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 16/Aug/25 12:12 PM | 04/Sep/25 5:58 PM |  | 3 | BFF |  |  |  | 28800 |  |  |  | [Dev][RD][Ecom] Sprint 6
Story | DEVRDECOM-39 | 29837 | [DEV][RD][Eco][Rewards-Member] Create API Endpoint for Email Verify Request | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Ready To Test |  | 16/Aug/25 12:11 PM | 05/Sep/25 9:41 AM |  | 8 | No-QA | rewards-member |  |  | 86400 |  |  |  | [Dev][RD][Ecom] Sprint 6
Sub-task | DEVRDCT-196 | 29813 | [QA] Create Test Case Auto push coupon | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Tong Panuwat Sirirak | 70121:08c3e61f-6853-41cf-86ae-506a1b0d4ff9 | Medium | Done |  | 14/Aug/25 3:39 PM | 29/Aug/25 10:57 AM | [7 empty] | มาจาก Sprint 5 |  |  | [Dev][CT] Sprint 5 | [Dev][CT] Sprint 6
Sub-task | DEVRDCT-195 | 29811 | [QA] Update Test Case | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Tong Panuwat Sirirak | 70121:08c3e61f-6853-41cf-86ae-506a1b0d4ff9 | Medium | To Do |  | 14/Aug/25 3:37 PM | 25/Aug/25 5:12 PM | [7 empty] | มาจาก Sprint 5 |  |  | [Dev][CT] Sprint 5 | [Dev][CT] Sprint 6
Sub-task | DEVRDCT-193 | 29807 | [QA] Update Test Case | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Tong Panuwat Sirirak | 70121:08c3e61f-6853-41cf-86ae-506a1b0d4ff9 | Medium | To Do |  | 14/Aug/25 3:30 PM | 25/Aug/25 5:12 PM | [7 empty] | มาจาก Sprint 5 | 86400 |  | [Dev][CT] Sprint 5 | [Dev][CT] Sprint 6
Sub-task | DEVRDCT-190 | 29801 | [QA] Create Test Case Club Binding feed to user properties | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Tong Panuwat Sirirak | 70121:08c3e61f-6853-41cf-86ae-506a1b0d4ff9 | Medium | To Do |  | 14/Aug/25 3:29 PM | 21/Aug/25 1:22 PM | [7 empty] | มาจาก Sprint 5 |  |  | [Dev][CT] Sprint 4 | [Dev][CT] Sprint 4 | [Dev][CT] Sprint 5 | [Dev][CT] Sprint 6
Sub-task | DEVRDCT-186 | 29793 | [QA] Create Test Case Auto push coupon | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Tong Panuwat Sirirak | 70121:08c3e61f-6853-41cf-86ae-506a1b0d4ff9 | Medium | Done |  | 14/Aug/25 3:24 PM | 29/Aug/25 11:11 AM | [7 empty] | มาจาก Sprint 5 |  |  | [Dev][CT] Sprint 5 | [Dev][CT] Sprint 6
Sub-task | DEVRDCT-185 | 29789 | [QA] Create Test Case Auto push coupon | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Tong Panuwat Sirirak | 70121:08c3e61f-6853-41cf-86ae-506a1b0d4ff9 | Medium | Done |  | 14/Aug/25 3:20 PM | 29/Aug/25 10:59 AM | [7 empty] | มาจาก Sprint 5 |  |  | [Dev][CT] Sprint 5 | [Dev][CT] Sprint 6
Sub-task | DEVRDCT-184 | 29787 | [QA] Create Test Case Auto push coupon | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Tong Panuwat Sirirak | 70121:08c3e61f-6853-41cf-86ae-506a1b0d4ff9 | Medium | Done |  | 14/Aug/25 3:13 PM | 29/Aug/25 10:57 AM | [7 empty] | มาจาก Sprint 5 |  |  | [Dev][CT] Sprint 5 | [Dev][CT] Sprint 6
Sub-task | DEVRDCT-183 | 29785 | No required QA |  |  | Tong Panuwat Sirirak | 70121:08c3e61f-6853-41cf-86ae-506a1b0d4ff9 | Medium | Done |  | 14/Aug/25 3:12 PM | 01/Sep/25 10:11 AM | [7 empty] | มาจาก Sprint 5 | 28800 -> 14400 |  | [Dev][CT] Sprint 5 | [Dev][CT] Sprint 6
Sub-task | DEVRDECOM-37 | 29779 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Tong Panuwat Sirirak | 70121:08c3e61f-6853-41cf-86ae-506a1b0d4ff9 | Medium | Done |  | 14/Aug/25 3:04 PM | 26/Aug/25 3:53 PM | [7 empty] | มาจาก Sprint 5 | 7200 |  | [Dev][RD][Ecom]Sprint 5 | [Dev][RD][Ecom] Sprint 6
Sub-task | DEVRD20THB-18 | 29763 | [QA] Create Test Case Using/Use Coupon with 20THB Campaign Checking | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Tong Panuwat Sirirak | 70121:08c3e61f-6853-41cf-86ae-506a1b0d4ff9 | Medium | Done |  | 14/Aug/25 2:56 PM | 04/Sep/25 5:42 PM | [7 empty] | มาจาก Sprint 5 | 57600 -> 28800 |  | [Dev][RD][20THB] Sprint 6
Sub-task | DEVRD20THB-16 | 29759 | [QA] Create Test Case Redeem Rewards with 20THB Campaign Checking | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Tong Panuwat Sirirak | 70121:08c3e61f-6853-41cf-86ae-506a1b0d4ff9 | Medium | Done |  | 14/Aug/25 2:53 PM | 02/Sep/25 2:21 AM | [7 empty] | มาจาก Sprint 5 |  |  | [Dev][RD][20THB] Sprint 6
Story | DEVRDCT-180 | 29679 | [Dev][RD][Rewards API] Add is_auto_push_enabled field to responses | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 14/Aug/25 9:25 AM | 01/Sep/25 4:17 PM | 15/Aug/25 12:00 AM | 1 | No-QA |  |  |  | 0 | มาจาก Sprint 5 | 3600 | Ready To Test | [Dev][CT] Sprint 5 | [Dev][CT] Sprint 6
Story | DEVRD20THB-11 | 29606 | [Dev][RD][20THB][BFF] Enhance mark coupon as using and used | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Highest | Ready to Staging |  | 12/Aug/25 9:31 AM | 28/Aug/25 1:48 PM | 27/Aug/25 12:00 AM | 3 | BFF | change-request |  |  | 28800 | มาจาก Sprint 5 |  | To Do | [Dev][RD][20THB] Sprint 6
Story | DEVRDCT-177 | 29558 | [DEV][RD][HR-Solution] Initial feed user properties Club Binding with tier | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 11/Aug/25 9:53 AM | 05/Sep/25 10:59 AM |  | 3 |  |  |  |  | 14400 | มาจาก Sprint 5 | 28800 -> 14400 | In Progress | [Dev][CT] Sprint 5 | [Dev][CT] Sprint 6
Story | DEVRDECOM-32 | 29546 | [DEV][RD][Eco][BFF] Create API endpoint to retrieve a list of all Shopify shops | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | High | Done |  | 10/Aug/25 5:37 PM | 27/Aug/25 4:53 PM |  | 3 | BFF |  |  |  | 0 | มาจาก Sprint 5 | 28800 | Ready To Test | [Dev][RD][Ecom]Sprint 5 | [Dev][RD][Ecom] Sprint 6
Story | DEVRDCT-175 | 29542 | [Dev][RD][SSO User] Update Sign Up Event to include default values for the fields MSG_Email and MSG_SMS | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready to Staging |  | 09/Aug/25 4:04 PM | 05/Sep/25 10:39 AM |  | 2 | sso-user |  |  |  | 7200 | มาจาก Sprint 5 |  | To Do | [Dev][CT] Sprint 5 | [Dev][CT] Sprint 6
Story | DEVRDCT-174 | 29541 | [Dev][RD][SSO User] Close function update MSG_Email and MSG_SMS from consent 1 | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready to Staging |  | 09/Aug/25 2:46 PM | 05/Sep/25 10:39 AM |  | 1 | sso-user |  |  |  | 7200 | มาจาก Sprint 5 |  | To Do | [Dev][CT] Sprint 5 | [Dev][CT] Sprint 6
Story | RDAPS-151 | 29538 | [Dev][RD][SSO-Messenger] Change OTP SMS for thai language | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Low | Ready to Staging |  | 09/Aug/25 9:00 AM | 26/Aug/25 1:39 PM |  | 1 | sso-heimdall | sso-messenger |  |  | 7200 | มาจาก Sprint 5 |  | Ready to Staging | [Dev][All project]Sprint 5 | [Dev][All project]Sprint 6
Story | DEVRDCT-170 | 29513 | [Dev][RD] Implement sent email to queue for redeemed transaction | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 08/Aug/25 10:57 AM | 04/Sep/25 6:06 PM |  | 2 | redemption-api |  |  |  | 0 | มาจาก Sprint 5 | 14400 | In Review | [Dev][CT] Sprint 5 | [Dev][CT] Sprint 6
Story | DEVRD20THB-5 | 29493 | [DEV][RD][20THB][BFF] Redeem endpoint Integrate 20thb campaign checking | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Highest | Ready to Staging |  | 07/Aug/25 3:32 PM | 04/Sep/25 7:13 AM |  | 3 | BFF | change-request | rewards-api |  | 28800 | มาจาก Sprint 5 |  | To Do | [Dev][RD][20THB] Sprint 6
Sub-task | RDAPS-146 | 29359 | BFF |  |  | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 06/Aug/25 11:40 AM | 26/Aug/25 1:39 PM | [7 empty] | มาจาก Sprint 5 |  |  | [Dev][All project]Sprint 3 | [Dev][All project]Sprint 4 | [Dev][All project]Sprint 5 | [Dev][All project]Sprint 6
Sub-task | RDAPS-145 | 29357 | Redemption API | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 06/Aug/25 11:40 AM | 08/Aug/25 9:00 AM | [7 empty] | มาจาก Sprint 5 | 57600 |  | [Dev][All project]Sprint 3 | [Dev][All project]Sprint 4 | [Dev][All project]Sprint 5 | [Dev][All project]Sprint 6
Story | RDAPS-143 | 29343 | [Dev][RD][RR-Backoffice] Enhance e-commerce rewards url open type | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 06/Aug/25 8:44 AM | 26/Aug/25 2:38 PM | 20/Aug/25 12:00 AM | 2 |  |  |  |  | 0 | มาจาก Sprint 5 | 14400 | Ready to Staging | [Dev][All project]Sprint 5 | [Dev][All project]Sprint 6
Task | RDAPS-141 | 29339 | [Dev][RD][POC][SMS sub-account to support new sender IDs] | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Progress |  | 05/Aug/25 5:01 PM | 05/Sep/25 10:58 AM | [7 empty] | มาจาก Sprint 5 |  | To Do | [Dev][All project]Sprint 4 | [Dev][All project]Sprint 5 | [Dev][All project]Sprint 6
Story | DEVRDSUP-75 | 29257 | [SUP-106][SUB] : Export receipt due to BCC auto email incident #LOT2 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | In Review |  | 04/Aug/25 5:40 PM | 26/Aug/25 1:39 PM | 05/Aug/25 12:00 AM | [6 empty] | มาจาก Sprint 5 |  | In Review | [Dev][All project]Sprint 4 | [Dev][All project]Sprint 5 | [Dev][All project]Sprint 6
Story | DEVRDCT-169 | 29199 | [Dev][RD][RR-Scheduler Consumer] Implement Redemption Email to Send to Customer | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 04/Aug/25 1:06 PM | 05/Sep/25 10:59 AM |  | 3 | rr-scheduler-consumer |  |  |  | 0 | มาจาก Sprint 5 | 28800 | Ready to Staging | [Dev][CT] Sprint 5 | [Dev][CT] Sprint 6
Story | DEVRDCT-167 | 29192 | [Dev][RD][RDS] Send event to CT | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Ready to Staging |  | 04/Aug/25 12:49 PM | 05/Sep/25 10:20 AM |  | 5 | redemption-consumer |  |  |  | 72000 |  |  |  | [Dev][CT] Sprint 6
Sub-task | DEVRDECOM-27 | 28965 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 30/Jul/25 3:26 PM | 27/Aug/25 10:25 AM | [7 empty] | มาจาก Sprint 5 |  |  | [Dev][RD][Ecom]Sprint 5 | [Dev][RD][Ecom] Sprint 6
Sub-task | DEVRDECOM-26 | 28962 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 30/Jul/25 3:26 PM | 27/Aug/25 10:15 AM | [7 empty] | มาจาก Sprint 5 |  |  | [Dev][RD][Ecom]Sprint 5 | [Dev][RD][Ecom] Sprint 6
Story | RDAPS-129 | 28895 | [Dev][RD][Redemption Consumer] Enhance coupon codes allocation process | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 29/Jul/25 4:53 PM | 01/Sep/25 4:40 PM |  | 2 | No-QA | redemption-consumer |  |  | 14400 |  |  |  | [Dev][All project]Sprint 6
Story | DEVRDCT-154 | 28838 | [Dev][CleverTap][RD] Implement Club Binding feed to user properties to replace partner binding | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 29/Jul/25 9:33 AM | 01/Sep/25 10:10 AM | 14/Aug/25 12:00 AM | 8 | hr-solution |  |  |  | 0 | มาจาก Sprint 5 | 172800 | Ready To Test | [Dev][CT] Sprint 4 | [Dev][CT] Sprint 4 | [Dev][CT] Sprint 5 | [Dev][CT] Sprint 6
Story | DEVRDECOM-21 | 28836 | [DEV][RD][Eco][BFF] Create API Endpoint for Mobile App Auto-Login to Shopify | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | High | Done |  | 29/Jul/25 9:06 AM | 27/Aug/25 10:25 AM |  | 3 | BFF |  |  |  |  | มาจาก Sprint 5 |  | Ready To Test | [Dev][RD][Ecom]Sprint 5 | [Dev][RD][Ecom] Sprint 6
Story | RDAPS-126 | 28823 | [Dev][RD][Member Tier][Partner Loyalty] Enhance Check RR member by trader ID API | Art_narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 28/Jul/25 7:07 PM | 05/Sep/25 2:13 AM |  | 1 | No-QA | partner-loyalty |  |  | 0 | มาจาก Sprint 5 | 28800 | Ready to Staging | [Dev][All project]Sprint 5 | [Dev][All project]Sprint 6
Story | RDAPS-125 | 28816 | [Dev][RD][Member Tier][HR-Solution] Create get member tier endpoint | Art_narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 28/Jul/25 6:22 PM | 27/Aug/25 10:14 AM |  | 5 | hr-solution |  |  |  | 0 | มาจาก Sprint 5 | 115200 | Ready to Staging | [Dev][All project]Sprint 5 | [Dev][All project]Sprint 6
Story | RDAPS-123 | 28814 | [Dev][RD][Member Tier][Partner Loyalty] Enhance Check RR member by phone API | Art_narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 28/Jul/25 6:21 PM | 27/Aug/25 10:14 AM |  | 2 | No-QA | partner-loyalty |  |  | 0 | มาจาก Sprint 5 | 28800 | Ready to Staging | [Dev][All project]Sprint 5 | [Dev][All project]Sprint 6
Story | DEVRDCT-145 | 28778 | [Dev][RD][Redemption Consumer] Allocate coupons | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 25/Jul/25 5:56 PM | 04/Sep/25 6:06 PM | 20/Aug/25 12:00 AM | 5 | redemption-consumer |  |  |  | 0 | มาจาก Sprint 5 | 72000 | Ready To Test | [Dev][CT] Sprint 5 | [Dev][CT] Sprint 6
Story | DEVRDCT-142 | 28764 | [Dev][RD][Redemption] Create a Webhook API for Pushing Coupons | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 24/Jul/25 8:37 PM | 04/Sep/25 6:06 PM |  | 3 | redemption-api |  |  |  | 0 | มาจาก Sprint 5 | 57600 | Ready to Staging | [Dev][CT] Sprint 5 | [Dev][CT] Sprint 6
Story | RDAPS-115 | 28754 | [Dev][RD][Redemption API] Enhance the API for redeeming the product | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 24/Jul/25 7:35 PM | 01/Sep/25 4:40 PM |  | 3 | No-QA | redemption-api |  |  | 0 | มาจาก Sprint 5 | 28800 | Ready to Staging | [Dev][All project]Sprint 4 | [Dev][All project]Sprint 5 | [Dev][All project]Sprint 6
Story | RDAPS-114 | 28753 | [Dev][RD][BFF API] Enhance API to get coupon by ID new fields for e-commerce type | Pimonrath Jaiyen | 712020:40dd6981-cd18-4bfa-bf85-aa0e1e302e96 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 24/Jul/25 7:25 PM | 04/Sep/25 10:04 AM |  | 2 | BFF | [7 empty] | [Dev][All project]Sprint 6
Story | RDAPS-113 | 28752 | [Dev][RD][Rewards API] Enhance API to get product by ID, Slug to support new fields for e-commerce type | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 24/Jul/25 7:25 PM | 01/Sep/25 4:39 PM |  | 2 | No-QA | rewards-api |  |  | 0 | มาจาก Sprint 5 | 14400 | Ready to Staging | [Dev][All project]Sprint 4 | [Dev][All project]Sprint 5 | [Dev][All project]Sprint 6
Bug | DEVRDSUP-57 | 28728 | [SUP-57][SUB] Found Sub TXN Offline via Cash Generate empty receipt | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | UNDER VALIDATION |  | 24/Jul/25 2:17 PM | 28/Aug/25 9:53 AM | 28/Jul/25 12:00 AM | [6 empty] | มาจาก Sprint 5 |  |  | [Dev][All project]Sprint 4 | [Dev][All project]Sprint 5 | [Dev][All project]Sprint 6
Bug | DEVRDSUP-50 | 28559 | [SUP-72][SUB] Some SUB TXN showing coupons as refunded but the package is still active. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | UNDER VALIDATION |  | 21/Jul/25 12:10 PM | 28/Aug/25 9:57 AM | 04/Aug/25 12:00 AM | [6 empty] | มาจาก Sprint 5 |  |  | [Dev][All project]Sprint 4 | [Dev][All project]Sprint 5 | [Dev][All project]Sprint 6
Story | DEVRDSUP-46 | 28505 | [SUP-58]SUB :(Root cause analysis/long term solution) Receipt ID not found in RR Backoffice |  |  | Chawins | 62947f0c9c88e7006fb44996 | Medium | To Do |  | 18/Jul/25 11:01 AM | 26/Aug/25 1:39 PM | [7 empty] | มาจาก Sprint 5 |  | To Do | [Dev][All project]Sprint 5 | [Dev][All project]Sprint 6
Story | RDAPS-99 | 28480 | [Dev][RD][Redemption API] Pass BTS station info when issuing BTS pass for coupons with 'offline' sale channel | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 17/Jul/25 7:32 PM | 26/Aug/25 1:39 PM |  | 2 | redemption-api |  |  |  | 0 | มาจาก Sprint 5 | 21600 | Ready To Test | [Dev][All project]Sprint 3 | [Dev][All project]Sprint 4 | [Dev][All project]Sprint 5 | [Dev][All project]Sprint 6
Story | DEVRDSUP-45 | 28458 | [SUP-60][NBO][Rewards Alert List] - Requesting all exclusive partner rewards list with remaining code count. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | To Do |  | 16/Jul/25 5:58 PM | 26/Aug/25 1:39 PM | 18/Jul/25 12:00 AM |  | No-QA |  |  |  |  | มาจาก Sprint 5 |  | To Do | [Dev][All project]Sprint 4 | [Dev][All project]Sprint 5 | [Dev][All project]Sprint 6
Bug | DEVRDSUP-42 | 28359 | [SUP-66][HRsolution] Many point issue TXN are stuck at "distributing" causing sum of point issue to be incorrect in Point Issuing Transaction Report | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Resolved |  | 15/Jul/25 7:48 PM | 26/Aug/25 1:39 PM |  | 3 | [5 empty] | มาจาก Sprint 5 |  |  | [Dev][All project]Sprint 3 | [Dev][All project]Sprint 4 | [Dev][All project]Sprint 5 | [Dev][All project]Sprint 6
Bug | DEVRDCT-133 | 28344 | [S4][CT][User Properties] Enrichment detail of user properties NOT match to sso_backoffice | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Resolved |  | 15/Jul/25 4:58 PM | 25/Aug/25 5:08 PM | [7 empty] | มาจาก Sprint 5 |  |  | [Dev][CT] Sprint 2 | [Dev][CT] Sprint 3 | [Dev][CT] Sprint 4 | [Dev][CT] Sprint 4 | [Dev][CT] Sprint 5 | [Dev][CT] Sprint 6
Task | RDAPS-91 | 28194 | [Dev][RD][POC Archive Old Data in MongoDB/RLP DB/PL DB] | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 14/Jul/25 7:04 PM | 04/Sep/25 1:52 PM |  | 2 |  |  |  |  | 0 | มาจาก Sprint 5 | 1800 | In Review | [Dev][All project]Sprint 3 | [Dev][All project]Sprint 4 | [Dev][All project]Sprint 5 | [Dev][All project]Sprint 6
Bug | DEVRDSUP-35 | 27880 | [SUP-56][NBO][Rewards Alert List] - Rewards Alert List email not being sent | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Solution Proposal Pending |  | 09/Jul/25 1:46 PM | 28/Aug/25 9:50 AM | 14/Jul/25 12:00 AM | 3 | [5 empty] | มาจาก Sprint 5 |  |  | [Dev][All project]Sprint 4 | [Dev][All project]Sprint 6
Bug | DEVRDSUP-30 | 27748 | [SUP-50][SUB] Some receipts are not generated after SUB TXN is made. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | UNDER VALIDATION |  | 08/Jul/25 1:43 PM | 28/Aug/25 9:52 AM | 11/Jul/25 12:00 AM | [6 empty] | มาจาก Sprint 5 |  |  | [Dev][All project]Sprint 4 | [Dev][All project]Sprint 5 | [Dev][All project]Sprint 6
57600
14400
28800
14400
14400
7200
10800
28800
57600
86400
86400
57600
86400
28800
3600
28800
36000
57600
86400
108000
21600
3600
36000
7200
28800
3600
28800
28800
21600
28800
86400
3600
28800
28800
28800
7200
7200
7200
14400
28800
14400
28800
72000
14400
172800
28800
115200
28800
72000
57600
28800
14400
21600
1800
1800
3600
10800
21600
14400
57600
14400
28800
14400
14400
7200
10800
28800
57600
86400
86400
57600
86400
28800
3600
28800
36000
57600
86400
108000
21600
3600
36000
7200
28800
3600
28800
28800
21600
28800
86400
3600
28800
28800
28800
7200
7200
7200
14400
28800
14400
28800
72000
14400
172800
28800
115200
28800
72000
57600
28800
14400
21600
1800
1800
3600
10800
21600
14400
57600
14400
28800
14400
14400
7200
10800
28800
57600
86400
86400
57600
86400
28800
3600
28800
36000
57600
86400
108000
21600
3600
36000
7200
28800
3600
28800
28800
21600
28800
86400
3600
28800
28800
28800
7200
7200
7200
14400
28800
14400
28800
72000
14400
172800
28800
115200
28800
72000
57600
28800
14400
21600
1800
1800
3600
10800
21600
14400
57600
14400
28800
14400
14400
7200
10800
28800
57600
86400
86400
57600
86400
28800
3600
28800
36000
57600
86400
108000
21600
3600
36000
7200
28800
3600
28800
28800
21600
28800
86400
3600
28800
28800
28800
7200
7200
7200
14400
28800
14400
28800
72000
14400
172800
28800
115200
28800
72000
57600
28800
14400
21600
1800
1800
3600
10800
21600
14400
57600
14400
28800
14400
14400
7200
10800
28800
57600
86400
86400
57600
86400
28800
3600
28800
36000
57600
86400
108000
21600
3600
36000
7200
28800
3600
28800
28800
21600
28800
86400
3600
28800
28800
28800
7200
7200
7200
14400
28800
14400
28800
72000
14400
172800
28800
115200
28800
72000
57600
28800
14400
21600
1800
1800
3600
10800
21600
14400
57600
14400
28800
14400
14400
7200
10800
28800
57600
86400
86400
57600
86400
28800
3600
28800
36000
57600
86400
108000
21600
3600
36000
7200
28800
3600
28800
28800
21600
28800
86400
3600
28800
28800
28800
7200
7200
7200
14400
28800
14400
28800
72000
14400
172800
28800
115200
28800
72000
57600
28800
14400
21600
1800

## Summarize Sprint 5
Column 1 | Total Stories Point | Total Manhour | Point Done | Manhour Done | Note
11 Aug - 22 Aug
Dev Resource Available |  | 383.5
Meeting Planned |  | 150 |  |  | Ref
Additional Meeting |  | 82.75 |  |  | Ref
Deployment |  | 8 |  |  | 3 ครั้ง 1. 5 คน 2. 3 คน 3. 0 คน
Development Sprint Total | 153 | 203.5 | 73 | 105
Ad-hoc Mid Sprint | 4 | 4.5 | 2 | 1
Requirement changes after refinement? | - | - | - | -
Aek | 21 | 34.5 | 19 | 34.5
A | 18 | 35 | 17 | 33
Aom | 17 | 15 | 6 | 3.5
Zan | 13 | 5 | 1 | 1
Mai | 25 | 33 | 10 | 17
Mac | 12 | 33 | 3 | 8
Mos | 25 | 32 | 9 | 8
Jack | 14 | 16 | 8 | 0
Art | 8 | 0 | 0 | 0

## Sprint 5
Issue Type | Issue key | Issue id | Summary | Assignee | Assignee Id | Reporter | Reporter Id | Priority | Status | Resolution | Created | Updated | Due date | Custom field (Story Points) | Labels | Labels | Labels | Original estimate | Sprint Movement | Note
Sub-task | DEVRDCT-209 | 30115 | [QA] Test execution Club binding User Propreties CT | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | In Progress |  | 22/Aug/25 11:43 AM | 22/Aug/25 12:01 PM
Test Plan | DEVRDCT-206 | 30109 | [TP][Rewards] Auto-push Sprint5 |  |  | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 22/Aug/25 11:07 AM | 22/Aug/25 11:10 AM
Test Execution | DEVRDCT-207 | 30108 | [TX][Rewards] Auto-push Sprint5 |  |  | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Progress |  | 22/Aug/25 11:06 AM | 22/Aug/25 11:11 AM
Test Set | DEVRDCT-208 | 30107 | [TS][Rewards] Auto-push Sprint5 |  |  | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 22/Aug/25 11:04 AM | 22/Aug/25 11:10 AM
Test Execution | DEVRDADJ-23 | 30053 | [TX][Adjust] Sprint5 |  |  | Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | To Do |  | 21/Aug/25 3:36 PM | 21/Aug/25 3:36 PM
Test Plan | DEVRDADJ-22 | 30052 | [TP][Adjust] Sprint5 |  |  | Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | To Do |  | 21/Aug/25 3:36 PM | 21/Aug/25 3:36 PM
Test Set | DEVRDADJ-21 | 30051 | [TS][Adjust] Sprint5 |  |  | Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Medium | To Do |  | 21/Aug/25 3:35 PM | 21/Aug/25 3:35 PM
Sub-task | DEVRDCT-205 | 30024 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 21/Aug/25 1:53 PM | 21/Aug/25 1:53 PM
Sub-task | DEVRDCT-204 | 30008 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Progress |  | 21/Aug/25 11:12 AM | 22/Aug/25 11:10 AM
Sub-task | RDAPS-163 | 29980 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 20/Aug/25 12:14 PM | 20/Aug/25 12:14 PM
Sub-task | RDAPS-162 | 29978 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 20/Aug/25 12:14 PM | 20/Aug/25 4:12 PM
Sub-task | DEVRDECOM-47 | 29926 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 19/Aug/25 4:17 PM | 19/Aug/25 4:17 PM
Bug | DEVRDCT-200 | 29917 | [S3][Clever Tap][Event Login][Rabbit Connect] Fail reason of login fail event doesn't show on CleverTap | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Closed |  | 19/Aug/25 2:48 PM | 21/Aug/25 3:16 PM
Sub-task | DEVRDCT-199 | 29914 | [QA] Test execution Event feeding for Subscription purchase report #2 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 19/Aug/25 1:50 PM | 21/Aug/25 8:28 PM
Sub-task | DEVRD20THB-22 | 29862 | [QA] Test execution OTP verification page via SMS Warning Message | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 18/Aug/25 1:46 PM | 18/Aug/25 2:44 PM
Sub-task | DEVRD20THB-21 | 29860 | [QA] Test execution OTP verification page via Email Warning Message | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 18/Aug/25 1:44 PM | 18/Aug/25 2:44 PM
Story | DEVRDSUP-91 | 29836 | [SUP-129][SUB] CRM Case ID: #20250800015492 Request to initiate Package | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 15/Aug/25 4:07 PM | 15/Aug/25 4:13 PM |  | 1 | mid-sprint |  |  | 1800
Story | DEVRDSUP-90 | 29835 | [SUP-131][SUB] Request to generate cancel receipts for 30/07/2025 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Done |  | 15/Aug/25 3:54 PM | 15/Aug/25 4:36 PM | 15/Aug/25 12:00 AM | 1 | mid-sprint |  |  | 1800
Story | DEVRD20THB-20 | 29833 | [DEV][RD][20THB][RLP] Enhance get member by card | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 15/Aug/25 2:33 PM | 21/Aug/25 4:06 PM |  | 1 | No-QA |  |  | 1800
Story | DEVRDECOM-38 | 29831 | [DEV][RD][Eco][RR-Ecommerce-Shopify] Create function to generate multi pass token | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | High | Done |  | 15/Aug/25 11:49 AM | 22/Aug/25 10:02 AM |  | 3 | No-QA | rr-ecommerce-shopify |  | 28800
Sub-task | DEVRDCT-198 | 29824 | [QA] Test execution Login Event for LinePay binding | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 15/Aug/25 10:08 AM | 21/Aug/25 11:42 AM
Sub-task | DEVRDCT-197 | 29822 | [QA] Test execution Login Event On Rabbit Connect for RR Client | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 15/Aug/25 10:07 AM | 19/Aug/25 11:53 PM
Story | DEVRDSUP-88 | 29816 | [SUP-127]#20250700013779 Please mark used to [Line pay] BTS - Free* 3 Trips for Adult 2025 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | In Review |  | 14/Aug/25 5:51 PM | 15/Aug/25 4:14 PM |  | 2 | mid-sprint |  |  | 12600
Sub-task | DEVRDCT-196 | 29813 | [QA] Create Test Case Auto push coupon | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Tong Panuwat Sirirak | 70121:08c3e61f-6853-41cf-86ae-506a1b0d4ff9 | Medium | To Do |  | 14/Aug/25 3:39 PM | 22/Aug/25 10:57 AM
Sub-task | DEVRDCT-195 | 29811 | Create Test Case | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Tong Panuwat Sirirak | 70121:08c3e61f-6853-41cf-86ae-506a1b0d4ff9 | Medium | To Do |  | 14/Aug/25 3:37 PM | 14/Aug/25 3:37 PM
Sub-task | DEVRDCT-194 | 29809 | [QA] Update Test Case Event feeding for Subscription purchase report | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Tong Panuwat Sirirak | 70121:08c3e61f-6853-41cf-86ae-506a1b0d4ff9 | Medium | To Do |  | 14/Aug/25 3:30 PM | 19/Aug/25 1:50 PM
Sub-task | DEVRDCT-193 | 29807 | Create Test Case | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Tong Panuwat Sirirak | 70121:08c3e61f-6853-41cf-86ae-506a1b0d4ff9 | Medium | To Do |  | 14/Aug/25 3:30 PM | 14/Aug/25 3:30 PM
Sub-task | DEVRDCT-192 | 29805 | Create Test Case | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Tong Panuwat Sirirak | 70121:08c3e61f-6853-41cf-86ae-506a1b0d4ff9 | Medium | To Do |  | 14/Aug/25 3:29 PM | 14/Aug/25 3:29 PM
Sub-task | DEVRDCT-191 | 29803 | Create Test Case | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Tong Panuwat Sirirak | 70121:08c3e61f-6853-41cf-86ae-506a1b0d4ff9 | Medium | To Do |  | 14/Aug/25 3:29 PM | 14/Aug/25 3:29 PM
Sub-task | DEVRDCT-190 | 29801 | [QA] Create Test Case Club Binding feed to user properties | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Tong Panuwat Sirirak | 70121:08c3e61f-6853-41cf-86ae-506a1b0d4ff9 | Medium | To Do |  | 14/Aug/25 3:29 PM | 21/Aug/25 1:22 PM
Sub-task | DEVRDCT-189 | 29799 | [QA] Create Test Case Login Event for LinePay binding | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Tong Panuwat Sirirak | 70121:08c3e61f-6853-41cf-86ae-506a1b0d4ff9 | Medium | Done |  | 14/Aug/25 3:25 PM | 21/Aug/25 11:43 AM
Sub-task | DEVRDCT-188 | 29797 | [QA] Create Test Case Login Event On Rabbit Connect for RR Client | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Tong Panuwat Sirirak | 70121:08c3e61f-6853-41cf-86ae-506a1b0d4ff9 | Medium | In Progress |  | 14/Aug/25 3:25 PM | 19/Aug/25 3:43 PM
Sub-task | DEVRDCT-187 | 29795 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Tong Panuwat Sirirak | 70121:08c3e61f-6853-41cf-86ae-506a1b0d4ff9 | Medium | Done |  | 14/Aug/25 3:25 PM | 21/Aug/25 3:18 PM
Sub-task | DEVRDCT-186 | 29793 | [QA] Create Test Case Auto push coupon | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Tong Panuwat Sirirak | 70121:08c3e61f-6853-41cf-86ae-506a1b0d4ff9 | Medium | To Do |  | 14/Aug/25 3:24 PM | 22/Aug/25 10:57 AM
Sub-task | RDAPS-159 | 29791 | Create Test Case | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Tong Panuwat Sirirak | 70121:08c3e61f-6853-41cf-86ae-506a1b0d4ff9 | Medium | To Do |  | 14/Aug/25 3:20 PM | 14/Aug/25 3:20 PM
Sub-task | DEVRDCT-185 | 29789 | [QA] Create Test Case Auto push coupon | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Tong Panuwat Sirirak | 70121:08c3e61f-6853-41cf-86ae-506a1b0d4ff9 | Medium | To Do |  | 14/Aug/25 3:20 PM | 22/Aug/25 10:57 AM
Sub-task | DEVRDCT-184 | 29787 | [QA] Create Test Case Auto push coupon | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Tong Panuwat Sirirak | 70121:08c3e61f-6853-41cf-86ae-506a1b0d4ff9 | Medium | To Do |  | 14/Aug/25 3:13 PM | 22/Aug/25 10:57 AM
Sub-task | DEVRDCT-183 | 29785 | [QA] Create Test Case - Ask Aom how to test this story. | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Tong Panuwat Sirirak | 70121:08c3e61f-6853-41cf-86ae-506a1b0d4ff9 | Medium | To Do |  | 14/Aug/25 3:12 PM | 14/Aug/25 4:24 PM
Sub-task | DEVRDCT-182 | 29783 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Tong Panuwat Sirirak | 70121:08c3e61f-6853-41cf-86ae-506a1b0d4ff9 | Medium | Done |  | 14/Aug/25 3:12 PM | 21/Aug/25 1:29 PM
Sub-task | DEVRDCT-181 | 29781 | [QA] Create Test Case - Ask Aom if this story request test or not. | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Tong Panuwat Sirirak | 70121:08c3e61f-6853-41cf-86ae-506a1b0d4ff9 | Medium | To Do |  | 14/Aug/25 3:10 PM | 14/Aug/25 3:39 PM
Sub-task | DEVRDECOM-37 | 29779 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Tong Panuwat Sirirak | 70121:08c3e61f-6853-41cf-86ae-506a1b0d4ff9 | Medium | Done |  | 14/Aug/25 3:04 PM | 20/Aug/25 4:15 PM
Sub-task | DEVRDADJ-13 | 29771 | [QA] Create Test Case - Create script to re-generate adjust deep link | Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Tong Panuwat Sirirak | 70121:08c3e61f-6853-41cf-86ae-506a1b0d4ff9 | Medium | To Do |  | 14/Aug/25 3:00 PM | 19/Aug/25 3:51 PM
Sub-task | DEVRDADJ-12 | 29769 | [QA] Create Test Case - Replace Adjust instead of firebase for manual import static deep link | Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Tong Panuwat Sirirak | 70121:08c3e61f-6853-41cf-86ae-506a1b0d4ff9 | Medium | To Do |  | 14/Aug/25 2:59 PM | 14/Aug/25 3:57 PM
Sub-task | DEVRDADJ-11 | 29767 | [QA] Create Test Case - Replace Adjust instead of firebase for deep link API | Nattawat Kunsuwan | 712020:4890dbbb-ff54-4627-991f-17d632f8c60a | Tong Panuwat Sirirak | 70121:08c3e61f-6853-41cf-86ae-506a1b0d4ff9 | Medium | To Do |  | 14/Aug/25 2:58 PM | 14/Aug/25 3:57 PM
Sub-task | DEVRD20THB-19 | 29765 | Create Test Case | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Tong Panuwat Sirirak | 70121:08c3e61f-6853-41cf-86ae-506a1b0d4ff9 | Medium | To Do |  | 14/Aug/25 2:57 PM | 14/Aug/25 2:57 PM
Sub-task | DEVRD20THB-18 | 29763 | Create Test Case | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Tong Panuwat Sirirak | 70121:08c3e61f-6853-41cf-86ae-506a1b0d4ff9 | Medium | To Do |  | 14/Aug/25 2:56 PM | 14/Aug/25 2:56 PM
Sub-task | DEVRD20THB-17 | 29761 | Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Tong Panuwat Sirirak | 70121:08c3e61f-6853-41cf-86ae-506a1b0d4ff9 | Medium | To Do |  | 14/Aug/25 2:54 PM | 15/Aug/25 10:05 AM
Sub-task | DEVRD20THB-16 | 29759 | Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Tong Panuwat Sirirak | 70121:08c3e61f-6853-41cf-86ae-506a1b0d4ff9 | Medium | To Do |  | 14/Aug/25 2:53 PM | 14/Aug/25 2:53 PM
Sub-task | DEVRD20THB-15 | 29757 | Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Tong Panuwat Sirirak | 70121:08c3e61f-6853-41cf-86ae-506a1b0d4ff9 | Medium | To Do |  | 14/Aug/25 2:51 PM | 14/Aug/25 2:51 PM
Sub-task | DEVRD20THB-14 | 29755 | [QA] Create Test Case OTP verification page via SMS Warning Message | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Tong Panuwat Sirirak | 70121:08c3e61f-6853-41cf-86ae-506a1b0d4ff9 | Medium | Done |  | 14/Aug/25 2:49 PM | 18/Aug/25 2:42 PM
Sub-task | DEVRD20THB-13 | 29753 | [QA] Create Test case OTP verification page via Email Warning Message | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Tong Panuwat Sirirak | 70121:08c3e61f-6853-41cf-86ae-506a1b0d4ff9 | Medium | Done |  | 14/Aug/25 2:49 PM | 18/Aug/25 2:41 PM
Story | DEVRDCT-180 | 29679 | [Dev][RD][Rewards API] Add is_auto_push_enabled field to responses | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 14/Aug/25 9:25 AM | 22/Aug/25 10:46 AM | 15/Aug/25 12:00 AM | 1 | No-QA |  |  | 3600
Story | RDAPS-157 | 29669 | [Dev][RD][[ADHOC][VISIONARY] Reverse transaction and reset campaign] | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 13/Aug/25 4:41 PM | 15/Aug/25 10:05 AM |  | 1
Story | RDAPS-156 | 29665 | [Dev][RD][Redemption Consumer] Implement send email to message queue | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 13/Aug/25 3:51 PM | 22/Aug/25 9:32 AM | 20/Aug/25 12:00 AM | 3 |  |  |  | 14400
Bug | DEVRDCT-179 | 29655 | [S3][[CleverTap][LineOA] LineOA field on User properties NOT Update when update any event (unbind, Blocked Line Friend) | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Rejected |  | 13/Aug/25 12:49 PM | 13/Aug/25 5:56 PM
Story | DEVRD20THB-12 | 29649 | [Dev][RD][20THB][Rabbit Connect] Enhance OTP verification page via SMS | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Highest | Done |  | 13/Aug/25 10:30 AM | 21/Aug/25 7:41 PM | 13/Aug/25 12:00 AM | 1 | sso-heimdall |  |  | 3600
Story | DEVRD20THB-11 | 29606 | [Dev][RD][20THB][BFF] Enhance mark coupon as using and used | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | To Do |  | 12/Aug/25 9:31 AM | 22/Aug/25 9:31 AM |  | 3 | BFF | change-request |  | 28800
Bug | DEVRDCT-178 | 29561 | [S3][CleverTap][Production][RR Cloud ID] User Profile Properties 'RABBIT_WALLET_CARD_ADDED_DATETIME' show incorrect (Time +7) when user Add Wallet Card | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | High | Closed |  | 11/Aug/25 10:41 AM | 14/Aug/25 1:58 PM | 13/Aug/25 12:00 AM |  | cloudid
Story | DEVRDCT-177 | 29558 | [DEV][RD][HR-Solution] Initial feed user properties Club Binding with tier | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Progress |  | 11/Aug/25 9:53 AM | 22/Aug/25 10:05 AM |  | 3
Story | DEVRDECOM-32 | 29546 | [DEV][RD][Eco][BFF] Create API endpoint to retrieve a list of all Shopify shops | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | High | Ready To Test |  | 10/Aug/25 5:37 PM | 22/Aug/25 10:07 AM |  | 3 | BFF |  |  | 28800
Story | DEVRDECOM-30 | 29545 | [DEV][RD][Eco][Ecommerce-Shopify] Create API endpoint to retrieve a list of all Shopify shops | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | High | Done |  | 10/Aug/25 5:32 PM | 22/Aug/25 10:05 AM | 18/Aug/25 12:00 AM | 2 | ecommerce-shopify-api | No-QA |  | 14400
Story | RDAPS-152 | 29543 | [Dev][RD][Adhoc][PL] Fix Laravel Log Error Caused by Permission Conflict | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 10/Aug/25 9:20 AM | 19/Aug/25 3:38 PM | 15/Aug/25 12:00 AM | 1 | No-QA |  |  | 3600
Story | DEVRDCT-175 | 29542 | [TBC][Dev][RD][SSO User] Update Sign Up Event to include default values for the fields MSG_Email and MSG_SMS |  |  | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 09/Aug/25 4:04 PM | 21/Aug/25 7:41 PM |  |  | sso-user
Story | DEVRDCT-174 | 29541 | [Dev][RD][SSO User] Close function update MSG_Email and MSG_SMS from consent 1 |  |  | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 09/Aug/25 2:46 PM | 21/Aug/25 7:41 PM |  |  | sso-user
Story | DEVRDCT-173 | 29540 | [Dev][RD][Initial data] Initial Club Binding event to CleverTap |  |  | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 09/Aug/25 10:06 AM | 21/Aug/25 7:41 PM
Story | DEVRDCT-172 | 29539 | [Dev][RD][HR Solution] Develop Club Binding feed to event and user properties |  |  | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 09/Aug/25 10:02 AM | 21/Aug/25 7:41 PM |  |  | hr-solution
Story | RDAPS-151 | 29538 | [Dev][RD][SSO-Messenger] Change OTP SMS for thai language | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Low | Ready to Staging |  | 09/Aug/25 9:00 AM | 20/Aug/25 10:55 AM |  | 1 | sso-heimdall | sso-messenger |  | 7200
Story | RDAPS-150 | 29537 | [Dev][RD][VGI ONE] Remove WPP - Wavemaker duplicate deducted transaction | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 09/Aug/25 8:50 AM | 15/Aug/25 2:11 PM |  | 3 | vgi-one
Bug | DEVRDCT-171 | 29530 | [S4][CleverTap][User Properties][Rabbit Wallet Card] Remove Rabbit Wallet card but CleverTap don't clear User Properties data | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Closed |  | 08/Aug/25 5:55 PM | 14/Aug/25 4:29 PM
Story | DEVRDCT-170 | 29513 | [Dev][RD] Implement sent email to queue for redeemed transaction | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 08/Aug/25 10:57 AM | 18/Aug/25 2:46 PM |  | 2 | redemption-api
Story | DEVRD20THB-8 | 29509 | [DEV][RD][20THB][SA] Analyze task | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 08/Aug/25 10:08 AM | 14/Aug/25 2:50 PM |  |  | No-QA
Story | DEVRD20THB-7 | 29508 | [DEV][RD][20THB][BFF] Offline subscription Integrate 20thb campaign's member | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 08/Aug/25 9:57 AM | 22/Aug/25 10:03 AM | 18/Aug/25 12:00 AM | 3 | change-request |  |  | 28800
Story | DEVRD20THB-6 | 29507 | [DEV][RD][20THB][BFF] Checkout endpoint Integrate 20thb campaign's member checking | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 08/Aug/25 9:57 AM | 22/Aug/25 10:05 AM | 18/Aug/25 12:00 AM | 3 | change-request |  |  | 28800
Story | RDAPS-148 | 29506 | [Dev][RD][RR-Scheduler] Improve command to update coupons is expired | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Done |  | 08/Aug/25 8:51 AM | 15/Aug/25 2:39 PM |  | 2 | rr-scheduler
Story | DEVRD20THB-5 | 29493 | [DEV][RD][20THB][BFF] Redeem endpoint Integrate 20thb campaign checking | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 07/Aug/25 3:32 PM | 22/Aug/25 9:26 AM |  | 3 | BFF | change-request | rewards-api
Story | DEVRD20THB-4 | 29492 | [DEV][RD][20THB][BFF] Service Integrate Rabbit API and get parton campaign | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Done |  | 07/Aug/25 2:47 PM | 22/Aug/25 9:35 AM | 15/Aug/25 12:00 AM | 3 | change-request |  |  | 28800
Story | DEVRD20THB-3 | 29487 | [Dev][RD][20THB][Rabbit Connect] Enhance OTP verification page via Email | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Highest | Done |  | 07/Aug/25 1:15 PM | 21/Aug/25 7:41 PM | 13/Aug/25 12:00 AM | 2 | sso-heimdall |  |  | 14400
Sub-task | RDAPS-146 | 29359 | BFF |  |  | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 06/Aug/25 11:40 AM | 12/Aug/25 11:11 AM | [6 empty] | มาจาก Sprint 4
Sub-task | RDAPS-145 | 29357 | Redemption API | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 06/Aug/25 11:40 AM | 08/Aug/25 9:00 AM | [6 empty] | มาจาก Sprint 4
Story | RDAPS-144 | 29345 | [Dev][RD][API Spec] Update APIs spec for BFF | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 06/Aug/25 8:45 AM | 18/Aug/25 9:19 AM |  | 1 | No-QA
Story | RDAPS-143 | 29343 | [Dev][RD][RR-Backoffice] Enhance e-commerce rewards url open type | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 06/Aug/25 8:44 AM | 21/Aug/25 3:33 PM | 20/Aug/25 12:00 AM | 2 |  |  |  | 14400
Task | RDAPS-141 | 29339 | [Dev][RD][POC][SMS sub-account to support new sender IDs] | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 05/Aug/25 5:01 PM | 12/Aug/25 11:11 AM | [6 empty] | มาจาก Sprint 4
Story | DEVRDSUP-75 | 29257 | [SUP-106][SUB] : Export receipt due to BCC auto email incident #LOT2 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | In Review |  | 04/Aug/25 5:40 PM | 13/Aug/25 2:49 PM | 05/Aug/25 12:00 AM | [5 empty] | มาจาก Sprint 4
Task | RDAPS-137 | 29214 | [Dev][RD][STG] Data migration for existing rewards | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 04/Aug/25 4:00 PM | 18/Aug/25 9:19 AM |  | 1 | No-QA | rewards-db |  | 1800
Story | DEVRDCT-169 | 29199 | [Dev][RD][RR-Scheduler Consumer] Implement Redemption Email to Send to Customer | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 04/Aug/25 1:06 PM | 21/Aug/25 11:57 PM |  | 3 | rr-scheduler-consumer
Story | DEVRDCT-168 | 29194 | [Dev][RD][RR-Backoffice] Algolia | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 04/Aug/25 12:50 PM | 21/Aug/25 3:20 PM |  | 1 | rr-backoffice
Sub-task | DEVRDCT-165 | 29162 | [QA] Test execution (SSO-User) Enhance User Property | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 04/Aug/25 10:12 AM | 15/Aug/25 10:01 AM | [6 empty] | มาจาก Sprint 4
Sub-task | DEVRDECOM-27 | 28965 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 30/Jul/25 3:26 PM | 14/Aug/25 5:42 PM
Sub-task | DEVRDECOM-26 | 28962 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 30/Jul/25 3:26 PM | 19/Aug/25 11:25 AM
Story | RDNDA-2 | 28910 | [Dev][RD] Get table of LP and LOA data] | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 30/Jul/25 9:21 AM | 21/Aug/25 4:10 PM |  | 5 | No-QA |  |  | 43200 | มาจาก Sprint 4
Story | DEVRDCT-154 | 28838 | [Dev][CleverTap][RD] Implement Club Binding feed to user properties to replace partner binding | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready To Test |  | 29/Jul/25 9:33 AM | 21/Aug/25 7:41 PM | 14/Aug/25 12:00 AM | 8 | hr-solution |  |  | 86400 | มาจาก Sprint 4 | 172800 -> 86400
Story | DEVRDECOM-21 | 28836 | [DEV][RD][Eco][BFF] Create API Endpoint for Mobile App Auto-Login to Shopify | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | High | Ready To Test |  | 29/Jul/25 9:06 AM | 22/Aug/25 10:05 AM |  | 3 | BFF
Story | DEVRDECOM-20 | 28829 | [DEV][RD][Eco][RR-Ecommerce-Shopify] Create API Endpoint for Mobile App Auto-Login to Shopify | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | High | Done |  | 28/Jul/25 9:45 PM | 22/Aug/25 10:05 AM |  | 3 | No-QA | rr-ecommerce-shopify
Story | DEVRDECOM-19 | 28828 | [DEV][RD][Eco][RR-Ecommerce-Shopify] Create Callback Endpoint and Generate Multipass Token | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | High | Done |  | 28/Jul/25 9:17 PM | 22/Aug/25 10:05 AM | 21/Aug/25 12:00 AM | 3 | No-QA | rr-ecommerce-shopify |  | 28800
Story | DEVRDECOM-18 | 28827 | [DEV][RD][Eco][RR-Ecommerce-Shopify] Create Endpoint for Rabbit Connect Login/Register Link | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | High | Done |  | 28/Jul/25 8:28 PM | 22/Aug/25 10:05 AM | 20/Aug/25 12:00 AM | 5 | No-QA | rr-ecommerce-shopify |  | 57600
Story | DEVRDCT-153 | 28826 | [Dev][CleverTap][RD] Implement The Data Transformation Module | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 28/Jul/25 7:30 PM | 18/Aug/25 5:13 PM |  | 5 | CleverTap | No-QA |  | 0 | มาจาก Sprint 4 | 86400
Story | DEVRDECOM-17 | 28825 | [DEV][RD][Eco][SA] Prepare configuration data for shopify_shops | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 28/Jul/25 7:29 PM | 22/Aug/25 10:05 AM | 13/Aug/25 12:00 AM | 1 | No-QA |  |  | 3600
Story | RDAPS-126 | 28823 | [Dev][RD][Member Tier][Partner Loyalty] Enhance Check RR member by trader ID API | Art_narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 28/Jul/25 7:07 PM | 22/Aug/25 10:13 AM |  | 1 | partner-loyalty
Story | RDAPS-125 | 28816 | [Dev][RD][Member Tier][HR-Solution] Create get member tier endpoint | Art_narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 28/Jul/25 6:22 PM | 20/Aug/25 6:19 PM |  | 5 | hr-solution
Story | RDAPS-123 | 28814 | [Dev][RD][Member Tier][Partner Loyalty] Enhance Check RR member by phone API | Art_narupontp | 712020:91749b74-687b-4bc7-86d9-f95cfa61b20e | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 28/Jul/25 6:21 PM | 22/Aug/25 10:13 AM |  | 2 | partner-loyalty
Story | DEVRDADJ-8 | 28811 | [Dev][Adjust][Deeplink][Link Notify] Replace Adjust instead of firebase for manual import static deeplink | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 28/Jul/25 5:26 PM | 22/Aug/25 12:04 PM |  | 3 | link-notify |  |  | 14400 | มาจาก Sprint 4 | 28800 -> 14400
Story | DEVRDCT-152 | 28810 | [DEV][CleverTap][RD][SSO-User] Enhance User Property | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 28/Jul/25 4:17 PM | 14/Aug/25 4:59 PM | 01/Aug/25 12:00 AM | 2 | sso-user |  |  | 0 | มาจาก Sprint 4 | 7200
Story | DEVRDCT-150 | 28808 | [DEV][RD][CleverTap] Implement Login Event for LinePay binding | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 28/Jul/25 3:54 PM | 21/Aug/25 7:41 PM | 08/Aug/25 12:00 AM | 5 | rlp-middleware |  |  | 28800 | มาจาก Sprint 4 | 57600 -> 28800
Story | DEVRDECOM-13 | 28806 | [DEV][RD][Eco][SA] Set up OAuth Clients for Rabbit Connect for Shopify Login/Registration | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 28/Jul/25 12:55 PM | 22/Aug/25 10:05 AM | 13/Aug/25 12:00 AM | 1 | No-QA |  |  | 3600
Story | DEVRDCT-149 | 28793 | [DEV][RD][CleverTap] Implement Login Event On Rabbit Connect for RR Client | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 28/Jul/25 12:27 AM | 21/Aug/25 7:41 PM | 04/Aug/25 12:00 AM | 5 | sso-heimdall |  |  | 0 | มาจาก Sprint 4 | 86400
Story | RDNDA-1 | 28784 | [Dev][RD][LinePay & LineOA][ETL to New Datamart] | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 27/Jul/25 1:42 PM | 21/Aug/25 4:10 PM |  | 5 | No-QA |  |  | 43200 | มาจาก Sprint 4
Story | DEVRDCT-145 | 28778 | [Dev][RD][Redemption Consumer] Allocate coupons | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 25/Jul/25 5:56 PM | 22/Aug/25 9:31 AM | 20/Aug/25 12:00 AM | 5 | redemption-consumer |  |  | 72000
Story | DEVRDCT-142 | 28764 | [Dev][RD][Redemption] Create a Webhook API for Pushing Coupons | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 24/Jul/25 8:37 PM | 22/Aug/25 9:20 AM |  | 3 | redemption-api |  |  | 57600
Story | DEVRDCT-141 | 28763 | [Dev][RD][DB] Create database migration | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 24/Jul/25 8:28 PM | 18/Aug/25 2:45 PM |  | 1 | rewards-db |  |  | 7200
Story | DEVRDCT-140 | 28762 | [Dev][RD][RR-Backoffice] Enhance the Rewards Setting Menu to Support Auto Push Coupon Toggle | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 24/Jul/25 8:28 PM | 21/Aug/25 1:52 PM | 19/Aug/25 12:00 AM | 2 | rr-backoffice |  |  | 14400
Story | RDAPS-115 | 28754 | [Dev][RD][Redemption API] Enhance the API for redeeming the product | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 24/Jul/25 7:35 PM | 13/Aug/25 1:33 PM |  | 3 | No-QA | redemption-api |  | 0 | มาจาก Sprint 4 | 28800
Story | RDAPS-113 | 28752 | [Dev][RD][Rewards API] Enhance API to get product by ID, Slug to support new fields for e-commerce type | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 24/Jul/25 7:25 PM | 13/Aug/25 1:33 PM |  | 2 | No-QA | rewards-api |  | 0 | มาจาก Sprint 4 | 14400
Bug | DEVRDSUP-57 | 28728 | [SUP-57][SUB] Found Sub TXN Offline via Cash Generate empty receipt | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | UNDER VALIDATION |  | 24/Jul/25 2:17 PM | 12/Aug/25 11:11 AM | [6 empty] | มาจาก Sprint 4
Task | DEVRDADJ-6 | 28661 | [Dev][Adjust][Deeplink][Link-Notify] Create script to re-generate adjust deeplink | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 23/Jul/25 1:40 PM | 21/Aug/25 7:41 PM | 15/Aug/25 12:00 AM | 3 | link-notify
Story | DEVRDADJ-5 | 28660 | [Dev][Adjust][Deeplink][Link Notify] Replace Adjust instead of firebase for deeplink API | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 23/Jul/25 1:40 PM | 21/Aug/25 7:41 PM | 05/Aug/25 12:00 AM | 5 |  |  |  | 0 | มาจาก Sprint 4 | 57600
Bug | DEVRDSUP-50 | 28559 | [SUP-72][SUB] Some SUB TXN showing coupons as refunded but the package is still active. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | UNDER VALIDATION |  | 21/Jul/25 12:10 PM | 15/Aug/25 12:10 PM | [6 empty] | มาจาก Sprint 4
Story | DEVRDSUP-46 | 28505 | [SUP-58]SUB :(Root cause analysis/long term solution) Receipt ID not found in RR Backoffice |  |  | Chawins | 62947f0c9c88e7006fb44996 | Medium | To Do |  | 18/Jul/25 11:01 AM | 13/Aug/25 4:34 PM
Story | RDAPS-99 | 28480 | [Dev][RD][Redemption API] Pass BTS station info when issuing BTS pass for coupons with 'offline' sale channel | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 17/Jul/25 7:32 PM | 12/Aug/25 11:11 AM |  | 2 | redemption-api |  |  | 0 | มาจาก Sprint 4 | 21600
Story | DEVRDSUP-45 | 28458 | [SUP-60][NBO][Rewards Alert List] - Requesting all exclusive partner rewards list with remaining code count. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | To Do |  | 16/Jul/25 5:58 PM | 15/Aug/25 11:53 AM | 18/Jul/25 12:00 AM |  | No-QA |  |  |  | มาจาก Sprint 4
Bug | DEVRDSUP-42 | 28359 | [SUP-66][HRsolution] Many point issue TXN are stuck at "distributing" causing sum of point issue to be incorrect in Point Issuing Transaction Report | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Resolved |  | 15/Jul/25 7:48 PM | 12/Aug/25 11:11 AM |  | 3 |  |  |  |  | มาจาก Sprint 4
Bug | DEVRDCT-133 | 28344 | [S4][CT][User Properties] Enrichment detail of user properties NOT match to sso_backoffice | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Resolved |  | 15/Jul/25 4:58 PM | 14/Aug/25 11:00 AM | [6 empty] | มาจาก Sprint 4
Task | RDAPS-91 | 28194 | [Dev][RD][POC Archive Old Data in MongoDB/RLP DB/PL DB] | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Review |  | 14/Jul/25 7:04 PM | 12/Aug/25 11:11 AM |  | 2 |  |  |  | 0 | มาจาก Sprint 4 | 1800
Task | DEVRDCT-124 | 28170 | [Dev][RD][CleverTap][Import Initial data of LineOA as of 1June - 13July] | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 14/Jul/25 3:06 PM | 22/Aug/25 10:04 AM |  | 1 | No-QA |  |  | 3600 | มาจาก Sprint 4
Story | DEVRDCT-121 | 28099 | [DEV][CLEVERTAP][RD] Implement Event feeding for Subscription purchase report #2 | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 12/Jul/25 8:52 AM | 21/Aug/25 8:29 PM |  | 3 | order-consumer |  |  | 0 | มาจาก Sprint 4 | 14400
Bug | DEVRDSUP-35 | 27880 | [SUP-56][NBO][Rewards Alert List] - Rewards Alert List email not being sent | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | ACCEPTED |  | 09/Jul/25 1:46 PM | 22/Aug/25 10:03 AM | [6 empty] | มาจาก Sprint 4
Bug | DEVRDSUP-30 | 27748 | [SUP-50][SUB] Some receipts are not generated after SUB TXN is made. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | UNDER VALIDATION |  | 08/Jul/25 1:43 PM | 12/Aug/25 11:11 AM | [6 empty] | มาจาก Sprint 4

## Summarize Sprint 4
Column 1 | Total Stories Point | Total Manhour | Point Done | Manhour Done | Note
29 July - 8 Aug
Dev Resource Available |  | 325
Meeting Planned |  | 146 |  |  | Ref
Additional Meeting |  | 17.5 |  |  | Ref
Deployment |  | 1 |  |  | 1 ครั้ง 1. 1 คน
Development Sprint Total | 186 | 282.08 | 81 | 86.08
Ad-hoc Mid Sprint | - | - | - | -
Requirement changes after refinement? | - | - | - | -
Aek | 27 | 50.5 | 8 | 8.5
A | 31 | 56 | 20 | 28
Aom | 26 | 31.33 | 18 | 31.33
Zan | 22 | 30.25 | 9 | 6.25
Mai | 22 | 34 | 10 | 0
Mac | 20 | 32 | 8 | 0
Mos | 24 | 24 | 5 | 12
Jack | 8 | 24 | 0 | 0

## Summarize Sprint 3
Column 1 | Total Stories Point | Total Manhour | Point Done | Manhour Done | Note
14 July - 25 July
Dev Resource Available |  | 442
Meeting Planned |  | 176.5 |  |  | Ref
Additional Meeting |  | 56.5 |  |  | Ref
Deployment |  | 10 |  |  | 2 ครั้ง 1. 4 คน 2. 2 คน
Development Sprint Total | 132 | 406 | 63 | 178
Ad-hoc Mid Sprint | 12 | 24 | 12 | 24 | 11 items
Requirement changes after refinement? |  |  |  |  | 2 items
Aek | 20 | 58 | 18 | 54
A | 11 | 40 | 0 | 0
Aom | 25 | 70 | 17 | 50
Zan | 8 | 30 | 2 | 4
Mai | 12 | 38 | 7 | 14
Mac | 19 | 60 | 0 | 0
First | 12 | 28 | 7 | 16
Mos | 8 | 18 | 0 | 0
Jack | 13 | 56 | 8 | 32
John | 4 | 8 | 4 | 8
*** หมายเหตุ คำนวณ Manhour จากตารางนี้
Story Point | 1 | 2 | 3 | 5 | 8
Manhour | ~<=2 | ~4 | ~6-8 | ~2-3d | 4d+

## Summarize Sprint 2
Column 1 | Total Stories Point | Total Manhour | Point Done | Manhour Done | Note
30 June - 11 July
Dev Resource Available |  | 435.5
Meeting Planned
Additional Meeting |  | 51.55
Deployment |  | 21
Development Sprint Total | 126 | 404 | 45 | 128
Ad-hoc Mid Sprint |  | 5 (10) |  |  | Reference
Requirement changes after refinement? |  | 1 (2) |  |  | Reference
Aek | 16 | 34 | 13 | 26
A | 13 | 44 | 0 | 0
Aom | 21 | 64 | 16 | 52
Zan | 17 | 44 | 5 | 12
Preaw | 6 | 16 | 0 | 0
Mai | 10 | 48 | 0 | 0
Mac | 10 | 48 | 0 | 0
First | 11 | 38 | 2 | 4
Mos | 7 | 18 | 0 | 0
Jack | 8 | 32 | 8 | 32
John | 7 | 18 | 1 | 2
*** หมายเหตุ คำนวณ Manhour จากตารางนี้
Story Point | 1 | 2 | 3 | 5 | 8
Manhour | ~<=2 | ~4 | ~6-8 | ~2-3d | 4d+

## Summarize Sprint 1
Column 1 | Total Stories Point | Total Manhour | Point Done | Manhour Done | Note
16 June - 27 June
Dev Resource Available |  | 554.25
Meeting Planned
Additional Meeting |  | 25.9
Deployment |  | 28 |  |  | กี่ครั้ง กี่คน
Development Sprint Total | 157 | 514 | 152 | 490
Ad-hoc Mid Sprint |  | 20 (68) |  |  | Reference
Requirement changes after refinement? |  | 1 (2) |  |  | Reference
Aek | 38 | 108 | 38 | 108
A | 13 | 56 | 13 | 56
Aom | 9 | 20 | 9 | 20
Zan | 24 | 76 | 24 | 76
Preaw | 10 | 26 | 10 | 26
Mai | 9 | 24 | 9 | 24
Mac | 13 | 56 | 13 | 56
First | 10 | 48 | 5 | 24
Mos | 4 | 8 | 4 | 8
Jack | 8 | 32 | 8 | 32
John | 6 | 16 | 6 | 16
*** หมายเหตุ คำนวณ Manhour จากตารางนี้
Story Point | 1 | 2 | 3 | 5 | 8
Manhour | ~<=2 | ~4 | ~6-8 | ~2-3d | 4d+

## Sprint 4
Issue Type | Issue key | Issue id | Summary | Assignee | Assignee Id | Reporter | Reporter Id | Priority | Status | Resolution | Created | Updated | Due date | Custom field (Story Points) | Labels | Labels | Original estimate | Sprint Movement | Note
Task | RDAPS-149 | 29515 | [Dev][RD][PROD] Manual update coupons status to expired | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 08/Aug/25 11:07 AM | 08/Aug/25 11:11 AM |  | 1 | mid-sprint | redemption-db
Sub-task | DEVRDSUP-82 | 29482 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 07/Aug/25 10:08 AM | 08/Aug/25 9:14 AM
Sub-task | DEVRDSUP-81 | 29480 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 07/Aug/25 10:03 AM | 07/Aug/25 3:45 PM
Sub-task | DEVRDSUP-80 | 29478 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 07/Aug/25 10:03 AM | 07/Aug/25 1:37 PM
Task | RDAPS-147 | 29447 | [Dev][RD] Rerun Redemption ETL | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 06/Aug/25 4:39 PM | 08/Aug/25 11:14 AM |  | 2 | mid-sprint |  | 120
Bug | DEVRDSUP-79 | 29445 | [S2] Unable to active reward when the current time is not met the reward end date | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 06/Aug/25 4:20 PM | 08/Aug/25 11:22 AM
Sub-task | RDAPS-146 | 29359 | BFF |  |  | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Review |  | 06/Aug/25 11:40 AM | 07/Aug/25 10:22 AM
Sub-task | RDAPS-145 | 29357 | Redemption API | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 06/Aug/25 11:40 AM | 08/Aug/25 9:00 AM
Story | RDAPS-142 | 29340 | [Dev][RD][SA] Analyze & split dev tasks for Rewards E-Commerce | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 05/Aug/25 7:42 PM | 08/Aug/25 9:01 AM |  | 2 |  |  | 12600
Task | RDAPS-141 | 29339 | [Dev][RD][POC][SMS sub-account to support new sender IDs] | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 05/Aug/25 5:01 PM | 05/Aug/25 5:02 PM
Bug | RDLOA-187 | 29319 | [S4][LineOA] Message respond incorrect when bidning failed case | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Rejected |  | 05/Aug/25 2:01 PM | 05/Aug/25 3:33 PM
Sub-task | RDLOA-186 | 29318 | [QA] Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 05/Aug/25 1:46 PM | 05/Aug/25 3:35 PM
Sub-task | RDLOA-185 | 29314 | [QA] Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 05/Aug/25 1:33 PM | 05/Aug/25 2:20 PM
Bug | RDAPS-140 | 29300 | [S3][Rewards] eCommerce reward inline error and de-select value are not work properly | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 05/Aug/25 10:43 AM | 06/Aug/25 10:14 AM
Story | RDNDA-4 | 29270 | [DEV][RD][DevOps] Create DB User for RLP and SSO on Prod | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Progress |  | 05/Aug/25 9:27 AM | 05/Aug/25 9:33 AM |  | 1
Story | RDNDA-3 | 29266 | [DEV][RD][SA] Analyze and get requirement | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Progress |  | 05/Aug/25 7:00 AM | 08/Aug/25 9:09 AM |  | 1 |  |  | 7200
Story | DEVRD20THB-2 | 29265 | [Dev][RD][SA] Impact and risk assessment | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 05/Aug/25 6:38 AM | 08/Aug/25 9:05 AM |  | 1 |  |  | 5400
Bug | DEVRDSUP-77 | 29264 | [SUP-109][SUB] Can't active a package, NBO says "Package Items must be Active" | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Closed |  | 05/Aug/25 2:07 AM | 08/Aug/25 11:22 AM | 06/Aug/25 12:00 AM
Story | DEVRDSUP-75 | 29257 | [SUP-106][SUB] : Export receipt due to BCC auto email incident #LOT2 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | In Review |  | 04/Aug/25 5:40 PM | 08/Aug/25 9:13 AM | 05/Aug/25 12:00 AM
Sub-task | RDLOA-184 | 29256 | [QA] Test Execution |  |  | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 04/Aug/25 4:58 PM | 04/Aug/25 5:00 PM
Sub-task | RDLOA-183 | 29254 | [QA] Test Execution |  |  | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 04/Aug/25 4:56 PM | 04/Aug/25 4:56 PM
Task | DEVRDADJ-10 | 29209 | [SA][Meeting] Clarify Adjust deeplink | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 04/Aug/25 3:02 PM | 05/Aug/25 9:59 AM
Sub-task | RDAPS-136 | 29206 | [QA] Test execution Default credit card (RR app UAT) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 04/Aug/25 2:42 PM | 05/Aug/25 3:14 PM
Task | RDAPS-135 | 29175 | [Dev][RD] Manual Rerun: Fix Missing Data in Redemption ETL | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Highest | Done |  | 04/Aug/25 10:40 AM | 08/Aug/25 11:14 AM |  | 1 | mid-sprint |  | 180
Sub-task | DEVRDCT-166 | 29164 | [QA] Test execution | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 04/Aug/25 10:15 AM | 04/Aug/25 10:15 AM
Sub-task | DEVRDCT-165 | 29162 | [QA] Test execution | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 04/Aug/25 10:12 AM | 04/Aug/25 10:12 AM
Story | DEVRDCT-164 | 29155 | [Dev][RD][SA] Analyze & split dev tasks for Auto push coupons | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 04/Aug/25 9:02 AM | 06/Aug/25 1:58 PM |  | 5
Bug | DEVRDSUP-69 | 29043 | [SUP-85]#20250700013935 ลูกค้าซื้อแพ็กเกจ แต่พบปัญหาวันหมดอายุแพ็กเกจขึ้นไม่ตรงกับวันหมดอายุคูปองข้างในแพ็กเกจ | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Closed |  | 31/Jul/25 6:42 PM | 08/Aug/25 11:22 AM |  |  | sub
Sub-task | DEVRDCT-163 | 29028 | [QA] Test execution add rabbit wallet card |  |  | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 31/Jul/25 11:03 AM | 31/Jul/25 11:03 AM
Sub-task | DEVRDCT-162 | 29025 | [QA] Create test case Add Card | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | In Progress |  | 31/Jul/25 11:02 AM | 01/Aug/25 10:09 AM
Sub-task | DEVRDCT-161 | 29022 | [QA] Test execution add rabbit Line pay card |  |  | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 31/Jul/25 11:01 AM | 31/Jul/25 11:01 AM
Sub-task | DEVRDCT-160 | 29019 | [QA] Create test case Add Card | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | In Progress |  | 31/Jul/25 11:01 AM | 01/Aug/25 10:09 AM
Sub-task | DEVRDCT-159 | 29016 | [QA] Test execution add rabbit card |  |  | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | In Progress |  | 31/Jul/25 11:00 AM | 08/Aug/25 10:58 AM
Sub-task | DEVRDCT-158 | 29013 | [QA] Create test case Add Card | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 31/Jul/25 10:59 AM | 08/Aug/25 10:58 AM
Story | DEVRDSUP-68 | 28980 | [SUP-97][SUB] Request to generate receipt for SUB TXN 30/07/2025 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Done |  | 30/Jul/25 6:19 PM | 31/Jul/25 1:13 PM |  |  | sub
Sub-task | RDAPS-132 | 28959 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 30/Jul/25 3:26 PM | 06/Aug/25 12:56 PM
Sub-task | RDAPS-131 | 28956 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 30/Jul/25 3:26 PM | 04/Aug/25 10:59 AM
Sub-task | RDAPS-130 | 28953 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 30/Jul/25 3:25 PM | 04/Aug/25 11:35 AM
Sub-task | DEVRDSUP-65 | 28950 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 30/Jul/25 3:24 PM | 31/Jul/25 11:03 AM
Task | DEVRDSUP-64 | 28947 | [Dev][RD] Investigate upload coupon code | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 30/Jul/25 1:51 PM | 04/Aug/25 9:37 AM |  | 2 |  |  | 18000
Task | DEVRDADJ-9 | 28946 | [Dev][Adjust][RD][SA] Adjust : Auto Generate Deeplink Solution Discussion & Line OA | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 30/Jul/25 1:47 PM | 05/Aug/25 9:59 AM |  | 1 |  |  | 4500
Story | RDNDA-2 | 28910 | [Dev][RD] Get table of LP and LOA data] | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Progress |  | 30/Jul/25 9:21 AM | 08/Aug/25 9:09 AM |  | 3 |  |  | 21600
Bug | RDAPS-128 | 28894 | [S2][Campaign BU allocation] Campaign BU allocation is not working properly | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | High | Closed |  | 29/Jul/25 3:57 PM | 08/Aug/25 9:52 AM |  |  | hr-solution
Sub-task | DEVRDCT-157 | 28853 | [QA] Test execution | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | In Progress |  | 29/Jul/25 2:45 PM | 05/Aug/25 3:50 PM
Story | RDAPS-127 | 28846 | [Dev][RD][Order] Implement default credit card feature | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 29/Jul/25 12:56 PM | 06/Aug/25 9:56 AM |  | 8 | order-api |  | 93600
Story | DEVRDSUP-61 | 28842 | [SUP-90][SUB] : Re-Generate receipt due to BCC auto email incident | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Done |  | 29/Jul/25 10:55 AM | 04/Aug/25 9:35 AM | 31/Jul/25 12:00 AM | 3 | No-QA |  | 28800
Story | DEVRDCT-156 | 28840 | [Dev][CleverTap][RD][RR Cloud ID] Implement Add Card Event (Rabbit Wallet) | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready To Test |  | 29/Jul/25 9:46 AM | 08/Aug/25 11:22 AM | 01/Aug/25 12:00 AM | 5 | CleverTap | rr-cloudid-api | 72000
Story | DEVRDCT-155 | 28839 | [Dev][CleverTap][RD][RLP] Implement Add Card Event (Rabbit Line Pay) | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready To Test |  | 29/Jul/25 9:45 AM | 08/Aug/25 11:22 AM | 04/Aug/25 12:00 AM | 5 | CleverTap | rlp-middleware | 43200
Story | DEVRDCT-154 | 28838 | [Dev][CleverTap][RD] Implement Club Binding feed to user properties to replace partner binding | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | In Progress |  | 29/Jul/25 9:33 AM | 07/Aug/25 10:26 AM |  | 8 | hr-solution
Story | DEVRDECOM-22 | 28837 | [DEV][RD][Eco][SA] Create API Specification | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 29/Jul/25 9:21 AM | 08/Aug/25 9:10 AM |  | 1 | No-QA |  | 7200
Story | DEVRDCT-153 | 28826 | [Dev][CleverTap][RD] Implement The Data Transformation Module | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready To Test |  | 28/Jul/25 7:30 PM | 06/Aug/25 10:24 AM |  | 5 | CleverTap | No-QA | 86400
Story | DEVRDECOM-16 | 28818 | [Dev][RD][Eco][POC] RR SSO-Shopify data synchronization | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 28/Jul/25 6:57 PM | 08/Aug/25 9:10 AM |  | 3 | No-QA |  | 14400
Story | DEVRDECOM-15 | 28817 | [DEV][RD][Eco][DevOps] Set up PR pipeline | Pui Wigrom Naddakul | 61d40990ce3652006ab55354 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 28/Jul/25 6:27 PM | 08/Aug/25 1:33 PM |  | 1 | No-QA
Story | RDLOA-109 | 28813 | [Dev][Line][RD][SSO-User] Get line log detail endpoint | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 28/Jul/25 6:00 PM | 06/Aug/25 4:52 PM | 04/Aug/25 12:00 AM | 2 | No-QA | sso-user | 14400
Story | RDLOA-108 | 28812 | [Dev][Line OA][RD][RR-Backoffice] Add transaction detail page | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 28/Jul/25 5:51 PM | 08/Aug/25 10:17 AM | 05/Aug/25 12:00 AM | 3 |  |  | 28800
Story | DEVRDADJ-8 | 28811 | [Dev][Adjust][Deeplink][Link Notify] Replace Adjust instead of firebase for manual import static deeblink | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Progress |  | 28/Jul/25 5:26 PM | 08/Aug/25 9:30 AM |  | 3
Story | DEVRDCT-152 | 28810 | [DEV][CleverTap][RD][SSO-User] Enhance User Property | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 28/Jul/25 4:17 PM | 05/Aug/25 1:10 PM | 01/Aug/25 12:00 AM | 2 | sso-user |  | 7200
Story | DEVRDCT-151 | 28809 | [DEV][CleverTap][RD][SSO-Mimir] Enhance User Property | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 28/Jul/25 4:04 PM | 08/Aug/25 12:06 PM | 01/Aug/25 12:00 AM | 2 | SSO-Mimir |  | 14400
Story | DEVRDCT-150 | 28808 | [DEV][RD][CleverTap] Implement Login Event for LinePay binding | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Progress |  | 28/Jul/25 3:54 PM | 08/Aug/25 11:22 AM | 08/Aug/25 12:00 AM | 5 | rlp-middleware |  | 57600
Story | DEVRDECOM-14 | 28807 | [DEV][RD][Eco][RR-Ecommerce-Shopify] Create a migration file | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 28/Jul/25 3:33 PM | 08/Aug/25 1:34 PM |  | 2 | No-QA |  | 14400
Story | DEVRDCT-149 | 28793 | [DEV][RD][CleverTap] Implement Login Event On Rabbit Connect for RR Client | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 28/Jul/25 12:27 AM | 08/Aug/25 12:05 PM | 04/Aug/25 12:00 AM | 5 | sso-heimdall |  | 86400
Task | DEVRDCT-148 | 28792 | [DEV][RD][CleverTap][Get Uid data from LineAPI to let RD map with member ID(trader ID)] | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Review |  | 27/Jul/25 11:26 PM | 08/Aug/25 9:30 AM |  | 5 | No-QA | rlp-middleware | 86400
Story | DEVRDECOM-12 | 28791 | [DEV][RD][Eco][DevOps] Set up CI/CD pipeline (GitHub Actions) | Pui Wigrom Naddakul | 61d40990ce3652006ab55354 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 27/Jul/25 8:54 PM | 08/Aug/25 1:33 PM |  |  | No-QA
Story | DEVRDECOM-11 | 28790 | [DEV][RD][Eco][RR-Ecommerce-Shopify] Create Dockerfile for NestJS Application | Pui Wigrom Naddakul | 61d40990ce3652006ab55354 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 27/Jul/25 8:48 PM | 08/Aug/25 1:33 PM |  | 2 | No-QA
Story | DEVRDECOM-10 | 28789 | [DEV][RD][Eco][RR-Ecommerce-Shopify] Create a new NestJS project, configure database connection and RabbitMQ | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 27/Jul/25 2:17 PM | 08/Aug/25 1:33 PM | 07/Aug/25 12:00 AM | 3 | No-QA |  | 57600
Story | DEVRDECOM-9 | 28788 | [DEV][RD][Eco][DevOps] Prepare Existing AWS VPC & Networking & AWS EKS Cluster for Ecommerce Service | Pui Wigrom Naddakul | 61d40990ce3652006ab55354 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 27/Jul/25 2:11 PM | 08/Aug/25 9:17 AM |  |  | No-QA
Story | DEVRDECOM-8 | 28787 | [DEV][RD][Eco][DevOps] Domain & DNS Setup for Ecommerce Service | Pui Wigrom Naddakul | 61d40990ce3652006ab55354 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 27/Jul/25 2:00 PM | 08/Aug/25 9:17 AM |  |  | No-QA
Story | DEVRDECOM-7 | 28786 | [DEV][RD][Eco][SA] Request a new RDS PostgreSQL instance specifically for this Ecommerce Service. | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 27/Jul/25 1:58 PM | 08/Aug/25 9:10 AM |  | 1 | No-QA |  | 3600
Story | DEVRDECOM-6 | 28785 | [DEV][RD][Eco][DevOps] Create a new GitHub repository named rr-ecommerce-shopify | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 27/Jul/25 1:48 PM | 01/Aug/25 7:18 PM |  | 1 | No-QA
Story | RDNDA-1 | 28784 | [Dev][RD][LinePay & LineOA][ETL to New Datamart] | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Progress |  | 27/Jul/25 1:42 PM | 08/Aug/25 9:08 AM |  | 3 |  |  | 21600
Story | DEVRDCT-147 | 28783 | [Dev][CleverTap][RD] Implement Sign up Event |  |  | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | To Do |  | 27/Jul/25 9:52 AM | 29/Jul/25 5:47 PM
Story | DEVRDCT-146 | 28782 | [Dev][CleverTap][RD] Implement Add Card Event (Rabbit Card) | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready to Staging |  | 27/Jul/25 7:57 AM | 08/Aug/25 11:22 AM | 31/Jul/25 12:00 AM | 5 | sso-user |  | 57600
Sub-task | DEVRDCT-144 | 28772 | [QA] Test execution Enhance registration source (SIGN UP Event) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 25/Jul/25 10:53 AM | 31/Jul/25 1:15 PM
Epic | RDAPS-121 | 28770 | E-Commerce Shopify MVP 1 |  |  | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | To Do |  | 25/Jul/25 8:17 AM | 08/Aug/25 11:28 AM
Story | DEVRDCT-138 | 28760 | [Dev][RD] POC Webhook for Auto Push Coupons | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 24/Jul/25 8:20 PM | 05/Aug/25 10:49 AM |  | 3 | No-QA |  | 900
Story | RDAPS-120 | 28759 | [Dev][RD] Update API specification for app | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 24/Jul/25 7:54 PM | 06/Aug/25 9:56 AM |  | 1 |  |  | 3600
Story | RDAPS-116 | 28755 | [Dev][RD][DB] Create database migration for products table | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 24/Jul/25 7:41 PM | 05/Aug/25 1:52 PM |  | 1
Story | RDAPS-115 | 28754 | [Dev][RD][Redemption API] Enhance the API for redeeming the product | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 24/Jul/25 7:35 PM | 06/Aug/25 10:28 AM |  | 3 | No-QA | redemption-api | 28800
Story | RDAPS-113 | 28752 | [Dev][RD][Rewards API] Enhance API to get product by ID, Slug to support new fields for e-commerce type | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 24/Jul/25 7:25 PM | 07/Aug/25 10:15 AM |  | 2 | No-QA | rewards-api | 14400
Story | RDAPS-112 | 28751 | [Dev][RD][RR-Backoffice] Enhance the Rewards setting menu to support e-commerce rewards type | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 24/Jul/25 7:22 PM | 08/Aug/25 11:22 AM |  | 3 | rr-backoffice |  | 43200
Bug | DEVRDSUP-57 | 28728 | [SUP-57][SUB] Found Sub TXN Offline via Cash Generate empty receipt | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Open |  | 24/Jul/25 2:17 PM | 05/Aug/25 12:59 AM
Story | DEVRDSUP-56 | 28726 | [SUP-89][SUB] : Investigate and generate dummy receipt for BTS202507-0262007 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Done |  | 24/Jul/25 1:15 PM | 04/Aug/25 8:47 AM | 01/Aug/25 12:00 AM | 1 | No-QA |  | 1800
Story | DEVRDADJ-5 | 28660 | [Dev][Adjust][Deeplink][Link Notify] Replace Adjust instead of firebase for deeplink API | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 23/Jul/25 1:40 PM | 07/Aug/25 1:43 PM | 05/Aug/25 12:00 AM | 5 |  |  | 57600
Sub-task | RDAPS-106 | 28615 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 22/Jul/25 4:54 PM | 08/Aug/25 9:20 AM |  |  |  |  | 0 | มาจาก Sprint 3
Sub-task | RDAPS-105 | 28612 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 22/Jul/25 4:54 PM | 08/Aug/25 9:20 AM | [5 empty] | มาจาก Sprint 3
Bug | DEVRDSUP-50 | 28559 | [SUP-72][SUB] Some SUB TXN showing coupons as refunded but the package is still active. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Open |  | 21/Jul/25 12:10 PM | 05/Aug/25 1:37 AM
Task | DEVRDCT-136 | 28551 | [Dev][RD][CT] Enhance registration source mapping | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 21/Jul/25 9:38 AM | 08/Aug/25 11:22 AM | [5 empty] | มาจาก Sprint 3
Bug | DEVRRBOF-148 | 28517 | [S2] The category location is deleted when update category detail on step1 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 18/Jul/25 5:32 PM | 06/Aug/25 6:16 PM |  |  | rr-backoffice
Task | RDLOA-102 | 28502 | [Dev][RD][LineOA][SSO-User] Change credential response data | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 18/Jul/25 9:43 AM | 31/Jul/25 11:23 AM |  | 1 |  |  | 0 | มาจาก Sprint 3 | ตัด 28800
Sub-task | RDLOA-101 | 28499 | [QA] Create Test Case & Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 18/Jul/25 8:48 AM | 05/Aug/25 3:36 PM | [5 empty] | มาจาก Sprint 3
Sub-task | RDLOA-100 | 28496 | [QA] Create Test Case & Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 18/Jul/25 8:48 AM | 04/Aug/25 4:12 PM | [5 empty] | มาจาก Sprint 3
Sub-task | RDLOA-99 | 28493 | [QA] Create Test Case & Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 18/Jul/25 8:47 AM | 04/Aug/25 4:12 PM | [5 empty] | มาจาก Sprint 3
Sub-task | RDLOA-98 | 28490 | [QA] Create Test Case & Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 18/Jul/25 8:47 AM | 24/Jul/25 10:04 AM | [5 empty] | มาจาก Sprint 3
Sub-task | RDLOA-97 | 28487 | [QA] Create Test Case & Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Ready To Test |  | 18/Jul/25 8:47 AM | 23/Jul/25 11:36 PM | [5 empty] | มาจาก Sprint 3
Sub-task | RDLOA-96 | 28484 | [QA] Create Test Case & Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Ready To Test |  | 18/Jul/25 8:47 AM | 23/Jul/25 11:36 PM | [5 empty] | มาจาก Sprint 3
Story | RDAPS-99 | 28480 | [Dev][RD][Redemption API] Pass BTS station info when issuing BTS pass for coupons with 'offline' sale channel | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 17/Jul/25 7:32 PM | 08/Aug/25 9:04 AM |  | 2 | redemption-api |  | 0 | มาจาก Sprint 3 | ตัด 21600
Story | DEVRDSUP-45 | 28458 | [SUP-60][NBO][Rewards Alert List] - Requesting all exclusive partner rewards list with remaining code count. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | To Do |  | 16/Jul/25 5:58 PM | 31/Jul/25 10:46 AM | 18/Jul/25 12:00 AM |  | No-QA
Bug | DEVRDSUP-42 | 28359 | [SUP-66][HRsolution] Many point issue TXN are stuck at "distributing" causing sum of point issue to be incorrect in Point Issuing Transaction Report | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Resolved |  | 15/Jul/25 7:48 PM | 08/Aug/25 11:29 AM |  | 3 |  |  |  | มาจาก Sprint 3
Bug | DEVRDCT-133 | 28344 | [S4][CT][User Properties] Enrichment detail of user properties NOT match to sso_backoffice | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Resolved |  | 15/Jul/25 4:58 PM | 30/Jul/25 1:58 PM | [5 empty] | มาจาก Sprint 3
Sub-task | DEVRDCT-132 | 28338 | [QA] Test execution (CT 1.3) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 15/Jul/25 3:37 PM | 29/Jul/25 10:55 AM | [5 empty] | มาจาก Sprint 3
Sub-task | DEVRDCT-130 | 28317 | [QA] Test execution DEVRDCT-99 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 15/Jul/25 2:53 PM | 30/Jul/25 1:16 PM | [5 empty] | มาจาก Sprint 3
Sub-task | DEVRDCT-129 | 28314 | [QA] Create test case DEVRDCT-99 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 15/Jul/25 2:52 PM | 15/Jul/25 2:53 PM | [5 empty] | มาจาก Sprint 3
Sub-task | DEVRDCT-127 | 28307 | [QA] Create test case DEVRDCT-117 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 15/Jul/25 2:26 PM | 29/Jul/25 5:42 PM | [5 empty] | มาจาก Sprint 3
Sub-task | DEVRDCT-126 | 28304 | [QA] Create test case DEVRDCT-119 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 15/Jul/25 2:16 PM | 30/Jul/25 2:02 PM | [5 empty] | มาจาก Sprint 3
Task | DEVRD20THB-1 | 28203 | [Dev][RD][Sub][20THB][API finalization] | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 14/Jul/25 8:29 PM | 08/Aug/25 9:05 AM | 17/Jul/25 12:00 AM | 2 |  |  | 0 | มาจาก Sprint 3 | 1800
Task | RDAPS-91 | 28194 | [Dev][RD][POC Archive Old Data in MongoDB/RLP DB/PL DB] | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Review |  | 14/Jul/25 7:04 PM | 08/Aug/25 9:06 AM |  | 2 |  |  | 0 | มาจาก Sprint 3 | 1800
Task | DEVRDCT-124 | 28170 | [Dev][RD][CleverTap][Import Initial data of LineOA as of 1June - 13July] | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 14/Jul/25 3:06 PM | 08/Aug/25 9:30 AM |  | 1 | No-QA |  |  | มาจาก Sprint 3
Story | DEVRDCT-122 | 28164 | [DEV][CLEVERTAP][RD] Change the endpoint URL for sending messages to use rr_clevertap endpoint | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Lowest | To Do |  | 14/Jul/25 1:52 PM | 31/Jul/25 10:31 AM |  | 1 | No-QA |  |  | มาจาก Sprint 3
Story | RDAPS-87 | 28157 | [Dev][RD][Adhoc][HR Solution] Creating new campaign does not auto apply to new BU. | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 14/Jul/25 10:35 AM | 08/Aug/25 10:17 AM | 17/Jul/25 12:00 AM | 5 | hr-solution |  |  | มาจาก Sprint 3
Story | RDAPS-86 | 28149 | [Dev][Adhoc][HR-Solution] If user creates creates new club and then create BU, when active club, the BU won't be assigned to the club automatically. | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 14/Jul/25 10:31 AM | 08/Aug/25 10:17 AM | 16/Jul/25 12:00 AM | 3 |  |  |  | มาจาก Sprint 3
Story | DEVRDCT-121 | 28099 | [TBC]DEV][CLEVERTAP][RD] Implement Event feeding for Subscription purchase report #2 | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready to Staging |  | 12/Jul/25 8:52 AM | 08/Aug/25 11:22 AM |  | 3 | No-QA | order-consumer | 0 | มาจาก Sprint 3 | 14400
Story | DEVRDCT-119 | 28097 | [DEV][CLEVERTAP][RD] EVENT Properties for Club binding for Unicorn and Visionary | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 11/Jul/25 9:08 PM | 08/Aug/25 9:52 AM |  | 5 | CleverTap |  | 0 | มาจาก Sprint 3 | 86400
Task | RDLOA-75 | 28080 | [Dev][RD][LineOA][BFF] Enhance binding Line Account support push message for failed case | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 11/Jul/25 4:33 PM | 08/Aug/25 11:22 AM |  | 1 | BFF |  |  | มาจาก Sprint 3
Task | RDLOA-74 | 28079 | [Dev][RD][LineOA][Link-Notify] Integrate Line OA push message | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 11/Jul/25 4:32 PM | 05/Aug/25 2:18 PM |  | 1 |  |  |  | มาจาก Sprint 3
Task | RDLOA-73 | 28078 | [Dev][RD][LineOA][BFF] Change matching message | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 11/Jul/25 4:16 PM | 08/Aug/25 11:21 AM |  | 1 |  |  |  | มาจาก Sprint 3
Task | RDLOA-72 | 28077 | [Dev][RD][LineOA][BFF] Enhance binding Line Account support new params | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 11/Jul/25 4:13 PM | 08/Aug/25 11:21 AM |  | 1 | BFF |  |  | มาจาก Sprint 3
Task | RDLOA-71 | 28076 | [Dev][RD][LineOA][SSO-User] Enhance binding line OA endpoint | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 11/Jul/25 4:12 PM | 30/Jul/25 1:45 PM |  | 1 | InternalAPI | sso-user |  | มาจาก Sprint 3
Story | DEVRDCT-117 | 28027 | [DEV][CLEVERTAP][RD] Implement Event feed with filtering former events | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Ready To Test |  | 11/Jul/25 1:44 PM | 08/Aug/25 11:22 AM | 04/Aug/25 12:00 AM | 3 | CleverTap |  | 0 | มาจาก Sprint 3 | 28800
Bug | DEVRDSUP-35 | 27880 | [SUP-56][NBO][Rewards Alert List] - Rewards Alert List email not being sent | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Open |  | 09/Jul/25 1:46 PM | 06/Aug/25 11:00 AM
Bug | DEVRDSUP-32 | 27766 | [SUP-52][Merchant][NBO] All merchants in NBO doesn't show category internal name but shows uuid of category instead. | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Lowest | Closed |  | 08/Jul/25 3:44 PM | 08/Aug/25 11:22 AM | 30/Jul/25 12:00 AM | 2
Bug | DEVRDSUP-30 | 27748 | [SUP-50][SUB] Some receipts are not generated after SUB TXN is made. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Open |  | 08/Jul/25 1:43 PM | 05/Aug/25 1:06 AM
Task | DEVRDCT-116 | 27493 | [Dev][RD][Initial User Property] Fix wrong card and enrichment detail | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 03/Jul/25 3:33 PM | 08/Aug/25 11:22 AM | 04/Jul/25 12:00 AM | 3 | sso-mimir |  | 0 | มาจาก Sprint 3 | 28800
Sub-task | DEVRDCT-111 | 27219 | [QA] Test execution Subscription Report |  |  | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 01/Jul/25 1:59 PM | 18/Jul/25 4:56 PM | [5 empty] | มาจาก Sprint 3
Sub-task | DEVRDCT-110 | 27216 | [QA] Create test case Subscription Report | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 01/Jul/25 1:59 PM | 18/Jul/25 4:56 PM | [5 empty] | มาจาก Sprint 3
Sub-task | DEVRDCT-109 | 27176 | [QA] Execution test Partner Binding |  |  | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 01/Jul/25 1:55 PM | 18/Jul/25 4:56 PM | [5 empty] | มาจาก Sprint 3
Sub-task | DEVRDCT-108 | 27173 | [QA] Create test case Partner Binding | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 01/Jul/25 1:55 PM | 18/Jul/25 4:56 PM | [5 empty] | มาจาก Sprint 3
Sub-task | DEVRDCT-107 | 27170 | [QA] Create test case Consent Events | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 01/Jul/25 1:54 PM | 07/Aug/25 2:15 PM | [5 empty] | มาจาก Sprint 3
Sub-task | DEVRDCT-106 | 27164 | [QA] Test execution Consent Events | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 01/Jul/25 1:54 PM | 21/Jul/25 4:48 PM | [5 empty] | มาจาก Sprint 3
Sub-task | DEVRDCT-105 | 27149 | [QA] Execution test Sign Up Event | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 01/Jul/25 1:53 PM | 29/Jul/25 10:56 AM | [5 empty] | มาจาก Sprint 3
Sub-task | DEVRDCT-104 | 27123 | [QA] Create test case Sign Up Event | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 01/Jul/25 1:42 PM | 25/Jul/25 4:30 PM | [5 empty] | มาจาก Sprint 3
Sub-task | DEVRDCT-103 | 27117 | [QA] Execution test Implement Update user profile #2 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 01/Jul/25 1:40 PM | 29/Jul/25 1:33 PM | [5 empty] | มาจาก Sprint 3
Sub-task | DEVRDCT-102 | 27114 | [QA] Create test case Implement Update user profile #2 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 01/Jul/25 1:39 PM | 08/Jul/25 10:20 AM | [5 empty] | มาจาก Sprint 3
Sub-task | DEVRDCT-101 | 27059 | Implement |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 30/Jun/25 5:18 PM | 30/Jun/25 5:18 PM | [5 empty] | มาจาก Sprint 3
Sub-task | DEVRDCT-100 | 27056 | POC SSO User can support this event |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 30/Jun/25 5:18 PM | 30/Jun/25 5:19 PM | [5 empty] | มาจาก Sprint 3
Story | DEVRDCT-99 | 27031 | [Dev][RD][CleverTap][SSO-Mimir] Enhance import LINE OA support upload user properties | thanyapath sunthornchaisadom | 6163a9eac7bea400698ab7af | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 30/Jun/25 1:33 PM | 08/Aug/25 10:17 AM |  | 3 |  |  | 0 | มาจาก Sprint 3 | 28800
Story | RDLOA-25 | 26988 | [Dev][RD][LineOA][RR-Backoffice][Member Detail] Line Account Logs page | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 29/Jun/25 5:04 PM | 08/Aug/25 10:17 AM | 21/Jul/25 12:00 AM | 1 | rr-backoffice |  |  | มาจาก Sprint 3
Story | RDLOA-24 | 26987 | [Dev][RD][LineOA][RR-Backoffice][Member Detail] Profile page | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 29/Jun/25 5:04 PM | 08/Aug/25 10:17 AM | 18/Jul/25 12:00 AM | 1 | rr-backoffice |  | 0 | มาจาก Sprint 3 | 57600
Story | RDLOA-23 | 26986 | [Dev][RD][LineOA][RR-Backoffice][Member Detail] Index Page | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 29/Jun/25 5:03 PM | 08/Aug/25 10:17 AM | 16/Jul/25 12:00 AM | 1 | rr-backoffice |  |  | มาจาก Sprint 3
Story | DEVRDCT-97 | 26981 | [Dev][RD][Clever Tap #2][Enhance] Subscription Report |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 29/Jun/25 12:52 AM | 30/Jul/25 1:58 PM |  |  | change-request |  |  | มาจาก Sprint 3
Story | DEVRDCT-95 | 26979 | [Dev][RD][Clever Tap #2] Partner Binding |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 29/Jun/25 12:50 AM | 30/Jul/25 1:58 PM |  |  | change-request |  |  | มาจาก Sprint 3
Story | DEVRDCT-94 | 26978 | [Dev][RD][Clever Tap #2] Consent events | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 29/Jun/25 12:49 AM | 08/Aug/25 10:17 AM | 09/Jul/25 12:00 AM | 3 | sso-user |  | 0 | มาจาก Sprint 3 | 28800
Story | DEVRDCT-89 | 26973 | [Dev][RD][Clever Tap #2] Sign Up Event | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 29/Jun/25 12:48 AM | 08/Aug/25 10:17 AM |  | 5 |  |  | 0 | มาจาก Sprint 3 | 86400
Story | DEVRDCT-88 | 26972 | [Dev][RD][Clever Tap #2] Implement Update user profile #2 to CT | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 29/Jun/25 12:47 AM | 08/Aug/25 10:17 AM | 07/Jul/25 12:00 AM | 5 | sso-user |  | 0 | มาจาก Sprint 3 | 86400
Story | RDLOA-21 | 26969 | [Dev][RD][LineOA][SSO-User] Create webhook endpoint and handle LINE OA Webhook | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 29/Jun/25 12:22 AM | 30/Jul/25 1:45 PM |  | 1 | sso-user |  |  | มาจาก Sprint 3
Story | RDLOA-20 | 26968 | [Dev][RD][LineOA][SSO-User] Create new endpoint for record line log event | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 29/Jun/25 12:12 AM | 30/Jul/25 1:46 PM |  | 1 |  |  |  | มาจาก Sprint 3
Story | RDLOA-19 | 26967 | [Dev][RD][LineOA][CT][SSO-User] Event x LINE account binding | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 28/Jun/25 11:15 PM | 08/Aug/25 10:17 AM |  | 1 | sso-user |  |  | มาจาก Sprint 3
Story | RDLOA-18 | 26966 | [Dev][RD][LineOA][CT][SSO-User] Profile x LINE account to CT | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 28/Jun/25 11:14 PM | 08/Aug/25 10:17 AM |  | 1 | sso-user |  |  | มาจาก Sprint 3

## Sprint 3
Issue Type | Issue key | Issue id | Summary | Assignee | Assignee Id | Reporter | Reporter Id | Priority | Status | Resolution | Created | Updated | Due date | Custom field (Story Points) | Labels | Labels | Labels | Original estimate | Manhour | Sprint Movement | Note
Task | RDAPS-119 | 28758 | [Dev][SUB][Re-State] Request dev to re-state 5 BTS coupons for CRM case lot 41. 24/07/2025 | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 24/Jul/25 7:52 PM | 24/Jul/25 7:53 PM | 25/Jul/25 12:00 AM | 1 | mid-sprint |  |  |  | 2
Task | RDAPS-118 | 28757 | [Dev][SUB][Re-State] Request dev to re-state 7 BTS coupons for CRM case lot 40. 24/07/2025 | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 24/Jul/25 7:50 PM | 24/Jul/25 7:50 PM | 24/Jul/25 12:00 AM | 1 | mid-sprint |  |  |  | 2
Story | RDAPS-111 | 28724 | [Dev][RD][SA] Analyze & split dev tasks for Rewards Ecommerce | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 24/Jul/25 11:36 AM | 24/Jul/25 8:18 PM |  | 3 |  |  |  |  | 8
Story | RDAPS-110 | 28675 | [Dev][RD] Prepare for Production Deployment on Jul 24 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 23/Jul/25 5:08 PM | 23/Jul/25 8:29 PM |  | 2 |  |  |  | 14400 | 4
Story | DEVRDCT-137 | 28674 | [Dev][RD][SA] Analyze & split dev tasks for Auto push coupons | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | In Progress |  | 23/Jul/25 4:43 PM | 24/Jul/25 8:40 PM |  | 3 |  |  |  |  | 8
Task | RDAPS-108 | 28623 | [Dev][SUB][Re-State] Request dev to re-state 11 BTS coupons for CRM case lot 39. 22/07/2025 | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 22/Jul/25 6:45 PM | 24/Jul/25 10:18 AM | 23/Jul/25 12:00 AM | 1 | mid-sprint |  |  |  | 2
Sub-task | RDAPS-106 | 28615 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 22/Jul/25 4:54 PM | 23/Jul/25 5:16 PM | [6 empty] | 0
Sub-task | RDAPS-105 | 28612 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 22/Jul/25 4:54 PM | 22/Jul/25 4:54 PM | [6 empty] | 0
Bug | DEVRDSUP-53 | 28609 | [SUP-82]CRM - Case ID: CS-20250700014561 Cannot Top up Pink Line pass 10 trips when Line Pay ID has been changed | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Closed |  | 22/Jul/25 4:23 PM | 24/Jul/25 10:53 PM |  |  | bts |  |  |  | 0
Task | RDAPS-103 | 28576 | [Dev][SUB][Re-State] Request dev to re-state 5 BTS coupons for CRM case lot 38. 21/07/2025 | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 21/Jul/25 5:54 PM | 22/Jul/25 5:54 PM | 22/Jul/25 12:00 AM | 1 | mid-sprint |  |  |  | 2
Story | DEVRDSUP-51 | 28564 | [SUP-70]SUB : Request to generate completed receipt | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 21/Jul/25 1:28 PM | 23/Jul/25 4:35 PM |  | 1 | mid-sprint |  |  | 7200 | 2
Task | RDAPS-102 | 28552 | [Dev][RD] Send historical Redemption coupon status data for June to DA | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Highest | Done |  | 21/Jul/25 9:42 AM | 23/Jul/25 4:35 PM |  | 2 | mid-sprint |  |  | 57600 | 4
Task | DEVRDCT-136 | 28551 | [Dev][RD][CT] Enhance registration source mapping | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 21/Jul/25 9:38 AM | 22/Jul/25 2:33 PM | [6 empty] | 0
Bug | RDAPS-101 | 28550 | [Dev][RD][RR-Scheduler] Investigate root cause and fix for missing data in Redemption coupon status ETL | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Resolved |  | 21/Jul/25 9:37 AM | 21/Jul/25 9:06 PM |  |  | mid-sprint | rr-scheduler |  |  | 0
Task | RDAPS-100 | 28513 | [Dev][SUB][Re-State] Request dev to re-state 6 BTS coupons for CRM case lot 37. 18/07/2025 | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 18/Jul/25 4:03 PM | 18/Jul/25 4:22 PM | 18/Jul/25 12:00 AM | 1 | mid-sprint |  |  |  | 2
Story | DEVRDSUP-47 | 28512 | [SUP-74]Customer has completed the payment but did not receive the package as expected. Kindly assist by manually initiating the package for the customer. | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | Medium | Done |  | 18/Jul/25 4:00 PM | 23/Jul/25 4:28 PM |  | 1 | mid-sprint |  |  | 1800 | 2
Test Execution | DEVRRBOF-147 | 28506 | [TX][Dev][RD][RR Backoffice] Sprint3 - UAT | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 18/Jul/25 1:33 PM | 24/Jul/25 10:29 AM |  |  | rr-backoffice |  |  |  | 0
Task | RDLOA-103 | 28503 | [Dev][RD][LineOA][SSO-User] Keep webhook data |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 18/Jul/25 10:39 AM | 18/Jul/25 10:39 AM | [6 empty] | 0
Task | RDLOA-102 | 28502 | [Dev][RD][LineOA][SSO-User] Change credential response data | First Nattapon | 64001d5e896d10ebd470f6c1 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 18/Jul/25 9:43 AM | 21/Jul/25 4:54 PM |  | 3 |  |  |  | 28800 | 8
Sub-task | RDLOA-101 | 28499 | [QA] Create Test Case & Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Ready To Test |  | 18/Jul/25 8:48 AM | 24/Jul/25 10:04 AM | [6 empty] | 0
Sub-task | RDLOA-100 | 28496 | [QA] Create Test Case & Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Ready To Test |  | 18/Jul/25 8:48 AM | 24/Jul/25 10:04 AM | [6 empty] | 0
Sub-task | RDLOA-99 | 28493 | [QA] Create Test Case & Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Ready To Test |  | 18/Jul/25 8:47 AM | 24/Jul/25 10:04 AM | [6 empty] | 0
Sub-task | RDLOA-98 | 28490 | [QA] Create Test Case & Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 18/Jul/25 8:47 AM | 24/Jul/25 10:04 AM | [6 empty] | 0
Sub-task | RDLOA-97 | 28487 | [QA] Create Test Case & Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Ready To Test |  | 18/Jul/25 8:47 AM | 23/Jul/25 11:36 PM | [6 empty] | 0
Sub-task | RDLOA-96 | 28484 | [QA] Create Test Case & Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Ready To Test |  | 18/Jul/25 8:47 AM | 23/Jul/25 11:36 PM | [6 empty] | 0
Story | RDAPS-99 | 28480 | [Dev][RD][Redemption API] Pass BTS station info when issuing BTS pass for coupons with 'offline' sale channel | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 17/Jul/25 7:32 PM | 24/Jul/25 5:16 PM |  | 2 | redemption-api |  |  | 21600 | 4
Bug | DEVRRBOF-145 | 28462 | [Dev][RD][RR-Backoffice] De-selecting value is not working properly | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Closed |  | 17/Jul/25 10:17 AM | 24/Jul/25 9:59 AM | [6 empty] | 0
Task | RDAPS-98 | 28459 | [Dev][SUB][Re-State] Request dev to re-state 7 BTS coupons for CRM case lot 36. 16/07/2025 | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 16/Jul/25 8:44 PM | 17/Jul/25 9:19 AM | 17/Jul/25 12:00 AM | 1 | mid-sprint |  |  |  | 2
Story | DEVRDSUP-44 | 28381 | [SUP-67]Request for the latest updated email list of Visionary members. | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Done |  | 16/Jul/25 2:31 PM | 18/Jul/25 1:34 PM | 16/Jul/25 12:00 AM | 1 | mid-sprint |  |  |  | 2
Bug | DEVRDSUP-43 | 28380 | [SUP-68]CRM - Case ID: CS-20250600013136 Cannot Top up BTS pass 35 trips when Line Pay ID has been changed | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Closed |  | 16/Jul/25 12:34 PM | 16/Jul/25 8:40 PM | 16/Jul/25 12:00 AM | [5 empty] | 0
Task | RDAPS-97 | 28368 | [Dev][SUB][Re-State] Request dev to re-state 5 BTS coupons for CRM case lot 35. 15/07/2025 | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 16/Jul/25 9:44 AM | 16/Jul/25 10:12 AM | 16/Jul/25 12:00 AM | 1 | mid-sprint |  |  |  | 2
Bug | DEVRDSUP-42 | 28359 | [SUP-66][HRsolution] Many point issue TXN are stuck at "distributing" causing sum of point issue to be incorrect in Point Issuing Transaction Report | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Open |  | 15/Jul/25 7:48 PM | 21/Jul/25 3:24 PM | [6 empty] | 0
Bug | DEVRDCT-133 | 28344 | [S4][CT][User Properties] Enrichment detail of user properties NOT match to sso_backoffice | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Resolved |  | 15/Jul/25 4:58 PM | 18/Jul/25 10:52 AM | [6 empty] | 0
Test Execution | DEVRRBOF-137 | 28343 | [TX][Dev][RD][RR Backoffice] Sprint3 - Staging | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 15/Jul/25 4:50 PM | 21/Jul/25 5:21 PM | [6 empty] | 0
Test Plan | DEVRRBOF-136 | 28342 | [TP][Dev][RD][RR Backoffice] Sprint3 |  |  | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 15/Jul/25 4:50 PM | 22/Jul/25 2:32 PM | [6 empty] | 0
Test Set | DEVRRBOF-135 | 28341 | [TS][Dev][RD][RR Backoffice] Sprint3 |  |  | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 15/Jul/25 4:50 PM | 22/Jul/25 2:32 PM | [6 empty] | 0
Sub-task | DEVRDCT-132 | 28338 | [QA] Test execution (CT 1.3) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | In Progress |  | 15/Jul/25 3:37 PM | 17/Jul/25 10:42 AM | [6 empty] | 0
Sub-task | DEVRRBOF-134 | 28335 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Progress |  | 15/Jul/25 3:36 PM | 17/Jul/25 1:22 PM | [6 empty] | 0
Sub-task | DEVRRBOF-133 | 28332 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 15/Jul/25 3:36 PM | 16/Jul/25 11:14 AM | [6 empty] | 0
Task | RDAPS-96 | 28323 | [DEV][RD][RDS] Upgrade RDS Engine | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 15/Jul/25 3:20 PM | 21/Jul/25 2:15 PM | 15/Jul/25 12:00 AM | 1 |  |  |  |  | 2
Sub-task | DEVRDCT-130 | 28317 | [QA] Test execution (CT 1.3) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 15/Jul/25 2:53 PM | 15/Jul/25 2:53 PM | [6 empty] | 0
Sub-task | DEVRDCT-129 | 28314 | [QA] Create test case DEVRDCT-99 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 15/Jul/25 2:52 PM | 15/Jul/25 2:53 PM | [6 empty] | 0
Sub-task | DEVRDCT-127 | 28307 | [QA] Create test case DEVRDCT-117 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 15/Jul/25 2:26 PM | 15/Jul/25 2:26 PM | [6 empty] | 0
Sub-task | DEVRDCT-126 | 28304 | [QA] Create test case DEVRDCT-119 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 15/Jul/25 2:16 PM | 15/Jul/25 2:16 PM | [6 empty] | 0
Sub-task | DEVRDCT-125 | 28301 | [QA] Create test case DEVRDCT-118 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 15/Jul/25 2:16 PM | 21/Jul/25 10:10 AM | [6 empty] | 0
Sub-task | DEVRRBOF-132 | 28241 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 15/Jul/25 10:48 AM | 21/Jul/25 10:05 AM | [6 empty] | 0
Sub-task | DEVRRBOF-131 | 28238 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 15/Jul/25 10:48 AM | 15/Jul/25 4:48 PM | [6 empty] | 0
Sub-task | DEVRRBOF-130 | 28235 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 15/Jul/25 10:48 AM | 17/Jul/25 11:49 AM | [6 empty] | 0
Sub-task | DEVRRBOF-129 | 28232 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 15/Jul/25 10:48 AM | 16/Jul/25 11:14 AM | [6 empty] | 0
Sub-task | DEVRRBOF-128 | 28220 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 15/Jul/25 10:43 AM | 16/Jul/25 4:39 PM | [6 empty] | 0
Sub-task | DEVRRBOF-127 | 28217 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 15/Jul/25 10:43 AM | 15/Jul/25 2:04 PM | [6 empty] | 0
Sub-task | DEVRRBOF-126 | 28214 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 15/Jul/25 10:43 AM | 21/Jul/25 10:05 AM | [6 empty] | 0
Sub-task | DEVRRBOF-125 | 28211 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 15/Jul/25 10:43 AM | 16/Jul/25 11:14 AM | [6 empty] | 0
Bug | RDAPS-95 | 28208 | [S4][RR App][Subscription][Full Basket] Error full basket message doesn't update to new message when meet the conditions | First Nattapon | 64001d5e896d10ebd470f6c1 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Closed |  | 14/Jul/25 8:47 PM | 15/Jul/25 1:28 PM | [6 empty] | 0
Task | RDAPS-94 | 28207 | [Dev][SUB][Re-State] Request dev to re-state 3 BTS coupons for CRM case lot 34. 14/07/2025 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | High | Done |  | 14/Jul/25 8:42 PM | 16/Jul/25 9:54 AM | 15/Jul/25 12:00 AM | 1 |  |  |  |  | 2
Task | DEVRDECOM-5 | 28206 | [DEV][RD][Eco][POC] Reverse Point on Order Cancellation | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 14/Jul/25 8:37 PM | 24/Jul/25 3:10 AM |  | 3 |  |  |  |  | 8
Task | DEVRDECOM-4 | 28205 | [DEV][RD][Eco][POC] Physical Product : Issue RR Point to Customer Defined by Order Status | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 14/Jul/25 8:34 PM | 24/Jul/25 3:10 AM |  | 3 |  |  |  |  | 8
Task | DEVRDECOM-3 | 28204 | [DEV][RD][Eco][POC] RR SSO: Enable Rabbit Rewards SSO Login via Multipass (Shopify Plus) | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 14/Jul/25 8:33 PM | 24/Jul/25 3:10 AM |  | 5 |  |  |  |  | 24
Task | DEVRD20THB-1 | 28203 | [Dev][RD][Sub][20THB][API finalization] | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 14/Jul/25 8:29 PM | 17/Jul/25 4:28 PM | 17/Jul/25 12:00 AM | 2 |  |  |  |  | 4
Sub-task | RDAPS-93 | 28197 | [QA] Test execution (App RR UAT) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 14/Jul/25 7:25 PM | 15/Jul/25 1:30 PM | [6 empty] | 0
Task | RDAPS-92 | 28195 | [DEV][ADHOC][RD] Request to create Rewards Group in UAT for Deeplink test | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 14/Jul/25 7:05 PM | 16/Jul/25 9:54 AM | 15/Jul/25 12:00 AM | 1 |  |  |  |  | 2
Task | RDAPS-91 | 28194 | [Dev][RD][POC Archive Old Data in MongoDB/RLP DB/PL DB] | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Review |  | 14/Jul/25 7:04 PM | 24/Jul/25 10:42 PM |  | 2 |  |  |  |  | 4
Task | RDAPS-89 | 28191 | [Dev][RD][Estimation][API Changes to support member tier status on POS system] | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 14/Jul/25 6:30 PM | 21/Jul/25 4:04 PM |  | 2 | API | partner-loyalty | turtle |  | 4
Bug | DEVRDSUP-36 | 28190 | [SUP-58]SUB :(Support manual generate receipt) Receipt ID not found in RR Backoffice | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | Closed |  | 14/Jul/25 6:18 PM | 23/Jul/25 4:26 PM | [5 empty] | 1800 | 0
Task | DEVRDCT-124 | 28170 | [Dev][RD][CleverTap][Import Initial data of LineOA as of 1June - 13July] | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 14/Jul/25 3:06 PM | 14/Jul/25 4:42 PM |  | 1 |  |  |  |  | 2
Task | DEVRDCT-123 | 28169 | [Dev][RD][Clever Tap] Export latest registration source in 1 years | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 14/Jul/25 3:06 PM | 15/Jul/25 10:49 AM |  | 1 |  |  |  |  | 2
Story | DEVRDCT-122 | 28164 | [DEV][CLEVERTAP][RD] Change the endpoint URL for sending messages to use rr_clevertap endpoint | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Lowest | To Do |  | 14/Jul/25 1:52 PM | 15/Jul/25 12:43 PM |  | 1 |  |  |  |  | 2
Story | DEVRRBOF-124 | 28163 | [Dev][RD][Redemption API] Able to Re-state for RLP and RW cards | First Nattapon | 64001d5e896d10ebd470f6c1 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 14/Jul/25 1:16 PM | 24/Jul/25 5:05 PM |  | 3 |  |  |  |  | 8
Story | RDAPS-88 | 28158 | [Dev][RD][Adhoc] Manual mark coupons as used on production | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Highest | Done |  | 14/Jul/25 10:51 AM | 23/Jul/25 4:22 PM |  | 1 |  |  |  | 5400 | 2
Story | RDAPS-87 | 28157 | [Dev][RD][Adhoc][HR Solution] Creating new campaign does not auto apply to new BU. | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 14/Jul/25 10:35 AM | 23/Jul/25 5:16 PM | 17/Jul/25 12:00 AM | 5 | hr-solution |  |  |  | 24
Story | RDAPS-86 | 28149 | [Dev][Adhoc][HR-Solution] If user creates creates new club and then create BU, when active club, the BU won't be assigned to the club automatically. | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 14/Jul/25 10:31 AM | 23/Jul/25 5:16 PM | 16/Jul/25 12:00 AM | 3 |  |  |  |  | 8
Bug | DEVRRBOF-123 | 28148 | [S2][Rewards] Item and value are not displayed in Reward setting | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 14/Jul/25 10:25 AM | 24/Jul/25 9:59 AM | 18/Jul/25 12:00 AM | [5 empty] | 0
Bug | RDAPS-85 | 28101 | [Dev][RD] Investigate on root cause with preventions | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Closed |  | 12/Jul/25 3:52 PM | 17/Jul/25 10:11 AM | [6 empty] | 0
Story | DEVRRBOF-122 | 28100 | [Dev][RD]Optimize Subscription Transaction Report Index Page to Prevent Initial Data Load | thanyapath sunthornchaisadom | 6163a9eac7bea400698ab7af | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 12/Jul/25 3:25 PM | 24/Jul/25 5:05 PM |  | 2 |  |  |  |  | 4
Story | DEVRDCT-121 | 28099 | [TBC]DEV][CLEVERTAP][RD] Implement Event feeding for Subscription purchase report #2 |  |  | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Lowest | To Do |  | 12/Jul/25 8:52 AM | 14/Jul/25 4:42 PM |  |  | CleverTap |  |  |  | 0
Story | DEVRDCT-120 | 28098 | [TBC][DEV][CLEVERTAP][RD][POC] Webhook for push rewards to user (AUTO PUSH COUPON) |  |  | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Lowest | To Do |  | 12/Jul/25 8:04 AM | 14/Jul/25 4:42 PM |  |  | CleverTap |  |  |  | 0
Story | DEVRDCT-119 | 28097 | [DEV][CLEVERTAP][RD] EVENT Properties for Club binding for Unicorn and Visionary | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | In Progress |  | 11/Jul/25 9:08 PM | 21/Jul/25 10:02 AM |  | 5 | CleverTap |  |  | 57600 | 24
Story | DEVRDCT-118 | 28096 | [DEV][CLEVERTAP][RD][POC] Develop Club Binding feed to user properties to replace partner binding | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Medium | Done |  | 11/Jul/25 7:51 PM | 25/Jul/25 9:01 AM |  | 8 | CleverTap |  |  | 115200 | 32
Story | DEVRRBOF-121 | 28087 | [Dev][RD][RR-Backoffice] Able to use “Back to Redeemed” feature for RLP and RW cards | First Nattapon | 64001d5e896d10ebd470f6c1 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 11/Jul/25 6:30 PM | 24/Jul/25 5:05 PM |  | 2 |  |  |  |  | 4
Story | RDHOP-6 | 28086 | [Dev][RD] High-level Estimation for Phase 1 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 11/Jul/25 6:27 PM | 23/Jul/25 4:38 PM | 23/Jul/25 12:00 AM | 3 |  |  |  | 36000 | 8
Story | DEVRRBOF-120 | 28085 | [Dev][RD[RR-Backoffice] Display Mark Used date display field | First Nattapon | 64001d5e896d10ebd470f6c1 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 11/Jul/25 6:09 PM | 24/Jul/25 5:05 PM |  | 2 |  |  |  |  | 4
Task | RDLOA-75 | 28080 | [Dev][RD][LineOA][BFF] Enhance binding Line Account support push message for failed case | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 11/Jul/25 4:33 PM | 24/Jul/25 10:02 AM |  | 3 | BFF |  |  |  | 8
Task | RDLOA-74 | 28079 | [Dev][RD][LineOA][Link-Notify] Integrate Line OA push message | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 11/Jul/25 4:32 PM | 24/Jul/25 9:28 AM |  | 3 |  |  |  |  | 8
Task | RDLOA-73 | 28078 | [Dev][RD][LineOA][BFF] Change matching message | First Nattapon | 64001d5e896d10ebd470f6c1 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 11/Jul/25 4:16 PM | 22/Jul/25 2:49 PM |  | 2 |  |  |  |  | 4
Task | RDLOA-72 | 28077 | [Dev][RD][LineOA][BFF] Enhance binding Line Account support new params | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 11/Jul/25 4:13 PM | 22/Jul/25 9:44 AM |  | 2 | BFF |  |  |  | 4
Task | RDLOA-71 | 28076 | [Dev][RD][LineOA][SSO-User] Enhance binding line OA endpoint | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 11/Jul/25 4:12 PM | 22/Jul/25 9:44 AM |  | 3 | InternalAPI | sso-user |  |  | 8
Story | DEVRDCT-117 | 28027 | [DEV][CLEVERTAP][RD] Implement Event feed with filtering former events | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Jack:Warin Kesorn | 61a98e8e744c4d00693281d1 | Low | To Do |  | 11/Jul/25 1:44 PM | 17/Jul/25 10:12 AM |  | 5 | CleverTap |  |  | 86400 | 24
Story | RDAPS-83 | 27956 | [Dev][RD][Rewards Service] Improve reserve and release product stock to avoid DB deadlock issue | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Done |  | 10/Jul/25 9:07 PM | 23/Jul/25 4:25 PM |  | 2 | rewards-api | rewards-consumer |  | 36000 | 4
Story | DEVRRBOF-114 | 27804 | [Dev][RD]Optimize Coupon Transaction Index Page to Prevent Initial Data Load | thanyapath sunthornchaisadom | 6163a9eac7bea400698ab7af | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 09/Jul/25 5:59 AM | 24/Jul/25 5:05 PM |  | 2 |  |  |  |  | 4
Story | RDAPS-80 | 27785 | [Dev][RD][BFF] Optimize workflow for using API v3 to reduce MongoDB query load | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Done |  | 08/Jul/25 10:14 PM | 23/Jul/25 4:24 PM |  | 5 | BFF |  |  | 108000 | 24
Bug | DEVRDSUP-33 | 27770 | [SUP-46][A920 BTS Reconciliation] Some Transactions of Cloud card those sold from A920 were stamped as online transaction | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Abhinaf Singh | 712020:a81c99dd-d5cd-44bd-950a-32f4ff7d56ac | High | ACCEPTED |  | 08/Jul/25 4:57 PM | 18/Jul/25 10:10 AM | [6 empty] | 0
Story | RDAPS-66 | 27732 | [Dev][RD][BFF] Change text information for Full Basket | First Nattapon | 64001d5e896d10ebd470f6c1 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 08/Jul/25 10:53 AM | 17/Jul/25 7:39 PM | 08/Jul/25 12:00 AM | 0 | BFF |  |  | 7200 | 0 | มาจาก Sprint 2 | ตัด 1 point จาก 1 point
Bug | RDAPS-62 | 27682 | [Dev][RD] E-Receipt Incomplete Generation Issue | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Closed |  | 07/Jul/25 2:27 PM | 22/Jul/25 4:03 PM |  |  | rr-scheduler-consumer |  |  |  | 0
Task | DEVRDCT-116 | 27493 | [Dev][RD][Initial User Property] Fix wrong card and enrichment detail | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 03/Jul/25 3:33 PM | 15/Jul/25 5:42 PM | 04/Jul/25 12:00 AM | 0 | sso-mimir |  |  | 28800 | 0 | มาจาก Sprint 2 | ตัด 3 point จาก 3 point
Sub-task | DEVRDCT-111 | 27219 | [QA] Test execution Subscription Report |  |  | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 01/Jul/25 1:59 PM | 18/Jul/25 4:56 PM | [6 empty] | 0
Sub-task | DEVRDCT-110 | 27216 | [QA] Create test case Subscription Report | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 01/Jul/25 1:59 PM | 18/Jul/25 4:56 PM | [6 empty] | 0
Sub-task | RDLOA-42 | 27213 | [QA] Create Test Case & Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 01/Jul/25 1:58 PM | 18/Jul/25 8:45 AM | [6 empty] | 0 | มาจาก Sprint 2
Sub-task | RDLOA-41 | 27210 | [QA] Create Test Case & Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 01/Jul/25 1:58 PM | 18/Jul/25 8:41 AM | [6 empty] | 0 | มาจาก Sprint 2
Sub-task | RDLOA-40 | 27207 | [QA] Create Test Case & Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 01/Jul/25 1:57 PM | 18/Jul/25 8:42 AM | [6 empty] | 0 | มาจาก Sprint 2
Sub-task | RDLOA-38 | 27201 | [QA] Create Test Case & Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 01/Jul/25 1:57 PM | 18/Jul/25 8:42 AM | [6 empty] | 0 | มาจาก Sprint 2
Sub-task | RDLOA-37 | 27198 | [QA] Create Test Case & Run Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 01/Jul/25 1:57 PM | 17/Jul/25 10:56 AM | [6 empty] | 0 | มาจาก Sprint 2
Sub-task | RDLOA-36 | 27195 | [QA] Create Test Case & Run Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 01/Jul/25 1:56 PM | 17/Jul/25 10:56 AM | [6 empty] | 0 | มาจาก Sprint 2
Sub-task | RDLOA-35 | 27192 | [QA] Create Test Case & Run Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 01/Jul/25 1:56 PM | 17/Jul/25 10:56 AM | [6 empty] | 0 | มาจาก Sprint 2
Sub-task | RDLOA-34 | 27189 | [QA] Create Test Case & Run Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 01/Jul/25 1:56 PM | 17/Jul/25 10:56 AM | [6 empty] | 0 | มาจาก Sprint 2
Sub-task | RDLOA-33 | 27186 | [QA] Create Test Case & Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 01/Jul/25 1:56 PM | 18/Jul/25 8:42 AM | [6 empty] | 0 | มาจาก Sprint 2
Sub-task | RDLOA-32 | 27183 | [QA] Create Test Case & Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 01/Jul/25 1:56 PM | 24/Jul/25 5:21 PM | [6 empty] | 0 | มาจาก Sprint 2
Sub-task | RDLOA-31 | 27179 | [QA] Create Test Case & Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 01/Jul/25 1:55 PM | 18/Jul/25 8:41 AM | [6 empty] | 0 | มาจาก Sprint 2
Sub-task | DEVRDCT-109 | 27176 | [QA] Execution test Partner Binding |  |  | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 01/Jul/25 1:55 PM | 18/Jul/25 4:56 PM | [6 empty] | 0
Sub-task | DEVRDCT-108 | 27173 | [QA] Create test case Partner Binding | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 01/Jul/25 1:55 PM | 18/Jul/25 4:56 PM | [6 empty] | 0
Sub-task | DEVRDCT-107 | 27170 | [QA] Create test case Consent Events | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 01/Jul/25 1:54 PM | 17/Jul/25 10:54 AM | [6 empty] | 0 | มาจาก Sprint 2
Sub-task | DEVRDCT-106 | 27164 | [QA] Test execution Consent Events | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 01/Jul/25 1:54 PM | 21/Jul/25 4:48 PM | [6 empty] | 0 | มาจาก Sprint 2
Sub-task | DEVRDCT-105 | 27149 | [QA] Execution test Sign Up Event | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 01/Jul/25 1:53 PM | 24/Jul/25 5:50 PM | [6 empty] | 0 | มาจาก Sprint 2
Sub-task | DEVRDCT-104 | 27123 | [QA] Create test case Sign Up Event | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | In Progress |  | 01/Jul/25 1:42 PM | 24/Jul/25 5:50 PM | [6 empty] | 0 | มาจาก Sprint 2
Sub-task | DEVRDCT-103 | 27117 | [QA] Execution test Implement Update user profile #2 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | In Progress |  | 01/Jul/25 1:40 PM | 15/Jul/25 2:48 PM | [6 empty] | 0 | มาจาก Sprint 2
Sub-task | DEVRDCT-102 | 27114 | [QA] Create test case Implement Update user profile #2 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 01/Jul/25 1:39 PM | 08/Jul/25 10:20 AM | [6 empty] | 0 | มาจาก Sprint 2
Sub-task | DEVRDCT-101 | 27059 | Implement |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 30/Jun/25 5:18 PM | 30/Jun/25 5:18 PM | [6 empty] | 0 | มาจาก Sprint 2
Sub-task | DEVRDCT-100 | 27056 | POC SSO User can support this event |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 30/Jun/25 5:18 PM | 30/Jun/25 5:19 PM | [6 empty] | 0 | มาจาก Sprint 2
Sub-task | RDLOA-30 | 27043 | Unit Test | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 30/Jun/25 3:49 PM | 07/Jul/25 11:11 AM | [6 empty] | 0 | มาจาก Sprint 2
Sub-task | RDLOA-29 | 27040 | Implement | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 30/Jun/25 3:49 PM | 07/Jul/25 11:11 AM | [6 empty] | 0 | มาจาก Sprint 2
Story | DEVRDCT-99 | 27031 | [Dev][RD][CleverTap][SSO-Mimir] Enhance import LINE OA support upload user properties | thanyapath sunthornchaisadom | 6163a9eac7bea400698ab7af | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 30/Jun/25 1:33 PM | 24/Jul/25 5:05 PM |  | 0 |  |  |  | 28800 | 0 | มาจาก Sprint 2 | ตัด 3 point จาก 3 point
Story | RDLOA-28 | 26991 | [Dev][RD][LineOA][SSO-User] Create new endpoint for unbind LINE Account | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 29/Jun/25 6:06 PM | 24/Jul/25 5:05 PM |  | 0 |  |  |  | 28800 | 0 | มาจาก Sprint 2 | ตัด 3 point จาก 3 point
Story | RDLOA-27 | 26990 | [Dev][RD][LineOA][SSO-User] Create new endpoint for get LINE event logs | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 29/Jun/25 5:41 PM | 24/Jul/25 5:25 PM |  | 0 |  |  |  | 28800 | 0 | มาจาก Sprint 2 | ตัด 3 point จาก 3 point
Story | RDLOA-26 | 26989 | [Dev][RD][LineOA][SSO-User] Create endpoint to check matching trader id | Wassana Mokman | 62835bb1ca7d7f00690051de | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 29/Jun/25 5:39 PM | 24/Jul/25 5:05 PM | 03/Jul/25 12:00 AM | 0 | sso-user |  |  | 28800 | 0 | มาจาก Sprint 2 | ตัด 3 point จาก 3 point
Story | RDLOA-25 | 26988 | [Dev][RD][LineOA][RR-Backoffice][Member Detail] Line Account Logs page | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 29/Jun/25 5:04 PM | 24/Jul/25 5:43 PM | 21/Jul/25 12:00 AM | 3 | rr-backoffice |  |  |  | 8
Story | RDLOA-24 | 26987 | [Dev][RD][LineOA][RR-Backoffice][Member Detail] Profile page | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 29/Jun/25 5:04 PM | 24/Jul/25 5:43 PM | 18/Jul/25 12:00 AM | 5 | rr-backoffice |  |  | 57600 | 24
Story | RDLOA-23 | 26986 | [Dev][RD][LineOA][RR-Backoffice][Member Detail] Index Page | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 29/Jun/25 5:03 PM | 24/Jul/25 5:43 PM | 16/Jul/25 12:00 AM | 2 | rr-backoffice |  |  |  | 4
Story | DEVRDCT-97 | 26981 | [Dev][RD][Clever Tap #2][Enhance] Subscription Report |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 29/Jun/25 12:52 AM | 18/Jul/25 4:59 PM |  |  | change-request |  |  |  | 0
Story | DEVRDCT-95 | 26979 | [Dev][RD][Clever Tap #2] Partner Binding |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 29/Jun/25 12:50 AM | 18/Jul/25 4:59 PM |  |  | change-request |  |  |  | 0
Story | DEVRDCT-94 | 26978 | [Dev][RD][Clever Tap #2] Consent events | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 29/Jun/25 12:49 AM | 24/Jul/25 5:05 PM | 09/Jul/25 12:00 AM | 0 | sso-user |  |  | 28800 | 0 | มาจาก Sprint 2 | ตัด 3 point จาก 3 point
Story | DEVRDCT-89 | 26973 | [Dev][RD][Clever Tap #2] Sign Up Event | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 29/Jun/25 12:48 AM | 25/Jul/25 9:13 AM |  | 0 |  |  |  | 86400 | 0 | มาจาก Sprint 2 | ตัด 5 point จาก 5 point
Story | DEVRDCT-88 | 26972 | [Dev][RD][Clever Tap #2] Implement Update user profile #2 to CT | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 29/Jun/25 12:47 AM | 24/Jul/25 5:05 PM | 07/Jul/25 12:00 AM | 0 | sso-user |  |  | 86400 | 0 | มาจาก Sprint 2 | ตัด 5 point จาก 5 point
Story | RDLOA-22 | 26970 | [Dev][RD][LineOA][POC] Integrate LINE OA Messaging API | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 29/Jun/25 12:45 AM | 21/Jul/25 9:27 AM |  | 0 |  |  |  |  | 0 | มาจาก Sprint 2 | ตัด 3 point จาก 3 point
Story | RDLOA-21 | 26969 | [Dev][RD][LineOA][SSO-User] Create webhook endpoint and handle LINE OA Webhook | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Review |  | 29/Jun/25 12:22 AM | 23/Jul/25 11:18 AM |  | 5 | sso-user |  |  |  | 24
Story | RDLOA-20 | 26968 | [Dev][RD][LineOA][SSO-User] Create new endpoint for record line log event | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 29/Jun/25 12:12 AM | 22/Jul/25 11:10 AM |  | 2 |  |  |  |  | 4
Story | RDLOA-19 | 26967 | [Dev][RD][LineOA][CT][SSO-User] Event x LINE account binding | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 28/Jun/25 11:15 PM | 24/Jul/25 5:43 PM |  | 3 | sso-user |  |  |  | 8
Story | RDLOA-18 | 26966 | [Dev][RD][LineOA][CT][SSO-User] Profile x LINE account to CT | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready to Staging |  | 28/Jun/25 11:14 PM | 24/Jul/25 5:43 PM |  | 3 | sso-user |  |  |  | 8
Story | RDLOA-15 | 26879 | [Dev][RD][LineOA][SSO-User] Implement API for LINE OA Binding | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 26/Jun/25 9:31 PM | 24/Jul/25 5:05 PM | 09/Jul/25 12:00 AM | 0 | sso-user |  |  | 86400 | 0 | มาจาก Sprint 2 | ตัด 5 point จาก 5 point
Story | RDLOA-14 | 26878 | [Dev][RD][LineOA][SSO-User] Implement API to Get LINE OA Consent Text | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 26/Jun/25 9:31 PM | 24/Jul/25 5:05 PM |  | 0 | sso-user |  |  | 28800 | 0 | มาจาก Sprint 2 | ตัด 3 point จาก 3 point
Story | RDLOA-13 | 26877 | [Dev][RD][LineOA][SSO-User] Enhance Get Rewards User Profile API to Include Bind Info | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 26/Jun/25 9:31 PM | 24/Jul/25 5:05 PM | 04/Jul/25 12:00 AM | 0 | sso-user |  |  | 86400 | 0 | มาจาก Sprint 2 | ตัด 5 point จาก 5 point
Story | RDLOA-12 | 26876 | [Dev][RD][LineOA][BFF] Enhance check Matching Account API | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 26/Jun/25 9:27 PM | 24/Jul/25 5:05 PM |  | 0 | BFF |  |  | 28800 | 0 | มาจาก Sprint 2 | ตัด 3 point จาก 3 point
Story | RDLOA-11 | 26875 | [Dev][RD][LineOA][BFF] Implement API for LINE OA Binding | Wassana Mokman | 62835bb1ca7d7f00690051de | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 26/Jun/25 9:27 PM | 24/Jul/25 5:05 PM |  | 0 | BFF |  |  | 28800 | 0 | มาจาก Sprint 2 | ตัด 3 point จาก 3 point
Story | RDLOA-10 | 26874 | [Dev][RD][LineOA][BFF] Implement API to Get LINE OA Consent Text | thanyapath sunthornchaisadom | 6163a9eac7bea400698ab7af | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 26/Jun/25 9:27 PM | 24/Jul/25 5:05 PM |  | 0 | BFF |  |  | 28800 | 0 | มาจาก Sprint 2 | ตัด 3 point จาก 3 point
Story | RDLOA-9 | 26873 | [Dev][RD][LineOA][BFF] Enhance get user profile API | Moss : Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 26/Jun/25 9:26 PM | 24/Jul/25 5:05 PM |  | 0 | BFF |  |  | 28800 | 0 | มาจาก Sprint 2 | ตัด 3 point จาก 3 point

## Sprint 2
Issue Type | Issue key | Issue id | Summary | Assignee | Assignee Id | Reporter | Reporter Id | Priority | Status | Resolution | Created | Updated | Due date | Custom field (Story Points) | Manhour | Sprint Movement | Note
Bug | DEVRRBOF-117 | 27879 | [S2][Coupon TXN] The card detail is not auto prefill | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 09/Jul/25 1:30 PM | 10/Jul/25 11:48 AM |  |  | 0
Bug | DEVRRBOF-116 | 27878 | [S2][Coupon TXN] Unable to retrieve coupon detail with redemption coupon | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | RETESTING |  | 09/Jul/25 1:28 PM | 11/Jul/25 9:42 AM |  |  | 0
Bug | RDAPS-81 | 27852 | [S3][API][Using/Used Coupon][Coupon Usage Limit] Changed logic of Coupon Usage Limit get "Daily coupon usage limit reached" after only used the coupon | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | UNDER VALIDATION |  | 09/Jul/25 10:51 AM | 11/Jul/25 9:12 AM |  |  | 0
Bug | DEVRRBOF-115 | 27850 | [S2][Coupon TXN] Unable to mark point earning coupon | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 09/Jul/25 10:20 AM | 09/Jul/25 6:56 PM |  |  | 0
Task | RDAPS-79 | 27769 | [Dev] Exported receipts and place in a google drive. | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | In Progress |  | 08/Jul/25 4:00 PM | 11/Jul/25 7:45 AM | 09/Jul/25 12:00 AM | 2 | 4
Task | RDAPS-76 | 27763 | [DEV][ADHOC][VISIONARY] Reverse transaction and reset campaign | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 08/Jul/25 3:28 PM | 11/Jul/25 7:24 AM | 08/Jul/25 12:00 AM | 1 | 2
Task | RDAPS-67 | 27754 | [Dev][RD][SUB][Re-State] Request dev to re-state 4 BTS coupons for CRM case lot 32. 08/07/2025 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | High | Done |  | 08/Jul/25 2:06 PM | 08/Jul/25 2:09 PM | 08/Jul/25 12:00 AM | 1 | 2
Bug | DEVRRBOF-113 | 27737 | [S2][Coupon TXN] Missing Coupon detail after mark coupon as used | nattapon napasai | 64001d5e896d10ebd470f6c1 | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 08/Jul/25 11:35 AM | 09/Jul/25 5:45 PM |  |  | 0
Story | RDAPS-66 | 27732 | [Dev][RD][BFF] Change text information for Full Basket | nattapon napasai | 64001d5e896d10ebd470f6c1 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 08/Jul/25 10:53 AM | 11/Jul/25 7:45 AM | 08/Jul/25 12:00 AM | 1 | 2
Sub-task | RDAPS-65 | 27729 | [QA] Test execution (version RDAPS 0.4) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | In Progress |  | 08/Jul/25 10:10 AM | 09/Jul/25 10:29 AM |  |  | 0
Bug | DEVRRBOF-112 | 27727 | [S2][Coupon TXN] Details on 'Mark used reward coupon' popup is incorrect | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 08/Jul/25 10:04 AM | 09/Jul/25 11:19 AM |  |  | 0
Bug | DEVRRBOF-110 | 27719 | [S2][Coupon TXN] Reward detail is incorrect for subscription coupon | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 07/Jul/25 6:24 PM | 09/Jul/25 11:28 AM |  |  | 0
Story | RDTHANA-8 | 27685 | [DEV][RD][Highly Estimation] Partner Loyalty | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 07/Jul/25 3:17 PM | 11/Jul/25 7:51 AM |  | 1 | 2
Test Execution | DEVRRBOF-90 | 27670 | [TX][Dev][RD][RR Backoffice] Sprint2 - Staging | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Progress |  | 07/Jul/25 1:20 PM | 10/Jul/25 11:48 AM |  |  | 0
Task | RDAPS-61 | 27582 | [Dev][RD][SUB][Re-State] Request dev to re-state 5 BTS coupons for CRM case lot 31. 04/07/2025 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | High | Done |  | 04/Jul/25 3:29 PM | 04/Jul/25 5:02 PM | 04/Jul/25 12:00 AM | 1 | 2
Task | DEVRDCT-116 | 27493 | [Dev][RD][Initial User Property] Fix wrong card and enrichment detail | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 03/Jul/25 3:33 PM | 08/Jul/25 2:26 PM | 04/Jul/25 12:00 AM | 3 | 8
Sub-task | DEVRDCT-115 | 27491 | [QA] Test execution (version 1.2) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 03/Jul/25 2:41 PM | 03/Jul/25 3:44 PM |  |  | 0
Task | DEVRDCT-114 | 27489 | [Dev][RD][Clever Tap][RR-Scheduler] Wrong Type USE_FOR | nattapon napasai | 64001d5e896d10ebd470f6c1 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 03/Jul/25 2:30 PM | 11/Jul/25 9:20 AM |  | 2 | 4
Bug | RDAPS-60 | 27483 | [Dev][RD] Root cause and prevention analysis | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Resolved |  | 03/Jul/25 10:10 AM | 07/Jul/25 2:31 PM |  |  | 0
Test Execution | APS-157 | 27482 | [TX][Back-office] PROD Deployment on 03 July 2025 |  |  | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | To Do |  | 03/Jul/25 9:52 AM | 03/Jul/25 11:43 AM |  |  | 0
Task | RDAPS-59 | 27462 | [Dev][RD][SUB][Re-State] Request dev to re-state 9 BTS coupons for CRM case lot 29. 02/07/2025 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | High | Done |  | 02/Jul/25 6:51 PM | 02/Jul/25 6:52 PM | 02/Jul/25 12:00 AM | 1 | 2
Task | RDAPS-58 | 27458 | [Dev][RD][SUB][Re-State] Request dev to re-state 6 BTS coupons for CRM case using to redeem lot 8. 02/07/2025 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | High | Done |  | 02/Jul/25 6:48 PM | 02/Jul/25 6:49 PM | 02/Jul/25 12:00 AM | 1 | 2
Bug | DEVRDCT-112 | 27308 | [S3][Clever Tap][Partner Loyalty] CleverTap Service NOT show Spending partner after make transaction success | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Closed |  | 02/Jul/25 3:50 PM | 02/Jul/25 6:36 PM |  |  | 0
Story | RDTHANA-7 | 27306 | [DEV][RD][Highly Estimation] APIs for Front-End | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | To Do |  | 02/Jul/25 3:04 PM | 11/Jul/25 9:22 AM |  | 2 | 4
Story | RDTHANA-6 | 27305 | [DEV][RD][Highly Estimation] Backoffice | Aom: Pornsawan Polnyiem |  | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 02/Jul/25 3:04 PM | 11/Jul/25 9:21 AM |  | 3 | 8
Story | RDAPS-57 | 27285 | [Dev][RD] Improve logic use coupon | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 02/Jul/25 1:21 PM | 09/Jul/25 10:52 PM |  | 3 | 8
Task | RDAPS-54 | 27241 | [DEV][RD][ADHOC][RR Request] Create Rewards Group for July 2025 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 01/Jul/25 6:01 PM | 02/Jul/25 10:02 AM | 01/Jul/25 12:00 AM | 1 | 2
Story | RDAPS-53 | 27221 | [Dev][RD][ADHOC] Super Turtle Plus Engagement Report | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 01/Jul/25 2:48 PM | 09/Jul/25 9:58 AM |  | 2 | 4
Sub-task | RDLOA-42 | 27213 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 01/Jul/25 1:58 PM | 01/Jul/25 1:58 PM |  |  | 0
Sub-task | RDLOA-41 | 27210 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Ready To Test |  | 01/Jul/25 1:58 PM | 08/Jul/25 10:16 AM |  |  | 0
Sub-task | RDLOA-40 | 27207 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Ready To Test |  | 01/Jul/25 1:57 PM | 08/Jul/25 10:16 AM |  |  | 0
Sub-task | RDLOA-39 | 27204 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 01/Jul/25 1:57 PM | 01/Jul/25 1:57 PM |  |  | 0
Sub-task | RDLOA-38 | 27201 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Ready To Test |  | 01/Jul/25 1:57 PM | 08/Jul/25 10:16 AM |  |  | 0
Sub-task | RDLOA-37 | 27198 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 01/Jul/25 1:57 PM | 07/Jul/25 10:15 AM |  |  | 0
Sub-task | RDLOA-36 | 27195 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 01/Jul/25 1:56 PM | 07/Jul/25 10:15 AM |  |  | 0
Sub-task | RDLOA-35 | 27192 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 01/Jul/25 1:56 PM | 07/Jul/25 10:15 AM |  |  | 0
Sub-task | RDLOA-34 | 27189 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 01/Jul/25 1:56 PM | 09/Jul/25 11:56 AM |  |  | 0
Sub-task | RDLOA-33 | 27186 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | To Do |  | 01/Jul/25 1:56 PM | 06/Jul/25 8:00 PM |  |  | 0
Sub-task | RDLOA-32 | 27183 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | In Progress |  | 01/Jul/25 1:56 PM | 08/Jul/25 10:22 AM |  |  | 0
Sub-task | RDLOA-31 | 27179 | [QA] Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Ready To Test |  | 01/Jul/25 1:55 PM | 08/Jul/25 10:16 AM |  |  | 0
Sub-task | DEVRDCT-107 | 27170 | [QA] Create test case Consent Events | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 01/Jul/25 1:54 PM | 01/Jul/25 1:54 PM |  |  | 0
Sub-task | DEVRDCT-106 | 27164 | [QA] Test execution Consent Events |  |  | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 01/Jul/25 1:54 PM | 01/Jul/25 1:54 PM |  |  | 0
Sub-task | DEVRDCT-105 | 27149 | [QA] Execution test Sign Up Event |  |  | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 01/Jul/25 1:53 PM | 01/Jul/25 1:53 PM |  |  | 0
Sub-task | DEVRDCT-104 | 27123 | [QA] Create test case Sign Up Event | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | In Progress |  | 01/Jul/25 1:42 PM | 08/Jul/25 3:30 PM |  |  | 0
Sub-task | DEVRDCT-103 | 27117 | [QA] Execution test Implement Update user profile #2 |  |  | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | To Do |  | 01/Jul/25 1:40 PM | 01/Jul/25 1:52 PM |  |  | 0
Sub-task | DEVRDCT-102 | 27114 | [QA] Create test case Implement Update user profile #2 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 01/Jul/25 1:39 PM | 08/Jul/25 10:20 AM |  |  | 0
Sub-task | DEVRRBOF-76 | 27101 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Progress |  | 01/Jul/25 1:25 PM | 07/Jul/25 1:30 PM |  |  | 0
Sub-task | DEVRRBOF-75 | 27098 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 01/Jul/25 1:25 PM | 07/Jul/25 1:27 PM |  |  | 0
Sub-task | DEVRRBOF-74 | 27092 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | In Progress |  | 01/Jul/25 1:25 PM | 07/Jul/25 8:52 PM |  |  | 0
Sub-task | DEVRRBOF-73 | 27089 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 01/Jul/25 1:25 PM | 04/Jul/25 12:52 PM |  |  | 0
Story | RDAPS-52 | 27075 | [Dev][RD][SUB] Many BTS coupons from A920 code 99999999 incident needs to be mark used | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 01/Jul/25 6:19 AM | 03/Jul/25 10:06 AM |  | 5 | 24
Task | RDAPS-51 | 27073 | [Dev][RD][SUB][Re-State] Request dev to re-state 7 BTS coupons for CRM case using to redeem lot 7. 30/06/2025 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | High | Done |  | 30/Jun/25 6:43 PM | 02/Jul/25 10:02 AM | 30/Jun/25 12:00 AM | 1 | 2
Task | RDAPS-50 | 27069 | [Dev][RD][SUB][Re-State] Request dev to re-state 4 BTS coupons for CRM case lot 29. 30/06/2025 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | High | Done |  | 30/Jun/25 6:23 PM | 02/Jul/25 10:02 AM | 30/Jun/25 12:00 AM | 1 | 2
Story | RDTHANA-5 | 27063 | [DEV][RD][Highly Estimation] HR solution | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | To Do |  | 30/Jun/25 5:39 PM | 11/Jul/25 9:21 AM |  | 3 | 8
Sub-task | DEVRDCT-101 | 27059 | Implement |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 30/Jun/25 5:18 PM | 30/Jun/25 5:18 PM |  |  | 0
Sub-task | DEVRDCT-100 | 27056 | POC SSO User can support this event |  |  | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | To Do |  | 30/Jun/25 5:18 PM | 30/Jun/25 5:19 PM |  |  | 0
Task | RDAPS-49 | 27053 | [Dev][RD][SUB][Re-State] Request dev to re-state 15 BTS coupons for CRM case using to redeem lot 6. 30/06/2025 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | High | Done |  | 30/Jun/25 4:40 PM | 30/Jun/25 4:53 PM | 30/Jun/25 12:00 AM | 1 | 2
Task | RDAPS-48 | 27049 | [Dev][RD][SUB][Re-State] Request dev to re-state 2 BTS coupons for CRM case lot 28. 30/06/2025 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | High | Done |  | 30/Jun/25 4:36 PM | 30/Jun/25 4:39 PM | 30/Jun/25 12:00 AM | 1 | 2
Sub-task | RDLOA-30 | 27043 | Unit Test | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 30/Jun/25 3:49 PM | 07/Jul/25 11:11 AM |  |  | 0
Sub-task | RDLOA-29 | 27040 | Implement | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 30/Jun/25 3:49 PM | 07/Jul/25 11:11 AM |  |  | 0
Bug | RDAPS-47 | 27038 | [Dev][RD][Some partner coupons in SUB doesn't expire within 30 mins as set the reward item.] | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Closed |  | 30/Jun/25 3:22 PM | 10/Jul/25 3:20 PM |  |  | 0
Story | DEVRDCT-99 | 27031 | [Dev][RD][CleverTap][SSO-Mimir] Enhance import LINE OA support upload user properties | thanyapath sunthornchaisadom | 6163a9eac7bea400698ab7af | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 30/Jun/25 1:33 PM | 11/Jul/25 9:39 AM |  | 3 | 8
Story | RDAPS-46 | 27030 | [Dev][RD][Order Consumer] Improve sync txn to DA | Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 30/Jun/25 12:51 PM | 04/Jul/25 5:55 PM |  | 1 | 2
Bug | DEVRDCT-98 | 26999 | [S3][Clever Tap] CleverTap event : MEMBER_COUPON NOT show "redeemed" on Clever Tap | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Closed |  | 30/Jun/25 10:14 AM | 02/Jul/25 6:45 PM |  |  | 0
Story | RDLOA-28 | 26991 | [Dev][RD][LineOA][SSO-User] Create new endpoint for unbind LINE Account | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 29/Jun/25 6:06 PM | 11/Jul/25 9:40 AM |  | 3 | 8
Story | RDLOA-27 | 26990 | [Dev][RD][LineOA][SSO-User] Create new endpoint for get LINE event logs | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 29/Jun/25 5:41 PM | 09/Jul/25 11:36 AM |  | 3 | 8
Story | RDLOA-26 | 26989 | [Dev][RD][LineOA][SSO-User] Create endpoint to check matching trader id | Wassana Mokman | 62835bb1ca7d7f00690051de | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 29/Jun/25 5:39 PM | 09/Jul/25 11:36 AM | 03/Jul/25 12:00 AM | 3 | 8
Story | DEVRDCT-96 | 26980 | [Dev][RD][Clever Tap #2.2][POC] Event filter | Warin Kesorn | 61a98e8e744c4d00693281d1 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 29/Jun/25 12:51 AM | 08/Jul/25 12:49 PM |  | 8 | 32
Story | DEVRDCT-94 | 26978 | [Dev][RD][Clever Tap #2] Consent events | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Progress |  | 29/Jun/25 12:49 AM | 11/Jul/25 9:36 AM | 09/Jul/25 12:00 AM | 3 | 8
Story | DEVRDCT-89 | 26973 | [Dev][RD][Clever Tap #2] Sign Up Event | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Progress |  | 29/Jun/25 12:48 AM | 11/Jul/25 9:35 AM |  | 5 | 24
Story | DEVRDCT-88 | 26972 | [Dev][RD][Clever Tap #2] Implement Update user profile #2 to CT | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Progress |  | 29/Jun/25 12:47 AM | 11/Jul/25 9:33 AM | 07/Jul/25 12:00 AM | 5 | 24
Story | RDLOA-22 | 26970 | [Dev][RD][LineOA][POC] Integrate LINE OA Messaging API | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | In Progress |  | 29/Jun/25 12:45 AM | 11/Jul/25 9:20 AM |  | 3 | 8
Bug | DEVRDCT-86 | 26950 | [S3][Clever Tap] CleverTap event : MEMBER_COUPON NOT show update status on Clever Tap | nattapon napasai | 64001d5e896d10ebd470f6c1 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Closed |  | 27/Jun/25 3:57 PM | 02/Jul/25 6:45 PM |  |  | 0 | มาจาก Sprint 1
Story | RDLOA-16 | 26880 | [Dev][RD][LineOA][SSO-User] Database Migrations | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 26/Jun/25 9:49 PM | 11/Jul/25 9:40 AM |  | 2 | 4
Story | RDLOA-15 | 26879 | [Dev][RD][LineOA][SSO-User] Implement API for LINE OA Binding | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Jun/25 9:31 PM | 09/Jul/25 6:20 PM | 09/Jul/25 12:00 AM | 5 | 24
Story | RDLOA-14 | 26878 | [Dev][RD][LineOA][SSO-User] Implement API to Get LINE OA Consent Text | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Jun/25 9:31 PM | 11/Jul/25 9:42 AM |  | 3 | 8
Story | RDLOA-13 | 26877 | [Dev][RD][LineOA][SSO-User] Enhance Get Rewards User Profile API to Include Bind Info | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Jun/25 9:31 PM | 09/Jul/25 11:36 AM | 04/Jul/25 12:00 AM | 5 | 24
Story | RDLOA-12 | 26876 | [Dev][RD][LineOA][BFF] Enhance check Matching Account API | Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Jun/25 9:27 PM | 10/Jul/25 11:26 PM |  | 3 | 8
Story | RDLOA-11 | 26875 | [Dev][RD][LineOA][BFF] Implement API for LINE OA Binding | Wassana Mokman | 62835bb1ca7d7f00690051de | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 26/Jun/25 9:27 PM | 11/Jul/25 9:41 AM |  | 3 | 8
Story | RDLOA-10 | 26874 | [Dev][RD][LineOA][BFF] Implement API to Get LINE OA Consent Text | thanyapath sunthornchaisadom | 6163a9eac7bea400698ab7af | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready to Staging |  | 26/Jun/25 9:27 PM | 11/Jul/25 9:41 AM |  | 3 | 8
Story | RDLOA-9 | 26873 | [Dev][RD][LineOA][BFF] Enhance get user profile API | Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 26/Jun/25 9:26 PM | 09/Jul/25 4:03 PM |  | 3 | 8
Story | DEVRRBOF-69 | 26830 | [Dev][RD][BE] Enhance mark used coupon v2 | nattapon napasai | 64001d5e896d10ebd470f6c1 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 25/Jun/25 8:07 PM | 09/Jul/25 11:19 AM | 04/Jul/25 12:00 AM | 8 | 32
Story | DEVRRBOF-68 | 26816 | [Dev][RD][RR Backoffice] Analyze mark use feature | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 25/Jun/25 4:28 PM | 04/Jul/25 10:03 AM |  | 3 | 8
Story | DEVRRBOF-67 | 26815 | [Dev][RD][RR Backoffice] Mark use coupon | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Ready To Test |  | 25/Jun/25 3:31 PM | 10/Jul/25 11:48 AM | 04/Jul/25 12:00 AM | 5 | 24
Story | RDAPS-36 | 26692 | [Dev][RD] ETL Enhancement for Redemption Vouchers Status | thanyapath sunthornchaisadom | 6163a9eac7bea400698ab7af | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 24/Jun/25 5:20 PM | 10/Jul/25 3:25 PM |  | 1 | 2
Story | RDAPS-32 | 26649 | [Dev][RD] ETL implementation for Redemption Vouchers Master | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 23/Jun/25 6:05 PM | 10/Jul/25 3:25 PM |  | 3 | 8
Task | DEVRDCT-48 | 26590 | [Dev][RD][Clever Tap][Batch#1][Scheduler] Feed Member Coupon to CleverTap Service for coupon update status | nattapon napasai | 64001d5e896d10ebd470f6c1 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 22/Jun/25 4:09 PM | 11/Jul/25 7:47 AM | 26/Jun/25 12:00 AM |  | 0 | มาจาก Sprint 1 | ตัด 5 point จาก 5 point
Sub-task | DEVRDCT-37 | 26499 | Run Test execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 20/Jun/25 1:37 PM | 02/Jul/25 5:27 PM |  |  | 0 | มาจาก Sprint 1
Sub-task | DEVRDCT-36 | 26496 | Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 20/Jun/25 1:37 PM | 02/Jul/25 5:26 PM |  |  | 0 | มาจาก Sprint 1
Story | RDAPS-12 | 25542 | [Dev][RD][Adhoc] Fix Sync RR Profile when import member | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 18/Jun/25 11:09 AM | 11/Jul/25 1:14 AM |  | 3 | 8
Task | DEVRDCT-11 | 24152 | [Dev][RD][Clever Tap][Batch#1][Import Initial] Member counpon | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 11/Jun/25 1:40 PM | 02/Jul/25 10:26 AM | 26/Jun/25 12:00 AM |  | 0 | มาจาก Sprint 1 | ตัด 3 point จาก 3 point
Task | DEVRDCT-3 | 24132 | [Dev][RD][Clever Tap][Batch#1][Partner Loyalty] Feed Spending partner to CleverTap Service | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 11/Jun/25 1:33 PM | 02/Jul/25 5:27 PM |  |  | 0 | มาจาก Sprint 1 | ตัด 3 point จาก 3 point
Story | RDAPS-82 | 23875 | Optimize Performance for updating expired coupons query | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Wassana Mokman | 62835bb1ca7d7f00690051de | Medium | Done |  | 16/May/25 10:10 AM | 10/Jul/25 7:16 PM |  | 2 | 4

## Sprint 1
Issue Type | Issue key | Issue id | Summary | Assignee | Assignee Id | Reporter | Reporter Id | Priority | Status | Resolution | Created | Updated | Due date | Custom field (Story Points) | Manhour
Task | RDAPS-45 | 26955 | [DEV][RD][SUB][Re-State] Request dev to re-state 4 BTS coupons for CRM case lot 27. 27/06/2025 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | High | Done |  | 27/Jun/25 5:40 PM | 27/Jun/25 5:45 PM | 27/Jun/25 12:00 AM | 1 | 2
Bug | DEVRDCT-86 | 26950 | [S3][Clever Tap] CleverTap event : MEMBER_COUPON NOT show update status on Clever Tap | nattapon napasai | 64001d5e896d10ebd470f6c1 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Closed |  | 27/Jun/25 3:57 PM | 02/Jul/25 6:45 PM |  |  | 0
Sub-task | DEVRDCT-84 | 26918 | [QA] Ctreate test cases MEMBER COUPON update status | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 27/Jun/25 10:31 AM | 27/Jun/25 10:32 AM |  |  | 0
Sub-task | DEVRDCT-83 | 26915 | [QA] Create test cases MEMBER COUPON | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 27/Jun/25 10:20 AM | 27/Jun/25 10:20 AM |  |  | 0
Sub-task | DEVRDCT-82 | 26912 | [QA] Create test cases Check-in | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 27/Jun/25 10:17 AM | 27/Jun/25 10:18 AM |  |  | 0
Task | RDAPS-44 | 26870 | [DEV][RD][SUB][Re-State] Request dev to re-state 4 BTS coupons for CRM case lot 26. 26/06/2025 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | High | Done |  | 26/Jun/25 6:02 PM | 26/Jun/25 6:07 PM | 26/Jun/25 12:00 AM | 1 | 2
Task | RDAPS-43 | 26866 | [DEV][RD][SUB][Re-State] Request dev to re-state 2 BTS coupons for CRM case using to redeem lot 5. 26/06/2025 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | High | Done |  | 26/Jun/25 5:57 PM | 26/Jun/25 6:00 PM | 26/Jun/25 12:00 AM | 1 | 2
Test Execution | DEVRRBOF-72 | 26847 | [TX][Dev][RD][RR Backoffice] Sprint1 - UAT | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 26/Jun/25 3:05 PM | 27/Jun/25 2:47 PM |  |  | 0
Sub-task | DEVRRBOF-70 | 26841 | [Redemption API] Support restate coupon back to redeemed status - usage channel | nattapon napasai | 64001d5e896d10ebd470f6c1 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 26/Jun/25 11:52 AM | 26/Jun/25 5:18 PM |  |  | 0
Task | RDAPS-42 | 26829 | [DEV][RD][SUB][Re-State] Request dev to re-state 8 BTS coupons for CRM case lot 25. 25/06/2025 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | High | Done |  | 25/Jun/25 6:05 PM | 25/Jun/25 6:11 PM | 25/Jun/25 12:00 AM | 1 | 2
Task | RDAPS-41 | 26825 | [DEV][RD][SUB][Re-State] Request dev to re-state 4 BTS coupons for CRM case using to redeem lot 4. 25/06/2025 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | High | Done |  | 25/Jun/25 5:57 PM | 25/Jun/25 6:01 PM | 25/Jun/25 12:00 AM | 1 | 2
Task | RDAPS-40 | 26819 | [DEV][ADHOC][VISIONARY][HR-Solution] Delete record in transactions table | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 25/Jun/25 5:12 PM | 26/Jun/25 9:30 AM |  | 1 | 2
Task | RDAPS-39 | 26818 | [DEV][ADHOC][VISIONARY][PL] Reverse transaction on PL | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 25/Jun/25 5:11 PM | 25/Jun/25 5:26 PM | 25/Jun/25 12:00 AM | 1 | 2
Sub-task | DEVRDCT-60 | 26805 | [QA] Test execution Check-in (version CT 1.1) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 25/Jun/25 2:24 PM | 27/Jun/25 10:17 AM |  |  | 0
Sub-task | DEVRDCT-59 | 26802 | [QA] Test execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 25/Jun/25 2:23 PM | 25/Jun/25 4:59 PM |  |  | 0
Sub-task | DEVRDCT-58 | 26709 | [QA] Test execution Member Coupon Update Status (version CT 1.1) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 25/Jun/25 10:27 AM | 25/Jun/25 5:03 PM |  |  | 0
Sub-task | DEVRDCT-57 | 26705 | [QA] Test execution MEMBER COUPON (version CT 1.1) | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 25/Jun/25 10:24 AM | 25/Jun/25 4:40 PM |  |  | 0
Task | DEVRDCT-56 | 26703 | [Dev][RD][Adjust] Export device id | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 25/Jun/25 9:47 AM | 01/Jul/25 12:07 AM |  | 1 | 2
Task | RDAPS-38 | 26701 | [DEV][RD][SUB][Re-State] Request dev to re-state 4 BTS coupons for CRM case using to redeem lot 3. 24/06/2025 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | High | Done |  | 24/Jun/25 6:46 PM | 24/Jun/25 6:46 PM | 24/Jun/25 12:00 AM | 1 | 2
Task | RDAPS-37 | 26697 | [DEV][RD][SUB][Re-State] Request dev to re-state 10 BTS coupons for CRM case lot 24. 24/06/2025 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | High | Done |  | 24/Jun/25 6:43 PM | 24/Jun/25 6:44 PM | 24/Jun/25 12:00 AM | 1 | 2
Task | RDAPS-35 | 26689 | [DEV][RD][ADHOC][A920 BTS Reconciliation][RW] Operating day in TD stamp wrong | Wassana Mokman | 62835bb1ca7d7f00690051de | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Highest | Done |  | 24/Jun/25 4:21 PM | 25/Jun/25 10:21 AM | 24/Jun/25 12:00 AM | 1 | 2
Bug | RDAPS-34 | 26685 | [S2][Redemption] Coupon usage detail is incorrect | Wassana Mokman | 62835bb1ca7d7f00690051de | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 24/Jun/25 2:14 PM | 26/Jun/25 5:17 PM | 25/Jun/25 12:00 AM |  | 0
Task | RDAPS-33 | 26684 | [DEV][RD][ADHOC][A920 BTS Reconciliation][LP] Operating day in TD stamp wrong | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Highest | Done |  | 24/Jun/25 1:58 PM | 24/Jun/25 4:42 PM | 24/Jun/25 12:00 AM | 1 | 2
Sub-task | DEVRDCT-55 | 26657 | Allow empty body Send 200 | thanyapath sunthornchaisadom | 6163a9eac7bea400698ab7af | thanyapath sunthornchaisadom | 6163a9eac7bea400698ab7af | Medium | Done |  | 24/Jun/25 10:22 AM | 26/Jun/25 10:13 AM |  |  | 0
Task | RDAPS-31 | 26648 | [DEV][RD][SUB][Re-State] Request dev to re-state 3 BTS coupons for CRM case lot 23. 23/06/2025 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | High | Done |  | 23/Jun/25 5:42 PM | 23/Jun/25 5:49 PM | 23/Jun/25 12:00 AM | 1 | 2
Story | RDAPS-30 | 26637 | [DEV][RD] Manual export packages information | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 23/Jun/25 3:59 PM | 23/Jun/25 4:43 PM |  | 1 | 2
Task | RDAPS-29 | 26632 | [DEV][RD][SUB][Re-State] Request dev to re-state 7 BTS coupons for CRM case using to redeem lot 2. 23/06/2025 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | High | Done |  | 23/Jun/25 1:27 PM | 23/Jun/25 1:37 PM | 23/Jun/25 12:00 AM | 1 | 2
Task | RDAPS-28 | 26628 | [DEV][RD][SUB][Re-State] Request dev to re-state 3 BTS coupons for CRM case lot 22. 23/06/2025 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | High | Done |  | 23/Jun/25 1:16 PM | 23/Jun/25 1:19 PM | 23/Jun/25 12:00 AM | 1 | 2
Bug | DEVRRBOF-66 | 26624 | [S3][Coupon TXN] Missing coupon details on 'Change reward coupon back to "Redeemed"' page | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 23/Jun/25 1:07 PM | 25/Jun/25 2:42 PM |  |  | 0
Task | DEVRDCT-54 | 26620 | [Dev][RD][Weekly Meeting] 2025-06-23 11:00 - 12:00 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 23/Jun/25 11:34 AM | 25/Jun/25 10:22 AM |  | 1 | 2
Bug | DEVRRBOF-65 | 26619 | [S2][Coupon TXN] Unable to re-state coupon status | Thanakorn Tawsan | 62c2971eeda95d2e3a68c3ed | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Closed |  | 23/Jun/25 11:14 AM | 10/Jul/25 3:32 PM |  |  | 0
Sub-task | DEVRDCT-53 | 26615 | Test execution - Member Coupon | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 23/Jun/25 10:18 AM | 25/Jun/25 2:51 PM |  |  | 0
Sub-task | DEVRDCT-52 | 26612 | Test execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 23/Jun/25 10:18 AM | 23/Jun/25 4:12 PM |  |  | 0
Sub-task | DEVRDCT-51 | 26609 | Test execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 23/Jun/25 10:17 AM | 23/Jun/25 4:10 PM |  |  | 0
Sub-task | DEVRDCT-50 | 26606 | Test execution - CheckIn Event | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 23/Jun/25 10:17 AM | 24/Jun/25 10:17 AM |  |  | 0
Sub-task | DEVRDCT-49 | 26603 | Test execution - SPENDING PARTNER | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 23/Jun/25 10:17 AM | 23/Jun/25 3:39 PM |  |  | 0
Task | DEVRDCT-48 | 26590 | [Dev][RD][Clever Tap][Batch#1][Scheduler] Feed Member Coupon to CleverTap Service for coupon update status | nattapon napasai | 64001d5e896d10ebd470f6c1 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Ready To Test |  | 22/Jun/25 4:09 PM | 11/Jul/25 7:47 AM | 26/Jun/25 12:00 AM | 5 | 24
Task | RDAPS-27 | 26555 | [DEV][RD][SUB][Re-State] Request dev to re-state 4 BTS coupons for CRM case lot 21. 20/06/2025 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | High | Done |  | 20/Jun/25 5:23 PM | 20/Jun/25 5:35 PM | 20/Jun/25 12:00 AM | 1 | 2
Task | RDAPS-26 | 26549 | [Dev][RD][SUB][Re-State] Request dev to re-state 4 BTS coupons for CRM case lot 20. 20/06/2025 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | High | Done |  | 20/Jun/25 5:14 PM | 20/Jun/25 5:34 PM | 20/Jun/25 12:00 AM | 1 | 2
Sub-task | DEVRDCT-47 | 26529 | [QA] Test execution SUBSCRIPTION_PURCHASE_REPORT | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 20/Jun/25 1:44 PM | 27/Jun/25 10:56 AM |  |  | 0
Sub-task | DEVRDCT-46 | 26526 | Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 20/Jun/25 1:44 PM | 26/Jun/25 1:55 PM |  |  | 0
Sub-task | DEVRDCT-45 | 26523 | [QA] Test execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 20/Jun/25 1:43 PM | 26/Jun/25 3:20 PM |  |  | 0
Sub-task | DEVRDCT-44 | 26520 | Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 20/Jun/25 1:43 PM | 26/Jun/25 3:17 PM |  |  | 0
Sub-task | DEVRDCT-43 | 26517 | [QA] Test execution Feed Created User Properties | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 20/Jun/25 1:42 PM | 27/Jun/25 10:08 AM |  |  | 0
Sub-task | DEVRDCT-42 | 26514 | Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 20/Jun/25 1:42 PM | 26/Jun/25 4:20 PM |  |  | 0
Sub-task | DEVRDCT-41 | 26511 | Run Test execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 20/Jun/25 1:41 PM | 01/Jul/25 4:00 PM |  |  | 0
Sub-task | DEVRDCT-40 | 26508 | Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 20/Jun/25 1:40 PM | 01/Jul/25 4:00 PM |  |  | 0
Sub-task | DEVRDCT-39 | 26505 | [QA] Test execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 20/Jun/25 1:39 PM | 26/Jun/25 3:07 PM |  |  | 0
Sub-task | DEVRDCT-38 | 26502 | Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 20/Jun/25 1:37 PM | 26/Jun/25 1:54 PM |  |  | 0
Sub-task | DEVRDCT-37 | 26499 | Run Test execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 20/Jun/25 1:37 PM | 02/Jul/25 5:27 PM |  |  | 0
Sub-task | DEVRDCT-36 | 26496 | Create Test Case | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done |  | 20/Jun/25 1:37 PM | 02/Jul/25 5:26 PM |  |  | 0
Sub-task | DEVRDCT-35 | 25703 | [QA] Test execution | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 20/Jun/25 10:41 AM | 01/Jul/25 1:44 PM |  |  | 0
Sub-task | DEVRDCT-34 | 25699 | Test execution |  |  | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 20/Jun/25 10:29 AM | 20/Jun/25 10:29 AM |  |  | 0
Sub-task | DEVRDCT-33 | 25693 | Run the command to generate the payload before importing it into CleverTap. | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Medium | Done |  | 20/Jun/25 9:26 AM | 25/Jun/25 10:05 AM |  |  | 0
Task | RDAPS-25 | 25691 | [Dev][RD][SUB][Re-State] Request dev to re-state 6 BTS coupons for CRM case lot 19. 19/06/2025 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | High | Done |  | 19/Jun/25 8:21 PM | 20/Jun/25 5:25 PM | 19/Jun/25 12:00 AM | 1 | 2
Story | RDAPS-24 | 25681 | Improve sync products stock process | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | High | Done |  | 19/Jun/25 5:06 PM | 24/Jun/25 1:28 PM |  | 2 | 4
Sub-task | RDAPS-22 | 25678 | [Redemption API] Change calculation logic for coupon_valid_until_at to Restate Process | Wassana Mokman | 62835bb1ca7d7f00690051de | Wassana Mokman | 62835bb1ca7d7f00690051de | Medium | Done |  | 19/Jun/25 5:00 PM | 20/Jun/25 10:11 AM |  |  | 0
Task | DEVRDCT-32 | 25676 | [Dev][RD] Create API Spec | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 19/Jun/25 3:56 PM | 27/Jun/25 10:40 AM |  | 5 | 24
Task | RDLOA-4 | 25674 | [Dev][RD] Create Line OA API Spec | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 19/Jun/25 3:51 PM | 27/Jun/25 10:11 AM |  | 8 | 32
Task | RDAPS-21 | 25673 | [Dev][RD][SUB][Re-State] Request dev to re-state 14 BTS coupons for CRM case lot 18. 19/06/2025 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | High | Done |  | 19/Jun/25 3:28 PM | 19/Jun/25 8:18 PM | 19/Jun/25 12:00 AM | 1 | 2
Task | RDAPS-20 | 25669 | Request to regen 3 cancel e-receipts due to an issue on RR back office where receipts can't be downloaded. | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | High | Done |  | 19/Jun/25 3:17 PM | 20/Jun/25 3:13 PM |  | 1 | 2
Task | RDAPS-19 | 25660 | [Dev][RD][SUB][Re-State] Request dev to re-state 3 BTS coupons from using to redeem for CRM case lot 1 19/06/2025 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | High | Done |  | 19/Jun/25 2:27 PM | 19/Jun/25 8:18 PM | 19/Jun/25 12:00 AM | 1 | 2
Sub-task | RDAPS-18 | 25645 | Test Execution | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Max (QA) : Surawut Sae-nim | 62d4e007098e73c4e5ee0d8d | Medium | Done | Done | 19/Jun/25 9:32 AM | 19/Jun/25 11:24 AM |  |  | 0
Sub-task | DEVRDCT-31 | 25632 | Unit Test | Wassana Mokman | 62835bb1ca7d7f00690051de | Wassana Mokman | 62835bb1ca7d7f00690051de | Medium | Done | Done | 18/Jun/25 4:49 PM | 18/Jun/25 5:58 PM |  |  | 0
Task | DEVRDCT-30 | 25629 | [Dev][RD][Clever Tap] Retest - MEMBER COUPON | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done | Done | 18/Jun/25 4:33 PM | 23/Jun/25 4:23 PM |  | 1 | 2
Task | DEVRDCT-29 | 25628 | [Dev][RD][Clever Tap] Retest - SUBSCRIPTION MEMBER | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done | Done | 18/Jun/25 4:33 PM | 23/Jun/25 4:01 PM |  | 1 | 2
Task | DEVRDCT-28 | 25626 | [Dev][RD][Clever Tap] Retest - REDEEM | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done | Done | 18/Jun/25 4:33 PM | 23/Jun/25 4:01 PM |  | 1 | 2
Task | DEVRDCT-27 | 25625 | [Dev][RD][Clever Tap] Retest - CheckIn Event | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done | Done | 18/Jun/25 4:33 PM | 23/Jun/25 4:24 PM |  | 1 | 2
Test Execution | DEVRDCT-25 | 25620 | [RD][CleverTab][Batch#1]Verify User Properties #1 data display on Clever Tab correctly | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Done |  | 18/Jun/25 3:43 PM | 27/Jun/25 10:34 AM |  |  | 0
Task | DEVRDCT-24 | 25619 | [Dev][RD][Clever Tap] Retest - SPENDING PARTNER | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done | Done | 18/Jun/25 3:41 PM | 23/Jun/25 4:24 PM |  | 1 | 2
Task | RDAPS-16 | 25607 | [Dev][RD][A920 Reconciliation Report] TD data timestamp on BSS Site, Some transaction got wrong timestamp | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | High | Done | Done | 18/Jun/25 2:00 PM | 20/Jun/25 5:25 PM | 18/Jun/25 12:00 AM | 1 | 2
Task | DEVRDCT-23 | 25561 | [Dev][RD][Clever Tap] Clear data user profile on PROD | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 18/Jun/25 1:30 PM | 19/Jun/25 3:58 PM |  | 2 | 4
Test Execution | DEVRRBOF-42 | 25560 | [TX][Dev][RD][RR Backoffice] Sprint1 - Staging | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 18/Jun/25 1:12 PM | 26/Jun/25 5:19 PM |  |  | 0
Test Plan | DEVRRBOF-41 | 25559 | [TP][Dev][RD][RR Backoffice] Sprint1 |  |  | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 18/Jun/25 1:07 PM | 30/Jun/25 3:12 PM |  |  | 0
Task | RDAPS-15 | 25545 | [Dev][RD][SUB][Re-State] Request dev to re-state 33 BTS coupons for CRM case lot 16 and 17. 18/06/2025 | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | High | Done | Done | 18/Jun/25 11:35 AM | 19/Jun/25 2:31 PM | 18/Jun/25 12:00 AM | 1 | 2
Story | RDAPS-11 | 25538 | [Dev][RD][SUB][Offline RC card mark used fail after purchase. 16/07/2025]: Add retry logic when couponPackages is empty in confirm purchase flow | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Highest | Done | Done | 18/Jun/25 10:52 AM | 19/Jun/25 11:24 AM | 19/Jun/25 12:00 AM | 3 | 8
Sub-task | DEVRRBOF-35 | 25528 | [Order Consumer] Implement update payment description Omise and RGW | Wassana Mokman | 62835bb1ca7d7f00690051de | Wassana Mokman | 62835bb1ca7d7f00690051de | Medium | Done | Done | 18/Jun/25 10:03 AM | 18/Jun/25 5:39 PM |  |  | 0
Sub-task | RDAPS-10 | 25525 | Enhance command | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done | Done | 18/Jun/25 1:57 AM | 18/Jun/25 10:56 AM |  |  | 0
Sub-task | RDAPS-9 | 25522 | Run command generate at night | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done | Done | 18/Jun/25 1:57 AM | 18/Jun/25 9:18 AM |  |  | 0
Task | RDTHANA-4 | 25476 | [Dev][RD][Thana solution discussion] | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 17/Jun/25 4:29 PM | 20/Jun/25 4:50 PM |  | 2 | 4
Task | RDTHANA-3 | 25475 | [Dev][RD][Thana solution discussion] | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 17/Jun/25 4:29 PM | 26/Jun/25 9:27 AM |  | 2 | 4
Task | RDTHANA-2 | 25474 | [Dev][RD][Thana solution discussion] | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 17/Jun/25 4:29 PM | 20/Jun/25 2:03 PM |  | 2 | 4
Task | RDHOP-4 | 25473 | [Dev][RD]: Discuss HOB Survey Concept | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 17/Jun/25 4:25 PM | 24/Jun/25 1:28 PM |  | 1 | 2
Task | RDHOP-3 | 25472 | [Dev][RD]: Discuss HOB Survey Concept | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 17/Jun/25 4:25 PM | 26/Jun/25 9:27 AM |  | 1 | 2
Task | RDHOP-2 | 25471 | [Dev][RD]: Discuss HOB Survey Concept | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 17/Jun/25 4:25 PM | 26/Jun/25 9:27 AM |  | 1 | 2
Bug | DEVRDCT-22 | 25462 | [S3][RD][Clever Tap][API] User properties data feeded does't match required fields | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Pueng Prachpreeya | 642a5328f8bc2116accac530 | Medium | Closed |  | 17/Jun/25 3:29 PM | 22/Jun/25 5:09 PM |  |  | 0
Sub-task | RDAPS-6 | 25387 | [Redemption Consumer] Change calculation logic for coupon_valid_until_at | Wassana Mokman | 62835bb1ca7d7f00690051de | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 17/Jun/25 10:21 AM | 20/Jun/25 10:10 AM |  |  | 0
Sub-task | RDAPS-5 | 25384 | [Order Consumer] Change calculation logic for package_valid_until_at | Wassana Mokman | 62835bb1ca7d7f00690051de | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 17/Jun/25 10:21 AM | 20/Jun/25 10:10 AM |  |  | 0
Story | DEVRDCT-21 | 25382 | [Dev][RD][Clever Tap][Batch#1][Redemption] Feed Member Coupon to CleverTap Service for coupon update status | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 17/Jun/25 9:29 AM | 30/Jun/25 1:19 PM | 25/Jun/25 12:00 AM | 5 | 24
Sub-task | RDAPS-4 | 25348 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 16/Jun/25 5:33 PM | 26/Jun/25 5:17 PM |  |  | 0
Sub-task | RDAPS-3 | 25345 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done | Done | 16/Jun/25 5:33 PM | 17/Jun/25 11:07 AM |  |  | 0
Sub-task | DEVRRBOF-11 | 25271 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 16/Jun/25 2:47 PM | 20/Jun/25 5:45 PM |  |  | 0
Sub-task | DEVRRBOF-10 | 25268 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done | Done | 16/Jun/25 2:46 PM | 17/Jun/25 3:10 PM |  |  | 0
Sub-task | DEVRRBOF-9 | 25265 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 16/Jun/25 2:46 PM | 26/Jun/25 5:18 PM |  |  | 0
Sub-task | DEVRRBOF-8 | 25262 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 16/Jun/25 2:46 PM | 20/Jun/25 3:22 PM |  |  | 0
Sub-task | DEVRRBOF-7 | 25259 | [QA] Test execution | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done |  | 16/Jun/25 2:46 PM | 24/Jun/25 3:52 PM |  |  | 0
Sub-task | DEVRRBOF-6 | 25256 | [QA] Create test case | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Plai Thanaporn Rimnong-ang | 62c2a5acefb17d6ce62e41bf | Medium | Done | Done | 16/Jun/25 2:45 PM | 18/Jun/25 11:14 AM |  |  | 0
Story | RDAPS-2 | 25254 | [Dev][RD][BU][Ad hoc]: Request to regenerate purchase receipt due to some receipts were mis-rendered. 13/06/2025 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done | Done | 16/Jun/25 2:41 PM | 18/Jun/25 10:56 AM |  | 5 | 24
Story | RDAPS-1 | 25253 | [Dev][RD][RR Backoffice][SUB]: Change on package validity calculation] | Wassana Mokman | 62835bb1ca7d7f00690051de | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 16/Jun/25 2:40 PM | 26/Jun/25 5:18 PM | 20/Jun/25 12:00 AM | 3 | 8
Story | DEVRDCT-20 | 25245 | [Dev][RD][Clever Tap][Point Issue] Enhance flow to transform webhook request and issue point | thanyapath sunthornchaisadom | 6163a9eac7bea400698ab7af | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 16/Jun/25 2:07 PM | 01/Jul/25 1:09 PM |  | 3 | 8
Story | DEVRDCT-19 | 25238 | [Dev][RD][Clever Tap][Webhook] Create endpoint support support webhook | Wassana Mokman | 62835bb1ca7d7f00690051de | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 16/Jun/25 1:52 PM | 01/Jul/25 1:09 PM |  | 3 | 8
Sub-task | DEVRRBOF-5 | 25204 | [Backoffice] Add "Back to Redeemed" button to UI Action button & Info page | Thanakorn Tawsan | 62c2971eeda95d2e3a68c3ed | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done | Done | 13/Jun/25 1:55 PM | 18/Jun/25 4:02 PM | 18/Jun/25 12:00 AM |  | 0
Sub-task | DEVRRBOF-4 | 25201 | [Redemption API] Support restate coupon back to redeemed status | nattapon napasai | 64001d5e896d10ebd470f6c1 | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done | Done | 13/Jun/25 1:44 PM | 26/Jun/25 11:53 AM |  |  | 0
Story | DEVRRBOF-3 | 25195 | [Dev][RD][RR Backoffice][Payment Gateway description] | Wassana Mokman | 62835bb1ca7d7f00690051de | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done | Done | 13/Jun/25 11:52 AM | 27/Jun/25 5:32 AM |  | 3 | 8
Task | DEVRDCT-15 | 25163 | [Dev][RD][Clever Tap][Batch#1][Partner Loyalty] Initial User profile - partner binding | nattapon napasai | 64001d5e896d10ebd470f6c1 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | High | Done |  | 13/Jun/25 4:21 AM | 27/Jun/25 9:25 AM |  | 5 | 24
Task | DEVRDCT-14 | 25162 | [Dev][RD][Clever Tap][Batch#1][SSO-USER] Feed User Properties to CleverTap Service | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 13/Jun/25 2:43 AM | 27/Jun/25 10:08 AM | 25/Jun/25 12:00 AM | 3 | 8
Task | DEVRDCT-13 | 24156 | [Dev][RD][Clever Tap][Batch#1][Import Initial] User Properties #2 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 11/Jun/25 1:41 PM | 30/Jun/25 12:05 PM |  | 3 | 8
Task | DEVRDCT-12 | 24154 | [Dev][RD][Clever Tap][Batch#1][Import Initial] Subscription member | thanyapath sunthornchaisadom | 6163a9eac7bea400698ab7af | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 11/Jun/25 1:41 PM | 25/Jun/25 10:20 AM |  | 3 | 8
Task | DEVRDCT-11 | 24152 | [Dev][RD][Clever Tap][Batch#1][Import Initial] Member counpon | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 11/Jun/25 1:40 PM | 02/Jul/25 10:26 AM | 26/Jun/25 12:00 AM | 3 | 8
Task | DEVRDCT-8 | 24150 | [Dev][RD][Clever Tap][Batch#1][Import Initial] Redeem | Warin Kesorn | 61a98e8e744c4d00693281d1 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 11/Jun/25 1:40 PM | 25/Jun/25 10:18 AM |  | 3 | 8
Task | DEVRDCT-10 | 24148 | [Dev][RD][Clever Tap][Batch#1][Import Initial] Spening partner | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 11/Jun/25 1:40 PM | 27/Jun/25 10:38 AM |  | 5 | 24
Task | DEVRDCT-9 | 24146 | [Dev][RD][Clever Tap][Batch#1][Import Initial] Check-in | Thanakorn Tawsan | 62c2971eeda95d2e3a68c3ed | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 11/Jun/25 1:40 PM | 26/Jun/25 11:46 PM |  | 3 | 8
Task | DEVRDCT-7 | 24144 | [Dev][RD][Clever Tap][Batch#1][Import Initial] User Properties #1 | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done | Done | 11/Jun/25 1:39 PM | 19/Jun/25 3:20 PM | 20/Jun/25 12:00 AM | 5 | 24
Task | DEVRDCT-6 | 24142 | [Dev][RD][Clever Tap][Batch#1][SSO USER] Enhance initial user properties command support full data | A:Phongthorn | 5b3c867ae263df2dc32f7e35 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 11/Jun/25 1:36 PM | 27/Jun/25 10:07 AM | 27/Jun/25 12:00 AM | 5 | 24
Task | DEVRDCT-5 | 24140 | [Dev][RD][Clever Tap][Batch#1][SSO MIMIR] Import Line OA data from DA | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 11/Jun/25 1:35 PM | 01/Jul/25 1:09 PM |  | 3 | 8
Task | DEVRDCT-4 | 24138 | [Dev][RD][Clever Tap][Batch#1][Order API] Feed Subscription member to CleverTap Service | Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 11/Jun/25 1:35 PM | 27/Jun/25 9:25 AM |  | 2 | 4
Task | DEVRDCT-1 | 24136 | [Dev][RD][Clever Tap][Batch#1][Redemption] Feed Member Coupon to CleverTap Service | Jarupong Pawichpongkul | 62c2a16240923988ba097c14 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 11/Jun/25 1:34 PM | 03/Jul/25 1:23 PM | 20/Jun/25 12:00 AM | 5 | 24
Task | DEVRDCT-2 | 24134 | [Dev][RD][Clever Tap][Batch#1][Redemption] Feed Redeem event to CleverTap Service | Warin Kesorn | 61a98e8e744c4d00693281d1 | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 11/Jun/25 1:33 PM | 27/Jun/25 9:25 AM | 23/Jun/25 12:00 AM | 5 | 24
Task | DEVRDCT-3 | 24132 | [Dev][RD][Clever Tap][Batch#1][Partner Loyalty] Feed Spending partner to CleverTap Service | Aek:Atiphat Nanthachitvanich | 5d48155f5b8ea70c7e4f1b0f | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 11/Jun/25 1:33 PM | 02/Jul/25 5:27 PM |  | 3 | 8
Task | DEVRDCT-18 | 24051 | [Dev][RD][Clever Tap][Batch#1][Order API] Publish CleverTap event : SUBSCRIPTION_PURCHASE_REPORT to rabbit MQ | Kittapath Sangvikukit | 712020:b33baa03-2b29-4662-9923-dbdc2bbf980d | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done |  | 03/Jun/25 9:57 PM | 27/Jun/25 10:43 AM |  | 2 | 4
Task | DEVRDCT-17 | 24047 | [Dev][RD][Clever Tap][Batch#1][HR-Solution] Feed Checkin Event to CleverTap Service | Thanakorn Tawsan | 62c2971eeda95d2e3a68c3ed | Zan : Isarapong Bulan | 5d4814e9da0c4d0c789a4bb7 | Medium | Done | Done | 03/Jun/25 9:50 PM | 02/Jul/25 2:46 PM | 13/Jun/25 12:00 AM | 2 | 4
Story | DEVRRBOF-2 | 23949 | [Dev][RD]Add Delete button to delete coupon by transaction in action button & info page | Mai:Sateta Abvanawong | 64000e4f15d668edd8edc7ea | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 26/May/25 7:29 PM | 10/Jul/25 3:32 PM | 19/Jun/25 12:00 AM | 3 | 8
Story | DEVRRBOF-1 | 23937 | [Dev][RD][RR Backoffice][Txn page]: Add Back to redeemed button to restate coupon in action buttion & info page | Thanakorn Tawsan | 62c2971eeda95d2e3a68c3ed | Aom: Pornsawan Polnyiem | 5d2ed694a666040c85096e17 | Medium | Done |  | 23/May/25 8:34 PM | 10/Jul/25 3:32 PM | 18/Jun/25 12:00 AM | 8 | 32

## Bck Resource Allocate
Resource Plan – Sprint 19 23 Feb - 6 Mar
Capacity รวมทั้งทีม 118.5 SP | 118.5
Allocation each project (exclude PE) | 70
Allocation PE | 48.5
New Point Engine | 45 | 3
Vimi Termination | 24 | 1
Thana | 33 | 2
Datamart | 3 | 1
AWS | 3 | 1
Dev Support | 7
Remaining | 3.5
Name | Availability | Capacity | Total Workload | Allocation PE | PE (SP) | Allocation VIMI (days) | VIMI (SP) | Allocation Thana (days) | Thana (SP) | Allocation Datamart (days) | Datamart (SP) | Allocation AWS (days) | AWS (SP) | Dev Support | Dev Support (SP)
A | 7 | 21 | 20 | 5 | 15 |  | 0 |  | 0 |  | 0 | 1 | 3 | 0 | 2
Mac | 6 | 18 | 18 |  | 0 |  | 0 | 6 | 18 |  | 0 |  | 0 | 0 | 0
Mai | 6 | 18 | 18 |  | 0 |  | 0 | 5 | 15 | 1 | 3 |  |  | 0 | 0
Mos | 7 | 21 | 18 | 5 | 15 | 1 | 3 |  |  |  | 0 |  |  | 0 | 0
Nim | 7 | 21 | 23 |  | 0 | 7 | 21 |  |  |  | 0 |  |  | 0 | 2
Arm | 6.5 | 19.5 | 18 | 5 | 15 |  | 0 |  |  |  | 0 |  |  | 0 | 3
Total |  | 118.5 | 115 | 15 | 45 | 8 | 24 | 11 | 33 | 1 | 3 | 1 | 3 | 0 | 7
Resource Plan – Sprint 20 9 Mar - 20 Mar
Capacity รวม 130.5 SP | 130.5
Allocation each project (exclude PE) | 59.5
Allocation PE | 71
New Point Engine | 66 | 4
Vimi Termination | 21 | 1
Thana | 34.5 | 2
Datamart | 0 | 0
AWS | 0 | 0
Dev Support | 1 | 1
Remaining | 5
Name | Availability | Capacity | Total Workload | Allocation PE | PE (SP) | Allocation VIMI (days) | VIMI (SP) | Allocation Thana (days) | Thana (SP) | Allocation AWS (days) | AWS (SP) | Allocation Adhoc (days) | Adhoc (SP) | Dev Support | Dev Support (SP)
A | 7 | 21 | 23.5 | 6.5 | 19.5 |  | 0 |  | 0 |  | 0 | 1 | 3 | 0 | 1
Mac | 7.5 | 22.5 | 24 | 1.5 | 4.5 |  | 0 | 6.5 | 19.5 |  | 0 |  |  | 0 | 0
Mai | 7 | 21 | 19.5 | 1.5 | 4.5 |  | 0 | 5 | 15 |  | 0 |  |  | 0 | 0
Mos | 7 | 21 | 19.5 | 6.5 | 19.5 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
Nim | 7 | 21 | 21 |  | 0 | 7 | 21 |  | 0 |  | 0 |  |  | 0 | 0
Arm | 8 | 24 | 18 | 6 | 18 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
Total |  | 130.5 | 125.5 | 22 | 66 | 7 | 21 | 11.5 | 34.5 | 0 | 0 | 1 | 3 | 0 | 1
Resource Plan – Sprint 21 23 Mar - 3 Apr | 228
Capacity SA รวม 91.5 SP | 91.5
Capacity DEV รวม 136.5 SP | 136.5
Allocation each project (exclude PE) | 15
Allocation PE | 121.5
New Point Engine | 105 | 5
Vimi Termination | 3 | 1
Thana & Datamart | 9 | 1
AWS | 0 | 0
Dev Support | 3 | 0
Remaining | 108
Name | Availability | Capacity | Total Workload | Allocation PE | PE (SP) | Allocation VIMI (days) | VIMI (SP) | Allocation Thana (days) | Thana (SP) | Allocation AWS (days) | AWS (SP) | Allocation Adhoc (days) | Adhoc (SP) | Dev Support | Dev Support (SP)
Aek | 7 | 21 | 15 |  | 0 |  | 0 |  | 0 |  | 0 | 5 | 15 | 0 | 0
Aom | 7.5 | 22.5 | 22.5 | 7.5 | 22.5 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
Zan | 8 | 24 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
Jack | 8 | 24 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
A | 7 | 21 | 21 | 7 | 21 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
Mac | 8 | 24 | 21 | 4 | 12 |  | 0 | 3 | 9 |  | 0 |  | 0 | 0 | 0
Mai | 8 | 24 | 21 | 7 | 21 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
Mos | 8 | 24 | 24 | 8 | 24 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
Nim | 7 | 21 | 15 | 4 | 12 | 1 | 3 |  | 0 |  | 0 |  | 0 | 0 | 0
Arm | 7.5 | 22.5 | 18 | 5 | 15 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 3
Total |  | 228 | 120 | 35 | 105 | 1 | 3 | 3 | 9 | 0 | 0 | 0 | 0 | 1 | 3
Resource Plan – Sprint 22 *Long weeked 6 Apr - 17 Apr | 99
Capacity SA รวม 48 SP | 30
Capacity รวม 69 SP | 69 | [9 empty] | 0 |  | 8
Allocation each project (exclude PE) | 0
Allocation PE | 69
New Point Engine |  | 0
Vimi Termination | 0 | 0
Thana & Datamart | 0 | 0
AWS | 0 | 0
Dev Support | 0 | 0
Remaining | 99
Name | Availability | Capacity | Total Workload | Allocation PE | PE (SP) | Allocation VIMI (days) | VIMI (SP) | Allocation Thana (days) | Thana (SP) | Allocation AWS (days) | AWS (SP) | Allocation Adhoc (days) | Adhoc (SP) | Dev Support | Dev Support (SP)
Aek | 3 | 9 | 0
Aom | 0 | 0 | 0
Zan | 3 | 9 | 0
Jack | 4 | 12 | 0
A | 4 | 12 | 0 | [7 empty] | 0 |  |  | 0 | 0
Mac | 3 | 9 | 0 | [7 empty] | 0 |  |  | 0 | 0
Mai | 4 | 12 | 0 | [7 empty] | 0 |  |  | 0 | 0
Mos | 4 | 12 | 0 | [7 empty] | 0 |  |  | 0 | 0
Nim | 4 | 12 | 0 | [7 empty] | 0 |  |  | 0 | 0
Arm | 4 | 12 | 0 | [7 empty] | 0 |  |  | 0 | 0
Total |  | 99 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Resource Plan – Sprint 23 20 Apr - 1 May
Capacity รวม 126 SP | 126 | [9 empty] | 0 |  | 8
Allocation each project (exclude PE) | 0
Allocation PE | 126
Name | Availability | Capacity | Total Workload | Allocation PE | PE (SP) | Allocation VIMI (days) | VIMI (SP) | Allocation Thana (days) | Thana (SP) | Allocation AWS (days) | AWS (SP) | Allocation Adhoc (days) | Adhoc (SP) | Dev Support | Dev Support (SP)
Aek
Aom
Zan
Jack
A | 7 | 21 | [8 empty] | 0 |  |  | 0 | 0
Mac | 7 | 21 | [8 empty] | 0 |  |  | 0 | 0
Mai | 7 | 21 | [8 empty] | 0 |  |  | 0 | 0
Mos | 7 | 21 | [8 empty] | 0 |  |  | 0 | 0
Nim | 7 | 21 | [8 empty] | 0 |  |  | 0 | 0
Arm | 7 | 21 | [8 empty] | 0 |  |  | 0 | 0
Total | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Resource Plan – Sprint 24 4 May - 15 May
Capacity รวม 126 SP | 126
Allocation each project (exclude PE) | 0
Allocation PE | 126
Name | Availability | Capacity | Total Workload | Allocation PE | PE (SP) | Allocation VIMI (days) | VIMI (SP) | Allocation Thana (days) | Thana (SP) | Allocation AWS (days) | AWS (SP) | Allocation Adhoc (days) | Adhoc (SP) | Dev Support | Dev Support (SP)
Aek
Aom
Zan
Jack
A | 7 | 21 | [8 empty] | 0 |  |  | 0 | 0
Mac | 7 | 21 | [8 empty] | 0 |  |  | 0 | 0
Mai | 7 | 21 | [8 empty] | 0 |  |  | 0 | 0
Mos | 7 | 21 | [8 empty] | 0 |  |  | 0 | 0
Nim | 7 | 21 | [8 empty] | 0 |  |  | 0 | 0
Arm | 7 | 21 | [8 empty] | 0 |  |  | 0 | 0
Total | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Resource Plan – Sprint 25 18 May - 29 May
Capacity รวม 129 SP | 129
Allocation each project (exclude PE) | 0
Allocation PE | 129
Name | Availability | Capacity | Total Workload | Allocation PE | PE (SP) | Allocation VIMI (days) | VIMI (SP) | Allocation Thana (days) | Thana (SP) | Allocation AWS (days) | AWS (SP) | Allocation Adhoc (days) | Adhoc (SP) | Dev Support | Dev Support (SP)
Aek
Aom
Zan
Jack
A | 7 | 21 | [8 empty] | 0 |  |  | 0 | 0
Mac | 8 | 24 | [8 empty] | 0 |  |  | 0 | 0
Mai | 4 | 12 | [8 empty] | 0 |  |  | 0 | 0
Mos | 8 | 24 | [8 empty] | 0 |  |  | 0 | 0
Nim | 8 | 24 | [8 empty] | 0 |  |  | 0 | 0
Arm | 8 | 24 | [8 empty] | 0 |  |  | 0 | 0
Total | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint Resource (old)
| Total Manhour/Sprint | [19 empty] | Sprint #2 Task | 30 Jun - 11 Jul |  | 442(106 + 336)
Sprint | Date | Zan | Aom | Aek | A | Mai | Preaw | Jack | John | Mos | First | Mac | Art | Kae | Nim | More | Hour/day | Day | Total Dev Hour | Remark |  |  |  | 221
1 | 2025-06-16 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 4 | 4 | 4 | 6.5 | 6.5 |  |  |  | 6.5 | [5 empty] | RDAPS- | 1 | 2
| day | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 7.5 | 8 |  |  |  | 7 |  |  |  | More ลาพักร้อน 20/6, First ลาป่ายครึ่งวัน 16/6 |  | RDAPS- | 1 | 2
| hour | 52 | 52 | 52 | 52 | 52 | 52 | 32 | 32 | 32 | 48.75 | 52 |  |  |  | 45.5 |  |  | 554.25 |  |  | RDAPS-32 | 3 | 8
[22 empty] | DEVRRBOF-67 | 5 | 24 | 24
2 | 2025-06-30 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 0 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 |  |  |  | 0 | [5 empty] | DEVRRBOF-69 | 5 | 24 | 24 | ไปใน solution เส้นใหม่
| day | 7 | 7 | 7 | 6 | 6 | 0 | 7 | 7 | 7 | 7 | 6 |  |  |  | 0 |  |  |  | Mac 30 jun, P'A 4 Jul, |  | DEVRDCT-88 | 5 | 24 | 24
| hour | 45.5 | 45.5 | 45.5 | 39 | 39 | 0 | 45.5 | 45.5 | 45.5 | 45.5 | 39 |  |  |  | 0 |  |  | 435.5 |  |  | DEVRDCT-89 | 5 | 16 | 16
3 | 2025-07-14 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 0 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 |  |  |  | 0 | [5 empty] | DEVRDCT-94 | 3 | 8 | 8
| day | 8 | 6.5 | 7.5 | 7 | 8 | 0 | 8 | 4 | 7 | 4 | 8 |  |  |  | 0 |  |  |  | Aom ลาป่วย, First ลาป่วย, A ลา, Aom ลาบ่าย, Aek ลาเช้า, Mos ลา
| hour | 52 | 42.25 | 48.75 | 45.5 | 52 | 0 | 52 | 26 | 45.5 | 26 | 52 |  |  |  | 0 |  |  | 442
4 | 29 Jul - 8 Aug | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 0 | 6.5 | 0 | 6.5 | 0 | 6.5 |  |  |  | 0
| day | 5 | 6.5 | 6 | 7 | 6.5 | 0 | 5 | 0 | 7 | 0 | 7 |  |  |  | 0
| hour | 32.5 | 42.25 | 39 | 45.5 | 42.25 | 0 | 32.5 | 0 | 45.5 | 0 | 45.5 |  |  |  | 0 |  |  | 325 | Zan 2, P'Jack 2, Aek 1, Aom 0.5, Mai 0.5
5 | 11 Aug - 22 Aug | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 0 | 6.5 | 0 | 6.5 | 0 | 6.5 | 3 |  |  | 0
| day | 6.5 | 6 | 7 | 6.5 | 7 | 0 | 6 | 0 | 6 | 0 | 7 | 7 |  |  | 0
| hour | 42.25 | 39 | 45.5 | 42.25 | 45.5 | 0 | 39 | 0 | 39 | 0 | 45.5 | 21 |  |  | 0 |  |  | 359 | Zan 0.5, Aom, 1, Jack 1, A 0.5, Mos 1
[22 empty] | DEVRDCT-99 | 3 | 8 | 8
[22 empty] | DEVRDCT-96 | 8 | 32 | 32
| SA, Support, Adhoc, Meeting Manhour /Sprint | [20 empty] | RDLOA-13 | 5 | 21
Sprint | Date | Zan | Aom | Aek | A | [11 empty] | Hour/day | Day | Total Dev Hour | Remark |  | 14 | 3 | 8
1 | 2025-06-16 | 4.5 | 4.5 | 4.5 | 2 | [11 empty] | 15.5 | 8 | 124 |  |  | 15 | 2 | 4
| hour | 36 | 36 | 36 | 16 | [13 empty] | 124 |  |  | RDLOA-26
2 | 2025-06-30 | 4.5 | 4.5 | 4.5 | 2 | [11 empty] | 15.5 | 7 |  | 1 Holiday (10 July อาสาฬห) |  | 9 | 3 | 8
| hour | 31.5 | 31.5 | 31.5 | 12 | [13 empty] | 106.5 |  |  | 11 | 3 | 8
3 | 2025-07-14 | 4.5 | 4.5 | 4.5 | 2 | [11 empty] | 15.5 | 8 |  |  |  | 12 | 3 | 8
| hour | 36 | 29.25 | 33.75 | 14 | [13 empty] | 113
4 | 2025-07-29 | 4.5 | 4.5 | 4.5 | 2 | [11 empty] | 15.5 | 7
| hour | 22.5 | 29.25 | 27 | 14 | [13 empty] | 92.75
5 | 2025-08-11 | 4.5 | 4.5 | 4.5 | 2 | [11 empty] | 15.5 | 7
| hour | 29.25 | 27 | 31.5 | 13 | [13 empty] | 100.75
6 | 2025-08-25 | 4.5 | 4.5 | 4.5 | 2 | [11 empty] | 15.5 | 8
| hour | 0 | 0 | 0 | 0 | [13 empty] | 0
7 | 8 Sep - 19 Sep | 4.5 | 4.5 | 4.5 | 2 | [11 empty] | 15.5 | 8
| hour | 0 | 0 | 0 | 0 | [13 empty] | 0
| Dev Manhour /Sprint | [20 empty] | RDLOA-28 | 3 | 8
Sprint | Date | Zan | Aom | Aek | A | Mai | Preaw | Jack | John | Mos | First | Mac | Art | Kae | Nim | More | Hour/day | Max Day | Total Dev Hour | Remark |  | 18 | 3 | 8
1 | 2025-06-16 | 2 | 2 | 2 | 4.5 | 6.5 | 6.5 | 4 | 4 | 4 | 6.5 | 6.5 |  |  |  | 6.5 | 48.5 | 8
| hour | 16 | 16 | 16 | 36 | 52 | 52 | 32 | 32 | 32 | 48.75 | 52 |  |  |  | 45.5 |  |  | 430.25
2 | 2025-06-30 | 2 | 2 | 2 | 4.5 | 6.5 | 0 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 |  |  |  | 0 | 49.5 | 7 |  | 1 Holiday (10 July อาสาฬห)
| hour | 14 | 14 | 14 | 27 | 39 | 0 | 45.5 | 45.5 | 45.5 | 45.5 | 39 |  |  |  | 0 |  |  | 329
3 | 2025-07-14 | 2 | 2 | 2 | 4.5 | 6.5 | 0 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 |  |  |  | 0 | 49.5 | 8
| hour | 16 | 13 | 15 | 31.5 | 52 | 0 | 52 | 26 | 45.5 | 26 | 52 |  |  |  | 0 |  |  | 329
4 | 2025-07-29 | 2 | 2 | 2 | 4.5 | 6.5 | 0 | 6.5 | 0 | 6.5 | 0 | 6.5 |  |  |  | 0 | 36.5 | 7
| hour | 10 | 13 | 12 | 31.5 | 42.25 | 0 | 32.5 | 0 | 45.5 | 0 | 45.5 |  |  |  | 0 | 0 | 0 | 232.25
5 | 2025-08-11 | 2 | 2 | 2 | 4.5 | 6.5 | 0 | 6.5 | 0 | 6.5 | 0 | 6.5 | 3 |  |  | 0 | 39.5 | 7
| hour | 13 | 12 | 14 | 29.25 | 45.5 | 0 | 39 | 0 | 39 | 0 | 45.5 | 21 |  |  | 0 | 0 | 0 | 258.25
6 | 2025-08-25 | 2 | 2 | 2 | 4.5 | 6.5 | 0 | 6.5 | 0 | 6.5 | 0 | 6.5 | 6.5 | 6.5 |  | 0 | 49.5 | 8
| hour | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
7 | 8 Sep - 19 Sep | 2 | 2 | 2 | 4.5 | 6.5 | 0 | 6.5 | 0 | 6.5 | 0 | 6.5 | 6.5 | 6.5 | 6.5 | 0 | 49.5 | 8
| hour | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## SSO Members
Total Members | 6646394
RR Members | 5095514
BSS Members | 1056915
2025-01-01 | 64103
2025-02-01 | 58898
2025-03-01 | 69689
2025-04-01 | 68655
2025-05-01 | 81885
2025-06-01 | 83286
2025-07-01 | 83127
2025-08-01 | 147217
2025-09-01 | 72251
2025-10-01 | 62875
2025-11-01 | 60218
2025-12-01 | 55598
2026-01-01 | 52666
2026-02-01 | 38122

## Sheet2
Project /Phase | Detail | Task | Requested by | Prioriize by PM/PO | SA,Dev | Dev Team | QA Team | Status | Note | Estimate Man-hour | Mar | Apr | May |  | Jun |  | Jul | Aug | Sep | Oct | Nov | Dec
Clevertap | [7 empty] | Inprogress | * requirment onboard 15 May |  |  |  |  | RQ 15
🔶 Batch1 | initial data & profile | Develop (RD) |  |  | 🧑‍🦰Zan | Based on data & service: 🧑‍🦰Jack, 🧑‍🦰John / Clevertap Service 🧑‍🦰A / SSO RR Profile#1, #2 🧑‍🦰Aek / PL,RLP 🧑‍🦰More / HR Solution 🧑‍🦰Preaw, 🧑‍🦰First / Order, Redemption |  | Inprogress | Review Document, Grooming | [5 empty] | 1 week
|  | Test |  |  |  | ??? |  | Not start
🔶 Batch2 & 3 | Events | Develop (RD) |  |  | 🧑‍🦰Zan | TBC on avail. resource next 🧑‍🦰Aek - PL, RLP 🧑‍🦰A, 🧑‍🦰Mai - SSO , Rabbit Connect 🧑‍🦰Preaw - CloudID |  | Not start | pre-estimate timeline (TBC after grooming) -> have enough info. wait for priority * Leaver: 3 Dev at 30 Jun | XX? | [6 empty] | guesstimate
|  | Test |  |  |  | ??? |  | Not start
Subscription | 1) Fixing & Enhance | Develop (RD) |  |  | 🧑‍🦰Aom | 🧑‍🦰Preaw 🧑‍🦰First 🧑‍🦰Mai 🧑‍🦰Mac 🧑‍🦰Aom |  | Inprogress
| 2) Send transaction to DA | Develop (RD) |  |  | 🧑‍🦰Aom | 🧑‍🦰Preaw 🧑‍🦰First |  | Inprogress | 1)UAT 13/6 2)RR to test & verify 3)Deploy to Prod
*Introduce Agile adoption | Payment Gateway - Add purchase package description in transaction detail |  | RR | Chawin |  |  |  | Not start | Jun 12: ยังไม่มี Jira project ให้เข้าไป Create task for Dev | 46 | [5 empty] | Guestimate
*Introduce Agile adoption | https://app.clickup.com/t/7514825/ITPE-3710 [Restate] | Develop (RD) | RR | Chawin | 🧑‍🦰Aom | 🧑‍🦰Preaw 🧑‍🦰First 🧑‍🦰Mai 🧑‍🦰Mac 🧑‍🦰More |  | Not start | Jun 12: ยังไม่มี Jira project ให้เข้าไป Create task for Dev | 54 | [5 empty] | Guestimate
*Introduce Agile adoption | https://app.clickup.com/t/7514825/ITPE-3710 [Delete coupon] |  | RR | Chawin |  |  |  | Not start | Jun 12: ยังไม่มี Jira project ให้เข้าไป Create task for Dev | 44 | [5 empty] | Guestimate
| https://app.clickup.com/t/7514825/ITPE-3710 [Mark used] |  | RR | Chawin |  |  |  | Not start |  | 122 | [5 empty] | Guestimate
| https://app.clickup.com/t/7514825/ITPE-3710 [Form search and Excel] | [6 empty] | Not start |  | 78
| https://app.clickup.com/t/7514825/ITPE-3710 [Replace Code] | [6 empty] | Not start |  | 78
| https://app.clickup.com/t/7514825/ITPE-3710 [Refund] | [6 empty] | Not start |  | 122
| https://app.clickup.com/t/7514825/ITPE-3710 [Hold] | [6 empty] | Not start |  | 114
| *Important but not urgent 4) Performance tuning - optimize query for each report - index | Develop (RD) | Dev |  | 🧑‍🦰Aom | 🧑‍🦰Preaw 🧑‍🦰Aom |  | Not start
| 5) Improve Subcategory Backoffice | Develop (RD) |  |  | 🧑‍🦰Aom | 🧑‍🦰 TBC with RR on priority |  | Not start | RR Cancelled on 11/6
| 6) BTS Coupon using status | Develop |  |  | 🧑‍🦰Aom | 🧑‍🦰 TBC with RR on priority |  | Not start | RR Cancelled on 10/6
| 7) Implement Automatic Cart Clearance | Develop (RD) |  |  | 🧑‍🦰Aom | 🧑‍🦰 TBC with RR on priority |  | Not start | TBC with RR
|  | Test | [5 empty] | Not start
LINE OA | RR & LINE OA Integration | Estimate Time |  |  | 🧑‍🦰Aek | - |  | Inprogress | Requirement: 23/5 Estimate time by : 9/6 |  |  |  |  | 23 | 9
|  | Develop (RD) |  |  | 🧑‍🦰Aek | 🧑‍🦰 TBC - After Estimated & Sprint Plan |  | Not start | After Estimated & Sprint Plan | [6 empty] | 16
|  | Test | [5 empty] | Not start